## Appendix K (i)
BUFFALO CITY METROPOLITAN MUNICIPALITY
STATEMENT OF FINANCIAL PERFORMANCE
APPENDIX K (i)
Description | 2010/11 Audited Outcome | 2011/12 Original Budget | 2011/12 Adjusted Budget | YearTD Actual | YearTD Variance | % Exp vs. Budget
Revenue by Vote
Vote 1 - Executive Support Services | 4034749.1 | 0 | 4421727 | 1792498 | 2629229 | 40.54%
Vote 2 - Municipal Manager's Office | 7431149 | 0 | 2668851 | 212230 | 2456621 | 7.952%
Vote 3 - Chief Operations Officer | 103955287.81 | 290582136.7955 | 98444918 | 32225918.81 | 66218999.19 | 32.73%
Vote 4 - Directorate of Financial Services | 850254110.18 | 1157024892.7506 | 1151320413 | 1171008102 | -19687689 | 101.7%
Vote 5 - Directorate of Corporate Services | 1009148 | 3235518.0347 | 3245800 | 3249622 | -3822 | 100.1%
Vote 6 - Directorate of Engineering Services | 1428668936.79 | 1727529282.3595 | 1718760744 | 1722141374.18 | -3380630.18 | 100.2%
Vote 7 - Directorate of Development Planning | 40041276.6 | 39117418.4316 | 41670541 | 34047390.24 | 7623150.76 | 81.71%
Vote 8 - Directorate of Health & Public Safety | 136313446.4 | 174861045.7164 | 174338358 | 182627208.11 | -8288850.11 | 104.8%
Vote 9 - Directorate of Community Services | 234912249.52 | 260938875.2011 | 253497235 | 263200742.02 | -9703507.02 | 103.8%
Total Revenue by Vote | 2806620353.4 | 3653289169.2894 | 3448368587 | 3410505085.36 | 37863501.64 | 98.9%
Expenditure by Vote
Vote 1 - Executive Support Services | 87944455.73 | 104510882.3889 | 127377542 | 108249727 | 19127815 | 84.98%
Vote 2 - Municipal Manager's Office | 46108575.47 | 37771065.0203 | 40654267 | 35195785 | 5458482 | 86.57%
Vote 3 - Chief Operations Officer | 89258482.76 | 312578880.0364 | 120308217 | 47785163.28 | 72523053.72 | 39.72%
Vote 4 - Directorate of Financial Services | 234162376.94 | 337166629.0768 | 322692364 | 306889528 | 15802836 | 95.1%
Vote 5 - Directorate of Corporate Services | 81709590.36 | 110558254.8967 | 104894927 | 93658995 | 11235932 | 89.29%
Vote 6 - Directorate of Engineering Services | 1867495860.57 | 2104625866.0202 | 2079821684 | 1981997932 | 97823752 | 95.3%
Vote 7 - Directorate of Development Planning | 183846880.7 | 208612660.5293 | 209155236 | 199382236 | 9773000 | 95.33%
Vote 8 - Directorate of Health & Public Safety | 200262377.67 | 257642893.5379 | 264470642 | 243596559 | 20874083 | 92.11%
Vote 9 - Directorate of Community Services | 442213395.52 | 453523859.19 | 454452887 | 421487056 | 32965831 | 92.75%
Total Expenditure by Vote | 3233001995.72 | 3926990990.6966 | 3723827766 | 3438242980.28 | 285584785.72 | 92.33%
Transfer from Reserves | 0 | -310740545.4488 | 310740545.4488 | 0
Transfers recognised - capital | 232733603.6 | 654418089 | 570538993 | 187131452.64
Transfer RDP Housing | 0 | 0 | 0 | -15793348.72
Contributed assets
Surplus/ (Deficit) for the year | -193648038.72 | 69975722.144 | 605820360.4488 | 143566334.13

## Appendix K (ii)
BUFFALO CITY METROPOLITAN MUNICIPALITY
STATEMENT OF FINANCIAL PERFORMANCE
APPENDIX K (ii)
Description | 2010/11 Audited Outcome | 2011/12 Original Budget | 2011/12 Adjusted Budget | YearTD Actual | YearTD Variance | % Exp vs. Budget
Revenue By Source
Property rates | 453306422.26 | 520510728 | 519835876 | 521930666.71 | -2094790.71 | 100.4%
Property rates - penalties & collection charges | 0 | 1235966 | 1235966 | 583813.47 | 652152.53 | 47.24%
Service charges - electricity revenue | 924517221.42 | 1142651893.5576 | 1142651894 | 1137197631.55 | 5454262.45 | 99.52%
Service charges - water revenue | 200157655.72 | 233282971.2795 | 225867262 | 239551504.1 | -13684242.1 | 106.1%
Service charges - sanitation revenue | 166162041.19 | 180202567.572 | 182819826 | 183646197.42 | -826371.42 | 100.5%
Service charges - refuse revenue | 157219213.81 | 173905216.394 | 176193101 | 175340727.61 | 852373.39 | 99.52%
Service charges - other | 16943708.99 | 22538901 | 22538901 | 20778161.94 | 1760739.06 | 92.19%
Rental of facilities and equipment | 14107440.47 | 12759012.9353 | 12759013 | 13387802.57 | -628789.57 | 104.9%
Interest earned - external investments | 32526922.17 | 30191671 | 30191671 | 58688995.05 | -28497324.05 | 194.4%
Interest earned - outstanding debtors | 21202461.26 | 22036057.0875 | 22036058 | 23919884.03 | -1883826.03 | 108.5%
Dividends received | 0 | 60334.05 | 60334 | 0 | 60334 | 0%
Fines | 7320910.47 | 10656828.2842 | 10656828 | 5455740.05 | 5201087.95 | 51.19%
Licences and permits | 15052974.46 | 15391120.6928 | 15391120 | 15707755.39 | -316635.39 | 102.1%
Agency services |  |  |  |  | 0 | #DIV/0!
Transfers recognised - operational | 679071348.65 | 966570087 | 763689501 | 724619308.05 | 39070192.95 | 94.88%
Other revenue | 118595012.9 | 321295820 | 322441236 | 288038468.45 | 34402767.55 | 89.33%
Gains on disposal of PPE | 437019.74 |  |  | 1658429.65 | -1658429.65 | #DIV/0!
Total Revenue | 2806620353.51 | 3653289174.8529 | 3448368587 | 3410505086.04 | 37863500.96 | 98.9%
Expenditure By Type
Employee related costs | 858017015.101 | 983308133.882 | 979841471.5233 | 956506002.76 | 23335468.7633 | 97.62%
Remuneration of councillors | 23277826.61 | 28870622.6225 | 42074354 | 42965668.12 | -891314.12 | 102.1%
Debt impairment | 210998042.73 | 165450000 | 165450000 | 64013323.81 | 101436676.19 | 38.69%
Depreciation & asset impairment |  | 473248010.1023 | 473248011 | 491014921.61 | -17766910.61 | 103.8%
Finance charges | 20517658.01 | 67067231 | 93951193 | 145370296.62 | -51419103.62 | 154.7%
Bulk purchases | 771252978.48 | 940527838.6781 | 928118537 | 915387162.25 | 12731374.75 | 98.63%
Other materials |  |  |  |  | 0 | #DIV/0!
Contracted services | 5907803.9 | 8317221.361 | 9673250 | 6839653.67 | 2833596.33 | 70.71%
Transfers and grants | 2990030.6 | 3431607.1088 | 27615564 | 15028737.06 | 12586826.94 | 54.42%
Other expenditure | 815832427.15 | 1256770336 | 1003855385 | 797972474.96 | 205882910.04 | 79.49%
Loss on disposal of PPE | 6045785.04 | 0 | 0 | 3144739.21 | -3144739.21 | #DIV/0!
Total Expenditure | 2714839567.621 | 3926991000.7547 | 3723827765.5233 | 3438242980.07 | 285584785.4533 | 92.33%
Transfer from Reserves | 0 | -310740545.4488 | 310740545.4488 | 0
Transfers recognised - capital | 232733603.6 | 654418089 | 570538993 | 187131452.64
Transfer RDP Housing | 0 | 0 | 0 | -15793348.72
Contributed assets
Surplus/(Deficit) | 324514389.489 | 69975717.6494 | 605820359.9254 | 143566335.02

## Appendix L
BUFFALO CITY METROPOLITAN MUNICIPALITY
CONDITIONAL GRANTS RECEIVED
APPENDIX L
Funding/Grant | 2011/2012 Conditional Grants Received | 2011/2012 Mid-Year Adjustment Budget | YTD Expenditure R | Variance R | % Exp vs. Budget
Department of Water affairs | 1714006 | 1718000 | 1711503 | 6497 | 99.62%
Electricity Demand Side Management | 4000000 | 4000000 | 3926791 | 73209 | 98.17%
DoE(Integrated National Electrification Programme) | 26895000 | 26895000 | 20641200.83 | 6253799.17 | 76.75%
Finance Management Grant | 1450000 | 1459000 | 1459000 | 0 | 100%
Public Transport Infrastructure Grant | 180000000 | 100000000 | 1283135 | 98716865 | 1.283%
TOTAL | 214059006 | 134072000 | 29021629.83 | 105050370.17 | 21.65%

## Appendix M (i)
BUFFALO CITY METROPOLITAN MUNICIPALITY
CAPITAL EXPENDITURE ON NEW ASSETS BY ASSET CLASS/SUB-CLASS
APPENDIX M (i)
Description | 2010/11 Audited Outcome | 2011/12 Original Budget | 2011/12 Adjusted Budget | YearTD Actual | YearTD Variance | % Exp vs. Budget
Infrastructure | 263970851 | 629903961.5 | 505690521.5 | 145226602 | 360463919.5 | 28.72%
Infrastructure - Road transport | 55314896 | 67375700 | 67375700 | 37136877 | 30238823 | 55.12%
Roads, Pavements & Bridges | 55314896 | 67375700 | 67375700 | 37136877 | 30238823 | 55.12%
Storm water |  |  |  |  | 0 | 0%
Infrastructure - Electricity | 40174250 | 23800000 | 23800000 | 20990119 | 2809881 | 88.19%
Generation | 37008699 | 0 | 0 | 0 | 0 | 0%
Transmission & Reticulation | 0 | 23800000 | 23800000 | 20990119 | 2809881 | 88.19%
Street Lighting | 3165551 | 0 | 0 | 0 | 0 | 0%
Infrastructure - Water | 60819812 | 21000000 | 26895000 | 16857343 | 10037657 | 62.68%
Dams & Reservoirs |  |  |  |  | 0 | #DIV/0!
Water purification |  |  |  |  | 0 | #DIV/0!
Reticulation | 60819812 | 21000000 | 26895000 | 16857343 | 10037657 | 62.68%
Infrastructure - Sanitation | 79666844 | 199000000 | 199000000 | 61547597 | 137452403 | 30.93%
Reticulation | 79666844 | 199000000 | 199000000 | 61547597 | 137452403 | 30.93%
Sewerage purification |  |  |  |  | 0 | #DIV/0!
Infrastructure - Other | 27995049 | 318728261.5 | 188619821.5 | 8694666 | 179925155.5 | 4.61%
Waste Management | 581621 | 11068479 | 5568479 | 2507733 | 3060746 | 45.03%
Transportation | 24035258 | 190405120.5 | 108164386.5 | 6186933 | 101977453.5 | 5.72%
Gas |  |  |  |  | 0 | #DIV/0!
Other | 3378170 | 117254662 | 74886956 | 0 | 74886956 | 0%
Community | 20446259 | 12881578 | 19754875 | 5726995 | 14027880 | 28.99%
Parks & gardens | 0 | 1016303 | 1016303 | 543405 | 472898 | 53.47%
Sportsfields & stadia | 5750511 | 137822 | 12720 | 0 | 12720 | 0%
Swimming pools |  |  |  |  | 0 | #DIV/0!
Community halls | 10998610 | 2000000 | 2000000 | 1934503 | 65497 | 96.73%
Libraries |  |  |  |  | 0 | #DIV/0!
Recreational facilities |  |  |  |  | 0 | #DIV/0!
Fire, safety & emergency |  |  |  |  | 0 | #DIV/0!
Security and policing |  |  |  |  | 0 | #DIV/0!
Buses | 0 | 0 | 5998399 | 3249087 | 2749312 | 54.17%
Clinics | 761760 | 0 | 0 | 0 | 0 | 0%
Museums & Art Galleries |  |  |  |  | 0 | #DIV/0!
Cemeteries |  |  |  |  | 0 | #DIV/0!
Social rental housing |  |  |  |  | 0 | #DIV/0!
Other | 2935378 | 9727453 | 10727453 | 0 | 10727453 | 0%
Heritage assets | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Buildings |  |  |  |  | 0 | #DIV/0!
Other |  |  |  |  | 0 | #DIV/0!
Investment properties | 6326456 | 0 | 644462 | 14023376 | -13378914 | 2176%
Housing development | 6326456 | 0 | 644462 | 14023376 | -13378914 | 2176%
Other |  |  |  |  | 0 | #DIV/0!
Other assets | 24885405 | 74492310.69 | 95820510.69 | 66146383 | 29674127.69 | 69.03%
General vehicles | 104080 | 11950000 | 14514459 | 16332029 | -1817570 | 112.5%
Specialised vehicles | 2762652 | 40636944 | 44590250 | 31563094 | 13027156 | 70.78%
Plant & equipment | 562140 | 2449260 | 5135861 | 3952381 | 1183480 | 76.96%
Computers - hardware/equipment | 1644825 | 0 | -225116 | 0 | -225116 | 0%
Furniture and other office equipment | 13494807 | 9285458.69 | 9285458.69 | 6281681 | 3003777.69 | 67.65%
Abattoirs |  |  |  |  | 0 | #DIV/0!
Markets | 1929808 | 0 | 0 | 0 | 0 | 0%
Civic Land and Buildings | 1367648 | 1100000 | 1700000 | 711207 | 988793 | 41.84%
Other Buildings | 1903434 | 0 | 0 | 0 | 0 | 0%
Other Land |  |  |  |  | 0 | #DIV/0!
Surplus Assets - (Investment or Inventory) |  |  |  |  | 0 | #DIV/0!
Other | 1116011 | 9070648 | 20819598 | 7305991 | 13513607 | 35.09%
[5 empty] | 0 | #DIV/0!
Agricultural assets | 0 | 0 | 0 | 0 | 0 | #DIV/0!
List sub-class |  |  |  |  | 0 | #DIV/0!
[5 empty] | 0 | #DIV/0!
[5 empty] | 0 | #DIV/0!
Biological assets | 0 | 0 | 0 | 0 | 0 | #DIV/0!
List sub-class |  |  |  |  | 0 | #DIV/0!
[5 empty] | 0 | #DIV/0!
[5 empty] | 0 | #DIV/0!
Intangibles | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Computers - software & programming |  |  |  |  | 0 | #DIV/0!
Other |  |  |  |  | 0 | #DIV/0!
Total Capital Expenditure on new assets | 315628971 | 717277850.19 | 621910369.19 | 231123356 | 390787013.19 | 37.16%
Specialised vehicles | 0 | 40636944 | 0 | 31563094 | -31563094 | #DIV/0!
Refuse |  | 26260000 |  |  | 0 | 0%
Fire |  | 14376944 | 0 | 31563094 | -31563094 | #DIV/0!
Conservancy |  |  |  |  | 0
Ambulances |  |  |  |  | 0

## Appendix M (ii)
BUFFALO CITY METROPOLITAN MUNICIPALITY
CAPITAL EXPENDITURE ON RENEWAL OF EXISTING ASSETS BY ASSET CLASS/SUB-CLASS
APPENDIX M (ii)
Description | 2010/11 Audited Outcome | 2011/12 Original Budget | 2011/12 Adjusted Budget | YearTD Actual | YearTD Variance | % Exp vs. Budget
Infrastructure | 45532764 | 25505980 | 74703041 | 35969887 | 38733154 | 48.15%
Infrastructure - Road transport | 25565504 | 11992904 | 48106748 | 15545844 | 32560904 | 32.32%
Roads, Pavements & Bridges | 25565504 | 11992904 | 48106748 | 15545844 | 32560904 | 32.32%
Storm water | 0 | 0 | 0 | 0 | 0 | 0%
Infrastructure - Electricity | 17325692 | 7645000 | 12517097 | 12581499 | -64402 | 100.5%
Generation | 17325692 | 0 | 0 | 0 | 0 | 0%
Transmission & Reticulation | 0 | 3645000 | 7317097 | 7755187 | -438090 | 106%
Street Lighting | 0 | 4000000 | 5200000 | 4826312 | 373688 | 92.81%
Infrastructure - Water | 2372739 | 0 | 8308936 | 0 | 8308936 | 0%
Dams & Reservoirs |  |  |  |  | 0 | #DIV/0!
Water purification |  |  |  |  | 0 | #DIV/0!
Reticulation | 2372739 | 0 | 8308936 | 0 | 8308936 | 0%
Infrastructure - Sanitation | 0 | 5868076 | 3357842 | 6233095 | -2875253 | 185.6%
Reticulation | 0 | 5868076 | 3357842 | 6233095 | -2875253 | 185.6%
Sewerage purification |  |  |  |  | 0 | #DIV/0!
Infrastructure - Other | 268829 | 0 | 2412418 | 1609449 | 802969 | 66.72%
Waste Management | 0 | 0 | 1764845 | 1329726 | 435119 | 75.35%
Transportation | 268829 | 0 | 647573 | 279723 | 367850 | 43.2%
Gas |  |  |  |  | 0 | #DIV/0!
Other |  |  |  |  | 0 | #DIV/0!
Community | 14743309 | 12908106 | 24863690 | 5804772 | 19058918 | 23.35%
Parks & gardens | 0 | 0 | -197247 | 0 | -197247 | 0%
Sportsfields & stadia | 11156773 | 4626698 | 16058646 | 1559028 | 14499618 | 9.708%
Swimming pools |  |  |  |  | 0 | #DIV/0!
Community halls | 2295211 | 2792507 | 3418271 | 2496073 | 922198 | 73.02%
Libraries |  | 363795 | 363795 | 406901 | -43106 | 111.8%
Recreational facilities | 426045 | 1526982 | 2026982 | 844113 | 1182869 | 41.64%
Fire, safety & emergency |  |  |  |  | 0 | #DIV/0!
Security and policing |  |  |  |  | 0 | #DIV/0!
Buses |  |  |  |  | 0 | #DIV/0!
Clinics | 634363 | 3598124 | 2798124 | 498657 | 2299467 | 17.82%
Museums & Art Galleries |  |  |  |  | 0 | #DIV/0!
Cemeteries |  |  |  |  | 0 | #DIV/0!
Social rental housing |  |  |  |  | 0 | #DIV/0!
Other | 230917 |  | 395119 |  | 395119 | 0%
Heritage assets | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Buildings |  |  |  |  | 0 | #DIV/0!
Other |  |  |  |  | 0 | #DIV/0!
Investment properties | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Housing development |  |  |  |  | 0 | #DIV/0!
Other |  |  |  |  | 0 | #DIV/0!
Other assets | 21798900 | 8977194 | 10064283 | 5989678 | 4074605 | 59.51%
General vehicles | 15596587 | 0 | 0 | 0 | 0 | 0%
Specialised vehicles |  |  |  |  | 0 | #DIV/0!
Plant & equipment |  |  |  |  | 0 | #DIV/0!
Computers - hardware/equipment |  |  |  |  | 0 | #DIV/0!
Furniture and other office equipment | 450624 | 0 | 0 | 0 | 0 | 0%
Abattoirs |  |  |  |  | 0 | #DIV/0!
Markets | 2515015 | 3320000 | 2959895 | 519758 | 2440137 | 17.56%
Civic Land and Buildings | 144706 | 5497194 | 6910513 | 401971 | 6508542 | 5.817%
Other Buildings | 970320 | 0 | 0 | 0 | 0 | 0%
Other Land |  |  |  |  | 0 | #DIV/0!
Surplus Assets - (Investment or Inventory) |  |  |  |  | 0 | #DIV/0!
Other | 2121648 | 160000 | 193875 | 5067949 | -4874074 | 2614%
Agricultural assets | 0 | 0 | 0 | 0 | 0
List sub-class |  |  |  |  | 0
0
Biological assets | 0 | 0 | 0 | 0 | 0
List sub-class |  |  |  |  | 0
0
Intangibles | 0 | 0 | 0 | 0 | 0
Computers - software & programming |  |  |  |  | 0
Other |  |  |  |  | 0
Total Capital Expenditure on renewal of existing assets | 82074973 | 47391280 | 109631014 | 47764337 | 61866677 | 43.57%
Specialised vehicles | 0 | 0 | 0 | 0 | 0
Refuse |  |  |  |  | 0
Fire |  |  |  |  | 0
Conservancy |  |  |  |  | 0
Ambulances |  |  |  |  | 0

## Appendix N
BUFFALO CITY METROPOLITAN MUNICIPALITY
APPENDIX N
CAPITAL PROGRAMME BY PROJECT REPORT AS AT 30 JUNE 2012
Project Name | Vote number | Vote number | Vote number | Vote number | NT | NT | NT | NT | NT | NT | A5 | Service | 34a & 34b | New Asset | Renewal of Existing Asset | Funding (source) | Approved Budget | Adjustment | Rollover Adjustment Budget | Adjustment | Mid -Year Adjustment Budget | Expenditure | Current Month Expenditure | YTD Exp. | Commitments | Variance | % Expenditure vs Rollover Adjustment Budget | % Expenditure vs Aproved Budget | % Expenditure vs Mid year Adjustment Budget | Date of 1st IDP adoption | Ward | Land of Ownership | Services(BIA) (BIA= bulk infra aval) | Planning(EIA, Designs, Survey,) | Dispute(legal etc. |  | SCM process(stage) (date of adv if applicable) | Date of Expected completion | Comments | VOTE NUMBER
EXECUTIVE SUPPORT SERVICES
Councillor's office | 105005 | 6 | 01 | 1100 | 05 | 01 | 01 | 01 | 311 | 002 | Executive and Council | Support Services |  | Yes |  | Own Funds c/o | #VALUE! | 2060845 | #VALUE! |  | 2060845 | 279870.93 | -10545.36 | 269325.57 |  | 1791519.43 | #VALUE! | #VALUE! | 13.07% | [9 empty] | The specification for the the furniture has been done and the tender will be advertised very soon. | 105/005/6/01/1100
Upgrading of Sisa Dukashe, New Lands, Ndevana Stadium | 105005 | 6 | 76 | 1100 | 05 | 01 | 01 | 01 | 160 | 002 | Executive and Council | Amenities |  |  | Yes | Department of Sports, Arts & Culture c/o (SARC) | #VALUE! | 2272303 | #VALUE! |  | 2272303 | 268581.65 | 134697.47 | 403279.12 |  | 1869023.88 | #VALUE! | #VALUE! | 17.75% | [7 empty] | Newlands & Ndevana need to be re-advertised |  | SISA DUKASHE & GOMPO - Project is complete & handed over to Community Srvices Directorate, NEWLANDS & NDEVANA - Project is on termination stage & waiting for approval. | 105/005/6/76/1100
Upgrading of Bisho, Dimbaza, Peelton, Madramini & Victoria Grounds Stadium | 105005 | 6 | 76 | 1101 | 05 | 01 | 01 | 01 | 160 | 002 | Executive and Council | Amenities |  |  | Yes | Department of Sports, Arts & Culture c/o (SARC) | #VALUE! | 6598469 | #VALUE! |  | 6598469 | 116772.58 | 109994.01 | 226766.59 |  | 6371702.41 | #VALUE! | #VALUE! | 3.437% | [7 empty] | Bisho, Peelton and Dimbaza projects need to be re-advertised |  | BISHO, PEELTON, DIMBAZA - Contractors doing the work was terminated due to poor performance, LOWER MNGQESHA - No funds VICTORIA GROUNDS - project is complete and handed over to community services. Only renovation to Floodlights that requires R1.5m to upgrade | 105/005/6/76/1101
Upgrading of Tsholomnqa, Parkside, Needs Camp & North | 105005 | 6 | 76 | 1102 | 05 | 01 | 01 | 01 | 160 | 002 | Sports and Recreation | Amenities |  |  | Yes | Department of Sports, Arts & Culture c/o (SARC) | #VALUE! | 2208935 | #VALUE! |  | 2208935 | 589162.22 | 0 | 589162.22 |  | 1619772.78 | #VALUE! | #VALUE! | 26.67% | [9 empty] | TSHOLOMNQA, PARKSIDE & NORTHEND: Project is complete & handed over to community services. NEEDSCAMP - Project is complete & water problem in the area & issue is currently addressed by BCMM water section & Amatola Water. | 105/005/6/76/1102
Laptop - V Tokwe - A11/90 | 105012 | 5 | 05 | 1246 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services |  | Yes |  | Own Funds |  |  |  |  | 9000 | 0 | 0 | 0 |  | 9000 |  |  | 0%
Leiden Twinning - Floodplain | 120005 | 6 | 83 | 1100 | 05 | 10 | 01 | 01 | 070 | 002 | Water | Water |  |  | Yes | Leiden Platform c/o | #VALUE! | 488000 | #VALUE! |  | 488000 | 0 | 0 | 0 |  | 488000 | #VALUE! | #VALUE! | 0% | [9 empty] | Transfer of land in Duncan Village from EC Dept of Local Government and traditional Affairs still a challenge. Funding for Floodplain/Safe Park; multiyear project | 120/005/6/83/1100
Leiden Twinning - Solid Waste Drop-off Points | 120005 | 6 | 83 | 1101 | 05 | 10 | 01 | 01 | 100 | 002 | Waste Management | Cleansing |  |  | Yes | Leiden Platform c/o | #VALUE! | 974718 | #VALUE! |  | 974718 | 0 | 0 | 0 |  | 974718 | #VALUE! | #VALUE! | 0% | [9 empty] | SCM and legal challenges. - Multiyear project | 120/005/6/83/1101
Leiden Twinning - Sanitation | 120005 | 6 | 83 | 1102 | 05 | 10 | 01 | 01 | 070 | 002 | Executive and Council | Waste Water |  |  | Yes | Leiden Platform c/o | #VALUE! | 746897 | #VALUE! |  | 746897 | 628798.84 | 101306.23 | 730105.07 |  | 16791.93 | #VALUE! | #VALUE! | 97.75% | [9 empty] | Challenges with Cambridge Location project - Sanitation department to sort out and advise progress with opening of facilities. | 120/005/6/83/1102
Leiden Twinning Project - Solid Waste | 120005 | 6 | 83 | 1103 | 05 | 10 | 01 | 01 | 100 | 002 | Waste Management | Cleansing |  |  | Yes | Leiden Platform c/o | #VALUE! | 512606 | #VALUE! |  | 512606 | 0 | 0 | 0 |  | 512606 | #VALUE! | #VALUE! | 0% | [9 empty] | Solid waste project for 2012/2013 following study by Utrecht university in Netherlands. | 120/005/6/83/1103
3 x Computers & Accessories - A10/107 | 120010 | 5 | 05 | 1224 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services | Renewal-270 | Yes |  | Own Funds | #VALUE! | 25000 | #VALUE! |  | 22146 | 22145.66 | 0 | 22145.66 |  | 0.34 | #VALUE! | #VALUE! | 100% | [9 empty] | Actioned | 120/010/5/05/1224
3 x Computers, Accessories, plasma - A10/124 | 120010 | 5 | 05 | 1223 | 05 | 02 | 01 | 01 | 270 | 001 | Executive and Council | Support Services | Renewal-270 | Yes |  | Own Funds | #VALUE! | 32000 | #VALUE! |  | 32000 | 0 | 26044.04 | 26044.04 |  | 5955.96 | #VALUE! | #VALUE! | 81.39% | [9 empty] | Requistion for Additional computers to be purchased for staff at call centre. IT has requisition. | 120/010/5/05/1223
TOTAL : EXECUTIVE SUPPORT SERVICES | [10 empty] | 1 | [5 empty] | #VALUE! | 15919773 | #VALUE! | 0 | 15925919 | 1905331.88 | 361496.39 | 2266828.27 | 0 | 13659090.73 | #VALUE! | #VALUE! | 14.23%
MUNICIPAL MANAGER
Furniture | 205005 | 4 | 01 | 1154 | 05 | 01 | 01 | 01 | 270 | 001 | Planning & Development | Transport Planning | New-270 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 50000 | 0 | 0 | 0 |  | 50000 | #VALUE! | #VALUE! | 0% | [7 empty] | The procurement of Councillor's notebooks has commenced. At this stage ICT department is trying to further expedite the procurements of laptops for Councillors, it is envisaged that within this financial year funding for this project will be fully utilised. | 2012-06-01 | Arrangements to procure furniture for the MPAC chairpersorn is underway, this budget was made available during the budget adjustment process. Expenditure will be completed within this financial year. | 205/005/4/01/1154
Councillor's IT requirements (Laptops) | 205005 | 4 | 01 | 1001 | 05 | 01 | 01 | 01 | 270 | 001 | Executive and Council | Support Services | New-270 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 865125.09 | 26271.93 | 891397.02 |  | 108602.98 | #VALUE! | #VALUE! | 89.14% | [7 empty] | The procurement of Councillor's notebooks has commenced. At this stage ICT department is trying to further expedite the procurements of laptops for Councillors, it is envisaged that within this financial year funding for this project will be fully utilised. | 2012-06-01 | The departnment is satisfied with the current expenditure for this project and it is anticipated that the project will be completed within this financial year. | 205/005/4/01/1001
TOTAL : MUNICIPAL MANAGER | [10 empty] | 2 | [5 empty] | #VALUE! | 0 | #VALUE! | #VALUE! | 1050000 | 865125.09 | 26271.93 | 891397.02 | 0 | 158602.98 | #VALUE! | #VALUE! | 84.89%
0
CHIEF OPERATIONS OFFICER
Mdantsane Zone 18 CC Phase 2-P3 | 255005 | 4 | 36 | 1001 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 21 | BCM | Bulk services are available on this site | Consultant completed Engineering Designs however unable to proceed with procurement due to not having EIA renewal. EIA were to be completed in the beginning of 2011. | The Directorate of Development facilitation (Kamva Qwede) to fast tract the EIA. Biotechnology & Environmental Specialist Consultancy Cc has been appointed to complete the EIA. They advised Full EIA will have to be completed, this time frame (6 months). The delays will affect USDG funding expenditure. |  | Once EIA has been finalised , tenders for the provision of internal services will be called in February 2012 and award contract by May 2012 through BEC and BAC approval | EIA will be completed by January 2012. Tender advertisement and commencement of provision of internal services will take place commencing after January 2012. Project will be completed in the 2012/2013 financial year | Budget adjusted due to planning challenges which delayed implementation. | 255/005/4/36/1001
Manyano & Thembelihle Phase 2-P3 | 255005 | 4 | 36 | 1002 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 19055300 | 5300336.83 | 2486388.51 | 7786725.34 |  | 11268574.66 | #VALUE! | #VALUE! | 40.86% | 2011-06-30 | 17 | BCM | Bulk services are available on this site | Previously completed | Contractor appointed Kulanti has temporary moved off site citing various challenges minor |  | None | Internal services in the 2011/2012 financial year | The project was delayed by labour disputes between the contractor and the community which had been resolved. Revised schedule which was agreed with the contractor is behind and the contractor has been informed of the penalties. Budget will be rolled over to 2012/2013 financial year. | 255/005/4/36/1002
Second Creek (Turn Key)-P3 | 255005 | 4 | 36 | 1003 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 13940770 | 177427.99 | 0 | 177427.99 |  | 13763342.01 | #VALUE! | #VALUE! | 1.273% | 2011-06-30 | 19 | BCM | Bulk services are available on this site | Turn key approach (construction of internal services/top structure) | none |  | Adjudication report done. To present report to BEC and BAC in few weeks time.Time delays are being experienced in finalizing this award between PMU unit and SCM. The challenges have been escalated to senior management to addressed and finalized The delays will affected budget expenditure and may result in the reducing of the allocated budget should an award not be finalized urgently | Internal services are anticipated to be completed in the 2012/2013 financial year depending on the appointment of the contractor. | The service provider has been appointed for the construction of both internal service and top structure. It is anticipated that the project will be completed in 13/14 financial year, however the funding is fully committed. Budget could not be spent in the current financial year due to procurement challenges. | 255/005/4/36/1003
Masibambane-P3 | 255005 | 4 | 36 | 1004 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 250000 | 1851.35 | 22710.05 | 24561.4 |  | 225438.6 | #VALUE! | #VALUE! | 9.825% | 2011-06-30 | 17 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | N/A |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1004
Masibulele-P3 | 255005 | 4 | 36 | 1005 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 250000 | 1335.39 | 99736.31 | 101071.7 |  | 148928.3 | #VALUE! | #VALUE! | 40.43% | 2011-06-30 | 17 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1005
Velwano | 255005 | 4 | 36 | 1006 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 450000 | 546.3 | 24015.1 | 24561.4 |  | 425438.6 | #VALUE! | #VALUE! | 5.458% | 2011-06-30 | 14 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager) as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1006
Chris Hani Park Phase 3-P3 | 255005 | 4 | 36 | 1007 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 200000 | 2291.43 | -2291.43 | 0 |  | 200000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 12 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1007
Ilinge -P 3 | 255005 | 4 | 36 | 1008 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 240000 | 0 | 240000 |  | 360000 | #VALUE! | #VALUE! | 40% | 2011-06-30 | 12 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1008
Gwentshe Village- P3 | 255005 | 4 | 36 | 1009 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 50000 | 0 | 24561.4 | 24561.4 |  | 25438.6 | #VALUE! | #VALUE! | 49.12% | 2011-06-30 | 14 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1009
Fynbos Informal 1-P3 | 255005 | 4 | 36 | 1013 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 500000 | 0 | 77000 | 77000 |  | 423000 | #VALUE! | #VALUE! | 15.4% | 2011-06-30 | 10 | BCM | Turn Key Project Stage 1 - Appointment of professional team feasibility, geotechnical study internal services design top structure foundation design Stage 2 - Procurement of contractor to role out internal services top structure | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed for the planning, design and project management. It is anticipated that the project will be completed in 14/15 financial year, however the funding is fully committed. | 255/005/4/36/1013
Fynbos Informal 2-P3 | 255005 | 4 | 36 | 1014 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 500000 | 0 | 0 | 0 |  | 500000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 10 | BCM | Turn Key Project Stage 1 - Appointment of professional team feasibility, geotechnical study internal services design top structure foundation design Stage 2 - Procurement of contractor to role out internal services top structure | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed for the planning, design and project management. It is anticipated that the project will be completed in 14/15 financial year, however the funding is fully committed. | 255/005/4/36/1014
Ndacama-P3 | 255005 | 4 | 36 | 1015 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 10 | BCM | Turn Key Project Stage 1 - Appointment of professional team feasibility, geotechnical study internal services design top structure foundation design Stage 2 - Procurement of contractor to role out internal services top structure | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Delays in completion of the EIA will affect the appointment of the contractor for the provision of internal services and top structures. Project will be completed in 2012 / 2013 financial year. | Service provider has been appointed for the planning, design and project management. It is anticipated that the project will be completed in 14/15 financial year, however the funding is fully commited. | 255/005/4/36/1015
Mathemba Vuso-P3 | 255005 | 4 | 36 | 1017 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 300000 | 0 | 24561.4 | 24561.4 |  | 275438.6 | #VALUE! | #VALUE! | 8.187% | 2011-06-30 | 14 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1017
Deluxolo Village-P3 | 255005 | 4 | 36 | 1018 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 200000 | 0 | 0 | 0 |  | 200000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 20 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1018
Francis Mei-P3 | 255005 | 4 | 36 | 1019 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 100091 | 0 | 0 | 0 |  | 100091 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 20 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1019
Mahlangu Village-P3 | 255005 | 4 | 36 | 1020 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 200000 | 0 | 0 | 0 |  | 200000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 21 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1020
Sisulu Village-P3 | 255005 | 4 | 36 | 1021 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 300000 | 0 | 0 | 0 |  | 300000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 11 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1021
Winnie Mandela-P3 | 255005 | 4 | 36 | 1022 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 400000 | 0 | 0 | 0 |  | 400000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 17 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1022
Dacawa-P3 | 255005 | 4 | 36 | 1023 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 400000 | 0 | 0 | 0 |  | 400000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 12 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1023
Sunny South-P3 | 255005 | 4 | 36 | 1025 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 1760.3 | 81064.26 | 82824.56 |  | 517175.44 | #VALUE! | #VALUE! | 13.8% | 2011-06-30 | 31 | BCM | To prepare Bid Specification report to appoint consultants to manage the provision of services and top structure construction. | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved |  |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Project will be completed in 2012 / 2013 financial year. | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1025
Potsdam Unit p : Stage 2 P3 | 255005 | 4 | 36 | 1132 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1360000 | 7385.96 | 1352614.03 | 1359999.99 |  | 0.01 | #VALUE! | #VALUE! | 100% | 2011-06-30 | 31 | BCM | To prepare Bid Specification report to appoint consultants to manage the provision of services and top structure construction. | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved |  |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Project will be completed in 2012 / 2013 financial year. | Site verifications were done by the consultant, annual contractor is on site finalizing the rectification of the sewer connections. | 255/005/4/36/1132
Block yard TRA-P3 | 255005 | 4 | 36 | 1133 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2500000 | 0 | 0 | 0 |  | 2500000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 31 | BCM | To prepare Bid Specification report to appoint consultants to manage the provision of services and top structure construction. | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved |  |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Project will be completed in 2012 / 2013 financial year. | Procurement delays due to budget shortfall. Additional funding has been allocated in the mid - year adjustment budget. Contractor has been appointed. There are delays in the commencement of the contractor due to insufficient documentation (working drawings) that are still held by the liquidated consultant. the matter is being resolved between Engineering and Legal department | 255/005/4/36/1133
Reeston Phase 3 Stage 2-P3 | 255005 | 4 | 35 | 1001 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Human Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 15000000 | 2743815.66 | 1210651.2 | 3954466.86 |  | 11045533.14 | #VALUE! | #VALUE! | 26.36% | 2011-06-30 | 13 | BCM | Bulk services are available on this site | No challenges, | None |  | Contractor appointed in December 2011 | Final completion anticipated only in 13/14 financial year. | Contractor has been appointed and site handover was held on 14 March 2012.Contractor is progressing on site | 255/005/4/35/1001
DVRI Pilot project 323 units (Mekeni ,Competition site,Haven Hills) | 255005 | 4 | 35 | 1002 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Human Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 7241014 | 553944.86 | -487212.46 | 66732.4 |  | 7174281.6 | #VALUE! | #VALUE! | 0.9216% | 2011-06-30 | 19 | BCM | Completed | Completed | NONE |  | Completed | Project will be completed in the current (2012 / 2013) financial year. | Project is about 50% complete, the challenge is that the contract of the Contractor has expired legal department is assisting with the renewal of the contract. The City Manager has approved the renewal however he has instructed that the report to be tabled to BAC. The Delays in construction of Block Yard TRA will have direct impact on construction progress in Competition site. | 255/005/4/35/1002
Mdantsane Access/Buffalo | 255005 | 4 | 35 | 1003 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Human Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 13 | BCM | Provision of temporary water and sanitation | DDP is to complete detailed planning of projects for DVR - turnkey development. Currently in progress. | None |  | Upon approval of site development plan by Council, informal tenderers will be invited to undertake the provision of temporary water and sanitation. | 2012 / 2013 | Budget adjusted due to planning challenges which delayed implementation. | 255/005/4/35/1003
Reeston Phase 3 Stage 3 | 255005 | 4 | 35 | 1004 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Human Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 13 | BCM | Turn Key Project Stage 1 - App of professional team feasibility, geotechnical study internal services design top structure foundation design Stage 2 - Procurement of contractor to role out internal services top structure | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | Directorate of Planning is to complete detailed planning of projects for Duncan Village Redevelopment. Turnkey Development - To prepare bid specification document for the appointment of professional team in March 2012 to undertake project management and internal services designs. |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant by January 2012, designs to be completed by April 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | 2012 / 2013 Financial year | Service provider has been appointed. The project is a multi- year, allocated funding to be spent by June 2012. | 255/005/4/35/1004
Block yard TRA-P3 | 255005 | 4 | 35 | 1005 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | Human Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 668500 | 0 | 0 | 0 |  | 668500 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 6 | BCM | Provision of temporary water and sanitation | DDP is to complete detailed planning of projects for DVR - turnkey development. | None |  | Contractor(Orae Construction) has been appointed in December 2011, site handover will be in January 2012 | 2012 / 2013 Financial year | Procurement delays due to budget shortfall. Additional funding has been allocated in the mid - year adjustment budget. Contractor has been appointed. There are delays in the commencement of the contractor due to insufficient documentation (working drawings) that are still held by the liquidated consultant. the matter is being resolved between Engineering and Legal Departments | 255/005/4/35/1005
Computers & Computer Equip. - A10/72 | 255005 | 5 | 05 | 1202 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services | Renewal-270 | Yes |  | Own Funds | #VALUE! | 7000 | #VALUE! |  | 5225 | 5224.74 | 0 | 5224.74 |  | 0.26 | #VALUE! | #VALUE! | 100% | [7 empty] | IT department is in the process of procuring the service provider. | 2011 / 2012 Financial year | Project complete, 100% expenditure incurred. | 255/005/5/05/1202
Potsdam Unit P: Stage 2: 1000 units: P3: Infrastructure | 255005 | 6 | 75 | 1100 | 05 | 06 | 01 | 01 | 080 | 002 | Housing | Housing |  | Yes |  | Local Government & Housing c/o (LGH) | #VALUE! | 336462 | #VALUE! |  | 336462 | 0 | 78881.75 | 78881.75 |  | 257580.25 | #VALUE! | #VALUE! | 23.44% | [7 empty] | Complete | 2011 / 2012 Financial year | Funding has been reserved for rectification of sewer connections to 115 sites but not sufficient, additional funds were allocated in the mid year budget adjustment. The consultant has completed verifications, contractor is on site finalising the rectifications. | 255/005/6/75/1100
Accreditation | 255005 | 6 | 75 | 1101 | 05 | 06 | 01 | 01 | 080 | 002 | Housing | Housing |  | Yes |  | Local Government & Housing c/o (LGH) | #VALUE! | 33903 | #VALUE! |  | 33903 | 0 | 0 | 0 |  | 33903 | #VALUE! | #VALUE! | 0% | [7 empty] | Housing is in the process of procuring the service provider | 2011 / 2012 Financial year | It is projected that the allocated budget will be spent in this current financial year. | 255/005/6/75/1101
Z.Soga: P3: Infrastructure | 255005 | 6 | 75 | 1102 | 05 | 06 | 01 | 01 | 080 | 002 | Housing | Housing |  | Yes |  | Local Government & Housing c/o (LGH) | #VALUE! | 274097 | #VALUE! | -274097 | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | [7 empty] | Complete | 2011 / 2012 Financial year | Project complete and the vote has been adjusted accordingly | 255/005/6/75/1102
TOTAL : CHIEF OPERATIONS OFFICER | [10 empty] | 3 | [5 empty] | #VALUE! | 651462 | #VALUE! | #VALUE! | 65441265 | 9035920.81 | 4992680.12 | 14028600.93 | 0 | 51412664.07 | #VALUE! | #VALUE! | 21.44% | 0% | 1030% | #VALUE! | #VALUE! | 4.17e-07% | #VALUE! | #VALUE! | #VALUE! | #VALUE!
DIRECTORATE OF FINANCIAL SERVICES
KWT Civic Centre Payments Hall Upgrade | 330020 | 6 | 01 | 1001 | 05 | 02 | 01 | 01 | 120 | 002 | Budget & Treasury | Support Services | Renewal-312 |  | Yes | Own Funds c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 700000 | 36000 | 186207.87 | 222207.87 |  | 477792.13 | #VALUE! | #VALUE! | 31.74% | 182.7273 |  | Municipal |  | Designs completed | None |  | tender awarded for designs | 2012-12-31 | Project to be restarted in the next financial year when additional funds are available. | 330/020/6/01/1001
Laptop insurance claim | 315005 | 5 | 05 | 1218 | 05 | 02 | 01 | 01 | 270 | 001 | Budget & Treasury | Support Services |  | Yes |  | Own Funds | #VALUE! | 9000 | #VALUE! |  | 7492 | 7492 | 0 | 7492 |  | 0 | #VALUE! | #VALUE! | 100% | [9 empty] | Project completed. | 315/005/5/05/1218
Implementation of Intenda Electronic Software System | 320010 | 6 | 75 | 1103 | 05 | 02 | 01 | 01 | 270 | 002 | Budget & Treasury | Support Services |  | Yes |  | Department of Local Government & Traditional Affairs c/o | #VALUE! | 10643 | #VALUE! |  | 10643 | 0 | 0 | 0 |  | 10643 | #VALUE! | #VALUE! | 0% | [9 empty] | Consultants to be on site in April / May. | 320/010/6/75/1103
Meter reading handheld machines | 330015 | 4 | 01 | 1157 | 05 | 02 | 01 | 01 | 260 | 002 | Budget & Treasury | Support Services |  | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 2856000 | 3298.68 | 2069368.32 | 2072667 |  | 783333 | #VALUE! | #VALUE! | 72.57% | [9 empty] | Tender at Evaluation stage. | 330/015/4/01/1157
Upgrading of All Zone Offices - Mdantsane | 330020 | 6 | 01 | 1002 | 05 | 02 | 01 | 01 | 120 | 002 | Budget & Treasury | Support Services | Renewal-312 |  | Yes | Own Funds c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 182.7273 |  | under dispute |  | Not appointed | land sale to be invetigated by Land admin |  | Not awarded. | N/A | Project being handled by Development Planning. | 330/020/6/01/1002
TOTAL : DIRECTORATE OF FINANCIAL SERVICES | [10 empty] | 4 | [5 empty] | #VALUE! | 19643 | #VALUE! | #VALUE! | 3574135 | 46790.68 | 2255576.19 | 2302366.87 | 0 | 1271768.13 | #VALUE! | #VALUE! | 64.42%
DIRECTORATE OF CORPORATE SERVICES
BCM IT Requirements (All Directorates) | 415015 | 4 | 01 | 1002 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services | New-270 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 5000000 | 2334790.77 | 2281759.1 | 4616549.87 |  | 383450.13 | #VALUE! | #VALUE! | 92.33% | 2011/ 2012 financial year IDP | N/A | N/A | N/A | N/A | Not at this stage |  | Tender closes on the 13/01/2012 and evaluation of the tender will be done on the 17 January 2012. Award is expected by Friday 14 January 2012. | 31/03/2012 | There are still outstanding invoice awaiting to be captured for payment at SCM. | 415/015/4/01/1002
Laptop - S.Fuma - A10/116 | 405010 | 5 | 05 | 1225 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services | Renewal-270 | Yes |  | Own Funds | #VALUE! | 8600 | #VALUE! |  | 7493 | 7492.88 | 0 | 7492.88 |  | 0.12 | #VALUE! | #VALUE! | 100% | [7 empty] | Insurance claim, procurement in progress. |  | Insurance claim. Project completed | 405/010/5/05/1225
Laptop - L. Kapp - A11/116 | 405010 | 5 | 05 | 1259 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services |  | Yes |  | Own Funds |  |  |  |  | 9000 |  | 6656.8 | 6656.8 |  | 2343.2 |  |  | 73.96% | [9 empty] | Project completed.
6XDesktop Computers & 2x Printers - A11/98 | 415025 | 5 | 05 | 1247 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services |  | Yes |  | Own Funds |  |  |  |  | 45000 | 0 | 0 | 0 |  | 45000 |  |  | 0% | [9 empty] | Invoice awaiting to be captured for payment by the SCM.
Telecommunication network system | 415025 | 6 | 01 | 1003 | 05 | 02 | 01 | 01 | 270 | 002 | Corporate Services | Support Services | New-270 | Yes |  | Own Funds c/o | #VALUE! | 94390 | #VALUE! |  | 202275 | 0 | 73966.32 | 73966.32 |  | 128308.68 | #VALUE! | #VALUE! | 36.57% | 2011/2012 financial year IDP | N/A | N/A | N/A | N/A | Not at this stage |  | Project underway. Expenditure is expected to show during the month of January 2012. | 30/11/2011 | Invoice awaiting to be captured for payment by the SCM. | 415/025/6/01/1003
Integrated Enterprise Resource planning System | 415025 | 4 | 01 | 1003 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services | New-270 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 2000000 | 0 | 0 | 0 |  | 2000000 | #VALUE! | #VALUE! | 0% | 2011/2012 financial year IDP | N/A | N/A | N/A | N/A | Not at this stage |  | Procurement through SITA has commenced and in process of creating an order. Once the order is created the service provider can commence work. It is estimated that it the project will take 4 months. |  | Feasibility study roject has commenced and it is 77% complete. The funding will be carried over to the next financial year for implementation. | 415/025/4/01/1003
Conferencing system | 415025 | 6 | 01 | 1004 | 05 | 02 | 01 | 01 | 270 | 002 | Corporate Services | Support Services | New-270 | Yes |  | Own Funds c/o | #VALUE! | -338911 | #VALUE! |  | 260030 | 248858.06 | 0 | 248858.06 |  | 11171.94 | #VALUE! | #VALUE! | 95.7% | 2011/2012 financial year IDP | N/A | N/A | N/A | N/A | Not at this stage |  | The service provider is on site and has commenced work. The expenditure is expected to show in January 2012. | 30/11/2011 | The project is complete | 415/025/6/01/1004
Radio Data Network - Mdantsane | 415025 | 6 | 01 | 1005 | 05 | 02 | 01 | 01 | 270 | 002 | Corporate Services | Support Services | New-270 | Yes |  | Own Funds c/o | #VALUE! | 8762 | #VALUE! |  | 175231 | 158129.14 | 12500 | 170629.14 |  | 4601.86 | #VALUE! | #VALUE! | 97.37% | 2011/2012 financial year IDP | N/A | N/A | N/A | N/A | Not at this stage |  | The service provider is on site and has commenced work. The expenditure is expected to show in January 2012. | 30/11/2011 | The project is complete | 415/025/6/01/1005
TOTAL : DIRECTORATE OF CORPORATE SERVICES | [10 empty] | 5 | [5 empty] | #VALUE! | -227159 | #VALUE! | #VALUE! | 7699029 | 2749270.85 | 2374882.22 | 5124153.07 | 0 | 2574875.93 | #VALUE! | #VALUE! | 66.56%
DIRECTORATE OF ENGINEERING SERVICES
Electrification | 535025 | 4 | 56 | 1001 | 05 | 13 | 01 | 01 | 060 | 001 | Electricity | Electricity | New-60 | Yes |  | DoE(Intergrated National Electrification Programme) | #VALUE! | 0 | #VALUE! | #VALUE! | 26895000 | 11709780.79 | 8931420.04 | 20641200.83 |  | 6253799.17 | #VALUE! | #VALUE! | 76.75% | (see breakdown below) | [6 empty] | Purchase using Annual Tender | 2012-06-01 | ED329-Electrification Bulk Infrastructure Queenspark is a multi year project to be completed by 2016. Additional R5,895,000 was allocated by DoE . ED357-Cambridge Electrification completed. ED361-Potsdam Unit P Electrification contractor performing poorly ROLL OVER of R5, 561,016 is required in order to continue with the Project. ED360-Reeston Electrification completed. ED363-Kwaklifu Electrification delay with start of project ROLL OVER OF R1M will be required. | 535/025/4/56/1001
Replacement of Street Lights | 535025 | 4 | 25 | 1001 | 05 | 13 | 03 | 01 | 090 | 001 | Electricity | Electricity | Renewal-90 |  | Yes | Electricity Demand Side Management Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 4000000 | 3773287 | 153504 | 3926791 |  | 73209 | #VALUE! | #VALUE! | 98.17% | 2011-06-30 | 15, 16, 18, 19, 20 | BCM | YES | n/a | n/a |  | Purchase using Annual Tender | 2012-06-01 | Energy Efficient Lighting Exchange Mdantsane - Installation of Lighting completed - Invoice for R73 000.00 submitted to SCM | 535/025/4/25/1001
Laptop - A11/71 | 505005 | 5 | 05 | 1241 | 05 | 02 | 01 | 01 | 270 | 001 | Waste Water Management | Support Services | renewal-320 | Yes |  | Own Funds | #VALUE! | 4890900 | #VALUE! |  | 9500 | 0 | 7716.84 | 7716.84 |  | 1783.16 | #VALUE! | #VALUE! | 81.23% | [9 empty] | This vote is in respect of those assets that are replaced due to insurance claims. No expenditure is recorded against this vote as budget is transferred from this vote to individual capital votes when asset insurance claims are approved by insurers for those assets to be replaced. The original budget amount was R10 million and an amount of R5 109 100 has been transferred leaving a balance of R4 890 900. | 505/005/5/05/1241
West Bank Restitution | 525020 | 4 | 36 | 1028 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 15000000 | 10142767.32 | 4268.88 | 10147036.2 |  | 4852963.8 | #VALUE! | #VALUE! | 67.65% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | The Roads construction is currently attending to the snags. The Bulk Sanitation infrastructure - contractor has been appointed end of May 2012. The Bulk Water infrastructure - tender was advertised on the 1 June 2012 and has closed on the 3 July 2012. | 525/020/4/36/1028
Rural Roads Upgrade | 525020 | 4 | 36 | 1029 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | Renewal-30 |  | Yes | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 5000000 | 1366253.27 | 483424.34 | 1849677.61 |  | 3150322.39 | #VALUE! | #REF! | 36.99% | 2011-06-30 | 7 | BCMM | YES | N/A | n/a |  | Duncan Village (R500 000): Contractor on site, completing surfacing of existing gravel roads | 2012-03-30 | Insufficient funds for upgrade & stormwater | 525/020/4/36/1029
Upgrading and Rehabilitation of BCMM Roads - Duncan Village | 525020 | 4 | 36 | 1114 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 978710.95 | 978710.95 |  | 21289.05 | #VALUE! | #VALUE! | 97.87% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1114
Upgrading and Rehabilitation of BCMM Roads - Ducats | 525020 | 4 | 36 | 1115 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1250000 | 0 | 0 | 0 |  | 1250000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1115
Upgrading and Rehabilitation of BCMM Roads - Zwelitsha | 525020 | 4 | 36 | 1116 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 1285526.28 | 1285526.28 |  | -285526.28 | #VALUE! | #VALUE! | 128.6% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1116
Upgrading and Rehabilitation of BCMM Roads - Dimbaza | 525020 | 4 | 36 | 1117 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 579363.23 | 579363.23 |  | 420636.77 | #VALUE! | #VALUE! | 57.94% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1117
Upgrading and Rehabilitation of BCMM Roads - Phakamisa | 525020 | 4 | 36 | 1118 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1250000 | 0 | 0 | 0 |  | 1250000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1118
Upgrading and Rehabilitation of BCMM Roads - Scenery park / Reeston | 525020 | 4 | 36 | 1119 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 117732.98 | 117732.98 |  | 882267.02 | #VALUE! | #VALUE! | 11.77% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1119
Upgrading and Rehabilitation of BCMM Roads - Nonkcampa | 525020 | 4 | 36 | 1120 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 588377.19 | 588377.19 |  | 11622.81 | #VALUE! | #VALUE! | 98.06% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1120
Upgrading and Rehabilitation of BCMM Roads - Ndileka | 525020 | 4 | 36 | 1121 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 0 | 0 |  | 600000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1121
Upgrading and Rehabilitation of BCMM Roads - Zabalaza | 525020 | 4 | 36 | 1122 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 0 | 0 |  | 600000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1122
Upgrading and Rehabilitation of BCMM Roads - Upper Mngqesha | 525020 | 4 | 36 | 1123 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 279166.66 | 279166.66 |  | 320833.34 | #VALUE! | #VALUE! | 46.53% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1123
Upgrading and Rehabilitation of BCMM Roads - Tsholomnqa | 525020 | 4 | 36 | 1131 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 106789 | 0 | 98807.89 | 98807.89 |  | 7981.11 | #VALUE! | #VALUE! | 92.53% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1131
Mdantsane Roads | 525025 | 4 | 36 | 1027 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 42375700 | 4987950.05 | 14792166.69 | 19780116.74 |  | 22595583.26 | #VALUE! | #VALUE! | 46.68% | 2011-06-30 |  |  |  | Forwarded proposal for design to be reviewed |  |  | Seek BAC Support pertaining to award of annual contracts and utilization of learner contractors. | 2012-02-29 | TORs for consultants to be presented to BSC in early January 2012 and advertise tender before end of January 2012. Work is being identified for the provision of sidewalks and overlays that can be done by annual contractors. Learner contractors to implement project for the remainder of 2011/12 | 525/025/4/36/1027
Rehabilitation of Rural Roads Upgrade | 525025 | 4 | 36 | 1030 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | Renewal-30 |  | Yes | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 5000000 | 1550309.14 | 661905.95 | 2212215.09 |  | 2787784.91 | #VALUE! | #VALUE! | 44.24% | 2011-06-30 | 32 | BCMM | YES | N/A | n/a |  | Tsholomnqa (R500 000): Requested daily tender for material, road reserve cleared in September 2011 | 2012-03-30 | Insufficient funds for rehabilitation,stormwater challenges | 525/025/4/36/1030
West Bank Restitution | 525025 | 6 | 82 | 1100 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  |  | Yes | DBSA Phase 4 & 5 c/o | #VALUE! | 5577424 | #VALUE! |  | 4309413 | 1192639.58 | 3116772.61 | 4309412.19 |  | 0.81 | #VALUE! | #VALUE! | 100% | [7 empty] | Funds to be utilized for completion of phase 1 and phase 2 of the project. | 2012-03-15 | ongoing | 525/025/6/82/1100
West Bank Restitution | 525025 | 6 | 01 | 1103 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  |  | Yes | Own Funds c/o |  |  |  |  | 1268011 |  | 0 | 0 |  | 1268011 |  |  | 0% | [10 empty] | 525/025/6/01/1103
Rural and Urban Roads | 525025 | 6 | 82 | 1101 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  |  | Yes | DBSA Phase 4 & 5 c/o | #VALUE! | 10000000 | #VALUE! |  | 5757674 | 2130674.88 | 3070868.21 | 5201543.09 |  | 556130.91 | #VALUE! | #VALUE! | 90.34% | [7 empty] | Daily tenders for material purchasing issued and labour mobilzation being undertaken. | 2012-03-30 | ongoing | 525/025/6/82/1101
Rural and Urban Roads | 525025 | 6 | 01 | 1104 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  |  | Yes | Own Funds c/o |  |  |  |  | 4242326 |  | 0 | 0 |  | 4242326 |  |  | 0%
Scada equipment-A11/82 | 515023 | 5 | 05 | 1243 | 05 | 02 | 01 | 01 | 260 | 001 | Waste Water Management | Support Services | renewal-320 | Yes |  | Own Funds | #VALUE! | 4890900 | #VALUE! |  | 93000 | 79476 | -4 | 79472 |  | 13528 | #VALUE! | #VALUE! | 85.45% | [9 empty] | This vote is in respect of those assets that are replaced due to insurance claims. No expenditure is recorded against this vote as budget is transferred from this vote to individual capital votes when asset insurance claims are approved by insurers for those assets to be replaced. The original budget amount was R10 million and an amount of R5 109 100 has been transferred leaving a balance of R4 890 900. | 515/023/5/05/1243
Nord Avenue Pump station | 515010 | 4 | 36 | 1031 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! |  | #VALUE! | #VALUE! | 4000000 | 1988.91 | 628299 | 630287.91 |  | 3369712.09 | #VALUE! | #VALUE! | 15.76% | 2011-06-30 | 29 | BCMM | Bulk services are available on this site | EIA not required, designs and survey completed | n/a |  | Tenders will close on the 28 February 2012. | 6 months construction period. | None of the bidders met the requirements, the tender to be re-advertised | 515/010/4/36/1031
Quinera Treatment Works | 515010 | 4 | 36 | 1032 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! |  | #VALUE! | #VALUE! | 39000000 | 280571.73 | 0 | 280571.73 |  | 38719428.27 | #VALUE! | #VALUE! | 0.7194% | 2011-06-30 | 27 | BCMM | Bulk services are available on this site | EIA not required, designs and survey completed | n/a |  | Report To be tabled on the next special BAC of the 10 February 2012. | 8 months construction period. | Delays were due in change from an electrical, mechanical and civil engineering to a water works treatment approach, contract awarded but delayed due to lengthy adjudication process. | 515/010/4/36/1032
Waste Water Treatment Capacity (Zwelitsha) | 515026 | 4 | 36 | 1033 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 15000000 | 11223273.73 | 1182125.13 | 12405398.86 |  | 2594601.14 | #VALUE! | #VALUE! | 82.7% | 2011-06-30 | 41 | BCMM | Bulk services are available on this site | Currently busy with design for Phase 2. | n/a |  | Phase 1 – contractor appointed | 2012-08-01 | At implementation with some contractual dispute that is delaying the project. | 515/026/4/36/1033
Reeston Phase 3 Bulk Services Sewer | 515027 | 4 | 36 | 1034 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 23500000 | 643420.8 | 811013.01 | 1454433.81 |  | 22045566.19 | #VALUE! | #VALUE! | 6.189% | 2011-06-30 | 13, 16 | BCMM | Yes | Complete | n/a |  | Report in ACM's office for approval. | 2013-10-01 | At implementation with anticipated completion in April 2013 | 515/027/4/36/1034
Relocation of Miblocks - Mdantsane | 515027 | 4 | 36 | 1105 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 13, 16 | BCMM | Yes | Complete | n/a |  | Report in ACM's office for approval. | 2013-10-01 | Vote not yet open for transactions | 515/027/4/36/1105
Coastal & Midlands Infrastructure | 515027 | 4 | 36 | 1108 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 13, 16 | BCMM | Yes | Complete | n/a |  | Report in ACM's office for approval. | 2013-10-01 | Vote not yet open for transactions | 515/027/4/36/1108
Bufferstrip Sanitation - Mdantsane | 515028 | 4 | 36 | 1035 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 15000000 | 6723860.44 | 7713673.37 | 14437533.81 |  | 562466.19 | #VALUE! | #VALUE! | 96.25% | 2011-06-30 | 17, 20 | BCMM | Yes | Complete | n/a |  | Project at implementation stage | 2012-04-01 | At implementation with anticipated completion end of July 2012. | 515/028/4/36/1035
KWT & Bisho Infrastructure ( water) | 515028 | 4 | 36 | 1104 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 17, 20 | BCMM | Yes | Complete | n/a |  | Project at implementation stage | 2012-04-01 | Vote not yet open for transactions | 515/028/4/36/1104
Augmentation of Water Treatment Capacity - Umzonyana/Raising Upper weir | 515028 | 4 | 36 | 1106 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 17, 20 | BCMM | Yes | Complete | n/a |  | Project at implementation stage | 2012-04-01 | Vote not yet open for transactions | 515/028/4/36/1106
Amahleke | 515028 | 4 | 36 | 1107 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 17, 20 | BCMM | Yes | Complete | n/a |  | Project at implementation stage | 2012-04-01 | Vote not yet open for transactions | 515/028/4/36/1107
Mdantsane Sewers - Refurbishment | 515031 | 4 | 36 | 1036 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | Renewal-70 |  | Yes | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 5000000 | 2777477.87 | 2057102.97 | 4834580.84 |  | 165419.16 | #VALUE! | #VALUE! | 96.69% | 2011-06-30 | 14 | BCMM | Internal toilets | Planning underway – to be undertaken internally. | n/a |  | Replacement of Pitch Fibre Sewers utilising the Annual Contractor. | 2012-06-01 | Service providers completed the Mdantsane Prison sewer and sewer connections within Gqozo Village Phase 1 in Mdantsane. . | 515/031/4/36/1036
Flow Meter Chamber Unit - A11/16 | 515032 | 5 | 05 | 1237 | 05 | 02 | 01 | 01 | 260 | 001 | Waste Water Management | Waste Water |  | Yes |  | Own Funds |  |  |  | 37000 | 26430 | 26430 | 0 | 26430 |  | 0 |  |  | 100%
Diversion of Amalinda and Wilsonia effluent to Reeston | 515010 | 4 | 36 | 1037 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! |  | #VALUE! | #VALUE! | 22000000 | 2448074.64 | 4349648.57 | 6797723.21 |  | 15202276.79 | #VALUE! | #VALUE! | 30.9% | 2011-06-30 | 12, 13, 16 | BCMM | Yes | Complete | n/a |  | Report recommended by the special BAC of the 7 February 2012. | 2013-02-01 | Wilsonia Interceptor Phase 1: An appointment has been made at the end of March 2012 with anticipated completion in March 2013 and drilling contract (investigation phase2) contractor has been appointed in May 2012 | 515/010/4/36/1037
Leak Detector Machine - A10/67 | 520005 | 5 | 05 | 1208 | 05 | 02 | 01 | 01 | 260 | 001 | Water | Water | Renewal-260 | Yes |  | Own Funds | #VALUE! | 232000 | #VALUE! |  | 232000 | 0 | 135182 | 135182 |  | 96818 | #VALUE! | #VALUE! | 58.27% | [9 empty] | Tender closed on 02 February 2012 and all tenders were non responsive, therefore it will be re-advertised. | 520/005/5/05/1208
Augmentation of Water Treatment Capacity - Umzonyana/Raising Upper weir | 520015 | 4 | 36 | 1038 | 05 | 12 | 01 | 01 | 040 | 001 | Water | Water | New-40 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 5000000 | 4948137.25 | 36285.95 | 4984423.2 |  | 15576.8 | #VALUE! | #VALUE! | 99.69% | 2011-06-30 | 1-31,33 |  | Upgrading of the bulk services are underway | COMPLETE | N/a |  | Project at implementation stage | 2014-06-30 | Roll over. Multi year project | 520/015/4/36/1038
Inland Rural Sanitation (Dimbaza Villages,Ngxwalane and Kwalini) | 515010 | 4 | 36 | 1040 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 36000000 | 13812757.91 | 2898815.19 | 16711573.1 |  | 19288426.9 | #VALUE! | #VALUE! | 46.42% | 2011-06-30 | 34, 36 | Private | n/a | Terms of reference complete. Implementation list of project areas is being finalised. | n/a |  | Report was approved by BSC subject to approval by ACM to split the Sanitation Project. Awaiting approval from ACM. | 2013-12-01 | Phase 2 delayed due to public participation processes that were conducted between August and December 2011. The tender report is with committees. | 515/010/4/36/1040
Eastern Beach Sewers | 515010 | 4 | 36 | 1100 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2000000 | 741940.97 | 1169293.44 | 1911234.41 |  | 88765.59 | #VALUE! | #VALUE! | 95.56% | 2011-06-30 | 34, 36 | Private | n/a | Terms of reference complete. Implementation list of project areas is being finalised. | n/a |  | Report was approved by BSC subject to approval by ACM to split the Sanitation Project. Awaiting approval from ACM. | 2013-12-01 | The appointed service provider is currently finalising the contract documentation for the eastern beach sewer. The EIA is in the process of being submitted to DEAT for approval. Funds for this phase of the project are fully committed for this financial year. | 515/010/4/36/1100
Chemical toilets | 515010 | 4 | 36 | 1101 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2000000 | 0 | 2000000 | 2000000 |  | 0 | #VALUE! | #VALUE! | 100% | 2011-06-30 | 34, 36 | Private | n/a | Terms of reference complete. Implementation list of project areas is being finalised. | n/a |  | Report was approved by BSC subject to approval by ACM to split the Sanitation Project. Awaiting approval from ACM. | 2013-12-01 | Contracts from last financial year 2010/11 have been completed. New contracts for this year to be advertised before end of February 2012. | 515/010/4/36/1101
Sludge handling facility | 515010 | 4 | 36 | 1102 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2800000 | 300780 | 806384.5 | 1107164.5 |  | 1692835.5 | #VALUE! | #VALUE! | 39.54% | 2011-06-30 | 34, 36 | Private | n/a | Terms of reference complete. Implementation list of project areas is being finalised. | n/a |  | Report was approved by BSC subject to approval by ACM to split the Sanitation Project. Awaiting approval from ACM. | 2013-12-01 | Service providers undertook the rehabilitation of the sludge drying beds at the Mdantsane East WWTW. Funding recieved in March 2012. Delays with the delivery of media for drying beds. | 515/010/4/36/1102
Winterstrand Water Supply | 515010 | 4 | 36 | 1103 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 34, 36 | Private | n/a | Terms of reference complete. Implementation list of project areas is being finalised. | n/a |  | Report was approved by BSC subject to approval by ACM to split the Sanitation Project. Awaiting approval from ACM. | 2013-12-01 | An annual contractor is to be used to install the emergency pipeline to Winterstrand. | 515/010/4/36/1103
Insurance vehicle replacement - M10/33 | 515010 | 5 | 05 | 1221 | 05 | 02 | 01 | 01 | 250 | 001 | Waste Water Management | Other - BCM Fleet |  | Yes |  | Own Funds | #VALUE! | 155000 | #VALUE! | 0 | 155000 | 0 | 144605.2 | 144605.2 |  | 10394.8 | #VALUE! | #VALUE! | 93.29% | [10 empty] | 515/010/5/05/1221
Quinera Treatment Works | 515010 | 6 | 61 | 1100 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 8508421 | 0 | 0 | 0 |  | 8508421 | #VALUE! | #VALUE! | 0% | [9 empty] | Tender report being considered by the Bid Committees. | 515/010/6/61/1100
Bufferstrip Sanitation - Mdantsane | 515010 | 6 | 61 | 1101 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 201328 | 0 | 0 | 0 |  | 201328 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 515/010/6/61/1101
Construct. High level reservoir - Breidbach | 515010 | 6 | 61 | 1104 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | [10 empty] | 515/010/6/61/1104
Bulk Water Supply - Needscamp | 515010 | 6 | 61 | 1108 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | [10 empty] | 515/010/6/61/1108
Rural Sanitation | 515010 | 6 | 61 | 1109 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 15000000 | 0 | 0 | 0 |  | 15000000 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 515/010/6/61/1109
Winterstrand Water Supply | 520005 | 4 | 36 | 1136 | 05 | 10 | 01 | 01 | 070 | 001 | Water | Water |  | Yes |  | Urban Settlement Development Grant |  |  |  | 2000000 | 2000000 | 84979.07 | 1799715.65 | 1884694.72 |  | 115305.28 |  |  | 94.23% | [9 empty] | Roll over. Multi year project under construction and to be completed in October 2012 with funding for 2012/2013. | 520/005/4/36/1136
Insurance vehicle replacement - M10/172 | 520005 | 5 | 05 | 1220 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | Own Funds | #VALUE! | 500000 | #VALUE! |  | 500000 | 0 | 0 | 0 |  | 500000 | #VALUE! | #VALUE! | 0% | [9 empty] | Funds allocated 11 November 2011. Fleet Management to purchase. | 520/005/5/05/1220
Bulk Water Supply - Needscamp | 520005 | 6 | 61 | 1120 | 05 | 05 | 01 | 01 | 070 | 002 | Water | Water |  | Yes |  | Municipal Infrastructure Grant c/o |  |  |  | 5300000 | 5300000 | 0 | 0 | 0 |  | 5300000 |  |  | 0% | [9 empty] | Mig roll over was approved in February 2012 and tender is at BAC stage, part of the fund will be utilised on the upgrading of the water scheme in ward 33 that is on-going.Awaiting letter of award. ROLL OVER TO 2012/13
Bulk Water Supply Newlands and other areas | 520021 | 4 | 36 | 1041 | 05 | 12 | 01 | 01 | 040 | 001 | Water | Water | New-40 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 428404.5 | 376857.94 | 805262.44 |  | 194737.56 | #VALUE! | #VALUE! | 80.53% | 2011-06-30 |  | BCMM | n/a | n/a | N/a |  | Implemented in house | 2012-06-01 | Spent | 520/021/4/36/1041
Augmentation of Water Treatment Capacity - Umzonyana/Raising Upper weir | 520021 | 4 | 36 | 1139 | 05 | 10 | 01 | 01 | 070 | 001 | Water | Water |  | Yes |  | Urban Settlement Development Grant |  |  |  | 2000000 | 2000000 | 845061.15 | 347063.14 | 1192124.29 |  | 807875.71 |  |  | 59.61% | [9 empty] | Roll over. Multi year project | 520/021/4/36/1139
Ward 33 Bulk Water Supply Scheme | 520025 | 4 | 36 | 1042 | 05 | 12 | 01 | 01 | 040 | 001 | Water | Water | New-40 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 7000000 | 1498734.01 | 790313.34 | 2289047.35 |  | 4710952.65 | #VALUE! | #VALUE! | 32.7% | 2011-06-30 |  |  | To be installed | COMPLETE | N/a |  | Report to be tabled in the next special BAC of the 10 February 2012. | 2013-06-01 | Awaiting letter of award. ROLL OVER TO 2012/13 | 520/025/4/36/1042
Bulk Water Supply Coastal Areas | 520025 | 4 | 36 | 1043 | 05 | 12 | 01 | 01 | 040 | 001 | Water | Water | New-40 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 8000000 | 7775042.22 | 690.35 | 7775732.57 |  | 224267.43 | #VALUE! | #VALUE! | 97.2% | 2011-06-30 |  |  | To be installed | COMPLETE | N/a |  | Project at implementation stage | 2012-04-01 | roll over, multi year project. Phase 1E and 1F have been completed. | 520/025/4/36/1043
KWT & Bisho Infrastructure ( water) | 520025 | 4 | 36 | 1137 | 05 | 10 | 01 | 01 | 070 | 001 | Water | Water |  | Yes |  | Urban Settlement Development Grant |  |  |  | 2500000 | 2500000 | 2165422.73 | -2165422.73 | 0 |  | 2500000 |  |  | 0% | [9 empty] | Spent | 520/025/4/36/1137
Amahleke | 520025 | 4 | 36 | 1140 | 05 | 10 | 01 | 01 | 070 | 001 | Water | Water |  | Yes |  | Urban Settlement Development Grant |  |  |  | 1000000 | 1000000 | 975349.32 | -975349.32 | 0 |  | 1000000 |  |  | 0% | [9 empty] | Committed for full expenditure | 520/025/4/36/1140
Amahleke Water Supply | 520025 | 6 | 61 | 1102 | 05 | 12 | 01 | 01 | 040 | 001 | Water | Water | New-40 | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 961009 | 961009 | 0 | 961009 |  | 0 | #VALUE! | #VALUE! | 100% | 2011-06-30 |  |  | To be installed | COMPLETE | N/a |  | Report to be tabled in the next special BAC of the 10 February 2012. | 2013-06-01 | spent | 520/025/6/61/1102
Bulk water supply - Newlands & other areas | 520025 | 6 | 61 | 1103 | 05 | 12 | 01 | 01 | 040 | 001 | Water | Water | New-40 | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 47927 | 0 | 41868 | 41868 |  | 6059 | #VALUE! | #VALUE! | 87.36% | 2011-06-30 |  |  | To be installed | COMPLETE | N/a |  | Report to be tabled in the next special BAC of the 10 February 2012. | 2013-06-01 | Roll over. Multi year project | 520/025/6/61/1103
Construct. High level reservoir - Breidbach | 520025 | 6 | 61 | 1119 | 05 | 05 | 01 | 01 | 070 | 002 | Water | Water |  | Yes |  | Municipal Infrastructure Grant c/o |  |  |  | 100000 | 100000 | 100000 | 0 | 100000 |  | 0 |  |  | 100% | [9 empty] | spent | 520/025/6/61/1119
Relocation of Miblocks - Mdantsane | 520026 | 4 | 36 | 1138 | 05 | 10 | 01 | 01 | 070 | 001 | Water | Water |  | Yes |  | Urban Settlement Development Grant |  |  |  | 3000000 | 3000000 | 2352255.74 | -2352255.74 | 0 |  | 3000000 |  |  | 0% | [9 empty] | spent | 520/026/4/36/1138
Laptop - A11/53 | 520026 | 5 | 05 | 1231 | 05 | 02 | 01 | 01 | 270 | 001 | Water | Water |  | Yes |  | Own Funds | #VALUE! | 9000 | #VALUE! |  | 9000 | 7741 | 0 | 7741 |  | 1259 | #VALUE! | #VALUE! | 86.01% | 2011-06-30 |  |  | To be installed | COMPLETE | N/a |  | Replacement of laptop | 2012-03-01 | Request to procure the laptop has been submitted to IT | 520/026/5/05/1231
Insurance vehicle insurance - M10/42 | 520026 | 5 | 05 | 1238 | 05 | 02 | 01 | 01 | 250 | 001 | Water | Water |  | Yes |  | Own Funds |  |  |  | 560000 | 560000 | 0 | 0 | 0 |  | 560000 |  |  | 0% | [10 empty] | 520/026/5/05/1238
Coastal & Midlands Infrastructure | 520030 | 4 | 36 | 1141 | 05 | 10 | 01 | 01 | 070 | 001 | Water | Water |  | Yes |  | Urban Settlement Development Grant |  |  |  | 1500000 | 1500000 | 1485353.84 | -1076619.74 | 408734.1 |  | 1091265.9 |  |  | 27.25% | [9 empty] | spent
Building Security | 505005 | 6 | 01 | 1006 | 05 | 11 | 05 | 13 | 120 | 002 | Waste Water Management | Electricity | New-312 |  | Yes | Own Funds c/o | #VALUE! | -174341 | #VALUE! |  | 125659 | 38814.69 | 18700 | 57514.69 |  | 68144.31 | #VALUE! | #VALUE! | 45.77% | [7 empty] | R117,000 has been paid in June for upgrading of CCTV system in the Engineering Building and the rest will be spent on improving lighting at the Chiselhurst Depot |  | Lights have been installed, invoice awaited to settle costs. More work to be done at the entrance of the Office bulidng. | 505/005/6/01/1006
Electrification - Counterfunding Reeston & Other Areas | 535005 | 6 | 01 | 1007 | 05 | 13 | 01 | 01 | 060 | 002 | Electricity | Electricity | New-60 |  | Yes | Own Funds c/o | #VALUE! | -2800000 | #VALUE! |  | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! |  | - | N/A | N/A | Complete | n/a |  |  | 2011-10-31 | NO BUDGET - Completed 2010/11 | 535/005/6/01/1007
Heritage Desk, 5 Tier Bookcase - A11/13 | 535005 | 5 | 05 | 1207 | 05 | 02 | 01 | 01 | 270 | 001 | Electricity | Electricity |  | Yes |  | Own Funds | #VALUE! | 24000 | #VALUE! |  | 24000 | 20696.35 | 0 | 20696.35 |  | 3303.65 | #VALUE! | #VALUE! | 86.23% | [9 empty] | Insurance Claim - Completed | 535/005/5/05/1207
Replacement: Brushcutters- A11/19 | 535010 | 5 | 05 | 1227 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Electricity |  | Yes |  | Own Funds | #VALUE! | 6400 | #VALUE! |  | 6400 | 5594.75 | 0 | 5594.75 |  | 805.25 | #VALUE! |  | 87.42% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1227
500KVA Mini-substation - Cemetery -RD -A11/32 | 535010 | 5 | 05 | 1228 | 05 | 02 | 01 | 01 | 060 | 001 | Electricity | Electricity |  | Yes |  | Own Funds | #VALUE! | 283600 | #VALUE! |  | 283600 | 248759.51 | 18725 | 267484.51 |  | 16115.49 | #VALUE! |  | 94.32% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1228
200KVA Pole Transformer: Taleni - A10/91 | 535010 | 5 | 05 | 1229 | 05 | 02 | 01 | 01 | 060 | 001 | Electricity | Electricity |  | Yes |  | Own Funds | #VALUE! | 53800 | #VALUE! |  | 53800 | 40716.96 | 0 | 40716.96 |  | 13083.04 | #VALUE! |  | 75.68% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1229
200KVA Pole Transformer: Taleni - A11/25 | 535010 | 5 | 05 | 1230 | 05 | 02 | 01 | 01 | 060 | 001 | Electricity | Electricity |  | Yes |  | Own Funds | #VALUE! | 46500 | #VALUE! |  | 46500 | 40716.96 | 0 | 40716.96 |  | 5783.04 | #VALUE! |  | 87.56% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1230
Dunlop Substation - A10/111 | 535010 | 5 | 05 | 1251 | 05 | 02 | 01 | 01 | 260 | 001 | Electricity | Electricity |  | Yes |  | Own Funds |  |  |  |  | 371000 | 370581.51 | 0 | 370581.51 |  | 418.49 |  |  | 99.89% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1251
Robbie de lange substation - A10/85 | 535010 | 5 | 05 | 1252 | 05 | 02 | 01 | 01 | 260 | 001 | Electricity | Electricity |  | Yes |  | Own Funds |  |  |  |  | 170870 | 170867.32 | -38771.7 | 132095.62 |  | 38774.38 |  |  | 77.31% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1252
Minibus : Ray Craib Crescent - A11/02 | 535010 | 5 | 05 | 1253 | 05 | 02 | 01 | 01 | 260 | 001 | Electricity | Electricity |  | Yes |  | Own Funds |  |  |  |  | 71000 | 62047.7 | -59561.7 | 2486 |  | 68514 |  |  | 3.501% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1253
Substation : Dunga Street - A11/26 | 535010 | 5 | 05 | 1254 | 05 | 02 | 01 | 01 | 260 | 001 | Electricity | Electricity |  | Yes |  | Own Funds |  |  |  |  | 20300 | 17777.57 | 0 | 17777.57 |  | 2522.43 |  |  | 87.57% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1254
Ring main unit: Shiden Drive - A10/93 | 535010 | 5 | 05 | 1255 | 05 | 02 | 01 | 01 | 260 | 001 | Electricity | Electricity |  | Yes |  | Own Funds |  |  |  |  | 79900 | 70017.75 | 0 | 70017.75 |  | 9882.25 |  |  | 87.63% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1255
Radio Repeater Transformer - A11/39 | 535010 | 5 | 05 | 1256 | 05 | 02 | 01 | 01 | 260 | 001 | Electricity | Electricity |  | Yes |  | Own Funds |  |  |  |  | 9960 | 9960 | 0 | 9960 |  | 0 |  |  | 100% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1256
High Mast Lighting - Sweetwaters | 535025 | 4 | 01 | 1150 | 05 | 13 | 01 | 01 | 090 | 001 | Electricity | Electricity | Renewal-60 |  | Yes | Own Funds | #VALUE! |  | #VALUE! | #VALUE! | 900000 | 0 | 602927.76 | 602927.76 |  | 297072.24 | #VALUE! | #VALUE! | 66.99% |  | 4 | BCM | n/a | n/a | n/a |  |  | 2012-06-01 | Hi-mast project awarded in February 2012. Completed | 535/025/4/01/1150
Streetlighting & Hymast | 535025 | 4 | 01 | 1151 | 05 | 13 | 03 | 01 | 090 | 001 | Electricity | Electricity | Renewal-60 |  | Yes | Own Funds | #VALUE! |  | #VALUE! | #VALUE! | 300000 | 75044.37 | 221549.04 | 296593.41 |  | 3406.59 | #VALUE! | #VALUE! | 98.86% |  | 4 | BCM | n/a | n/a | n/a |  |  | 2012-06-01 | Completed | 535/025/4/01/1151
Electrification - Counterfunding Reeston & Other areas | 535025 | 4 | 01 | 1152 | 05 | 13 | 01 | 01 | 060 | 001 | Electricity | Electricity | Renewal-60 |  | Yes | Own Funds | #VALUE! |  | #VALUE! | #VALUE! | 2000000 | 0 | 0 | 0 |  | 2000000 | #VALUE! | #VALUE! | 0% |  | 4 | BCM | n/a | n/a | n/a |  |  | 2012-06-01 | Funding allocated in March 2012 - Adjustment Budget - Top up funding for electrification projects and electrification of infill - ROLL OVER REQUESTED | 535/025/4/01/1152
Upgrade of Bulk Electricity Infrastructure | 535025 | 4 | 01 | 1153 | 05 | 13 | 01 | 01 | 060 | 001 | Electricity | Electricity | Renewal-60 |  | Yes | Own Funds | #VALUE! |  | #VALUE! | #VALUE! | 1889492 | 1875410.04 | -335092.79 | 1540317.25 |  | 349174.75 | #VALUE! | #VALUE! | 81.52% |  | 4 | BCM | n/a | n/a | n/a |  |  | 2012-06-01 | Switchgear ordered Requisitions submitted to SCM 7/3/12 - some items have a long delivery period. A number of Panels have arrived payments are in process. ROLL OVER REQUESTED | 535/025/4/01/1153
Electricity Building Upgrade- Ablution Blocks | 535025 | 6 | 01 | 1008 | 05 | 13 | 01 | 01 | 060 | 002 | Electricity | Electricity | Renewal-60 |  | Yes | Own Funds c/o | #VALUE! | 20923 | #VALUE! |  | 165923 | 81619.62 | 71796.24 | 153415.86 | 225212.1 | 12507.14 | #VALUE! | #VALUE! | 92.46% |  | 4 | BCM | n/a | n/a | n/a |  |  | 2012-06-01 | Tender awarded to service provider for the building of generator room at the Beacon Bay Civic Centre - completed | 535/025/6/01/1008
Upgrade-Bulk Electricity Infrastructure | 535025 | 4 | 82 | 1100 | 05 | 13 | 01 | 01 | 060 | 001 | Electricity | Electricity | Renewal-60 |  | Yes | DBSA Phase 4 |  |  |  |  | 3662418 |  | 3662418 | 3662418 |  | 0 |  |  | 0%
Upgrade-Bulk Electricity Infrastructure | 535025 | 4 | 82 | 1101 | 05 | 13 | 01 | 01 | 060 | 001 | Electricity | Electricity | Renewal-60 |  | Yes | DBSA Phase 5 |  |  |  |  | 2348090 |  | 2348090 | 2348090 |  | 0 |  |  | 0%
Insurance vehicle replacement-M10/103 | 525025 | 5 | 05 | 1240 | 05 | 02 | 01 | 01 | 250 | 001 | Road Transport | Support Services | renewal-320 | Yes |  | Own Funds | #VALUE! | 4890900 | #VALUE! |  | 450000 | 0 | 0 | 0 |  | 450000 | #VALUE! | #VALUE! | 0% | [9 empty] | This vote is in respect of those assets that are replaced due to insurance claims. No expenditure is recorded against this vote as budget is transferred from this vote to individual capital votes when asset insurance claims are approved by insurers for those assets to be replaced. The original budget amount was R10 million and an amount of R5 109 100 has been transferred leaving a balance of R4 890 900. | 525/025/5/05/1240
Upgrade Electricity Reticulation (KWT and Coastal) | 535025 | 6 | 01 | 1009 | 05 | 13 | 01 | 01 | 060 | 002 | Electricity | Electricity | Renewal-60 |  | Yes | Own Funds c/o | #VALUE! | -3448826 | #VALUE! |  | 51174 | 50945.81 | 0 | 50945.81 |  | 228.19 | #VALUE! | #VALUE! | 99.55% |  |  |  |  | Complete |  |  |  |  | Completion of Greenacres and Gullsway - project complete | 535/025/6/01/1009
Vehicle V382 - FBR 776 EC - M09/182 | 525025 | 5 | 05 | 1244 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | Own Funds |  |  |  |  | 510000 | 0 | 0 | 0 |  | 510000 |  |  | 0% | [9 empty] | insurance claim | 525/025/5/05/1244
Rehabilitation of BCM bridges and culverts( Breidbach, Dimbaza, Quigney) | 525025 | 6 | 01 | 1010 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | Renewal-30 |  | Yes | Own Funds c/o | #VALUE! | -19908 | #VALUE! |  | 1972996 | 1583700.96 | 389295.04 | 1972996 |  | 0 | #VALUE! | #VALUE! | 100% |  | 34, 36, 3 | BCMM | N/A | N/A | No despute |  |  |  | R51,174 used for completion of Capital Project in Gullsway & Greenacres switch houses. Payment for R 23 295 is in process for work completed. Insufficient Capital funding to carry out any additional electrical projects | 525/025/6/01/1010
Rehabilitation of Rural Roads Upgrade | 525025 | 6 | 61 | 1105 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 856328 | 0 | 0 | 0 |  | 856328 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1105
Upgrading and Rehabilitation of BCMM Roads - Nomgwadla | 525025 | 6 | 61 | 1110 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 0 | 0 |  | 600000 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1110
Upgrading and Rehabilitation of BCMM Roads - Ngxwalana | 525025 | 6 | 61 | 1111 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 0 | 0 |  | 600000 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1111
Upgrading and Rehabilitation of BCMM Roads - Msintsini | 525025 | 6 | 61 | 1112 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 0 | 0 |  | 600000 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1112
Upgrading and Rehabilitation of BCMM Roads - Kwelera | 525025 | 6 | 61 | 1113 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 0 | 0 |  | 600000 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1113
Upgrading and Rehabilitation of BCMM Roads - Balasi | 525025 | 6 | 61 | 1114 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 0 | 0 |  | 600000 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1114
Upgrading and Rehabilitation of BCMM Roads - Ncera Villages 5-9 | 525025 | 6 | 61 | 1115 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 588157.89 | 588157.89 |  | 411842.11 | #VALUE! | #VALUE! | 58.82% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1115
Upgrading and Rehabilitation of BCMM Roads - Kuni, Needscamp | 525025 | 6 | 61 | 1116 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 0 | 0 |  | 1000000 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1116
Upgrading and Rehabilitation of BCMM Roads - Tsholomqa | 525025 | 6 | 61 | 1117 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 493211 | 0 | 465320.26 | 465320.26 |  | 27890.74 | #VALUE! | #VALUE! | 94.35% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1117
Rehabilitation of underground stormwater - Storm water Management System | 525025 | 4 | 36 | 1109 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater |  | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1100000 | 470000 | 259473.64 | 729473.64 |  | 370526.36 | #VALUE! | #VALUE! | 66.32% | [10 empty] | 525/025/4/36/1109
Rehabilitation of underground stormwater - Amalinda forest | 525025 | 4 | 36 | 1110 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater |  | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | 1000000 | 1000000 | 0 | 318749.12 | 318749.12 |  | 681250.88 | #VALUE! | #VALUE! | 31.87% | [10 empty] | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012.
Rehabilitation of underground stormwater - Duncan village | 525025 | 4 | 36 | 1111 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater |  | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 243808.28 | 243808.28 |  | 756191.72 | #VALUE! | #VALUE! | 24.38% | [10 empty] | 525/025/4/36/1111
Rehabilitation of underground stormwater - Dimbaza | 525025 | 4 | 36 | 1112 | 05 | 02 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater |  | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 0 | 0 |  | 1000000 | #VALUE! | #VALUE! | 0% | [10 empty] | 525/025/4/36/1112
Rehabilitation of underground stormwater - West Bank | 525025 | 4 | 36 | 1113 | 05 | 02 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater |  | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1100000 | 894852.18 | 41677.95 | 936530.13 |  | 163469.87 | #VALUE! | #VALUE! | 85.14% | [10 empty] | 525/025/4/36/1113
Upgrade Augmentation | 515021 | 6 | 01 | 1011 | 05 | 10 | 01 | 01 | 070 | 002 | Waste Water Management | Electricity | Renewal-70 |  | Yes | Own Funds c/o | #VALUE! | 415030 | #VALUE! |  | 525250 | 0 | 0 | 0 |  | 525250 | #VALUE! | #VALUE! | 0% | [7 empty] | Payment of invoices for committed rollover funding. | 2012-01-01 |  | 515/021/6/01/1011
Ablution Blocks Duncan Village | 515021 | 4 | 01 | 1004 | 05 | 10 | 01 | 01 | 070 | 001 | Waste Water Management | Electricity | New-120 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 2095378 | 217792.92 | 8329.87 | 226122.79 |  | 1869255.21 | #VALUE! | #VALUE! | 10.79% | 2011-06-30 | 1 | BCMM | Yes | n/a | n/a |  |  | 2012-06-01 | Tender has been re-advertised on 3 February 2012 and the closing date of the tender is 17 February 2012. | 515/021/4/01/1004
Bulk Sanitation | 515035 | 6 | 83 | 1104 | 05 | 10 | 01 | 01 | 070 | 002 | Waste water Management | Waste Water |  |  | Yes | Eastern Cape Development Corperation c/o (ECDC) | #VALUE! | 67358 | #VALUE! |  | 67358 | 0 | 0 | 0 |  | 67358 | #VALUE! | #VALUE! | 0% | [9 empty] | Project completed in 10/11. | 515/035/6/83/1104
Upgrading of the Laboratory infrastructure and equipment | 510005 | 6 | 01 | 1012 | 05 | 10 | 01 | 01 | 070 | 002 | Waste water Management | Electricity | Renewal-70 |  | Yes | Own Funds c/o | #VALUE! | 150732 | #VALUE! |  | 908588 | 517803.55 | 150605.2 | 668408.75 |  | 240179.25 | #VALUE! | #VALUE! | 73.57% | [7 empty] | Payment of invoices for committed rollover funding. | 2012-02-01 | LIMS as invoiced. Informal tenders for equipment | 510/005/6/01/1012
3 x Desktop Computers - A11/20 | 530010 | 5 | 05 | 1206 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services |  | Yes |  | Own Funds | #VALUE! | 24000 | #VALUE! |  | 20693 | 20692.11 | 0 | 20692.11 |  | 0.89 | #VALUE! | #VALUE! | 100% | [9 empty] | insurance claim | 530/010/5/05/1206
Traffic and Law Enforcement Fleet | 530020 | 6 | 01 | 1102 | 05 | 05 | 01 | 01 | 250 | 002 | Road Transport | Other - BCM Fleet |  | Yes |  | Own Funds c/o | #VALUE! | 3000000 | #VALUE! |  | 3000000 | 0 | 352367.96 | 352367.96 |  | 2647632.04 | #VALUE! | #VALUE! | 11.75% | [9 empty] | All vehicles have been delivered. | 530/020/6/01/1102
Replacement of Bus Fleet | 530020 | 6 | 01 | 1101 | 05 | 05 | 01 | 01 | 250 | 002 | Road Transport | Other - BCM Fleet |  | Yes |  | Own Funds c/o | #VALUE! | 5998399 | #VALUE! |  | 5998399 | 0 | 5796900 | 5796900 |  | 201499 | #VALUE! | #VALUE! | 96.64% | [9 empty] | Waiting for the suppliers to deliver within a week or two | 530/020/6/01/1101
BCM Fleet | 530020 | 4 | 01 | 1005 | 05 | 11 | 01 | 01 | 250 | 001 | Road Transport | Other - BCM Fleet | New-250 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 7500000 | 3471251.5 | 4057824.16 | 7529075.66 |  | -29075.66 | #VALUE! | #VALUE! | 100.4% | 2011-06-30 | [6 empty] | Specifications will be called from all Directorates and considered against institutional needs. Specifications will be done by the Fleet Manager who has since moved out of the Engineering Directorate. |  | Waiting for the suppliers to deliver within a week or two | 530/020/4/01/1005
TOTAL : DIRECTORATE OF ENGINEERING SERVICES | [10 empty] | 6 | [5 empty] | #VALUE! | 34793791 | #VALUE! | #VALUE! | 401036815 | 109896868.99 | 75052307.18 | 184949176.17 | 225212.1 | 216087638.83 | #VALUE! | #VALUE! | 46.12%
DIRECTORATE OF DEVELOPMENT PLANNING
Insurance vehicle replacement - M10/32 | 615075 | 5 | 05 | 1214 | 05 | 02 | 01 | 01 | 250 | 001 | Planning & Development | Other - BCM Fleet |  | Yes |  | Own Funds | #VALUE! | 155000 | #VALUE! |  | 155000 | 3104.64 | -3104.64 | 0 |  | 155000 | #VALUE! | #VALUE! | 0% | [7 empty] | Request sent to Mechanical Workshop for them to do procurement to replace the vehicle that was stolen. | 2012-06-30 | Tenders awarded, but still waiting for the suppliers to deliver. | 615/075/5/05/1214
Land Acquisition - Construction of Westbank Restitution Reservoir | 615080 | 4 | 01 | 1163 | 05 | 02 | 01 | 01 | 311 | 001 | Planning & Development | Other - BCM Fleet |  | Yes |  | Own Funds | #VALUE! |  | #VALUE! | #VALUE! | 600000 | 31085.24 | 410796.47 | 441881.71 |  | 158118.29 | #VALUE! | #VALUE! | 73.65% | [7 empty] | Request sent to Mechanical Workshop for them to do procurement to replace the vehicle that was stolen. | 2012-06-30 | Conveyancer has prepared documents for lodgement. | 615/080/4/01/1163
West Bank Restitution Project | 615080 | 6 | 54 | 1100 | 05 | 03 | 01 | 01 | 311 | 002 | Planning & Development | Housing |  |  | Yes | Department of Land Affairs c/o | #VALUE! | 4141303 | #VALUE! |  | 4141303 | 50350 | -50350 | 0 |  | 4141303 | #VALUE! | #VALUE! | 0% | [9 empty] | Judgement has been reserved by the Court, as the Conveyancer has appealed. | 615/080/6/54/1100
West Bank Land Restitution | 615080 | 6 | 54 | 1101 | 05 | 03 | 01 | 01 | 311 | 002 | Planning & Development | Housing |  |  | Yes | Department of Land Affairs c/o | #VALUE! | 243551 | #VALUE! |  | 243551 | 0 | 0 | 0 |  | 243551 | #VALUE! | #VALUE! | 0% | [9 empty] | Judgement has been reserved by the Court, as the Conveyancer has appealed. | 615/080/6/54/1101
Construction of BRT lanes | 620005 | 4 | 68 | 1003 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 | Yes |  | Public Transport Infrastructure and Systems Grant (PTIS) | #VALUE! | 0 | #VALUE! | #VALUE! | 100000000 | 1210726.34 | 72408.41 | 1283134.75 |  | 98716865.25 | #VALUE! | #VALUE! | 1.283% | R110,470,000 - awards to consultants | 42,12.11,13,16,5,10,16,8,7,9,2,1,3,47,19 | N/A | N/A | Planning and Detailed designs stage | N/A |  | Tender has been awarded by Acting City Manager on the recommendation of the Bid Adjudication Committee. Service Level Agreement to be entered into. | 2014-06-01 | Tender has been awarded for full consultant team, including detailed designs and business planning. Service Level Agreement can only be entered into once legal challenge from one of the bidders can be resolved. | 620/005/4/68/1003
BCM Urban Agriculture Infrastructure Development | 635005 | 4 | 36 | 1044 | 05 | 03 | 01 | 01 | 320 | 001 | Planning & Development | Transport Planning | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 3000000 | 3053278.5 | -53278.5 | 3000000 |  | 0 | #VALUE! | #VALUE! | 100% |  | 21,23 | BCMM | Construction of Hydroponics | Designs already approved | Not Applicable |  | The Contractor appointed on 05 October 2011. work has commenced on the two identified sites in wards 21 and 23. Invoice of R1, 60000.00 has been processed . 50% construction at Ward 21, completing site levelling at ward 23. Project in progress. | End March 2012 | Project complete. A journal has been forwarded to Finance for the Correction of misallocation. | 635/005/4/36/1044
Taxi Ranks | 620005 | 4 | 36 | 1045 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 3200000 | 456430.96 | 387319.04 | 843750 |  | 2356250 | #VALUE! | #VALUE! | 26.37% | R3,359,437- awarded to consultant | 34,36,39,41,43,49,25,40,44,37 | N/A | N/A | Designs Stage | N/A |  | Tender has been awarded and service level agreement to be entered into. | 2013-12-01 | Tender awarded for civil engineering consultants and designs are in progress. Tender for implementation in 2012/13 and 2013/14. Two stakeholder consultation meetings have been held and stage 2 of design process has been complete (concept and viability). The third PSC meeting has been scheduled for 18 July 2012. | 620/005/4/36/1045
Gonubie Main Road | 620005 | 4 | 36 | 1046 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-30 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 10000000 | 2973397.53 | 933822.66 | 3907220.19 |  | 6092779.81 | #VALUE! | #VALUE! | 39.07% | R10,000,000 - awarded to consultants | 28,27,29 | N/A | N/A | Preliminary and detailed designs progressing | N/A |  | N/A | 2012-06-01 | Draft tender documents and designs currently being reviewed by BCMM Roads Branch. Invoices to the value of R3.67m have been processed. Service provider currently busy with designs for Gonubie Service Lanes. Invoices in the amount R 230 000 have been processed. | 620/005/4/36/1046
Potsdam/Needs Camp Bridge Feasibility Study | 620005 | 6 | 81 | 1001 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 | Yes |  | BCMET c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 233787 | 0 | 0 | 0 |  | 233787 | #VALUE! | #VALUE! | 0% | R233,787 - awarded to consultant | 33,23 | N/A | N/A | Feasibility Study | N/A |  | Awarded to service provider. | 2012-06-01 | Work in Progress. 1st draft of report is being reviewed by department Awaiting first invoice from service provider | 620/005/6/81/1001
Rural non Motorised Transport facilities | 620005 | 6 | 01 | 1018 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 | Yes |  | Own Funds c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 330600 | 152828.33 | 0 | 152828.33 |  | 177771.67 | #VALUE! | #VALUE! | 46.23% | R330,000 - awarded to consultant | All | N/A | N/A | Feasibility Study and design | N/A |  | Awarded to service provider. | 2012-04-01 | Work in Progress. Awaiting first draft report from service provider. | 620/005/6/01/1018
Traffic Management Measures | 620005 | 6 | 01 | 1019 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 |  | Yes | Own Funds c/o | #VALUE! | 714607 | #VALUE! |  | 1814607 | 199221.5 | 18998.39 | 218219.89 |  | 1596387.11 | #VALUE! | #VALUE! | 12.03% | R600,000 committed to smaller projects - informal tenders being considered. Other projects to be completed through annual contract 98, report to be submitted to BSC | All | N/A | N/A | N/A | N/A |  | New contract 98 to be submitted to the BSC for early March 2012: Informal tenders to the value of R600 000.00(Traffic calming measure) still being finalised between this department and SCM and award in February 2012: Traffic signal equipment and Traffic signal heads tenders, we have requested for the readvertisement as there were no bidders who met the requirements: Informal tenders to the value of R400 000.00(Traffic Signal Equipment and LED signal heads) to posted on the SCM notice board on Friday 10 February 2012. | 2012-06-01 | Signal heads and traffic controllers have been purchased. Informal tenders for Traffic Calming Measures to the value of +/- R 600,000 have been awarded. | 620/005/6/01/1019
Pedestrian facilities | 620005 | 6 | 01 | 1020 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 |  | Yes | Own Funds c/o | #VALUE! | -256092 | #VALUE! |  | 343908 | 0 | 0 | 0 |  | 343908 | #VALUE! | #VALUE! | 0% | R350,000 committed to smaller projects - informal tenders being considered. Other projects to be completed through annual contract 98, report to be submitted to BSC | All | N/A | N/A | N/A | N/A |  | New contract 98 to be submitted to the BSC for early March 2012. TOR for Informal tenders to the value of R350 000.00 (Installation of Tactile paving & Physically chalanged ped push buttons) still being finalised at SCM and award in late February 2012. Work commencing there after. | 2012-06-01 | Audible Pedestrian Signals have been purchased. | 620/005/6/01/1020
Guidance Signage | 620005 | 6 | 01 | 1021 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 |  | Yes | Own Funds c/o | #VALUE! | -13554 | #VALUE! |  | 586446 | 1067.22 | -1067.22 | 0 |  | 586446 | #VALUE! | #VALUE! | 0% | R600,000 committed - report progressing to Bid Adjudication Committee | 46,1,9,16,13,4,35,37 | N/A | N/A | N/A | N/A |  | Returned back to the BEC from the BAC because of funding in the outer years. | 2012-06-01 | Contract cancelled because the validity period expired and tender to be re-advertised. | 620/005/6/01/1021
Yellowwoods River Bridge | 620005 | 6 | 01 | 1022 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 |  | Yes | Own Funds c/o | #VALUE! | 202612 | #VALUE! |  | 2102612 | 1111506.37 | 0 | 1111506.37 |  | 991105.63 | #VALUE! | #VALUE! | 52.86% | R200,000 required to finalise this multi-year project. | 44 | N/A | N/A | N/A | N/A |  | N/A | 2011-08-01 | Project complete, final payment certificates to be processed | 620/005/6/01/1022
Yellowwoods River Bridge | 620005 | 4 | 01 | 1155 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 |  | Yes | Own Funds | #VALUE! |  | #VALUE! | #VALUE! | 200000 | 0 | 0 | 0 |  | 200000 | #VALUE! | #VALUE! | 0% | R200,000 required to finalise this multi-year project. | 44 | N/A | N/A | N/A | N/A |  | N/A | 2011-08-01 | Project complete, final payment certificates to be processed | 620/005/4/01/1155
Economic Infrastructure | 635005 | 4 | 36 | 1047 | 05 | 03 | 01 | 01 | 320 | 001 | Planning & Development | Transport Planning | New-120 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 6000000 | 4705703.94 | -1041671.12 | 3664032.82 |  | 2335967.18 | #VALUE! | #VALUE! | 61.07% |  | 26, 40 | Communal | Top up funding for construction of Hydroponics at newlands and Qongqotha | Designs already approved | Not Applicable |  |  | End March 2012 | The programme has two projects Construction of Hydroponics and Steve Biko Foundation project. R2 million transfered to the Steve Biko Foundation. Nu 18 Hydroponics is about 60 % complete and is due to be finished by end May 2012. | 635/005/4/36/1047
Hydro-ponics - MDT | 635005 | 6 | 15 | 1100 | 05 | 03 | 01 | 01 | 320 | 002 | Planning & Development | Transport Planning |  |  | Yes | Department of Economic Affairs and Tourism c/o (DEDEAT) | #VALUE! | 5239 | #VALUE! |  | 5239 | 0 | 0 | 0 |  | 5239 | #VALUE! | #VALUE! | 0% | [9 empty] | Project is complete. Funds utilised for installation of Electricity for Kwakhanya Cooperative | 635/005/6/15/1100
Inner City Regeneration- Pedestrian Priority Zone | 635005 | 6 | 79 | 1100 | 05 | 03 | 01 | 01 | 320 | 002 | Planning & Development | Transport Planning |  |  | Yes | Provincial Treasury Office - LED Support Programme c/o | #VALUE! | 375269 | #VALUE! |  | 375269 | 0 | 0 | 0 |  | 375269 | #VALUE! | #VALUE! | 0% | R296000 final payment to consultant once funding is received from Provincial Treasury | [8 empty] | Project complete. Awaiting final payment from Provincial Treasury. | 635/005/6/79/1100
Desktop Computer - A10/58 | 635005 | 5 | 05 | 1201 | 05 | 02 | 01 | 01 | 270 | 001 | Planning & Development | Transport Planning |  | Yes |  | Own Funds | #VALUE! | 9500 | #VALUE! |  | 7850 | 7850 | 0 | 7850 |  | 0 | #VALUE! | #VALUE! | 100% | [7 empty] | 04.01.2012 | 2012-02-01 | Project Complete | 635/005/5/05/1201
Tourism infrastructure development | 635005 | 6 | 01 | 1013 | 05 | 03 | 01 | 01 | 320 | 001 | Planning & Development | Transport Planning | New-320 |  | Yes | Own Funds c/o | #VALUE! | 797478 | #VALUE! |  | 1797478 | 581578.94 | 0 | 581578.94 |  | 1215899.06 | #VALUE! | #VALUE! | 32.36% |  | 32 | Water and Sanitation available | EC PARKS & TOURISM AGENCIES | Designs already approved | n/A |  | Phase: 1 of the project is complete. Balance will used for Phase: 2 which is construction of access road. Project is will be omplete in june 2012. |  | Phase: 1 of the project is complete. Balance will be used for Phase: 2 which is construction of access road. Project will be completed in 1st Quarter of the new finncial year. | 635/005/6/01/1013
Roll – Out Hydroponics | 635005 | 6 | 01 | 1014 | 05 | 03 | 01 | 01 | 320 | 001 | Planning & Development | Transport Planning | New-320 |  | Yes | Own Funds c/o | #VALUE! | 130503 | #VALUE! |  | 3630503 | 489392.97 | 2023436.82 | 2512829.79 |  | 1117673.21 | #VALUE! | #VALUE! | 69.21% |  | 40 | Communal/ BCMM | Construction of Hydroponics at Newlands/Nxaruni | Designs already approved | Not applicable |  | Service Provider appointed, work on site. Invoices are being processed on completion of milestone. |  | Project commenced Phase 1 completed. Payment of R2,022,900.00 has been processed and project will be completed in the 1st Quarter of the Financial year. | 635/005/6/01/1014
Buffalo City Agric & Rural Development Infrastructure | 635005 | 6 | 01 | 1015 | 05 | 03 | 01 | 01 | 320 | 001 | Planning & Development | Transport Planning | New-320 |  | Yes | Own Funds c/o | #VALUE! | -199740 | #VALUE! |  | 2793001 | 589002.32 | 999498.36 | 1588500.68 |  | 1204500.32 | #VALUE! | #VALUE! | 56.87% |  | 39 | Communal/ BCMM | Diptank and Livestock, fencing | Designs already approved | Not Applicable |  | Project in progress and will be completed end of June 2012 | End June 2012 | Request a roll over of R500 000,00 due to the fact that the department had experienced challenges during the site handover due to the community dynamics anticipating completion by July 2012. | 635/005/6/01/1015
Cooperative Support Programme | 635005 | 6 | 01 | 1016 | 05 | 03 | 01 | 01 | 320 | 001 | Planning & Development | Transport Planning | New-320 |  | Yes | Own Funds c/o | #VALUE! | -1202733 | #VALUE! |  | 246455 | 0 | 0 | 0 |  | 246455 | #VALUE! | #VALUE! | 0% |  | All BCMM Wards | N/A | N/A | N/A | N/A |  | Project is complete | Project is complete | Project is complete Funds will be utilised for cooperative needs before the end of financial year. | 635/005/6/01/1016
Upgrade of Market | 635010 | 6 | 01 | 1017 | 05 | 03 | 01 | 01 | 290 | 001 | Other | Transport Planning | Renewal -290 |  | Yes | Own Funds c/o | #VALUE! | -360105 | #VALUE! |  | 959895 | 429396.44 | 90361.84 | 519758.28 |  | 440136.72 | #VALUE! | #VALUE! | 54.15% |  | 12 | BCM Land | N/A | N/A | N/A |  | Funds to be utilised on completion of phase 2 of extension of sales hall. | 2012-05-01 | Remaining funds to be utilised on phase 2 for extension of sales hall in the 1st Quarter of the new financial year. | 635/010/6/01/1017
Extension of Sales Hall | 635010 | 4 | 01 | 1006 | 05 | 03 | 01 | 01 | 290 | 001 | Planning & Development | Transport Planning | Renewal -290 |  | Yes | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 2000000 | 1717.35 | -1717.35 | 0 |  | 2000000 | #VALUE! | #VALUE! | 0% |  | 12 | BCM Land | N/A | N/A | N/A |  | Tender to be re-advertised for the 3rd time due to non responsive bids. The scope of work has been amended, tender process will start end Janaury 2012. | 2012-05-01 | Tender was re-dvertised in April 2012 and is going to BEC on the 11 June 2012. Anticipated to commnence in the new financial year. | 635/010/4/01/1006
TOTAL :DIRECTORATE OF DEVELOPMENT PLANNING | [10 empty] | 7 | [5 empty] | #REF! | #REF! | #REF! | #REF! | 144767504 | 84539.88 | 3785453.16 | 19833091.75 | 0 | 124934412.25 | #REF! | #REF! | 13.7%
DIRECTORATE OF HEALTH AND PUBLIC SAFETY
Fire Station - KWT | 725010 | 4 | 36 | 1053 | 05 | 04 | 01 | 01 | 200 | 001 | Health | Public safety | New-220 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 6227453 | 1527869.15 | 1490236.98 | 3018106.13 |  | 3209346.87 | #VALUE! | #VALUE! | 48.46% | 2011-06-30 | 37 | BCM | n/a | Plan finalised by PMU | n/a |  | Approved by BAC on 10/11/2011. Min No 373/11 | June 2012 | Project in progress. Multi year project, completion will be January 2013. | 725/010/4/36/1053
Generator - A11/73 | 725010 | 5 | 05 | 1245 | 05 | 02 | 01 | 01 | 260 | 001 | Public Safety | Public Safety |  | Yes |  | Own Funds |  |  |  |  | 9000 | 7140 | 0 | 7140 |  | 1860 |  |  | 79.33% | [9 empty] | Project Completed
Upgrade Mdantsane Fire Stations | 725010 | 6 | 83 | 1105 | 05 | 07 | 01 | 01 | 311 | 002 | Public safety | Public safety |  |  | Yes | European Commission c/o | #VALUE! | 171183 | #VALUE! | -171183 | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | [7 empty] | Works orders issued for work to be done. | May 2012 | Funding withdrawn as per Budget Adjustment | 725/010/6/83/1105
Computer & Globe Surfer - A10/113 | 710020 | 5 | 05 | 1217 | 05 | 02 | 01 | 01 | 270 | 001 | Community and social services | Health Services |  | Yes |  | Own Funds | #VALUE! | 9500 | #VALUE! |  | 9246 | 9245.95 | 0 | 9245.95 |  | 0.05 | #VALUE! | #VALUE! | 100% | [7 empty] | MIS in process of procurring computer and globe surfer for Zanempilo Clinic | February 2012 | Project Completed. | 710/020/5/05/1217
3 x Fridges - A10/106 | 710020 | 5 | 05 | 1222 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Health Services |  | Yes |  | Own Funds | #VALUE! | 9500 | #VALUE! |  | 7103 | 7102.63 | 0 | 7102.63 |  | 0.37 | #VALUE! | #VALUE! | 99.99% | [7 empty] | Fridges have been received by Gompo C | January 2012 | Project Completed. | 710/020/5/05/1222
Clinics | 710020 | 6 | 36 | 1001 | 05 | 04 | 01 | 01 | 200 | 001 | Health | Health Services | Renewal-200 |  | Yes | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2100000 | 3354.24 | -3354.24 | 0 |  | 2100000 | #VALUE! | #VALUE! | 0% | JUNE 2011 | Ward 46 | BCMM | BIA |  | N/A |  | Appointment letter signed on 6-12-2011. Waiting for construction guarantee from contractor | End June 2012 | Contract cancelled due to contractor not providing construction guarantee certificate. PHC taken over by Province from July 2012. | 710/020/6/36/1001
Air quality monitoring station equipment | 710040 | 6 | 01 | 1031 | 05 | 04 | 01 | 01 | 270 | 001 | Community and social services | Environmental Services | New-270 | Yes |  | Own Funds c/o | #VALUE! | -311895 | #VALUE! |  | 100268 | 0 | 83600 | 83600 |  | 16668 | #VALUE! | #VALUE! | 83.38% | MAY 2010 | All wards | BCMM | Yes | N/A | Non |  | MIS to process requisition in order for SCM to procure computer. | End March 2012 | Awaiting delivery of laptop and printer ordered by MIS costing R10 414 - 63. | 710/040/6/01/1031
Mobile Clinics Equipment | 710020 | 6 | 01 | 1032 | 05 | 04 | 01 | 01 | 200 | 001 | Health | Health Services | New-260 | Yes |  | Own Funds c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 235495 | 219641.91 | 11339.25 | 230981.16 |  | 4513.84 | #VALUE! | #VALUE! | 98.08% | JUNE 2011 | Ward 31;44 | BCMM | N/A | N/A | N/A |  | SCM is updating BCMM Suppliers Database | 2012-05-01 | Project Completed | 710/020/6/01/1032
Upgrading of Clinics - Ginsberg | 710020 | 6 | 01 | 1033 | 05 | 04 | 01 | 01 | 200 | 001 | Health | Health Services | Renewal-200 |  | Yes | Own Funds c/o | #VALUE! | 100000 | #VALUE! |  | 698124 | 404287.12 | 94370 | 498657.12 |  | 199466.88 | #VALUE! | #VALUE! | 71.43% | MAY 2010 | Ward 39 | BCMM | BIA | N/A | N/A |  | Orders have been placed with Service Providers and some equipment already received. Requisitions to be submitted to SCM for balance of equipment. | Mid March 2012 | Project Completed | 710/020/6/01/1033
Desktop computer - A10/56 | 710020 | 5 | 05 | 1233 | 05 | 02 | 01 | 01 | 270 | 001 | Community and social services | Health Services |  | Yes |  | Own Funds | #VALUE! | 9500 | #VALUE! |  | 7235 | 7234.21 | 0 | 7234.21 |  | 0.79 | #VALUE! | #VALUE! | 99.99% | MAY 2010 | Ward 39 | BCMM | BIA | N/A | N/A |  | Total expenditure is R370,348 | End February 2012 | Project Completed. | 710/020/5/05/1233
KWT Fire Station | 725010 | 6 | 1 | 1105 | 05 | 07 | 01 | 01 | 311 | 002 | Public safety | Public safety |  |  | Yes | Own Funds c/o |  |  |  |  | 1999999 |  | 401971 | 401971 |  | 1598028 |  |  | 0%
Fire Engine R/O | 725010 | 6 | 82 | 1103 | 05 | 07 | 02 | 01 | 360 | 002 | Public safety | Public safety | New-360 | Yes |  | DBSA Phase 4 |  |  |  |  | 11651923 |  | 11651923 | 11651923 |  | 0 |  |  | 0%
Insurance vehicle replacement - M10/189 | 725015 | 5 | 05 | 1212 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | Own Funds | #VALUE! | 265000 | #VALUE! |  | 265000 | 0 | 0 | 0 |  | 265000 | #VALUE! | #VALUE! | 0% | [7 empty] | Request for advertising of tender submitted to Fleet Mang. | May 2012 | Fleet requested to purchase vehicles - project to be rolled over | 725/015/5/05/1212
Insurance vehicle replacement- M10/27 | 725020 | 5 | 05 | 1213 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | Own Funds | #VALUE! | 265000 | #VALUE! |  | 265000 | 0 | 0 | 0 |  | 265000 | #VALUE! | #VALUE! | 0% | [7 empty] | Request for advertising of tender submitted to Fleet Mang. | May 2012 | Fleet requested to purchase vehicles - project to be rolled over | 725/020/5/05/1213
Law Enforcement Equipment | 725015 | 6 | 01 | 1034 | 05 | 07 | 02 | 01 | 270 | 001 | Corporate Services | Public safety | New-260 | Yes |  | Own Funds c/o | #VALUE! | -161398 | #VALUE! |  | 18602 | 18186.67 | 0 | 18186.67 |  | 415.33 | #VALUE! | #VALUE! | 97.77% |  | 27 & 41 | n/a | n/a | n/a | n/a |  | Project completed. | December 2011 | Project completed. | 725/015/6/01/1034
Traffic Vehicles | 725020 | 4 | 01 | 1021 | 05 | 07 | 02 | 01 | 250 | 001 | Public safety | Public safety | New-250 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 450000 | 0 | 42607.82 | 42607.82 |  | 407392.18 | #VALUE! | #VALUE! | 9.468% |  | All | n/a | n/a | n/a | n/a |  | Tender for M/cycles closed on 20 Dec. 2011. Tender for mini bus to be advertised. | March 2012 | Fleet requested to purchase vehicles - project to be rolled over | 725/020/4/01/1021
Insurance vehicle replacement - M09/131 | 725020 | 5 | 05 | 1210 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | Own Funds | #VALUE! | 220000 | #VALUE! |  | 220000 | 0 | 0 | 0 |  | 220000 | #VALUE! | #VALUE! | 0% | [7 empty] | Request for advertising of tender submitted to Fleet Mang. | May 2012 | Fleet requested to purchase vehicles - project to be rolled over | 725/020/5/05/1210
Learners Licence Centre - Mdantsane | 725035 | 4 | 01 | 1022 | 05 | 07 | 02 | 01 | 312 | 001 | Public safety | Public safety | New-312 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 3298.68 | -3298.68 | 0 |  | 1000000 | #VALUE! | #VALUE! | 0% |  | All | n/a | n/a | n/a | n/a |  | Land identified, plans approved, awaiting further funding as R 2.5m will be required for completion | 2012-06-30 | Tender closed on 30 March 2012, in evaluation stage. Project to be rolled over | 725/035/4/01/1022
Fire Engines Roll 0ver | 725010 | 6 | 01 | 1035 | 05 | 07 | 02 | 01 | 360 | 002 | Public safety | Public safety | New-360 | Yes |  | Own Funds c/o | #VALUE! | 4456705 | #VALUE! |  | 4106923 | 11911338.36 | -10623800.12 | 1287538.24 |  | 2819384.76 | #VALUE! | #VALUE! | 31.35% |  | All | n/a | n/a | Waiting delivery | n/a |  | 2 x Aerial Appiances have been delivered. Delivery of Urban Rescue vehicle due in February 2012. | End February 2012 | Project completed. | 725/010/6/01/1035
Fire Engine Equipment | 725010 | 6 | 01 | 1036 | 05 | 07 | 02 | 01 | 360 | 002 | Public safety | Public safety | New-360 | Yes |  | Own Funds c/o | #VALUE! | -503399 | #VALUE! |  | 2371404 | 1575941.33 | 364836.76 | 1940778.09 |  | 430625.91 | #VALUE! | #VALUE! | 81.84% |  | All | n/a | n/a | Waiting delivery | n/a |  | Procurement in progress. | May 2012 | Project completed. | 725/010/6/01/1036
KWT Fire Station | 725010 | 6 | 82 | 1102 | 05 | 07 | 01 | 01 | 311 | 002 | Public safety | Public safety |  |  | Yes | DBSA Phase 4 & 5 c/o | #VALUE! | 2000000 | #VALUE! |  | 1 | 401971.16 | -401971 | 0.16 |  | 0.84 | #VALUE! | #VALUE! | 16% | [7 empty] | As per line 186/Vote 725/010/4/36/1053 above. | June 2012 | To be used in conjunction with the R6m provided for KWT Fire Station. Funding to be rolled over, completion date January 2013. | 725/010/6/82/1102
Flood Relocation (DM Structures) | 725055 | 6 | 89 | 1100 | 05 | 07 | 01 | 01 | 311 | 002 | Public safety | Public safety |  |  | Yes | Disaster Management Fund c/o | #VALUE! | 41025 | #VALUE! |  | 41025 | 0 | 0 | 0 |  | 41025 | #VALUE! | #VALUE! | 0% | [9 empty] | Development Planning requested to utilise funding as per D.V.R.I. Roll over required | 725/055/6/89/1100
Disaster Management Capacity | 725055 | 6 | 89 | 1001 | 05 | 07 | 04 | 01 | 320 | 002 | Public Safety | Public safety | New-320 |  | Yes | Disaster Management Fund c/o | #VALUE! | -7150 | #VALUE! |  | 36790 | 23729.76 | 0 | 23729.76 |  | 13060.24 | #VALUE! | #VALUE! | 64.5% | 2006/7 | All | n/a | n/a | n/a | n/a |  | Purchase of equipment in progress. | March 2012 | Balance to be rolled over. | 725/055/6/89/1001
Disaster Management Centres | 725055 | 6 | 89 | 1002 | 05 | 07 | 04 | 01 | 320 | 002 | Public Safety | Public safety | New-320 | Yes |  | Disaster Management Fund c/o | #VALUE! | 0 | #VALUE! |  | 84779 | 84779 | 0 | 84779 |  | 0 | #VALUE! | #VALUE! | 100% | 2005/6 | All | n/a | n/a | n/a | n/a |  | Tender awarded to Sidiki Trading for supply & installation of Automatic Fire detection & Inhert Gas Extinguishing System. | February 2012 | Project Completed | 725/055/6/89/1002
TOTAL : DIRECTORATE OF HEALTH AND PUBLIC SAFETY | [10 empty] | 8 | [5 empty] | #VALUE! | 6563571 | #VALUE! | #VALUE! | 31905370 | 16205120.17 | 3108460.77 | 19313580.94 | 0 | 12591789.06 | #VALUE! | #VALUE! | 60.53%
DIRECTORATE OF COMMUNITY SERVICES
Development of Community Parks(Mdantsane, Potsdam, Reeston) | 755010 | 4 | 36 | 1048 | 05 | 03 | 01 | 01 | 150 | 001 | Community and social services | Amenities | New-150 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1016303 | 101904.99 | 441500 | 543404.99 |  | 472898.01 | #VALUE! | #VALUE! | 53.47% | 2011-07-01 | 20,23 | BCMM | Not required | Consultation complete, land identified. | None |  | SCM busy with adjudication of the tenders received |  | Play park equipment has been ordered and await installation by the Service Provider. To re advertise for informal tender for the fencing of 3 parks and purchasing of park furniture, trees and signage. A roll over will be required to complete the project. | 755/010/4/36/1048
Brushcutter - A10/102 | 755010 | 5 | 05 | 1203 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Environmental Services |  | Yes |  | Own Funds | #VALUE! | 9600 | #VALUE! |  | 8373 | 8372.5 | 0 | 8372.5 |  | 0.5 | #VALUE! | #VALUE! | 99.99% | [7 empty] | Order created by SCM for the service provider |  | Machine received in January 2012 | 755/010/5/05/1203
3 x Brushcutters - A11/15 | 755010 | 5 | 05 | 1205 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Environmental Services |  | Yes |  | Own Funds | #VALUE! | 30000 | #VALUE! |  | 25602 | 25601.97 | 0 | 25601.97 |  | 0.03 | #VALUE! | #VALUE! | 100% | [7 empty] | Awaiting SCM to process the order |  | Machines received. | 755/010/5/05/1205
Development of 3 New Cemetries(Inland, Midland and Coastal) | 755025 | 4 | 36 | 1049 | 05 | 05 | 04 | 01 | 320 | 001 | Community and social services | Environmental Services | New-220 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 3000000 | 372906.58 | 184273.01 | 557179.59 |  | 2442820.41 | #VALUE! | #VALUE! | 18.57% | 2011-07-01 | 36, 22, 37 | BCMM | BIA | Work instruction submitted to Engineering for the design, plan and tarring of roads and ablutions facilities at KWT and Dimbaza. | None |  | Consultants Ages (PTY, LTD) appointed to conduct feasibility studies in the Midland and Inland area as well as the feasibility study for the construction of an access bridge at the King Williams Town Extension Cemetery. |  | The construction branch have appointed a service provider to deveop and establish road in Dimbaza and KWT Cemeteries but according to the construction branch the project was delayed due to the fact that SCM onlyprocessed Works orders on 21 June and the work will be completed in the new financial year therefore a roll over is required. | 755/025/4/36/1049
Insurance vehicle replacement - M07/212 | 755025 | 5 | 05 | 1239 | 05 | 02 | 01 | 01 | 250 | 001 | Environmental Protection | Environmental Services |  | Yes |  | Own Funds |  |  |  | 298224 | 0 | 0 |  | 0 |  | 0 |  |  | #DIV/0! | [9 empty] | Insurance replacement | 755/025/5/05/1239
Desktop Computer - A10/127 | 760010 | 5 | 05 | 1204 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services |  | Yes |  | Own Funds | #VALUE! | 8500 | #VALUE! |  | 7328 | 7327.78 | 0 | 7327.78 |  | 0.22 | #VALUE! | #VALUE! | 100% | [9 empty] | Computer purchased and commissioned into use. | 760/010/5/05/1204
Scenery Park Community Hall | 760025 | 4 | 36 | 1050 | 05 | 05 | 03 | 01 | 170 | 001 | Community and social services | Amenities | New-170 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2000000 | 1908763.29 | 25739.86 | 1934503.15 |  | 65496.85 | #VALUE! | #VALUE! | 96.73% | 2011-09-10 | 5 | BCM | n/a | n/a | n/a |  | Complete | 16 January 2012 | Project completed. Balance of the funding to be spent on sewer/water connections in 2012/2013. Roll over requested. | 760/025/4/36/1050
Viper Polisher - A09/105 | 760025 | 5 | 05 | 1211 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Amenities |  | Yes |  | Own Funds | #VALUE! | 10000 | #VALUE! |  | 8500 | 8500 |  | 8500 |  | 0 | #VALUE! | #VALUE! | 100% | [7 empty] | To be determined by SCM processes. |  | The polisher has been received and commissioned into use. | 760/025/5/05/1211
Insurance vehicle replacemen - M11/55 | 760025 | 5 | 05 | 1232 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | Own Funds | #VALUE! | 285000 | #VALUE! |  | 285000 | 0 |  | 0 |  | 285000 | #VALUE! | #VALUE! | 0% | [7 empty] | To be determined by Mechanical Workshops & SCM processes | To be determined by SCM processes | Insurance Claim - Mechanical Workshops (Mr Gijana) confirmed to Mr Mahomed 06/07/2012 that the vehicle tender was still with the Bid Committee. Vehicle expected to be replaced by end of July 2012. | 760/025/5/05/1232
Insurance vehicle replacement - M09/153 | 765030 | 5 | 05 | 1219 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | Own Funds | #VALUE! | 350000 | #VALUE! |  | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | [7 empty] | Vehicle was handed over to Beaches | Completed: insurance claim | Vehicle has been delivered, handed over to beaches. | 765/030/5/05/1219
Solid waste management | 770030 | 4 | 36 | 1051 | 05 | 10 | 01 | 01 | 100 | 001 | Waste Management | Cleansing |  | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2800000 | 1284893.77 | 450300.99 | 1735194.76 |  | 1064805.24 | #VALUE! | #REF! | 61.97% | 2011-06-30 |  | BCMM | n/a | n/a | n/a |  | Construction of Drop Off Points (R2.8 million) - Project at Bid Evaluation Stage | To be determined by SCM processes | Project completed. Balance declared as savings | 770/030/4/36/1051
Planning of designs of Third Cell | 770030 | 4 | 36 | 1135 | 05 | 05 | 04 | 01 | 100 | 001 | Environmental Protection | Environmental Services | New-220 | Yes |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 500000 | 0 | 88334.71 | 88334.71 |  | 411665.29 | #VALUE! | #VALUE! | 17.67% | 2011-07-01 | 36, 22, 37 | BCMM | BIA | Work instruction submitted to Engineering for the design, plan and tarring of roads and ablutions facilities at KWT and Dimbaza. | None |  | Consultants Ages (PTY, LTD) appointed to conduct feasibility studies in the Midland and Inland area as well as the feasibility study for the construction of an access bridge at the King Williams Town Extension Cemetery. |  | Contractor is on site doing bush clearing. A request has been submitted for the balance to be rolled over to complete the project. | 770/030/4/36/1135
Sport Facilities | 765010 | 4 | 36 | 1052 | 05 | 10 | 01 | 01 | 160 | 001 | Sports and Recreation | Cleansing | Renewal-160 |  | Yes | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2000000 | 289497.13 | -7973.23 | 281523.9 |  | 1718476.1 | #VALUE! | #VALUE! | 14.08% | 2011-10-11 | 7,12,13,28,29,35,37,38,44 | BCM | N/A | Specifications submitted to SCM | n/a |  | Projects will be handled as informal tenders. Informal tender forms are being drafted | 30/06/2012 | Bid specification documents was on the agenda of the BSC meeting on 24/2/12.BSC requested that the PMU must assist in the finalisation of the Bill of Quantities which will form part of the bid spec document. PMU indicated that that they do not have capacity to assist.The Community Services Directorate attempted to meet the BSC to clarify that the Bill of Quantities may not be needed for purposes of the specification document. The Director Community Services did not obtain confirmation from chairperson of the BSC for a date of the meeting. There is no committment for the project, therefore it cannot be rolled over. | 765/010/4/36/1052
Insurance vehicle replacement - M11/02 | 770005 | 5 | 05 | 1226 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet | Renewal-250 | Yes |  | Own Funds | #VALUE! | 160000 | #VALUE! |  | 160000 | 0 | 0 | 0 |  | 160000 | #VALUE! | #VALUE! | 0% | [9 empty] | Tender awarded. Awaiting delivery | 770/005/5/05/1226
Purchase of 7 Refuse Compactor Trucks - Mdantsane | 770010 | 4 | 01 | 1007 | 05 | 05 | 01 | 01 | 350 | 001 | Waste Management | Cleansing | New-350 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 10500000 | 2913.6 | 8666291.64 | 8669205.24 |  | 1830794.76 | #VALUE! | #VALUE! | 82.56% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | To be submitted to BEC |  | Tender awarded. Awaiting delivery | 770/010/4/01/1007
Purchase of 3 Refuse Compactor Trucks (Mdantsane) | 770010 | 4 | 01 | 1008 | 05 | 05 | 01 | 01 | 350 | 001 | Waste Management | Cleansing | New-350 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 4500000 | 0 | 0 | 0 |  | 4500000 | #VALUE! | #VALUE! | 0% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | To be submitted to BEC |  | Tender awarded. Awaiting delivery | 770/010/4/01/1008
Purchase of 2 x LDV Bakkie's | 770010 | 4 | 01 | 1009 | 05 | 05 | 01 | 01 | 250 | 001 | Waste Management | Cleansing | New-350 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 460000 | 0 |  | 0 |  | 460000 | #VALUE! | #VALUE! | 0% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | To be submitted to BEC |  | Tender awarded. Awaiting delivery | 770/010/4/01/1009
Purchase of 1 X Load lugger | 770010 | 4 | 01 | 1010 | 05 | 05 | 01 | 01 | 250 | 001 | Waste Management | Cleansing | New-350 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 800000 | 0 |  | 0 |  | 800000 | #VALUE! | #VALUE! | 0% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | To be seubmitted to BEC |  | Tender awarded. Awaiting delivery | 770/010/4/01/1010
Refuse 5 Compactor Trucks - Coastal Region | 750005 | 4 | 01 | 1011 | 05 | 05 | 01 | 01 | 350 | 001 | Community and social services | Cleansing | New-350 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 10000000 | 8013649.82 | 0 | 8013649.82 |  | 1986350.18 | #VALUE! | #VALUE! | 80.14% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | All trucks delivered | Completed | Tender awarded. Awaiting delivery | 750/005/4/01/1011
Vehicles for Solid Waste Supervisors, Safety Officers, District Cleansing Officers and Superintendents -(9 X Sedans, 8 LDV's, 3 X Double Cabs, 2X3 Ton Trucks (Inland,Midlands and Coastal Areas) | 750005 | 4 | 01 | 1012 | 05 | 10 | 11 | 01 | 250 | 001 | Waste Management | Cleansing | New-250 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 4000000 | 3104.7 | 2463368.07 | 2466472.77 |  | 1533527.23 | #VALUE! | #VALUE! | 61.66% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | To be submitted to BEC |  | Tender awarded. | 750/005/4/01/1012
Miscallaneous Bins | 750005 | 6 | 01 | 1023 | 05 | 10 | 11 | 01 | 100 | 002 | Waste Management | Cleansing | New-100 | Yes |  | Own Funds c/o | #VALUE! | -58000 | #VALUE! |  | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | Complete, balance declared as savings |  | Completed | 750/005/6/01/1023
9 x Brushcutters - A10/117 | 755010 | 5 | 05 | 1215 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Environmental Services |  | Yes |  | Own Funds | #VALUE! | 87000 | #VALUE! |  | 76005 | 76005 | 0 | 76005 |  | 0 | #VALUE! | #VALUE! | 100% | [9 empty] | 9x Brushcutters purchased and delivered to Workshop | 755/010/5/05/1215
6 x Brushcutters, Pruner, Chainsaw - A11/22 | 755010 | 5 | 05 | 1216 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Environmental Services |  | Yes |  | Own Funds | #VALUE! | 78000 | #VALUE! |  | 78000 | 70822 |  | 70822 |  | 7178 | #VALUE! | #VALUE! | 90.8% | [9 empty] | Machines received and currently at Meadow Road depot | 755/010/5/05/1216
Rotovor - A11/30 | 755010 | 5 | 05 | 1234 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Environmental Services |  | Yes |  | Own Funds | #VALUE! | 15000 | #VALUE! |  | 15000 | 11841.23 |  | 11841.23 |  | 3158.77 | #VALUE! | #VALUE! | 78.94% | [8 empty] | Completed | Rotovator received and sent to the Nursery | 755/010/5/05/1234
3xBrushcutters & 1 x Blower -A11/30 | 755010 | 5 | 05 | 1236 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Environmental Services |  | Yes |  | Own Funds |  |  |  | 35000 | 35000 | 30035.77 | 0 | 30035.77 |  | 4964.23 |  |  | 85.82% | [9 empty] | Machines received | 755/010/5/05/1236
Insurance vehicle replacement - M07/212 | 755025 | 4 | 01 | 1013 | 05 | 05 | 04 | 01 | 250 | 001 | Environmental Protection | Other - BCM Fleet | New-260 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 298224 | 0 |  | 0 |  | 298224 | #VALUE! | #VALUE! | 0% | 2011-07-01 | 7 | Insurance Claim | N/A | N/A | None |  | N/A | Completed | Completed | 755/025/4/01/1013
Fencing of Rural Cemeteries Upgrade | 755025 | 6 | 01 | 1024 | 05 | 05 | 04 | 01 | 320 | 002 | Community and social services | Environmental Services | Renewal-320 |  | Yes | Own Funds c/o | #VALUE! | 154956 | #VALUE! |  | 314956 | 69100 | 142210 | 211310 |  | 103646 | #VALUE! | #VALUE! | 67.09% | 2011-07-01 | 41 | BCMM | BIA | N/A | None |  | None | March 2012 | Pallisade fencing 30meters completed in needs camp cemetery. The contractor appointed for the kuni village cemtery is near completion. A further R79 000 will be utilised to fence one of the rural cemeteries and a roll over is required. | 755/025/6/01/1024
3x Brushcutters - A11/105 | 755025 | 5 | 05 | 1239 | 05 | 02 | 01 | 01 | 250 | 001 | Community and social services | Amenities |  | Yes |  | Own Funds |  |  |  |  | 33000 | 0 | 0 | 0 |  | 33000 |  |  | 0% | [9 empty] | Machines have been ordered and will be delivered in June 2012. | 755/025/5/05/1239
9x Brushcutters - A11/95 | 755025 | 5 | 05 | 1258 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Amenities |  | Yes |  | Own Funds |  |  |  |  | 88000 |  | 76726.89 | 76726.89 |  | 11273.11 |  |  | 87.19% | [9 empty] | Machines delivered | 755/025/5/05/1258
Dry Sanitation & Greywater Recycling | 755035 | 6 | 63 | 1100 | 05 | 09 | 01 | 01 | 320 | 002 | Waste Water Management | Waste Water |  |  | Yes | Department of Science & Technology c/o (DST) | #VALUE! | 173830 | #VALUE! |  | 173830 | 0 | 0 | 0 |  | 173830 | #VALUE! | #VALUE! | 0% | [9 empty] | Project has been transferred to Sanitation Department by IED' office | 755/035/6/63/1100
Waste Minimisation | 755035 | 6 | 63 | 1101 | 05 | 09 | 01 | 01 | 320 | 002 | Community and social services | Cleansing |  |  | Yes | Department of Science & Technology c/o (DST) | #VALUE! | 160317 | #VALUE! |  | 160317 | 0 | 150000 | 150000 |  | 10317 | #VALUE! | #VALUE! | 93.56% | [9 empty] | Waste Minimisation infrasturture being procudred through informal tender | 755/035/6/63/1101
Egerton Railway Station Massacre Memorail Site | 760005 | 6 | 78 | 1100 | 05 | 03 | 01 | 01 | 190 | 002 | Sports and Recreation | Amenities |  |  | Yes | Office of the Premier c/o | #VALUE! | 500000 | #VALUE! |  | 500000 | 145538.39 | 287041 | 432579.39 |  | 67420.61 | #VALUE! | #VALUE! | 86.52% | [7 empty] | Service provider appointed. | 2012-03-01 | Project complete | 760/005/6/78/1100
Continuation of refurbishment of KWT Hall / Cambridge | 760025 | 4 | 01 | 1014 | 05 | 08 | 01 | 01 | 170 | 001 | Community and social services | Amenities | Renewal-170 |  | Yes | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 2792507 | 1114241.49 | 600431.97 | 1714673.46 |  | 1077833.54 | #VALUE! | #VALUE! | 61.4% | 2011-09-10 | 42 | BCM | n/a | Complete | n/a |  | Tender closed 05/08/2011 |  | KWT Town Hall - validity period expired. To be resubmitted to BAC in the new financial year. Roll over requested. Cambridge Town Hall - Phase 1: complete. Phase 2 has commenced and project to be complete by the end of August 2012. | 760/025/4/01/1014
Upgrading of Beacon Bay Library | 760025 | 4 | 01 | 1015 | 05 | 08 | 01 | 01 | 170 | 001 | Community and social services | Amenities | Renewal-180 |  | Yes | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 363795 | 333656.82 | 23512.79 | 357169.61 |  | 6625.39 | #VALUE! | #VALUE! | 98.18% | 2011-11-12 | 29 | BCM | n/a | Complete | n/a |  | Tender closed 05/08/2011 | May 2012 | Project complete and balance of funds requested to be rolled over and to be utilised for the refurbishment of the kitchen. | 760/025/4/01/1015
Rural Communit Halls Rehabilitation ( Airport St Mary) | 760025 | 6 | 61 | 1106 | 05 | 08 | 01 | 01 | 170 | 001 | Community and social services | Amenities | Renewal-180 |  | Yes | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 625764 | 312280.7 | 111948.79 | 424229.49 |  | 201534.51 | #VALUE! | #VALUE! | 67.79% | 2011-11-12 | 29 | BCM | n/a | Complete | n/a |  | Tender closed 05/08/2011 | May 2012 | Rehabilitation of both halls have been completed. Released the retention payments. Roll over requested. | 760/025/6/61/1106
1X Lawnmower & 1 X Brushcutter -A11/59 | 765010 | 5 | 05 | 1242 | 05 | 02 | 01 | 01 | 260 | 002 | Community and social services | Support Services | renewal-320 | Yes |  | Own Funds | #VALUE! | 4890900 | #VALUE! |  | 36000 | 0 | 24931.48 | 24931.48 |  | 11068.52 | #VALUE! | #VALUE! | 69.25% | [9 empty] | Equipment replaced as per insurance claim. Project complete. | 765/010/5/05/1242
1xBlower, Pole Pruner, Microphone - A11/88 | 765010 | 5 | 05 | 1248 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Amenities |  | Yes |  | Own Funds |  |  |  |  | 56000 | 0 | 45832.57 | 45832.57 |  | 10167.43 |  |  | 81.84% | [9 empty] | Equipment replaced as per insurance claim. Project complete. | 765/010/5/05/1248
Rural Sports Facilities | 765010 | 6 | 61 | 1107 | 05 | 08 | 01 | 01 | 180 | 001 | Sports and Recreation | Amenities | Renewal-180 |  | Yes | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 406901 | 406901 | 0 | 406901 |  | 0 | #VALUE! | #VALUE! | 100% | 2011-11-12 | 29 | BCM | n/a | Complete | n/a |  | Tender closed 05/08/2011 | May 2012 | The amount R406, 901 was journalized into the Sports Facilities USDG vote 7650104361052 as the funds from the sports facilities project was utilized to pay service providers for the MIG funded project of Rural Sports Facilities due to MIG funding not being rolled over at that stage of the financial year (July 2011). | 765/010/6/61/1107
CCTV Camera System - A10/30 | 765010 | 5 | 05 | 1209 | 05 | 02 | 01 | 01 | 270 | 001 | Community and social services | Amenities |  | Yes |  | Own Funds | #VALUE! | 17100 | #VALUE! |  | 17100 | 14933.96 | 0 | 14933.96 |  | 2166.04 | #VALUE! | #VALUE! | 87.33% | [9 empty] | CCTV system was replaced at BC Stadium as per insurance claim. Project complete. | 765/010/5/05/1209
Upgrading of Needs Camp Sportfield | 765010 | 6 | 01 | 1025 | 05 | 08 | 01 | 01 | 160 | 001 | Sports and Recreation | Amenities | Renewal-160 |  | Yes | Own Funds c/o | #VALUE! | 149123 | #VALUE! |  | 2500000 | 3104.64 | -3104.64 | 0 |  | 2500000 | #VALUE! | #VALUE! | 0% | 9/10 | 33 | BCM | Bulk Infstructure needed | Bid documents for the appoitnment of a professional service provider submitted to SCM | n/a |  | Waiting for item to be placed on BSC agenda |  | Tender advert closed on the 04 April 2012. SCM have finalized price/ HDI Ranking. There is no committment for this project, therefore the project cannot proceed. | 765/010/6/01/1025
Upgrading of Rural Sportsfields | 765010 | 6 | 01 | 1026 | 05 | 08 | 01 | 01 | 160 | 001 | Sports and Recreation | Amenities | Renewal-160 |  | Yes | Own Funds c/o | #VALUE! | -203783 | #VALUE! |  | 72038 | 71759.17 | -13462.68 | 58296.49 |  | 13741.51 | #VALUE! | #VALUE! | 80.92% | 09/10 | 45 | BCM | Bulk Infstructure needed | n/a | n/a |  | Orders awarded for phases 1, 2 and 3 | 31/03/2012 | Perimeter fencing at Nkqonkweni has been done. Phase 1 completed. Phase 2 grass seeding to be done. Phase 3 which involves maintenance of the field to follow there after. Orders for phase 2 and phase 3 have been issued by SCM in the last financial year. | 765/010/6/01/1026
Ruth Belonsky Swimming Pool | 765015 | 4 | 01 | 1016 | 05 | 03 | 01 | 01 | 160 | 001 | Community and social services | Amenities | New-160 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 12720 | 12719.3 | -12719.3 | 0 |  | 12720 | #VALUE! | #VALUE! | 0% | 10/11 | 5 | BCM | n/a | n/a | n/a |  | Project complete |  | Project was Completed in September 2011 | 765/015/4/01/1016
Zoo CCTV Camera System - A11/84 | 765025 | 5 | 05 | 1250 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Amenities |  | Yes |  | Own Funds |  |  |  |  | 46000 | 45984 | 0 | 45984 |  | 16 |  |  | 99.97% | [9 empty] | Project Completed | 765/025/5/05/1250
3X Brushcutters - A11/112 | 760025 | 5 | 05 | 1257 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Amenities |  | Yes |  | Own Funds |  |  |  |  | 33000 |  | 28860 | 28860 |  | 4140 |  |  | 87.45% | [9 empty] | Completed | 760/025/5/05/1257
Upgrading Of Zoo Offices & Ablution Blocks | 765025 | 6 | 01 | 1027 | 05 | 03 | 01 | 01 | 190 | 001 | Sports and Recreation | Amenities | Renewal-190 |  | Yes | Own Funds c/o | #VALUE! | -197247 | #VALUE! |  | 723254 | 83600 | 89276.18 | 172876.18 |  | 550377.82 | #VALUE! | #VALUE! | 23.9% | 9/10 | 22 | BCM | n/a | Planning and specifications done by Architects division | n/a |  | N/A |  | The service provider that was appointed by the tender process has made very little progress on site as he has indicated that he is experiencing cash flow problems. The Architects Division who are Project Managers has issued the service provider with 3 letters instructing him to show due diligence. Due to slow progress contractor working to penalties of R750.00 a day from 25 May 2012 until completion. A roll over has been requested | 765/025/6/01/1027
Fencing Of Zoo c/o | 765025 | 6 | 01 | 1028 | 05 | 03 | 01 | 01 | 190 | 001 | Sports and Recreation | Amenities | Renewal-190 |  | Yes | Own Funds c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 606481 | 238111.2 | 546.49 | 238657.69 |  | 367823.31 | #VALUE! | #VALUE! | 39.35% | 09/10 | 22 | BCM | n/a | Planning and specifications done by Architects division | n/a |  | N/A |  | The service provider that was appointed by the tender process has made very little progress on site as he has indicated that he is experiencing cash flow problems. The Architects Division who are Project Managers has issued the service provider with 3 letters instructing him to show due diligence. Due to slow progress contractor working to penalties of R750.00 a day from 25 May 2012 until completion.A roll over has been requested | 765/025/6/01/1028
Intergrated Beach Front hub | 765035 | 4 | 01 | 1017 | 05 | 09 | 01 | 01 | 220 | 001 | Community and social services | Amenities | New-220 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 500000 | 460.53 | -460.53 | 0 |  | 500000 | #VALUE! | #VALUE! | 0% | 9/10 | 5 | BCM | n/a | n/a | n/a |  | N/A |  | Vote number has been given to Director of Engineering Services to utilize for for Engineering related projects in Marina Glen as per Top Management decision. A roll over has been requested. | 765/035/4/01/1017
Isuzu NQR 500 Cage Tipper - M09/153 | 765030 | 6 | 01 | 1029 | 05 | 08 | 01 | 01 | 250 | 001 | Community and social services | Other - BCM Fleet | New-260 | Yes |  | Own Funds c/o | #VALUE! | -348765 | #VALUE! |  | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 9/10 | N/A | BCM | N/A | Planning and specifications done by Mechanical Services | n/a |  | Vehicle was handed over to Beaches | Completed: insurance claim | Project completed | 765/030/6/01/1029
Grass Cutting Equipment | 770005 | 4 | 01 | 1018 | 05 | 08 | 01 | 01 | 260 | 001 | Community and social services | Cleansing | New-260 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 1300000 | 146711.14 | 415649.78 | 562360.92 |  | 737639.08 | #VALUE! | #VALUE! | 43.26% | 2011-07-01 | All | BCMM | BIA | n/a | None |  | Specs submitted to SCM |  | Orders for the grass mowing equipment is with SCM and the machines will be delivered in July 2012. Second phase purchasing is to be submitted to SCM for re-advertisement. | 770/005/4/01/1018
Insurance vehicle replacement : M09/198 | 770005 | 5 | 05 | 1235 | 05 | 08 | 01 | 01 | 260 | 001 | Other | Cleansing | New-260 | Yes |  | Own Funds | #VALUE! | 1700000 | #VALUE! |  | 1700000 | 0 | 0 | 0 |  | 1700000 | #VALUE! | #VALUE! | 0% | [9 empty] | Tender process in place - Replacement vehicle | 770/005/5/05/1235
Refuse removal Skips | 770015 | 4 | 01 | 1019 | 05 | 10 | 01 | 01 | 100 | 001 | Waste Management | Cleansing | New-100 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 684204 | 0 | 684204 |  | 315796 | #VALUE! | #VALUE! | 68.42% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | Tender awarded by the Bid Adjudication Committee in October 2011 | Completed | Project completed, savings identified. | 770/015/4/01/1019
Drop Off Points - Solid Waste | 770030 | 6 | 01 | 1030 | 05 | 10 | 01 | 01 | 100 | 001 | Waste Management | Cleansing | New-100 |  | Yes | Own Funds c/o | #VALUE! | -210479 | #VALUE! |  | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | Funding spent | 2011-05-01 | Completed | 770/030/6/01/1030
Regional Waste Disposal Site | 770030 | 4 | 01 | 1020 | 05 | 10 | 01 | 01 | 100 | 001 | Waste Management | Cleansing | New- 100 | Yes |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 8644.7 | -8644.7 | 0 |  | 1000000 | #VALUE! | #VALUE! | 0% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | Project to be implemented by Engineering - Roads Department | June 2012 | Engineering Roads Department confirmed that Tender for Contract 26 has been awarded and all processes of construction will take place. | 770/030/4/01/1020
TOTAL : DIRECTORATE OF COMMUNITY SERVICES | [10 empty] | 9 | [5 empty] | #VALUE! | 7761052 | #VALUE! | #VALUE! | 57634998 | 15762552.78 | 14270411.14 | 30178502.31 | 0 | 27456495.69 | #VALUE! | #VALUE! | 52.36%
TOTAL: CAPITAL PROJECTS - ALL DIRECTORATES | [18 empty] | #REF! | #REF! | 729035035 | 172660158.23 | 106227539.1 | 278887697.33 | 225212.1 | 450147337.67 | #REF! |  | 38.25%
Insurance Asset Replacement | 320005 | 5 | 05 | 1200 | 05 | 02 | 01 | 01 | 320 | 002 | Budget & Treasury | Support Services | renewal-320 | Yes |  | Own Funds | #VALUE! | 4890900 | #VALUE! |  | 2506349 | 0 | 0 | 0 |  | 2506349 | #VALUE! | #VALUE! | 0% | [9 empty] | This contingent vote( institutional) is in respect of those assets that are replaced due to insurance claims. When ever an insurance loss occurrs and an asset is to be replaced , an equivalent amount of the asset is transferred from this budget to the relevant department in oder to capitalise the asset. | 320/005/5/05/1200
TOTAL: CAPITAL PROJECTS - GRAND TOTAL | [16 empty] | #REF! | #REF! | #REF! | #REF! | 731541384 | 172660158.23 | 106227539.1 | 278887697.33 | 225212.1 | 452653686.67 | #REF! | #REF! | 38.12%
[17 empty] | #VALUE! | #VALUE! | #VALUE! |  |  | 0 |  |  |  |  | #VALUE!
[17 empty] | #VALUE! | #VALUE! | #VALUE! |  |  | 0 |  |  |  |  | #VALUE!
[17 empty] | #VALUE! | #VALUE! | #VALUE! |  |  | 0 |  |  |  |  | #VALUE!
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%
[22 empty] | 0 |  |  |  |  | 0%

## Appendix O
BUFFALO CITY METROPOLITAN MUNICIPALITY
APPENDIX O
CAPITAL PROGRAMME BY PROJECT BY WARD REPORT AS AT 30 JUNE 2012
Project Name | Vote number | Vote number | Vote number | Vote number | NT | NT | NT | NT | NT | NT | A5 | Service | 34a & 34b | New Asset | Renewal of Existing Asset | Ward No. | Funding (source) | Approved Budget | Adjustment | Rollover Adjustment Budget | Adjustment | Mid -Year Adjustment Budget | Expenditure | Current Month Expenditure | YTD Exp. | Commitments | Variance | % Expenditure vs Rollover Adjustment Budget | % Expenditure vs Aproved Budget | % Expenditure vs Mid year Adjustment Budget | Date of 1st IDP adoption | Ward | Land of Ownership | Services(BIA) (BIA= bulk infra aval) | Planning(EIA, Designs, Survey,) | Dispute(legal etc. |  | SCM process(stage) (date of adv if applicable) | Date of Expected completion | COMMENTS | VOTE NUMBER
EXECUTIVE SUPPORT SERVICES
Councillor's office | 105005 | 6 | 01 | 1100 | 05 | 01 | 01 | 01 | 311 | 002 | Executive and Council | Support Services |  | Yes |  | 1-50 | Own Funds c/o | #VALUE! | 2060845 | #VALUE! |  | 2060845 | 279870.93 | -10545.36 | 269325.57 |  | 1791519.43 | #VALUE! | #VALUE! | 13.07% | [9 empty] | The specification for the the furniture has been done and the tender will be advertised very soon. | 105/005/6/01/1100
Upgrading of Sisa Dukashe, New Lands, Ndevana Stadium | 105005 | 6 | 76 | 1100 | 05 | 01 | 01 | 01 | 160 | 002 | Executive and Council | Amenities |  |  | Yes | 11,49,26 | Department of Sports, Arts & Culture c/o (SARC) | #VALUE! | 2272303 | #VALUE! |  | 2272303 | 268581.65 | 134697.47 | 403279.12 |  | 1869023.88 | #VALUE! | #VALUE! | 17.75% | [7 empty] | Newlands & Ndevana need to be re-advertised |  | SISA DUKASHE & GOMPO - Project is complete & handed over to Community Srvices Directorate, NEWLANDS & NDEVANA - Project is on termination stage & waiting for approval. | 105/005/6/76/1100
Upgrading of Bisho, Dimbaza, Peelton, Madramini & Victoria Grounds Stadium | 105005 | 6 | 76 | 1101 | 05 | 01 | 01 | 01 | 160 | 002 | Executive and Council | Amenities |  |  | Yes | 36,37,45,43 | Department of Sports, Arts & Culture c/o (SARC) | #VALUE! | 6598469 | #VALUE! |  | 6598469 | 116772.58 | 109994.01 | 226766.59 |  | 6371702.41 | #VALUE! | #VALUE! | 3.437% | [7 empty] | Bisho, Peelton and Dimbaza projects need to be re-advertised |  | BISHO, PEELTON, DIMBAZA - Contractors doing the work was terminated due to poor performance, LOWER MNGQESHA - No funds VICTORIA GROUNDS - project is complete and handed over to community services. Only renovation to Floodlights that requires R1.5m to upgrade | 105/005/6/76/1101
Upgrading of Tsholomnqa, Parkside, Needs Camp & North | 105005 | 6 | 76 | 1102 | 05 | 01 | 01 | 01 | 160 | 002 | Sports and Recreation | Amenities |  |  | Yes | 32,10,38,47 | Department of Sports, Arts & Culture c/o (SARC) | #VALUE! | 2208935 | #VALUE! |  | 2208935 | 589162.22 | 0 | 589162.22 |  | 1619772.78 | #VALUE! | #VALUE! | 26.67% | [9 empty] | TSHOLOMNQA, PARKSIDE & NORTHEND: Project is complete & handed over to community services. NEEDSCAMP - Project is complete & water problem in the area & issue is currently addressed by BCMM water section & Amatola Water. | 105/005/6/76/1102
Laptop - V Tokwe - A11/90 | 105012 | 5 | 05 | 1246 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services |  | Yes |  | N/A | Own Funds |  |  |  |  | 9000 | 0 | 0 | 0 |  | 9000 |  |  | 0%
Leiden Twinning - Floodplain | 120005 | 6 | 83 | 1100 | 05 | 10 | 01 | 01 | 070 | 002 | Water | Water |  |  | Yes |  | Leiden Platform c/o | #VALUE! | 488000 | #VALUE! |  | 488000 | 0 | 0 | 0 |  | 488000 | #VALUE! | #VALUE! | 0% | [9 empty] | Transfer of land in Duncan Village from EC Dept of Local Government and traditional Affairs still a challenge. Funding for Floodplain/Safe Park; multiyear project | 120/005/6/83/1100
Leiden Twinning - Solid Waste Drop-off Points | 120005 | 6 | 83 | 1101 | 05 | 10 | 01 | 01 | 100 | 002 | Waste Management | Cleansing |  |  | Yes | 6,7,8,9,10 | Leiden Platform c/o | #VALUE! | 974718 | #VALUE! |  | 974718 | 0 | 0 | 0 |  | 974718 | #VALUE! | #VALUE! | 0% | [9 empty] | SCM and legal challenges. - Multiyear project | 120/005/6/83/1101
Leiden Twinning - Sanitation | 120005 | 6 | 83 | 1102 | 05 | 10 | 01 | 01 | 070 | 002 | Executive and Council | Waste Water |  |  | Yes |  | Leiden Platform c/o | #VALUE! | 746897 | #VALUE! |  | 746897 | 628798.84 | 101306.23 | 730105.07 |  | 16791.93 | #VALUE! | #VALUE! | 97.75% | [9 empty] | Challenges with Cambridge Location project - Sanitation department to sort out and advise progress with opening of facilities. | 120/005/6/83/1102
Leiden Twinning Project - Solid Waste | 120005 | 6 | 83 | 1103 | 05 | 10 | 01 | 01 | 100 | 002 | Waste Management | Cleansing |  |  | Yes | 6,7,8,9,10 | Leiden Platform c/o | #VALUE! | 512606 | #VALUE! |  | 512606 | 0 | 0 | 0 |  | 512606 | #VALUE! | #VALUE! | 0% | [9 empty] | Solid waste project for 2012/2013 following study by Utrecht university in Netherlands. | 120/005/6/83/1103
3 x Computers & Accessories - A10/107 | 120010 | 5 | 05 | 1224 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services | Renewal-270 | Yes |  | N/A | Own Funds | #VALUE! | 25000 | #VALUE! |  | 22146 | 22145.66 | 0 | 22145.66 |  | 0.34 | #VALUE! | #VALUE! | 100% | [9 empty] | Actioned | 120/010/5/05/1224
3 x Computers, Accessories, plasma - A10/124 | 120010 | 5 | 05 | 1223 | 05 | 02 | 01 | 01 | 270 | 001 | Executive and Council | Support Services | Renewal-270 | Yes |  | N/A | Own Funds | #VALUE! | 32000 | #VALUE! |  | 32000 | 0 | 26044.04 | 26044.04 |  | 5955.96 | #VALUE! | #VALUE! | 81.39% | [9 empty] | Requistion for Additional computers to be purchased for staff at call centre. IT has requisition. | 120/010/5/05/1223
TOTAL : EXECUTIVE SUPPORT SERVICES | [10 empty] | 1 | [6 empty] | #VALUE! | 15919773 | #VALUE! | 0 | 15925919 | 1905331.88 | 361496.39 | 2266828.27 | 0 | 13659090.73 | #VALUE! | #VALUE! | 14.23%
MUNICIPAL MANAGER
Furniture | 205005 | 4 | 01 | 1154 | 05 | 01 | 01 | 01 | 270 | 001 | Planning & Development | Transport Planning | New-270 | Yes |  | N/A | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 50000 | 0 | 0 | 0 |  | 50000 | #VALUE! | #VALUE! | 0% | [7 empty] | The procurement of Councillor's notebooks has commenced. At this stage ICT department is trying to further expedite the procurements of laptops for Councillors, it is envisaged that within this financial year funding for this project will be fully utilised. | 2012-06-01 | Arrangements to procure furniture for the MPAC chairpersorn is underway, this budget was made available during the budget adjustment process. Expenditure will be completed within this financial year. | 205/005/4/01/1154
Councillor's IT requirements (Laptops) | 205005 | 4 | 01 | 1001 | 05 | 01 | 01 | 01 | 270 | 001 | Executive and Council | Support Services | New-270 | Yes |  | N/A | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 865125.09 | 26271.93 | 891397.02 |  | 108602.98 | #VALUE! | #VALUE! | 89.14% | [7 empty] | The procurement of Councillor's notebooks has commenced. At this stage ICT department is trying to further expedite the procurements of laptops for Councillors, it is envisaged that within this financial year funding for this project will be fully utilised. | 2012-06-01 | The departnment is satisfied with the current expenditure for this project and it is anticipated that the project will be completed within this financial year. | 205/005/4/01/1001
TOTAL : MUNICIPAL MANAGER | [10 empty] | 2 | [6 empty] | #VALUE! | 0 | #VALUE! | #VALUE! | 1050000 | 865125.09 | 26271.93 | 891397.02 | 0 | 158602.98 | #VALUE! | #VALUE! | 84.89%
0
CHIEF OPERATIONS OFFICER
Mdantsane Zone 18 CC Phase 2-P3 | 255005 | 4 | 36 | 1001 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 21 | BCM | Bulk services are available on this site | Consultant completed Engineering Designs however unable to proceed with procurement due to not having EIA renewal. EIA were to be completed in the beginning of 2011. | The Directorate of Development facilitation (Kamva Qwede) to fast tract the EIA. Biotechnology & Environmental Specialist Consultancy Cc has been appointed to complete the EIA. They advised Full EIA will have to be completed, this time frame (6 months). The delays will affect USDG funding expenditure. |  | Once EIA has been finalised , tenders for the provision of internal services will be called in February 2012 and award contract by May 2012 through BEC and BAC approval | EIA will be completed by January 2012. Tender advertisement and commencement of provision of internal services will take place commencing after January 2012. Project will be completed in the 2012/2013 financial year | Budget adjusted due to planning challenges which delayed implementation. | 255/005/4/36/1001
Manyano & Thembelihle Phase 2-P3 | 255005 | 4 | 36 | 1002 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 17 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 19055300 | 5300336.83 | 2486388.51 | 7786725.34 |  | 11268574.66 | #VALUE! | #VALUE! | 40.86% | 2011-06-30 | 17 | BCM | Bulk services are available on this site | Previously completed | Contractor appointed Kulanti has temporary moved off site citing various challenges minor |  | None | Internal services in the 2011/2012 financial year | The project was delayed by labour disputes between the contractor and the community which had been resolved. Revised schedule which was agreed with the contractor is behind and the contractor has been informed of the penalties. Budget will be rolled over to 2012/2013 financial year. | 255/005/4/36/1002
Second Creek (Turn Key)-P3 | 255005 | 4 | 36 | 1003 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 19 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 13940770 | 177427.99 | 0 | 177427.99 |  | 13763342.01 | #VALUE! | #VALUE! | 1.273% | 2011-06-30 | 19 | BCM | Bulk services are available on this site | Turn key approach (construction of internal services/top structure) | none |  | Adjudication report done. To present report to BEC and BAC in few weeks time.Time delays are being experienced in finalizing this award between PMU unit and SCM. The challenges have been escalated to senior management to addressed and finalized The delays will affected budget expenditure and may result in the reducing of the allocated budget should an award not be finalized urgently | Internal services are anticipated to be completed in the 2012/2013 financial year depending on the appointment of the contractor. | The service provider has been appointed for the construction of both internal service and top structure. It is anticipated that the project will be completed in 13/14 financial year, however the funding is fully committed. Budget could not be spent in the current financial year due to procurement challenges. | 255/005/4/36/1003
Masibambane-P3 | 255005 | 4 | 36 | 1004 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 17 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 250000 | 1851.35 | 22710.05 | 24561.4 |  | 225438.6 | #VALUE! | #VALUE! | 9.825% | 2011-06-30 | 17 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | N/A |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1004
Masibulele-P3 | 255005 | 4 | 36 | 1005 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 17 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 250000 | 1335.39 | 99736.31 | 101071.7 |  | 148928.3 | #VALUE! | #VALUE! | 40.43% | 2011-06-30 | 17 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1005
Velwano | 255005 | 4 | 36 | 1006 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 14 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 450000 | 546.3 | 24015.1 | 24561.4 |  | 425438.6 | #VALUE! | #VALUE! | 5.458% | 2011-06-30 | 14 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager) as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1006
Chris Hani Park Phase 3-P3 | 255005 | 4 | 36 | 1007 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 12 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 200000 | 2291.43 | -2291.43 | 0 |  | 200000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 12 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1007
Ilinge -P 3 | 255005 | 4 | 36 | 1008 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 12 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 240000 | 0 | 240000 |  | 360000 | #VALUE! | #VALUE! | 40% | 2011-06-30 | 12 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1008
Gwentshe Village- P3 | 255005 | 4 | 36 | 1009 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 14 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 50000 | 0 | 24561.4 | 24561.4 |  | 25438.6 | #VALUE! | #VALUE! | 49.12% | 2011-06-30 | 14 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1009
Fynbos Informal 1-P3 | 255005 | 4 | 36 | 1013 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 10 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 500000 | 0 | 77000 | 77000 |  | 423000 | #VALUE! | #VALUE! | 15.4% | 2011-06-30 | 10 | BCM | Turn Key Project Stage 1 - Appointment of professional team feasibility, geotechnical study internal services design top structure foundation design Stage 2 - Procurement of contractor to role out internal services top structure | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed for the planning, design and project management. It is anticipated that the project will be completed in 14/15 financial year, however the funding is fully committed. | 255/005/4/36/1013
Fynbos Informal 2-P3 | 255005 | 4 | 36 | 1014 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 10 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 500000 | 0 | 0 | 0 |  | 500000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 10 | BCM | Turn Key Project Stage 1 - Appointment of professional team feasibility, geotechnical study internal services design top structure foundation design Stage 2 - Procurement of contractor to role out internal services top structure | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed for the planning, design and project management. It is anticipated that the project will be completed in 14/15 financial year, however the funding is fully committed. | 255/005/4/36/1014
Ndacama-P3 | 255005 | 4 | 36 | 1015 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 10 | BCM | Turn Key Project Stage 1 - Appointment of professional team feasibility, geotechnical study internal services design top structure foundation design Stage 2 - Procurement of contractor to role out internal services top structure | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Delays in completion of the EIA will affect the appointment of the contractor for the provision of internal services and top structures. Project will be completed in 2012 / 2013 financial year. | Service provider has been appointed for the planning, design and project management. It is anticipated that the project will be completed in 14/15 financial year, however the funding is fully commited. | 255/005/4/36/1015
Mathemba Vuso-P3 | 255005 | 4 | 36 | 1017 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 14 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 300000 | 0 | 24561.4 | 24561.4 |  | 275438.6 | #VALUE! | #VALUE! | 8.187% | 2011-06-30 | 14 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1017
Deluxolo Village-P3 | 255005 | 4 | 36 | 1018 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 20 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 200000 | 0 | 0 | 0 |  | 200000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 20 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1018
Francis Mei-P3 | 255005 | 4 | 36 | 1019 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 20 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 100091 | 0 | 0 | 0 |  | 100091 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 20 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1019
Mahlangu Village-P3 | 255005 | 4 | 36 | 1020 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 21 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 200000 | 0 | 0 | 0 |  | 200000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 21 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1020
Sisulu Village-P3 | 255005 | 4 | 36 | 1021 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 11 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 300000 | 0 | 0 | 0 |  | 300000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 11 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1021
Winnie Mandela-P3 | 255005 | 4 | 36 | 1022 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 17 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 400000 | 0 | 0 | 0 |  | 400000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 17 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1022
Dacawa-P3 | 255005 | 4 | 36 | 1023 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 12 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 400000 | 0 | 0 | 0 |  | 400000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 12 | BCM | Bulk services are available on this site | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | EIA which has lapsed should have been completed in the beginning of the 2010 / 2011 financial year. The lapsed record of decision must be addressed within the next four weeks to avoid the delays with engineering design for internal services design which could ultimately delay the construction on site . |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Financial year 2013 / 2014 | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1023
Sunny South-P3 | 255005 | 4 | 36 | 1025 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 31 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 1760.3 | 81064.26 | 82824.56 |  | 517175.44 | #VALUE! | #VALUE! | 13.8% | 2011-06-30 | 31 | BCM | To prepare Bid Specification report to appoint consultants to manage the provision of services and top structure construction. | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved |  |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Project will be completed in 2012 / 2013 financial year. | Service provider has been appointed. The project is a multi- year, allocated unspent funding to rolled over to 2012/2013 financial year. | 255/005/4/36/1025
Potsdam Unit p : Stage 2 P3 | 255005 | 4 | 36 | 1132 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 21 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1360000 | 7385.96 | 1352614.03 | 1359999.99 |  | 0.01 | #VALUE! | #VALUE! | 100% | 2011-06-30 | 31 | BCM | To prepare Bid Specification report to appoint consultants to manage the provision of services and top structure construction. | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved |  |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Project will be completed in 2012 / 2013 financial year. | Site verifications were done by the consultant, annual contractor is on site finalizing the rectification of the sewer connections. | 255/005/4/36/1132
Block yard TRA-P3 | 255005 | 4 | 36 | 1133 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 6 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2500000 | 0 | 0 | 0 |  | 2500000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 31 | BCM | To prepare Bid Specification report to appoint consultants to manage the provision of services and top structure construction. | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved |  |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant to be made by March 2012, designs to be completed by May 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | Project will be completed in 2012 / 2013 financial year. | Procurement delays due to budget shortfall. Additional funding has been allocated in the mid - year adjustment budget. Contractor has been appointed. There are delays in the commencement of the contractor due to insufficient documentation (working drawings) that are still held by the liquidated consultant. the matter is being resolved between Engineering and Legal department | 255/005/4/36/1133
Reeston Phase 3 Stage 2-P3 | 255005 | 4 | 35 | 1001 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 13 | Human Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 15000000 | 2743815.66 | 1210651.2 | 3954466.86 |  | 11045533.14 | #VALUE! | #VALUE! | 26.36% | 2011-06-30 | 13 | BCM | Bulk services are available on this site | No challenges, | None |  | Contractor appointed in December 2011 | Final completion anticipated only in 13/14 financial year. | Contractor has been appointed and site handover was held on 14 March 2012.Contractor is progressing on site | 255/005/4/35/1001
DVRI Pilot project 323 units (Mekeni ,Competition site,Haven Hills) | 255005 | 4 | 35 | 1002 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 6,8 | Human Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 7241014 | 553944.86 | -487212.46 | 66732.4 |  | 7174281.6 | #VALUE! | #VALUE! | 0.9216% | 2011-06-30 | 19 | BCM | Completed | Completed | NONE |  | Completed | Project will be completed in the current (2012 / 2013) financial year. | Project is about 50% complete, the challenge is that the contract of the Contractor has expired legal department is assisting with the renewal of the contract. The City Manager has approved the renewal however he has instructed that the report to be tabled to BAC. The Delays in construction of Block Yard TRA will have direct impact on construction progress in Competition site. | 255/005/4/35/1002
Mdantsane Access/Buffalo | 255005 | 4 | 35 | 1003 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  |  | Human Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 13 | BCM | Provision of temporary water and sanitation | DDP is to complete detailed planning of projects for DVR - turnkey development. Currently in progress. | None |  | Upon approval of site development plan by Council, informal tenderers will be invited to undertake the provision of temporary water and sanitation. | 2012 / 2013 | Budget adjusted due to planning challenges which delayed implementation. | 255/005/4/35/1003
Reeston Phase 3 Stage 3 | 255005 | 4 | 35 | 1004 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  |  | Human Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 13 | BCM | Turn Key Project Stage 1 - App of professional team feasibility, geotechnical study internal services design top structure foundation design Stage 2 - Procurement of contractor to role out internal services top structure | Turn key approach (Internal services and top structure role out): Stage 1: (Appointment of project consultants) to undertake the internal services design, project manage internal services and top structure provision. EIA requires renewal, to be addressed by Kamva Qwede ( Manager)as a matter of urgency: Stage 2: procurement of contractor for the provision of internal services also including top structure as per operating budget. this will be undertaken was consultants have been procured and designs completed/ approved | Directorate of Planning is to complete detailed planning of projects for Duncan Village Redevelopment. Turnkey Development - To prepare bid specification document for the appointment of professional team in March 2012 to undertake project management and internal services designs. |  | The tender closed on 28th October 2011 and the bid documents are currently under evaluation for BEC consideration. Appointment of consultant by January 2012, designs to be completed by April 2012. Call for tenders to award contract for internal services including top structure provision (Operating budget) by June 2012. | 2012 / 2013 Financial year | Service provider has been appointed. The project is a multi- year, allocated funding to be spent by June 2012. | 255/005/4/35/1004
Block yard TRA-P3 | 255005 | 4 | 35 | 1005 | 05 | 06 | 01 | 01 | 080 | 001 | Housing | Housing | New-120 | Yes |  | 6 | Human Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 668500 | 0 | 0 | 0 |  | 668500 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 6 | BCM | Provision of temporary water and sanitation | DDP is to complete detailed planning of projects for DVR - turnkey development. | None |  | Contractor(Orae Construction) has been appointed in December 2011, site handover will be in January 2012 | 2012 / 2013 Financial year | Procurement delays due to budget shortfall. Additional funding has been allocated in the mid - year adjustment budget. Contractor has been appointed. There are delays in the commencement of the contractor due to insufficient documentation (working drawings) that are still held by the liquidated consultant. the matter is being resolved between Engineering and Legal Departments | 255/005/4/35/1005
Computers & Computer Equip. - A10/72 | 255005 | 5 | 05 | 1202 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services | Renewal-270 | Yes |  | N/A | Own Funds | #VALUE! | 7000 | #VALUE! |  | 5225 | 5224.74 | 0 | 5224.74 |  | 0.26 | #VALUE! | #VALUE! | 100% | [7 empty] | IT department is in the process of procuring the service provider. | 2011 / 2012 Financial year | Project complete, 100% expenditure incurred. | 255/005/5/05/1202
Potsdam Unit P: Stage 2: 1000 units: P3: Infrastructure | 255005 | 6 | 75 | 1100 | 05 | 06 | 01 | 01 | 080 | 002 | Housing | Housing |  | Yes |  | 21 | Local Government & Housing c/o (LGH) | #VALUE! | 336462 | #VALUE! |  | 336462 | 0 | 78881.75 | 78881.75 |  | 257580.25 | #VALUE! | #VALUE! | 23.44% | [7 empty] | Complete | 2011 / 2012 Financial year | Funding has been reserved for rectification of sewer connections to 115 sites but not sufficient, additional funds were allocated in the mid year budget adjustment. The consultant has completed verifications, contractor is on site finalising the rectifications. | 255/005/6/75/1100
Accreditation | 255005 | 6 | 75 | 1101 | 05 | 06 | 01 | 01 | 080 | 002 | Housing | Housing |  | Yes |  | 1-50 | Local Government & Housing c/o (LGH) | #VALUE! | 33903 | #VALUE! |  | 33903 | 0 | 0 | 0 |  | 33903 | #VALUE! | #VALUE! | 0% | [7 empty] | Housing is in the process of procuring the service provider | 2011 / 2012 Financial year | It is projected that the allocated budget will be spent in this current financial year. | 255/005/6/75/1101
Z.Soga: P3: Infrastructure | 255005 | 6 | 75 | 1102 | 05 | 06 | 01 | 01 | 080 | 002 | Housing | Housing |  | Yes |  |  | Local Government & Housing c/o (LGH) | #VALUE! | 274097 | #VALUE! | -274097 | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | [7 empty] | Complete | 2011 / 2012 Financial year | Project complete and the vote has been adjusted accordingly | 255/005/6/75/1102
TOTAL : CHIEF OPERATIONS OFFICER | [10 empty] | 3 | [6 empty] | #VALUE! | 651462 | #VALUE! | #VALUE! | 65441265 | 9035920.81 | 4992680.12 | 14028600.93 | 0 | 51412664.07 | #VALUE! | #VALUE! | 21.44% | 0% | 1030% | #VALUE! | #VALUE! | 4.17e-07% | #VALUE! | #VALUE! | #VALUE! | #VALUE!
DIRECTORATE OF FINANCIAL SERVICES | [15 empty] | N/A
KWT Civic Centre Payments Hall Upgrade | 330020 | 6 | 01 | 1001 | 05 | 02 | 01 | 01 | 120 | 002 | Budget & Treasury | Support Services | Renewal-312 |  | Yes | N/A | Own Funds c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 700000 | 36000 | 186207.87 | 222207.87 |  | 477792.13 | #VALUE! | #VALUE! | 31.74% | 182.7273 |  | Municipal |  | Designs completed | None |  | tender awarded for designs | 2012-12-31 | Project to be restarted in the next financial year when additional funds are available. | 330/020/6/01/1001
Laptop insurance claim | 315005 | 5 | 05 | 1218 | 05 | 02 | 01 | 01 | 270 | 001 | Budget & Treasury | Support Services |  | Yes |  | N/A | Own Funds | #VALUE! | 9000 | #VALUE! |  | 7492 | 7492 | 0 | 7492 |  | 0 | #VALUE! | #VALUE! | 100% | [9 empty] | Project completed. | 315/005/5/05/1218
Implementation of Intenda Electronic Software System | 320010 | 6 | 75 | 1103 | 05 | 02 | 01 | 01 | 270 | 002 | Budget & Treasury | Support Services |  | Yes |  | N/A | Department of Local Government & Traditional Affairs c/o | #VALUE! | 10643 | #VALUE! |  | 10643 | 0 | 0 | 0 |  | 10643 | #VALUE! | #VALUE! | 0% | [9 empty] | Consultants to be on site in April / May. | 320/010/6/75/1103
Meter reading handheld machines | 330015 | 4 | 01 | 1157 | 05 | 02 | 01 | 01 | 260 | 002 | Budget & Treasury | Support Services |  | Yes |  | N/A | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 2856000 | 3298.68 | 2069368.32 | 2072667 |  | 783333 | #VALUE! | #VALUE! | 72.57% | [9 empty] | Tender at Evaluation stage. | 330/015/4/01/1157
Upgrading of All Zone Offices - Mdantsane | 330020 | 6 | 01 | 1002 | 05 | 02 | 01 | 01 | 120 | 002 | Budget & Treasury | Support Services | Renewal-312 |  | Yes |  | Own Funds c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 182.7273 |  | under dispute |  | Not appointed | land sale to be invetigated by Land admin |  | Not awarded. | N/A | Project being handled by Development Planning. | 330/020/6/01/1002
TOTAL : DIRECTORATE OF FINANCIAL SERVICES | [10 empty] | 4 | [6 empty] | #VALUE! | 19643 | #VALUE! | #VALUE! | 3574135 | 46790.68 | 2255576.19 | 2302366.87 | 0 | 1271768.13 | #VALUE! | #VALUE! | 64.42%
DIRECTORATE OF CORPORATE SERVICES
BCM IT Requirements (All Directorates) | 415015 | 4 | 01 | 1002 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services | New-270 | Yes |  | N/A | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 5000000 | 2334790.77 | 2281759.1 | 4616549.87 |  | 383450.13 | #VALUE! | #VALUE! | 92.33% | 2011/ 2012 financial year IDP | N/A | N/A | N/A | N/A | Not at this stage |  | Tender closes on the 13/01/2012 and evaluation of the tender will be done on the 17 January 2012. Award is expected by Friday 14 January 2012. | 31/03/2012 | There are still outstanding invoice awaiting to be captured for payment at SCM. | 415/015/4/01/1002
Laptop - S.Fuma - A10/116 | 405010 | 5 | 05 | 1225 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services | Renewal-270 | Yes |  | N/A | Own Funds | #VALUE! | 8600 | #VALUE! |  | 7493 | 7492.88 | 0 | 7492.88 |  | 0.12 | #VALUE! | #VALUE! | 100% | [7 empty] | Insurance claim, procurement in progress. |  | Insurance claim. Project completed | 405/010/5/05/1225
Laptop - L. Kapp - A11/116 | 405010 | 5 | 05 | 1259 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services |  | Yes |  | N/A | Own Funds |  |  |  |  | 9000 |  | 6656.8 | 6656.8 |  | 2343.2 |  |  | 73.96% | [9 empty] | Project completed.
6XDesktop Computers & 2x Printers - A11/98 | 415025 | 5 | 05 | 1247 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services |  | Yes |  | N/A | Own Funds |  |  |  |  | 45000 | 0 | 0 | 0 |  | 45000 |  |  | 0% | [9 empty] | Invoice awaiting to be captured for payment by the SCM.
Telecommunication network system | 415025 | 6 | 01 | 1003 | 05 | 02 | 01 | 01 | 270 | 002 | Corporate Services | Support Services | New-270 | Yes |  | N/A | Own Funds c/o | #VALUE! | 94390 | #VALUE! |  | 202275 | 0 | 73966.32 | 73966.32 |  | 128308.68 | #VALUE! | #VALUE! | 36.57% | 2011/2012 financial year IDP | N/A | N/A | N/A | N/A | Not at this stage |  | Project underway. Expenditure is expected to show during the month of January 2012. | 30/11/2011 | Invoice awaiting to be captured for payment by the SCM. | 415/025/6/01/1003
Integrated Enterprise Resource planning System | 415025 | 4 | 01 | 1003 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services | New-270 | Yes |  | N/A | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 2000000 | 0 | 0 | 0 |  | 2000000 | #VALUE! | #VALUE! | 0% | 2011/2012 financial year IDP | N/A | N/A | N/A | N/A | Not at this stage |  | Procurement through SITA has commenced and in process of creating an order. Once the order is created the service provider can commence work. It is estimated that it the project will take 4 months. |  | Feasibility study roject has commenced and it is 77% complete. The funding will be carried over to the next financial year for implementation. | 415/025/4/01/1003
Conferencing system | 415025 | 6 | 01 | 1004 | 05 | 02 | 01 | 01 | 270 | 002 | Corporate Services | Support Services | New-270 | Yes |  | N/A | Own Funds c/o | #VALUE! | -338911 | #VALUE! |  | 260030 | 248858.06 | 0 | 248858.06 |  | 11171.94 | #VALUE! | #VALUE! | 95.7% | 2011/2012 financial year IDP | N/A | N/A | N/A | N/A | Not at this stage |  | The service provider is on site and has commenced work. The expenditure is expected to show in January 2012. | 30/11/2011 | The project is complete | 415/025/6/01/1004
Radio Data Network - Mdantsane | 415025 | 6 | 01 | 1005 | 05 | 02 | 01 | 01 | 270 | 002 | Corporate Services | Support Services | New-270 | Yes |  | N/A | Own Funds c/o | #VALUE! | 8762 | #VALUE! |  | 175231 | 158129.14 | 12500 | 170629.14 |  | 4601.86 | #VALUE! | #VALUE! | 97.37% | 2011/2012 financial year IDP | N/A | N/A | N/A | N/A | Not at this stage |  | The service provider is on site and has commenced work. The expenditure is expected to show in January 2012. | 30/11/2011 | The project is complete | 415/025/6/01/1005
TOTAL : DIRECTORATE OF CORPORATE SERVICES | [10 empty] | 5 | [6 empty] | #VALUE! | -227159 | #VALUE! | #VALUE! | 7699029 | 2749270.85 | 2374882.22 | 5124153.07 | 0 | 2574875.93 | #VALUE! | #VALUE! | 66.56%
DIRECTORATE OF ENGINEERING SERVICES
Electrification | 535025 | 4 | 56 | 1001 | 05 | 13 | 01 | 01 | 060 | 001 | Electricity | Electricity | New-60 | Yes |  | 13,25,43,34, 6 | DoE(Intergrated National Electrification Programme) | #VALUE! | 0 | #VALUE! | #VALUE! | 26895000 | 11709780.79 | 8931420.04 | 20641200.83 |  | 6253799.17 | #VALUE! | #VALUE! | 76.75% | (see breakdown below) | [6 empty] | Purchase using Annual Tender | 2012-06-01 | ED329-Electrification Bulk Infrastructure Queenspark is a multi year project to be completed by 2016. Additional R5,895,000 was allocated by DoE . ED357-Cambridge Electrification completed. ED361-Potsdam Unit P Electrification contractor performing poorly ROLL OVER of R5, 561,016 is required in order to continue with the Project. ED360-Reeston Electrification completed. ED363-Kwaklifu Electrification delay with start of project ROLL OVER OF R1M will be required. | 535/025/4/56/1001
Replacement of Street Lights | 535025 | 4 | 25 | 1001 | 05 | 13 | 03 | 01 | 090 | 001 | Electricity | Electricity | Renewal-90 |  | Yes | 11,12,14,17, 20,21,22,23 ,30 | Electricity Demand Side Management Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 4000000 | 3773287 | 153504 | 3926791 |  | 73209 | #VALUE! | #VALUE! | 98.17% | 2011-06-30 | 15, 16, 18, 19, 20 | BCM | YES | n/a | n/a |  | Purchase using Annual Tender | 2012-06-01 | Energy Efficient Lighting Exchange Mdantsane - Installation of Lighting completed - Invoice for R73 000.00 submitted to SCM | 535/025/4/25/1001
Laptop - A11/71 | 505005 | 5 | 05 | 1241 | 05 | 02 | 01 | 01 | 270 | 001 | Waste Water Management | Support Services | renewal-320 | Yes |  | N/A | Own Funds | #VALUE! | 4890900 | #VALUE! |  | 9500 | 0 | 7716.84 | 7716.84 |  | 1783.16 | #VALUE! | #VALUE! | 81.23% | [9 empty] | This vote is in respect of those assets that are replaced due to insurance claims. No expenditure is recorded against this vote as budget is transferred from this vote to individual capital votes when asset insurance claims are approved by insurers for those assets to be replaced. The original budget amount was R10 million and an amount of R5 109 100 has been transferred leaving a balance of R4 890 900. | 505/005/5/05/1241
West Bank Restitution | 525020 | 4 | 36 | 1028 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | 46 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 15000000 | 10142767.32 | 4268.88 | 10147036.2 |  | 4852963.8 | #VALUE! | #VALUE! | 67.65% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | The Roads construction is currently attending to the snags. The Bulk Sanitation infrastructure - contractor has been appointed end of May 2012. The Bulk Water infrastructure - tender was advertised on the 1 June 2012 and has closed on the 3 July 2012. | 525/020/4/36/1028
Rural Roads Upgrade | 525020 | 4 | 36 | 1029 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | Renewal-30 |  | Yes | 24-27,31-33,34,39,44 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 5000000 | 1366253.27 | 483424.34 | 1849677.61 |  | 3150322.39 | #VALUE! | #REF! | 36.99% | 2011-06-30 | 7 | BCMM | YES | N/A | n/a |  | Duncan Village (R500 000): Contractor on site, completing surfacing of existing gravel roads | 2012-03-30 | Insufficient funds for upgrade & stormwater | 525/020/4/36/1029
Upgrading and Rehabilitation of BCMM Roads - Duncan Village | 525020 | 4 | 36 | 1114 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | 1,8 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 978710.95 | 978710.95 |  | 21289.05 | #VALUE! | #VALUE! | 97.87% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1114
Upgrading and Rehabilitation of BCMM Roads - Ducats | 525020 | 4 | 36 | 1115 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | 29 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1250000 | 0 | 0 | 0 |  | 1250000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1115
Upgrading and Rehabilitation of BCMM Roads - Zwelitsha | 525020 | 4 | 36 | 1116 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | 41 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 1285526.28 | 1285526.28 |  | -285526.28 | #VALUE! | #VALUE! | 128.6% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1116
Upgrading and Rehabilitation of BCMM Roads - Dimbaza | 525020 | 4 | 36 | 1117 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | 34,36 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 579363.23 | 579363.23 |  | 420636.77 | #VALUE! | #VALUE! | 57.94% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1117
Upgrading and Rehabilitation of BCMM Roads - Phakamisa | 525020 | 4 | 36 | 1118 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | 25 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1250000 | 0 | 0 | 0 |  | 1250000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1118
Upgrading and Rehabilitation of BCMM Roads - Scenery park / Reeston | 525020 | 4 | 36 | 1119 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | 13, | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 117732.98 | 117732.98 |  | 882267.02 | #VALUE! | #VALUE! | 11.77% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1119
Upgrading and Rehabilitation of BCMM Roads - Nonkcampa | 525020 | 4 | 36 | 1120 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | 38 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 588377.19 | 588377.19 |  | 11622.81 | #VALUE! | #VALUE! | 98.06% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1120
Upgrading and Rehabilitation of BCMM Roads - Ndileka | 525020 | 4 | 36 | 1121 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | 40 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 0 | 0 |  | 600000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1121
Upgrading and Rehabilitation of BCMM Roads - Zabalaza | 525020 | 4 | 36 | 1122 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | 36 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 0 | 0 |  | 600000 | #VALUE! | #VALUE! | 0% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1122
Upgrading and Rehabilitation of BCMM Roads - Upper Mngqesha | 525020 | 4 | 36 | 1123 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | 36 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 279166.66 | 279166.66 |  | 320833.34 | #VALUE! | #VALUE! | 46.53% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1123
Upgrading and Rehabilitation of BCMM Roads - Tsholomnqa | 525020 | 4 | 36 | 1131 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | 32 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 106789 | 0 | 98807.89 | 98807.89 |  | 7981.11 | #VALUE! | #VALUE! | 92.53% | 2011-06-30 | 46 | BCMM | Bulk services are available on this site | COMPLETE | n/a |  | Project at implementation stage | 2012-06-22 | At implementation, completion anticipated mid December 2011, delays due to unavailability of asphalt from the suppliers, phase 2 tender report is currently at SCM for point scoring. | 525/020/4/36/1131
Mdantsane Roads | 525025 | 4 | 36 | 1027 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | New-30 | Yes |  | Mdantsane (All) | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 42375700 | 4987950.05 | 14792166.69 | 19780116.74 |  | 22595583.26 | #VALUE! | #VALUE! | 46.68% | 2011-06-30 |  |  |  | Forwarded proposal for design to be reviewed |  |  | Seek BAC Support pertaining to award of annual contracts and utilization of learner contractors. | 2012-02-29 | TORs for consultants to be presented to BSC in early January 2012 and advertise tender before end of January 2012. Work is being identified for the provision of sidewalks and overlays that can be done by annual contractors. Learner contractors to implement project for the remainder of 2011/12 | 525/025/4/36/1027
Rehabilitation of Rural Roads Upgrade | 525025 | 4 | 36 | 1030 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | Renewal-30 |  | Yes | All Wards | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 5000000 | 1550309.14 | 661905.95 | 2212215.09 |  | 2787784.91 | #VALUE! | #VALUE! | 44.24% | 2011-06-30 | 32 | BCMM | YES | N/A | n/a |  | Tsholomnqa (R500 000): Requested daily tender for material, road reserve cleared in September 2011 | 2012-03-30 | Insufficient funds for rehabilitation,stormwater challenges | 525/025/4/36/1030
West Bank Restitution | 525025 | 6 | 82 | 1100 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  |  | Yes | 46 | DBSA Phase 4 & 5 c/o | #VALUE! | 5577424 | #VALUE! |  | 4309413 | 1192639.58 | 3116772.61 | 4309412.19 |  | 0.81 | #VALUE! | #VALUE! | 100% | [7 empty] | Funds to be utilized for completion of phase 1 and phase 2 of the project. | 2012-03-15 | ongoing | 525/025/6/82/1100
West Bank Restitution | 525025 | 6 | 01 | 1103 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  |  | Yes | 46 | Own Funds c/o |  |  |  |  | 1268011 |  | 0 | 0 |  | 1268011 |  |  | 0% | [10 empty] | 525/025/6/01/1103
Rural and Urban Roads | 525025 | 6 | 82 | 1101 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  |  | Yes | 24-27,31-33,34,39,44 | DBSA Phase 4 & 5 c/o | #VALUE! | 10000000 | #VALUE! |  | 5757674 | 2130674.88 | 3070868.21 | 5201543.09 |  | 556130.91 | #VALUE! | #VALUE! | 90.34% | [7 empty] | Daily tenders for material purchasing issued and labour mobilzation being undertaken. | 2012-03-30 | ongoing | 525/025/6/82/1101
Rural and Urban Roads | 525025 | 6 | 01 | 1104 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  |  | Yes | 24-27,31-33,34,39,44 | Own Funds c/o |  |  |  |  | 4242326 |  | 0 | 0 |  | 4242326 |  |  | 0%
Scada equipment-A11/82 | 515023 | 5 | 05 | 1243 | 05 | 02 | 01 | 01 | 260 | 001 | Waste Water Management | Support Services | renewal-320 | Yes |  | N/A | Own Funds | #VALUE! | 4890900 | #VALUE! |  | 93000 | 79476 | -4 | 79472 |  | 13528 | #VALUE! | #VALUE! | 85.45% | [9 empty] | This vote is in respect of those assets that are replaced due to insurance claims. No expenditure is recorded against this vote as budget is transferred from this vote to individual capital votes when asset insurance claims are approved by insurers for those assets to be replaced. The original budget amount was R10 million and an amount of R5 109 100 has been transferred leaving a balance of R4 890 900. | 515/023/5/05/1243
Nord Avenue Pump station | 515010 | 4 | 36 | 1031 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | 29 | Urban Settlement Development Grant | #VALUE! |  | #VALUE! | #VALUE! | 4000000 | 1988.91 | 628299 | 630287.91 |  | 3369712.09 | #VALUE! | #VALUE! | 15.76% | 2011-06-30 | 29 | BCMM | Bulk services are available on this site | EIA not required, designs and survey completed | n/a |  | Tenders will close on the 28 February 2012. | 6 months construction period. | None of the bidders met the requirements, the tender to be re-advertised | 515/010/4/36/1031
Quinera Treatment Works | 515010 | 4 | 36 | 1032 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | 28 | Urban Settlement Development Grant | #VALUE! |  | #VALUE! | #VALUE! | 39000000 | 280571.73 | 0 | 280571.73 |  | 38719428.27 | #VALUE! | #VALUE! | 0.7194% | 2011-06-30 | 27 | BCMM | Bulk services are available on this site | EIA not required, designs and survey completed | n/a |  | Report To be tabled on the next special BAC of the 10 February 2012. | 8 months construction period. | Delays were due in change from an electrical, mechanical and civil engineering to a water works treatment approach, contract awarded but delayed due to lengthy adjudication process. | 515/010/4/36/1032
Waste Water Treatment Capacity (Zwelitsha) | 515026 | 4 | 36 | 1033 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | 39 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 15000000 | 11223273.73 | 1182125.13 | 12405398.86 |  | 2594601.14 | #VALUE! | #VALUE! | 82.7% | 2011-06-30 | 41 | BCMM | Bulk services are available on this site | Currently busy with design for Phase 2. | n/a |  | Phase 1 – contractor appointed | 2012-08-01 | At implementation with some contractual dispute that is delaying the project. | 515/026/4/36/1033
Reeston Phase 3 Bulk Services Sewer | 515027 | 4 | 36 | 1034 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | 13 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 23500000 | 643420.8 | 811013.01 | 1454433.81 |  | 22045566.19 | #VALUE! | #VALUE! | 6.189% | 2011-06-30 | 13, 16 | BCMM | Yes | Complete | n/a |  | Report in ACM's office for approval. | 2013-10-01 | At implementation with anticipated completion in April 2013 | 515/027/4/36/1034
Relocation of Miblocks - Mdantsane | 515027 | 4 | 36 | 1105 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 13, 16 | BCMM | Yes | Complete | n/a |  | Report in ACM's office for approval. | 2013-10-01 | Vote not yet open for transactions | 515/027/4/36/1105
Coastal & Midlands Infrastructure | 515027 | 4 | 36 | 1108 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 13, 16 | BCMM | Yes | Complete | n/a |  | Report in ACM's office for approval. | 2013-10-01 | Vote not yet open for transactions | 515/027/4/36/1108
Bufferstrip Sanitation - Mdantsane | 515028 | 4 | 36 | 1035 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | 14, 42 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 15000000 | 6723860.44 | 7713673.37 | 14437533.81 |  | 562466.19 | #VALUE! | #VALUE! | 96.25% | 2011-06-30 | 17, 20 | BCMM | Yes | Complete | n/a |  | Project at implementation stage | 2012-04-01 | At implementation with anticipated completion end of July 2012. | 515/028/4/36/1035
KWT & Bisho Infrastructure ( water) | 515028 | 4 | 36 | 1104 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 17, 20 | BCMM | Yes | Complete | n/a |  | Project at implementation stage | 2012-04-01 | Vote not yet open for transactions | 515/028/4/36/1104
Augmentation of Water Treatment Capacity - Umzonyana/Raising Upper weir | 515028 | 4 | 36 | 1106 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 17, 20 | BCMM | Yes | Complete | n/a |  | Project at implementation stage | 2012-04-01 | Vote not yet open for transactions | 515/028/4/36/1106
Amahleke | 515028 | 4 | 36 | 1107 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 17, 20 | BCMM | Yes | Complete | n/a |  | Project at implementation stage | 2012-04-01 | Vote not yet open for transactions | 515/028/4/36/1107
Mdantsane Sewers - Refurbishment | 515031 | 4 | 36 | 1036 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | Renewal-70 |  | Yes | 42 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 5000000 | 2777477.87 | 2057102.97 | 4834580.84 |  | 165419.16 | #VALUE! | #VALUE! | 96.69% | 2011-06-30 | 14 | BCMM | Internal toilets | Planning underway – to be undertaken internally. | n/a |  | Replacement of Pitch Fibre Sewers utilising the Annual Contractor. | 2012-06-01 | Service providers completed the Mdantsane Prison sewer and sewer connections within Gqozo Village Phase 1 in Mdantsane. . | 515/031/4/36/1036
Flow Meter Chamber Unit - A11/16 | 515032 | 5 | 05 | 1237 | 05 | 02 | 01 | 01 | 260 | 001 | Waste Water Management | Waste Water |  | Yes |  | N/A | Own Funds |  |  |  | 37000 | 26430 | 26430 | 0 | 26430 |  | 0 |  |  | 100%
Diversion of Amalinda and Wilsonia effluent to Reeston | 515010 | 4 | 36 | 1037 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | 5 | Urban Settlement Development Grant | #VALUE! |  | #VALUE! | #VALUE! | 22000000 | 2448074.64 | 4349648.57 | 6797723.21 |  | 15202276.79 | #VALUE! | #VALUE! | 30.9% | 2011-06-30 | 12, 13, 16 | BCMM | Yes | Complete | n/a |  | Report recommended by the special BAC of the 7 February 2012. | 2013-02-01 | Wilsonia Interceptor Phase 1: An appointment has been made at the end of March 2012 with anticipated completion in March 2013 and drilling contract (investigation phase2) contractor has been appointed in May 2012 | 515/010/4/36/1037
Leak Detector Machine - A10/67 | 520005 | 5 | 05 | 1208 | 05 | 02 | 01 | 01 | 260 | 001 | Water | Water | Renewal-260 | Yes |  | N/A | Own Funds | #VALUE! | 232000 | #VALUE! |  | 232000 | 0 | 135182 | 135182 |  | 96818 | #VALUE! | #VALUE! | 58.27% | [9 empty] | Tender closed on 02 February 2012 and all tenders were non responsive, therefore it will be re-advertised. | 520/005/5/05/1208
Augmentation of Water Treatment Capacity - Umzonyana/Raising Upper weir | 520015 | 4 | 36 | 1038 | 05 | 12 | 01 | 01 | 040 | 001 | Water | Water | New-40 | Yes |  | 1-33,45-50 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 5000000 | 4948137.25 | 36285.95 | 4984423.2 |  | 15576.8 | #VALUE! | #VALUE! | 99.69% | 2011-06-30 | 1-31,33 |  | Upgrading of the bulk services are underway | COMPLETE | N/a |  | Project at implementation stage | 2014-06-30 | Roll over. Multi year project | 520/015/4/36/1038
Inland Rural Sanitation (Dimbaza Villages,Ngxwalane and Kwalini) | 515010 | 4 | 36 | 1040 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | 35, 36, 37, 39, 40, 41, 43, 44 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 36000000 | 13812757.91 | 2898815.19 | 16711573.1 |  | 19288426.9 | #VALUE! | #VALUE! | 46.42% | 2011-06-30 | 34, 36 | Private | n/a | Terms of reference complete. Implementation list of project areas is being finalised. | n/a |  | Report was approved by BSC subject to approval by ACM to split the Sanitation Project. Awaiting approval from ACM. | 2013-12-01 | Phase 2 delayed due to public participation processes that were conducted between August and December 2011. The tender report is with committees. | 515/010/4/36/1040
Eastern Beach Sewers | 515010 | 4 | 36 | 1100 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | 18 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2000000 | 741940.97 | 1169293.44 | 1911234.41 |  | 88765.59 | #VALUE! | #VALUE! | 95.56% | 2011-06-30 | 34, 36 | Private | n/a | Terms of reference complete. Implementation list of project areas is being finalised. | n/a |  | Report was approved by BSC subject to approval by ACM to split the Sanitation Project. Awaiting approval from ACM. | 2013-12-01 | The appointed service provider is currently finalising the contract documentation for the eastern beach sewer. The EIA is in the process of being submitted to DEAT for approval. Funds for this phase of the project are fully committed for this financial year. | 515/010/4/36/1100
Chemical toilets | 515010 | 4 | 36 | 1101 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | 8, 28, 36, 45, 50 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2000000 | 0 | 2000000 | 2000000 |  | 0 | #VALUE! | #VALUE! | 100% | 2011-06-30 | 34, 36 | Private | n/a | Terms of reference complete. Implementation list of project areas is being finalised. | n/a |  | Report was approved by BSC subject to approval by ACM to split the Sanitation Project. Awaiting approval from ACM. | 2013-12-01 | Contracts from last financial year 2010/11 have been completed. New contracts for this year to be advertised before end of February 2012. | 515/010/4/36/1101
Sludge handling facility | 515010 | 4 | 36 | 1102 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  | 20 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2800000 | 300780 | 806384.5 | 1107164.5 |  | 1692835.5 | #VALUE! | #VALUE! | 39.54% | 2011-06-30 | 34, 36 | Private | n/a | Terms of reference complete. Implementation list of project areas is being finalised. | n/a |  | Report was approved by BSC subject to approval by ACM to split the Sanitation Project. Awaiting approval from ACM. | 2013-12-01 | Service providers undertook the rehabilitation of the sludge drying beds at the Mdantsane East WWTW. Funding recieved in March 2012. Delays with the delivery of media for drying beds. | 515/010/4/36/1102
Winterstrand Water Supply | 515010 | 4 | 36 | 1103 | 05 | 10 | 01 | 01 | 070 | 001 | Waste water Management | Waste Water | New-70 | Yes |  |  | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 | 34, 36 | Private | n/a | Terms of reference complete. Implementation list of project areas is being finalised. | n/a |  | Report was approved by BSC subject to approval by ACM to split the Sanitation Project. Awaiting approval from ACM. | 2013-12-01 | An annual contractor is to be used to install the emergency pipeline to Winterstrand. | 515/010/4/36/1103
Insurance vehicle replacement - M10/33 | 515010 | 5 | 05 | 1221 | 05 | 02 | 01 | 01 | 250 | 001 | Waste Water Management | Other - BCM Fleet |  | Yes |  | N/A | Own Funds | #VALUE! | 155000 | #VALUE! | 0 | 155000 | 0 | 144605.2 | 144605.2 |  | 10394.8 | #VALUE! | #VALUE! | 93.29% | [10 empty] | 515/010/5/05/1221
Quinera Treatment Works | 515010 | 6 | 61 | 1100 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | 28 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 8508421 | 0 | 0 | 0 |  | 8508421 | #VALUE! | #VALUE! | 0% | [9 empty] | Tender report being considered by the Bid Committees. | 515/010/6/61/1100
Bufferstrip Sanitation - Mdantsane | 515010 | 6 | 61 | 1101 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | 14, 42 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 201328 | 0 | 0 | 0 |  | 201328 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 515/010/6/61/1101
Construct. High level reservoir - Breidbach | 515010 | 6 | 61 | 1104 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | [10 empty] | 515/010/6/61/1104
Bulk Water Supply - Needscamp | 515010 | 6 | 61 | 1108 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  |  | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | [10 empty] | 515/010/6/61/1108
Rural Sanitation | 515010 | 6 | 61 | 1109 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | 35, 36, 37, 39, 40, 41, 43, 44 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 15000000 | 0 | 0 | 0 |  | 15000000 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 515/010/6/61/1109
Winterstrand Water Supply | 520005 | 4 | 36 | 1136 | 05 | 10 | 01 | 01 | 070 | 001 | Water | Water |  | Yes |  | 28,42 | Urban Settlement Development Grant |  |  |  | 2000000 | 2000000 | 84979.07 | 1799715.65 | 1884694.72 |  | 115305.28 |  |  | 94.23% | [9 empty] | Roll over. Multi year project under construction and to be completed in October 2012 with funding for 2012/2013. | 520/005/4/36/1136
Insurance vehicle replacement - M10/172 | 520005 | 5 | 05 | 1220 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | N/A | Own Funds | #VALUE! | 500000 | #VALUE! |  | 500000 | 0 | 0 | 0 |  | 500000 | #VALUE! | #VALUE! | 0% | [9 empty] | Funds allocated 11 November 2011. Fleet Management to purchase. | 520/005/5/05/1220
Bulk Water Supply - Needscamp | 520005 | 6 | 61 | 1120 | 05 | 05 | 01 | 01 | 070 | 002 | Water | Water |  | Yes |  | 33 | Municipal Infrastructure Grant c/o |  |  |  | 5300000 | 5300000 | 0 | 0 | 0 |  | 5300000 |  |  | 0% | [9 empty] | Mig roll over was approved in February 2012 and tender is at BAC stage, part of the fund will be utilised on the upgrading of the water scheme in ward 33 that is on-going.Awaiting letter of award. ROLL OVER TO 2012/13
Bulk Water Supply Newlands and other areas | 520021 | 4 | 36 | 1041 | 05 | 12 | 01 | 01 | 040 | 001 | Water | Water | New-40 | Yes |  | 13-23 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 428404.5 | 376857.94 | 805262.44 |  | 194737.56 | #VALUE! | #VALUE! | 80.53% | 2011-06-30 |  | BCMM | n/a | n/a | N/a |  | Implemented in house | 2012-06-01 | Spent | 520/021/4/36/1041
Augmentation of Water Treatment Capacity - Umzonyana/Raising Upper weir | 520021 | 4 | 36 | 1139 | 05 | 10 | 01 | 01 | 070 | 001 | Water | Water |  | Yes |  | 12,13 | Urban Settlement Development Grant |  |  |  | 2000000 | 2000000 | 845061.15 | 347063.14 | 1192124.29 |  | 807875.71 |  |  | 59.61% | [9 empty] | Roll over. Multi year project | 520/021/4/36/1139
Ward 33 Bulk Water Supply Scheme | 520025 | 4 | 36 | 1042 | 05 | 12 | 01 | 01 | 040 | 001 | Water | Water | New-40 | Yes |  | 33 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 7000000 | 1498734.01 | 790313.34 | 2289047.35 |  | 4710952.65 | #VALUE! | #VALUE! | 32.7% | 2011-06-30 |  |  | To be installed | COMPLETE | N/a |  | Report to be tabled in the next special BAC of the 10 February 2012. | 2013-06-01 | Awaiting letter of award. ROLL OVER TO 2012/13 | 520/025/4/36/1042
Bulk Water Supply Coastal Areas | 520025 | 4 | 36 | 1043 | 05 | 12 | 01 | 01 | 040 | 001 | Water | Water | New-40 | Yes |  | 31 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 8000000 | 7775042.22 | 690.35 | 7775732.57 |  | 224267.43 | #VALUE! | #VALUE! | 97.2% | 2011-06-30 |  |  | To be installed | COMPLETE | N/a |  | Project at implementation stage | 2012-04-01 | roll over, multi year project. Phase 1E and 1F have been completed. | 520/025/4/36/1043
KWT & Bisho Infrastructure ( water) | 520025 | 4 | 36 | 1137 | 05 | 10 | 01 | 01 | 070 | 001 | Water | Water |  | Yes |  | 28,42 | Urban Settlement Development Grant |  |  |  | 2500000 | 2500000 | 2165422.73 | -2165422.73 | 0 |  | 2500000 |  |  | 0% | [9 empty] | Spent | 520/025/4/36/1137
Amahleke Water Supply | 520025 | 4 | 36 | 1140 | 05 | 10 | 01 | 01 | 070 | 001 | Water | Water |  | Yes |  | 37 | Urban Settlement Development Grant |  |  |  | 1000000 | 1000000 | 975349.32 | -975349.32 | 0 |  | 1000000 |  |  | 0% | [9 empty] | Committed for full expenditure | 520/025/4/36/1140
Amahleke Water Supply | 520025 | 6 | 61 | 1102 | 05 | 12 | 01 | 01 | 040 | 001 | Water | Water | New-40 | Yes |  | 37 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 961009 | 961009 | 0 | 961009 |  | 0 | #VALUE! | #VALUE! | 100% | 2011-06-30 |  |  | To be installed | COMPLETE | N/a |  | Report to be tabled in the next special BAC of the 10 February 2012. | 2013-06-01 | spent | 520/025/6/61/1102
Bulk water supply - Newlands & other areas | 520025 | 6 | 61 | 1103 | 05 | 12 | 01 | 01 | 040 | 001 | Water | Water | New-40 | Yes |  | 13-23 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 47927 | 0 | 41868 | 41868 |  | 6059 | #VALUE! | #VALUE! | 87.36% | 2011-06-30 |  |  | To be installed | COMPLETE | N/a |  | Report to be tabled in the next special BAC of the 10 February 2012. | 2013-06-01 | Roll over. Multi year project | 520/025/6/61/1103
Construct. High level reservoir - Breidbach | 520025 | 6 | 61 | 1119 | 05 | 05 | 01 | 01 | 070 | 002 | Water | Water |  | Yes |  | 42 | Municipal Infrastructure Grant c/o |  |  |  | 100000 | 100000 | 100000 | 0 | 100000 |  | 0 |  |  | 100% | [9 empty] | spent | 520/025/6/61/1119
Relocation of Miblocks - Mdantsane | 520026 | 4 | 36 | 1138 | 05 | 10 | 01 | 01 | 070 | 001 | Water | Water |  | Yes |  | Mdantsane (All) | Urban Settlement Development Grant |  |  |  | 3000000 | 3000000 | 2352255.74 | -2352255.74 | 0 |  | 3000000 |  |  | 0% | [9 empty] | spent | 520/026/4/36/1138
Laptop - A11/53 | 520026 | 5 | 05 | 1231 | 05 | 02 | 01 | 01 | 270 | 001 | Water | Water |  | Yes |  | N/A | Own Funds | #VALUE! | 9000 | #VALUE! |  | 9000 | 7741 | 0 | 7741 |  | 1259 | #VALUE! | #VALUE! | 86.01% | 2011-06-30 |  |  | To be installed | COMPLETE | N/a |  | Replacement of laptop | 2012-03-01 | Request to procure the laptop has been submitted to IT | 520/026/5/05/1231
Insurance vehicle insurance - M10/42 | 520026 | 5 | 05 | 1238 | 05 | 02 | 01 | 01 | 250 | 001 | Water | Water |  | Yes |  | N/A | Own Funds |  |  |  | 560000 | 560000 | 0 | 0 | 0 |  | 560000 |  |  | 0% | [10 empty] | 520/026/5/05/1238
Coastal & Midlands Infrastructure | 520030 | 4 | 36 | 1141 | 05 | 10 | 01 | 01 | 070 | 001 | Water | Water |  | Yes |  | 1-33,45-50 | Urban Settlement Development Grant |  |  |  | 1500000 | 1500000 | 1485353.84 | -1076619.74 | 408734.1 |  | 1091265.9 |  |  | 27.25% | [9 empty] | spent
Building Security | 505005 | 6 | 01 | 1006 | 05 | 11 | 05 | 13 | 120 | 002 | Waste Water Management | Electricity | New-312 |  | Yes | N/A | Own Funds c/o | #VALUE! | -174341 | #VALUE! |  | 125659 | 38814.69 | 18700 | 57514.69 |  | 68144.31 | #VALUE! | #VALUE! | 45.77% | [7 empty] | R117,000 has been paid in June for upgrading of CCTV system in the Engineering Building and the rest will be spent on improving lighting at the Chiselhurst Depot |  | Lights have been installed, invoice awaited to settle costs. More work to be done at the entrance of the Office bulidng. | 505/005/6/01/1006
Electrification - Counterfunding Reeston & Other Areas | 535005 | 6 | 01 | 1007 | 05 | 13 | 01 | 01 | 060 | 002 | Electricity | Electricity | New-60 |  | Yes |  | Own Funds c/o | #VALUE! | -2800000 | #VALUE! |  | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! |  | - | N/A | N/A | Complete | n/a |  |  | 2011-10-31 | NO BUDGET - Completed 2010/11 | 535/005/6/01/1007
Heritage Desk, 5 Tier Bookcase - A11/13 | 535005 | 5 | 05 | 1207 | 05 | 02 | 01 | 01 | 270 | 001 | Electricity | Electricity |  | Yes |  | N/A | Own Funds | #VALUE! | 24000 | #VALUE! |  | 24000 | 20696.35 | 0 | 20696.35 |  | 3303.65 | #VALUE! | #VALUE! | 86.23% | [9 empty] | Insurance Claim - Completed | 535/005/5/05/1207
Replacement: Brushcutters- A11/19 | 535010 | 5 | 05 | 1227 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Electricity |  | Yes |  | N/A | Own Funds | #VALUE! | 6400 | #VALUE! |  | 6400 | 5594.75 | 0 | 5594.75 |  | 805.25 | #VALUE! |  | 87.42% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1227
500KVA Mini-substation - Cemetery -RD -A11/32 | 535010 | 5 | 05 | 1228 | 05 | 02 | 01 | 01 | 060 | 001 | Electricity | Electricity |  | Yes |  | 6 | Own Funds | #VALUE! | 283600 | #VALUE! |  | 283600 | 248759.51 | 18725 | 267484.51 |  | 16115.49 | #VALUE! |  | 94.32% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1228
200KVA Pole Transformer: Taleni - A10/91 | 535010 | 5 | 05 | 1229 | 05 | 02 | 01 | 01 | 060 | 001 | Electricity | Electricity |  | Yes |  | 15 | Own Funds | #VALUE! | 53800 | #VALUE! |  | 53800 | 40716.96 | 0 | 40716.96 |  | 13083.04 | #VALUE! |  | 75.68% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1229
200KVA Pole Transformer: Taleni - A11/25 | 535010 | 5 | 05 | 1230 | 05 | 02 | 01 | 01 | 060 | 001 | Electricity | Electricity |  | Yes |  | 15 | Own Funds | #VALUE! | 46500 | #VALUE! |  | 46500 | 40716.96 | 0 | 40716.96 |  | 5783.04 | #VALUE! |  | 87.56% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1230
Dunlop Substation - A10/111 | 535010 | 5 | 05 | 1251 | 05 | 02 | 01 | 01 | 260 | 001 | Electricity | Electricity |  | Yes |  | 13 | Own Funds |  |  |  |  | 371000 | 370581.51 | 0 | 370581.51 |  | 418.49 |  |  | 99.89% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1251
Robbie de lange substation - A10/85 | 535010 | 5 | 05 | 1252 | 05 | 02 | 01 | 01 | 260 | 001 | Electricity | Electricity |  | Yes |  | 13 | Own Funds |  |  |  |  | 170870 | 170867.32 | -38771.7 | 132095.62 |  | 38774.38 |  |  | 77.31% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1252
Minibus : Ray Craib Crescent - A11/02 | 535010 | 5 | 05 | 1253 | 05 | 02 | 01 | 01 | 260 | 001 | Electricity | Electricity |  | Yes |  | 28 | Own Funds |  |  |  |  | 71000 | 62047.7 | -59561.7 | 2486 |  | 68514 |  |  | 3.501% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1253
Substation : Dunga Street - A11/26 | 535010 | 5 | 05 | 1254 | 05 | 02 | 01 | 01 | 260 | 001 | Electricity | Electricity |  | Yes |  | 1 | Own Funds |  |  |  |  | 20300 | 17777.57 | 0 | 17777.57 |  | 2522.43 |  |  | 87.57% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1254
Ring main unit: Shiden Drive - A10/93 | 535010 | 5 | 05 | 1255 | 05 | 02 | 01 | 01 | 260 | 001 | Electricity | Electricity |  | Yes |  | 28 | Own Funds |  |  |  |  | 79900 | 70017.75 | 0 | 70017.75 |  | 9882.25 |  |  | 87.63% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1255
Radio Repeater Transformer - A11/39 | 535010 | 5 | 05 | 1256 | 05 | 02 | 01 | 01 | 260 | 001 | Electricity | Electricity |  | Yes |  | 35 | Own Funds |  |  |  |  | 9960 | 9960 | 0 | 9960 |  | 0 |  |  | 100% | [9 empty] | Insurance Claim - Completed | 535/010/5/05/1256
High Mast Lighting - Sweetwaters | 535025 | 4 | 01 | 1150 | 05 | 13 | 01 | 01 | 090 | 001 | Electricity | Electricity | Renewal-60 |  | Yes | 44 | Own Funds | #VALUE! |  | #VALUE! | #VALUE! | 900000 | 0 | 602927.76 | 602927.76 |  | 297072.24 | #VALUE! | #VALUE! | 66.99% |  | 4 | BCM | n/a | n/a | n/a |  |  | 2012-06-01 | Hi-mast project awarded in February 2012. Completed | 535/025/4/01/1150
Streetlighting & Hymast | 535025 | 4 | 01 | 1151 | 05 | 13 | 03 | 01 | 090 | 001 | Electricity | Electricity | Renewal-60 |  | Yes | 11,12,14,17, 20,21,22,23 ,30 | Own Funds | #VALUE! |  | #VALUE! | #VALUE! | 300000 | 75044.37 | 221549.04 | 296593.41 |  | 3406.59 | #VALUE! | #VALUE! | 98.86% |  | 4 | BCM | n/a | n/a | n/a |  |  | 2012-06-01 | Completed | 535/025/4/01/1151
Electrification - Counterfunding Reeston & Other areas | 535025 | 4 | 01 | 1152 | 05 | 13 | 01 | 01 | 060 | 001 | Electricity | Electricity | Renewal-60 |  | Yes | 12 | Own Funds | #VALUE! |  | #VALUE! | #VALUE! | 2000000 | 0 | 0 | 0 |  | 2000000 | #VALUE! | #VALUE! | 0% |  | 4 | BCM | n/a | n/a | n/a |  |  | 2012-06-01 | Funding allocated in March 2012 - Adjustment Budget - Top up funding for electrification projects and electrification of infill - ROLL OVER REQUESTED | 535/025/4/01/1152
Upgrade of Bulk Electricity Infrastructure | 535025 | 4 | 01 | 1153 | 05 | 13 | 01 | 01 | 060 | 001 | Electricity | Electricity | Renewal-60 |  | Yes | 16, 18 | Own Funds | #VALUE! |  | #VALUE! | #VALUE! | 1889492 | 1875410.04 | -335092.79 | 1540317.25 |  | 349174.75 | #VALUE! | #VALUE! | 81.52% |  | 4 | BCM | n/a | n/a | n/a |  |  | 2012-06-01 | Switchgear ordered Requisitions submitted to SCM 7/3/12 - some items have a long delivery period. A number of Panels have arrived payments are in process. ROLL OVER REQUESTED | 535/025/4/01/1153
Electricity Building Upgrade- Ablution Blocks | 535025 | 6 | 01 | 1008 | 05 | 13 | 01 | 01 | 060 | 002 | Electricity | Electricity | Renewal-60 |  | Yes | 1 | Own Funds c/o | #VALUE! | 20923 | #VALUE! |  | 165923 | 81619.62 | 71796.24 | 153415.86 | 225212.1 | 12507.14 | #VALUE! | #VALUE! | 92.46% |  | 4 | BCM | n/a | n/a | n/a |  |  | 2012-06-01 | Tender awarded to service provider for the building of generator room at the Beacon Bay Civic Centre - completed | 535/025/6/01/1008
Upgrade-Bulk Electricity Infrastructure | 535025 | 4 | 82 | 1100 | 05 | 13 | 01 | 01 | 060 | 001 | Electricity | Electricity | Renewal-60 |  | Yes | 16, 18 | DBSA Phase 4 |  |  |  |  | 3662418 |  | 3662418 | 3662418 |  | 0 |  |  | 0%
Upgrade-Bulk Electricity Infrastructure | 535025 | 4 | 82 | 1101 | 05 | 13 | 01 | 01 | 060 | 001 | Electricity | Electricity | Renewal-60 |  | Yes | 16, 18 | DBSA Phase 5 |  |  |  |  | 2348090 |  | 2348090 | 2348090 |  | 0 |  |  | 0%
Insurance vehicle replacement-M10/103 | 525025 | 5 | 05 | 1240 | 05 | 02 | 01 | 01 | 250 | 001 | Road Transport | Support Services | renewal-320 | Yes |  | All Wards | Own Funds | #VALUE! | 4890900 | #VALUE! |  | 450000 | 0 | 0 | 0 |  | 450000 | #VALUE! | #VALUE! | 0% | [9 empty] | This vote is in respect of those assets that are replaced due to insurance claims. No expenditure is recorded against this vote as budget is transferred from this vote to individual capital votes when asset insurance claims are approved by insurers for those assets to be replaced. The original budget amount was R10 million and an amount of R5 109 100 has been transferred leaving a balance of R4 890 900. | 525/025/5/05/1240
Upgrade Electricity Reticulation (KWT and Coastal) | 535025 | 6 | 01 | 1009 | 05 | 13 | 01 | 01 | 060 | 002 | Electricity | Electricity | Renewal-60 |  | Yes | 42 | Own Funds c/o | #VALUE! | -3448826 | #VALUE! |  | 51174 | 50945.81 | 0 | 50945.81 |  | 228.19 | #VALUE! | #VALUE! | 99.55% |  |  |  |  | Complete |  |  |  |  | Completion of Greenacres and Gullsway - project complete | 535/025/6/01/1009
Vehicle V382 - FBR 776 EC - M09/182 | 525025 | 5 | 05 | 1244 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | All Wards | Own Funds |  |  |  |  | 510000 | 0 | 0 | 0 |  | 510000 |  |  | 0% | [9 empty] | insurance claim | 525/025/5/05/1244
Rehabilitation of BCM bridges and culverts( Breidbach, Dimbaza, Quigney) | 525025 | 6 | 01 | 1010 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater | Renewal-30 |  | Yes | 34,44 | Own Funds c/o | #VALUE! | -19908 | #VALUE! |  | 1972996 | 1583700.96 | 389295.04 | 1972996 |  | 0 | #VALUE! | #VALUE! | 100% |  | 34, 36, 3 | BCMM | N/A | N/A | No despute |  |  |  | R51,174 used for completion of Capital Project in Gullsway & Greenacres switch houses. Payment for R 23 295 is in process for work completed. Insufficient Capital funding to carry out any additional electrical projects | 525/025/6/01/1010
Rehabilitation of Rural Roads Upgrade | 525025 | 6 | 61 | 1105 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | All Wards | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 856328 | 0 | 0 | 0 |  | 856328 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1105
Upgrading and Rehabilitation of BCMM Roads - Nomgwadla | 525025 | 6 | 61 | 1110 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | 36 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 0 | 0 |  | 600000 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1110
Upgrading and Rehabilitation of BCMM Roads - Ngxwalana | 525025 | 6 | 61 | 1111 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | 39 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 0 | 0 |  | 600000 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1111
Upgrading and Rehabilitation of BCMM Roads - Msintsini | 525025 | 6 | 61 | 1112 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | 24 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 0 | 0 |  | 600000 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1112
Upgrading and Rehabilitation of BCMM Roads - Kwelera | 525025 | 6 | 61 | 1113 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | 27 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 0 | 0 |  | 600000 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1113
Upgrading and Rehabilitation of BCMM Roads - Balasi | 525025 | 6 | 61 | 1114 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | 35 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 600000 | 0 | 0 | 0 |  | 600000 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1114
Upgrading and Rehabilitation of BCMM Roads - Ncera Villages 5-9 | 525025 | 6 | 61 | 1115 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | 5-9 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 588157.89 | 588157.89 |  | 411842.11 | #VALUE! | #VALUE! | 58.82% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1115
Upgrading and Rehabilitation of BCMM Roads - Kuni, Needscamp | 525025 | 6 | 61 | 1116 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | 33 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 0 | 0 |  | 1000000 | #VALUE! | #VALUE! | 0% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1116
Upgrading and Rehabilitation of BCMM Roads - Tsholomqa | 525025 | 6 | 61 | 1117 | 05 | 11 | 01 | 01 | 030 | 002 | Road transport | Roads and Stormwater |  | Yes |  | 32 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 493211 | 0 | 465320.26 | 465320.26 |  | 27890.74 | #VALUE! | #VALUE! | 94.35% | [9 empty] | No expenditure has been incurred on the funding because the funds were made available during February 2012 through the Mid year adjustment budget. | 525/025/6/61/1117
Rehabilitation of underground stormwater - Storm water Management System | 525025 | 4 | 36 | 1109 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater |  | Yes |  | All Wards | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1100000 | 470000 | 259473.64 | 729473.64 |  | 370526.36 | #VALUE! | #VALUE! | 66.32% | [10 empty] | 525/025/4/36/1109
Rehabilitation of underground stormwater - Amalinda forest | 525025 | 4 | 36 | 1110 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater |  | Yes |  | 5 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | 1000000 | 1000000 | 0 | 318749.12 | 318749.12 |  | 681250.88 | #VALUE! | #VALUE! | 31.87% | [10 empty] | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012. | Funding allocated in the mid year adjustment budget and is expected to be spent by June 2012.
Rehabilitation of underground stormwater - Duncan village | 525025 | 4 | 36 | 1111 | 05 | 11 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater |  | Yes |  | 1,8 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 243808.28 | 243808.28 |  | 756191.72 | #VALUE! | #VALUE! | 24.38% | [10 empty] | 525/025/4/36/1111
Rehabilitation of underground stormwater - Dimbaza | 525025 | 4 | 36 | 1112 | 05 | 02 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater |  | Yes |  | 34,36 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 0 | 0 | 0 |  | 1000000 | #VALUE! | #VALUE! | 0% | [10 empty] | 525/025/4/36/1112
Rehabilitation of underground stormwater - West Bank | 525025 | 4 | 36 | 1113 | 05 | 02 | 01 | 01 | 030 | 001 | Road transport | Roads and Stormwater |  | Yes |  | 46 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1100000 | 894852.18 | 41677.95 | 936530.13 |  | 163469.87 | #VALUE! | #VALUE! | 85.14% | [10 empty] | 525/025/4/36/1113
Upgrade Augmentation | 515021 | 6 | 01 | 1011 | 05 | 10 | 01 | 01 | 070 | 002 | Waste Water Management | Electricity | Renewal-70 |  | Yes | 3 | Own Funds c/o | #VALUE! | 415030 | #VALUE! |  | 525250 | 0 | 0 | 0 |  | 525250 | #VALUE! | #VALUE! | 0% | [7 empty] | Payment of invoices for committed rollover funding. | 2012-01-01 |  | 515/021/6/01/1011
Ablution Blocks Duncan Village | 515021 | 4 | 01 | 1004 | 05 | 10 | 01 | 01 | 070 | 001 | Waste Water Management | Electricity | New-120 | Yes |  | 1,8 | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 2095378 | 217792.92 | 8329.87 | 226122.79 |  | 1869255.21 | #VALUE! | #VALUE! | 10.79% | 2011-06-30 | 1 | BCMM | Yes | n/a | n/a |  |  | 2012-06-01 | Tender has been re-advertised on 3 February 2012 and the closing date of the tender is 17 February 2012. | 515/021/4/01/1004
Bulk Sanitation | 515035 | 6 | 83 | 1104 | 05 | 10 | 01 | 01 | 070 | 002 | Waste water Management | Waste Water |  |  | Yes | 25 | Eastern Cape Development Corperation c/o (ECDC) | #VALUE! | 67358 | #VALUE! |  | 67358 | 0 | 0 | 0 |  | 67358 | #VALUE! | #VALUE! | 0% | [9 empty] | Project completed in 10/11. | 515/035/6/83/1104
Upgrading of the Laboratory infrastructure and equipment | 510005 | 6 | 01 | 1012 | 05 | 10 | 01 | 01 | 070 | 002 | Waste water Management | Electricity | Renewal-70 |  | Yes | All Wards | Own Funds c/o | #VALUE! | 150732 | #VALUE! |  | 908588 | 517803.55 | 150605.2 | 668408.75 |  | 240179.25 | #VALUE! | #VALUE! | 73.57% | [7 empty] | Payment of invoices for committed rollover funding. | 2012-02-01 | LIMS as invoiced. Informal tenders for equipment | 510/005/6/01/1012
3 x Desktop Computers - A11/20 | 530010 | 5 | 05 | 1206 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services |  | Yes |  | N/A | Own Funds | #VALUE! | 24000 | #VALUE! |  | 20693 | 20692.11 | 0 | 20692.11 |  | 0.89 | #VALUE! | #VALUE! | 100% | [9 empty] | insurance claim | 530/010/5/05/1206
Traffic and Law Enforcement Fleet | 530020 | 6 | 01 | 1102 | 05 | 05 | 01 | 01 | 250 | 002 | Road Transport | Other - BCM Fleet |  | Yes |  | All Wards | Own Funds c/o | #VALUE! | 3000000 | #VALUE! |  | 3000000 | 0 | 352367.96 | 352367.96 |  | 2647632.04 | #VALUE! | #VALUE! | 11.75% | [9 empty] | All vehicles have been delivered. | 530/020/6/01/1102
Replacement of Bus Fleet | 530020 | 6 | 01 | 1101 | 05 | 05 | 01 | 01 | 250 | 002 | Road Transport | Other - BCM Fleet |  | Yes |  | All Wards | Own Funds c/o | #VALUE! | 5998399 | #VALUE! |  | 5998399 | 0 | 5796900 | 5796900 |  | 201499 | #VALUE! | #VALUE! | 96.64% | [9 empty] | Waiting for the suppliers to deliver within a week or two | 530/020/6/01/1101
BCM Fleet | 530020 | 4 | 01 | 1005 | 05 | 11 | 01 | 01 | 250 | 001 | Road Transport | Other - BCM Fleet | New-250 | Yes |  | All Wards | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 7500000 | 3471251.5 | 4057824.16 | 7529075.66 |  | -29075.66 | #VALUE! | #VALUE! | 100.4% | 2011-06-30 | [6 empty] | Specifications will be called from all Directorates and considered against institutional needs. Specifications will be done by the Fleet Manager who has since moved out of the Engineering Directorate. |  | Waiting for the suppliers to deliver within a week or two | 530/020/4/01/1005
TOTAL : DIRECTORATE OF ENGINEERING SERVICES | [10 empty] | 6 | [6 empty] | #VALUE! | 34793791 | #VALUE! | #VALUE! | 401036815 | 109896868.99 | 75052307.18 | 184949176.17 | 225212.1 | 216087638.83 | #VALUE! | #VALUE! | 46.12%
DIRECTORATE OF DEVELOPMENT PLANNING
Insurance vehicle replacement - M10/32 | 615075 | 5 | 05 | 1214 | 05 | 02 | 01 | 01 | 250 | 001 | Planning & Development | Other - BCM Fleet |  | Yes |  | N/A | Own Funds | #VALUE! | 155000 | #VALUE! |  | 155000 | 3104.64 | -3104.64 | 0 |  | 155000 | #VALUE! | #VALUE! | 0% | [7 empty] | Request sent to Mechanical Workshop for them to do procurement to replace the vehicle that was stolen. | 2012-06-30 | Tenders awarded, but still waiting for the suppliers to deliver. | 615/075/5/05/1214
Land Acquisition - Construction of Westbank Restitution Reservoir | 615080 | 4 | 01 | 1163 | 05 | 02 | 01 | 01 | 311 | 001 | Planning & Development | Other - BCM Fleet |  | Yes |  | 46 | Own Funds | #VALUE! |  | #VALUE! | #VALUE! | 600000 | 31085.24 | 410796.47 | 441881.71 |  | 158118.29 | #VALUE! | #VALUE! | 73.65% | [7 empty] | Request sent to Mechanical Workshop for them to do procurement to replace the vehicle that was stolen. | 2012-06-30 | Conveyancer has prepared documents for lodgement. | 615/080/4/01/1163
West Bank Restitution Project | 615080 | 6 | 54 | 1100 | 05 | 03 | 01 | 01 | 311 | 002 | Planning & Development | Housing |  |  | Yes | 46 | Department of Land Affairs c/o | #VALUE! | 4141303 | #VALUE! |  | 4141303 | 50350 | -50350 | 0 |  | 4141303 | #VALUE! | #VALUE! | 0% | [9 empty] | Judgement has been reserved by the Court, as the Conveyancer has appealed. | 615/080/6/54/1100
West Bank Land Restitution | 615080 | 6 | 54 | 1101 | 05 | 03 | 01 | 01 | 311 | 002 | Planning & Development | Housing |  |  | Yes | 46 | Department of Land Affairs c/o | #VALUE! | 243551 | #VALUE! |  | 243551 | 0 | 0 | 0 |  | 243551 | #VALUE! | #VALUE! | 0% | [9 empty] | Judgement has been reserved by the Court, as the Conveyancer has appealed. | 615/080/6/54/1101
Construction of BRT lanes | 620005 | 4 | 68 | 1003 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 | Yes |  | 1, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 2, 20, 21, 22, 23, 24, 25, 28, 3, 4, 5, 6, 7, 8, 9 | Public Transport Infrastructure and Systems Grant (PTIS) | #VALUE! | 0 | #VALUE! | #VALUE! | 100000000 | 1210726.34 | 72408.41 | 1283134.75 |  | 98716865.25 | #VALUE! | #VALUE! | 1.283% | R110,470,000 - awards to consultants | 42,12.11,13,16,5,10,16,8,7,9,2,1,3,47,19 | N/A | N/A | Planning and Detailed designs stage | N/A |  | Tender has been awarded by Acting City Manager on the recommendation of the Bid Adjudication Committee. Service Level Agreement to be entered into. | 2014-06-01 | Tender has been awarded for full consultant team, including detailed designs and business planning. Service Level Agreement can only be entered into once legal challenge from one of the bidders can be resolved. | 620/005/4/68/1003
BCM Urban Agriculture Infrastructure Development | 635005 | 4 | 36 | 1044 | 05 | 03 | 01 | 01 | 320 | 001 | Planning & Development | Transport Planning | New-120 | Yes |  | All Wards | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 3000000 | 3053278.5 | -53278.5 | 3000000 |  | 0 | #VALUE! | #VALUE! | 100% |  | 21,23 | BCMM | Construction of Hydroponics | Designs already approved | Not Applicable |  | The Contractor appointed on 05 October 2011. work has commenced on the two identified sites in wards 21 and 23. Invoice of R1, 60000.00 has been processed . 50% construction at Ward 21, completing site levelling at ward 23. Project in progress. | End March 2012 | Project complete. A journal has been forwarded to Finance for the Correction of misallocation. | 635/005/4/36/1044
Taxi Ranks | 620005 | 4 | 36 | 1045 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 | Yes |  | 37 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 3200000 | 456430.96 | 387319.04 | 843750 |  | 2356250 | #VALUE! | #VALUE! | 26.37% | R3,359,437- awarded to consultant | 34,36,39,41,43,49,25,40,44,37 | N/A | N/A | Designs Stage | N/A |  | Tender has been awarded and service level agreement to be entered into. | 2013-12-01 | Tender awarded for civil engineering consultants and designs are in progress. Tender for implementation in 2012/13 and 2013/14. Two stakeholder consultation meetings have been held and stage 2 of design process has been complete (concept and viability). The third PSC meeting has been scheduled for 18 July 2012. | 620/005/4/36/1045
Gonubie Main Road | 620005 | 4 | 36 | 1046 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-30 | Yes |  | 27,28 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 10000000 | 2973397.53 | 933822.66 | 3907220.19 |  | 6092779.81 | #VALUE! | #VALUE! | 39.07% | R10,000,000 - awarded to consultants | 28,27,29 | N/A | N/A | Preliminary and detailed designs progressing | N/A |  | N/A | 2012-06-01 | Draft tender documents and designs currently being reviewed by BCMM Roads Branch. Invoices to the value of R3.67m have been processed. Service provider currently busy with designs for Gonubie Service Lanes. Invoices in the amount R 230 000 have been processed. | 620/005/4/36/1046
Potsdam/Needs Camp Bridge Feasibility Study | 620005 | 6 | 81 | 1001 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 | Yes |  | 21 | BCMET c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 233787 | 0 | 0 | 0 |  | 233787 | #VALUE! | #VALUE! | 0% | R233,787 - awarded to consultant | 33,23 | N/A | N/A | Feasibility Study | N/A |  | Awarded to service provider. | 2012-06-01 | Work in Progress. 1st draft of report is being reviewed by department Awaiting first invoice from service provider | 620/005/6/81/1001
Rural non Motorised Transport facilities | 620005 | 6 | 01 | 1018 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 | Yes |  | 40 | Own Funds c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 330600 | 152828.33 | 0 | 152828.33 |  | 177771.67 | #VALUE! | #VALUE! | 46.23% | R330,000 - awarded to consultant | All | N/A | N/A | Feasibility Study and design | N/A |  | Awarded to service provider. | 2012-04-01 | Work in Progress. Awaiting first draft report from service provider. | 620/005/6/01/1018
Traffic Management Measures | 620005 | 6 | 01 | 1019 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 |  | Yes | All Wards | Own Funds c/o | #VALUE! | 714607 | #VALUE! |  | 1814607 | 199221.5 | 18998.39 | 218219.89 |  | 1596387.11 | #VALUE! | #VALUE! | 12.03% | R600,000 committed to smaller projects - informal tenders being considered. Other projects to be completed through annual contract 98, report to be submitted to BSC | All | N/A | N/A | N/A | N/A |  | New contract 98 to be submitted to the BSC for early March 2012: Informal tenders to the value of R600 000.00(Traffic calming measure) still being finalised between this department and SCM and award in February 2012: Traffic signal equipment and Traffic signal heads tenders, we have requested for the readvertisement as there were no bidders who met the requirements: Informal tenders to the value of R400 000.00(Traffic Signal Equipment and LED signal heads) to posted on the SCM notice board on Friday 10 February 2012. | 2012-06-01 | Signal heads and traffic controllers have been purchased. Informal tenders for Traffic Calming Measures to the value of +/- R 600,000 have been awarded. | 620/005/6/01/1019
Pedestrian facilities | 620005 | 6 | 01 | 1020 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 |  | Yes | All Wards | Own Funds c/o | #VALUE! | -256092 | #VALUE! |  | 343908 | 0 | 0 | 0 |  | 343908 | #VALUE! | #VALUE! | 0% | R350,000 committed to smaller projects - informal tenders being considered. Other projects to be completed through annual contract 98, report to be submitted to BSC | All | N/A | N/A | N/A | N/A |  | New contract 98 to be submitted to the BSC for early March 2012. TOR for Informal tenders to the value of R350 000.00 (Installation of Tactile paving & Physically chalanged ped push buttons) still being finalised at SCM and award in late February 2012. Work commencing there after. | 2012-06-01 | Audible Pedestrian Signals have been purchased. | 620/005/6/01/1020
Guidance Signage | 620005 | 6 | 01 | 1021 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 |  | Yes | All Wards | Own Funds c/o | #VALUE! | -13554 | #VALUE! |  | 586446 | 1067.22 | -1067.22 | 0 |  | 586446 | #VALUE! | #VALUE! | 0% | R600,000 committed - report progressing to Bid Adjudication Committee | 46,1,9,16,13,4,35,37 | N/A | N/A | N/A | N/A |  | Returned back to the BEC from the BAC because of funding in the outer years. | 2012-06-01 | Contract cancelled because the validity period expired and tender to be re-advertised. | 620/005/6/01/1021
Yellowwoods River Bridge | 620005 | 6 | 01 | 1022 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 |  | Yes | 42 | Own Funds c/o | #VALUE! | 202612 | #VALUE! |  | 2102612 | 1111506.37 | 0 | 1111506.37 |  | 991105.63 | #VALUE! | #VALUE! | 52.86% | R200,000 required to finalise this multi-year project. | 44 | N/A | N/A | N/A | N/A |  | N/A | 2011-08-01 | Project complete, final payment certificates to be processed | 620/005/6/01/1022
Yellowwoods River Bridge | 620005 | 4 | 01 | 1155 | 05 | 03 | 01 | 01 | 050 | 001 | Planning & Development | Transport Planning | New-50 |  | Yes | 42 | Own Funds | #VALUE! |  | #VALUE! | #VALUE! | 200000 | 0 | 0 | 0 |  | 200000 | #VALUE! | #VALUE! | 0% | R200,000 required to finalise this multi-year project. | 44 | N/A | N/A | N/A | N/A |  | N/A | 2011-08-01 | Project complete, final payment certificates to be processed | 620/005/4/01/1155
Economic Infrastructure | 635005 | 4 | 36 | 1047 | 05 | 03 | 01 | 01 | 320 | 001 | Planning & Development | Transport Planning | New-120 | Yes |  | All Wards | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 6000000 | 4705703.94 | -1041671.12 | 3664032.82 |  | 2335967.18 | #VALUE! | #VALUE! | 61.07% |  | 26, 40 | Communal | Top up funding for construction of Hydroponics at newlands and Qongqotha | Designs already approved | Not Applicable |  |  | End March 2012 | The programme has two projects Construction of Hydroponics and Steve Biko Foundation project. R2 million transfered to the Steve Biko Foundation. Nu 18 Hydroponics is about 60 % complete and is due to be finished by end May 2012. | 635/005/4/36/1047
Hydro-ponics - MDT | 635005 | 6 | 15 | 1100 | 05 | 03 | 01 | 01 | 320 | 002 | Planning & Development | Transport Planning |  |  | Yes | Mdantsane (All) | Department of Economic Affairs and Tourism c/o (DEDEAT) | #VALUE! | 5239 | #VALUE! |  | 5239 | 0 | 0 | 0 |  | 5239 | #VALUE! | #VALUE! | 0% | [9 empty] | Project is complete. Funds utilised for installation of Electricity for Kwakhanya Cooperative | 635/005/6/15/1100
Inner City Regeneration- Pedestrian Priority Zone | 635005 | 6 | 79 | 1100 | 05 | 03 | 01 | 01 | 320 | 002 | Planning & Development | Transport Planning |  |  | Yes | EL CBD | Provincial Treasury Office - LED Support Programme c/o | #VALUE! | 375269 | #VALUE! |  | 375269 | 0 | 0 | 0 |  | 375269 | #VALUE! | #VALUE! | 0% | R296000 final payment to consultant once funding is received from Provincial Treasury | [8 empty] | Project complete. Awaiting final payment from Provincial Treasury. | 635/005/6/79/1100
Desktop Computer - A10/58 | 635005 | 5 | 05 | 1201 | 05 | 02 | 01 | 01 | 270 | 001 | Planning & Development | Transport Planning |  | Yes |  | N/A | Own Funds | #VALUE! | 9500 | #VALUE! |  | 7850 | 7850 | 0 | 7850 |  | 0 | #VALUE! | #VALUE! | 100% | [7 empty] | 04.01.2012 | 2012-02-01 | Project Complete | 635/005/5/05/1201
Tourism infrastructure development | 635005 | 6 | 01 | 1013 | 05 | 03 | 01 | 01 | 320 | 001 | Planning & Development | Transport Planning | New-320 |  | Yes | All Wards | Own Funds c/o | #VALUE! | 797478 | #VALUE! |  | 1797478 | 581578.94 | 0 | 581578.94 |  | 1215899.06 | #VALUE! | #VALUE! | 32.36% |  | 32 | Water and Sanitation available | EC PARKS & TOURISM AGENCIES | Designs already approved | n/A |  | Phase: 1 of the project is complete. Balance will used for Phase: 2 which is construction of access road. Project is will be omplete in june 2012. |  | Phase: 1 of the project is complete. Balance will be used for Phase: 2 which is construction of access road. Project will be completed in 1st Quarter of the new finncial year. | 635/005/6/01/1013
Roll – Out Hydroponics | 635005 | 6 | 01 | 1014 | 05 | 03 | 01 | 01 | 320 | 001 | Planning & Development | Transport Planning | New-320 |  | Yes | All Wards | Own Funds c/o | #VALUE! | 130503 | #VALUE! |  | 3630503 | 489392.97 | 2023436.82 | 2512829.79 |  | 1117673.21 | #VALUE! | #VALUE! | 69.21% |  | 40 | Communal/ BCMM | Construction of Hydroponics at Newlands/Nxaruni | Designs already approved | Not applicable |  | Service Provider appointed, work on site. Invoices are being processed on completion of milestone. |  | Project commenced Phase 1 completed. Payment of R2,022,900.00 has been processed and project will be completed in the 1st Quarter of the Financial year. | 635/005/6/01/1014
Buffalo City Agric & Rural Development Infrastructure | 635005 | 6 | 01 | 1015 | 05 | 03 | 01 | 01 | 320 | 001 | Planning & Development | Transport Planning | New-320 |  | Yes | All Wards | Own Funds c/o | #VALUE! | -199740 | #VALUE! |  | 2793001 | 589002.32 | 999498.36 | 1588500.68 |  | 1204500.32 | #VALUE! | #VALUE! | 56.87% |  | 39 | Communal/ BCMM | Diptank and Livestock, fencing | Designs already approved | Not Applicable |  | Project in progress and will be completed end of June 2012 | End June 2012 | Request a roll over of R500 000,00 due to the fact that the department had experienced challenges during the site handover due to the community dynamics anticipating completion by July 2012. | 635/005/6/01/1015
Cooperative Support Programme | 635005 | 6 | 01 | 1016 | 05 | 03 | 01 | 01 | 320 | 001 | Planning & Development | Transport Planning | New-320 |  | Yes | All Wards | Own Funds c/o | #VALUE! | -1202733 | #VALUE! |  | 246455 | 0 | 0 | 0 |  | 246455 | #VALUE! | #VALUE! | 0% |  | All BCMM Wards | N/A | N/A | N/A | N/A |  | Project is complete | Project is complete | Project is complete Funds will be utilised for cooperative needs before the end of financial year. | 635/005/6/01/1016
Upgrade of Market | 635010 | 6 | 01 | 1017 | 05 | 03 | 01 | 01 | 290 | 001 | Other | Transport Planning | Renewal -290 |  | Yes | All Wards | Own Funds c/o | #VALUE! | -360105 | #VALUE! |  | 959895 | 429396.44 | 90361.84 | 519758.28 |  | 440136.72 | #VALUE! | #VALUE! | 54.15% |  | 12 | BCM Land | N/A | N/A | N/A |  | Funds to be utilised on completion of phase 2 of extension of sales hall. | 2012-05-01 | Remaining funds to be utilised on phase 2 for extension of sales hall in the 1st Quarter of the new financial year. | 635/010/6/01/1017
Extension of Sales Hall | 635010 | 4 | 01 | 1006 | 05 | 03 | 01 | 01 | 290 | 001 | Planning & Development | Transport Planning | Renewal -290 |  | Yes | All Wards | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 2000000 | 1717.35 | -1717.35 | 0 |  | 2000000 | #VALUE! | #VALUE! | 0% |  | 12 | BCM Land | N/A | N/A | N/A |  | Tender to be re-advertised for the 3rd time due to non responsive bids. The scope of work has been amended, tender process will start end Janaury 2012. | 2012-05-01 | Tender was re-dvertised in April 2012 and is going to BEC on the 11 June 2012. Anticipated to commnence in the new financial year. | 635/010/4/01/1006
TOTAL :DIRECTORATE OF DEVELOPMENT PLANNING | [10 empty] | 7 | [6 empty] | #REF! | #REF! | #REF! | #REF! | 144767504 | 84539.88 | 3785453.16 | 19833091.75 | 0 | 124934412.25 | #REF! | #REF! | 13.7%
DIRECTORATE OF HEALTH AND PUBLIC SAFETY
Fire Station - KWT | 725010 | 4 | 36 | 1053 | 05 | 04 | 01 | 01 | 200 | 001 | Health | Public safety | New-220 | Yes |  | 42 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 6227453 | 1527869.15 | 1490236.98 | 3018106.13 |  | 3209346.87 | #VALUE! | #VALUE! | 48.46% | 2011-06-30 | 37 | BCM | n/a | Plan finalised by PMU | n/a |  | Approved by BAC on 10/11/2011. Min No 373/11 | June 2012 | Project in progress. Multi year project, completion will be January 2013. | 725/010/4/36/1053
Generator - A11/73 | 725010 | 5 | 05 | 1245 | 05 | 02 | 01 | 01 | 260 | 001 | Public Safety | Public Safety |  | Yes |  | N/A | Own Funds |  |  |  |  | 9000 | 7140 | 0 | 7140 |  | 1860 |  |  | 79.33% | [9 empty] | Project Completed
Upgrade Mdantsane Fire Stations | 725010 | 6 | 83 | 1105 | 05 | 07 | 01 | 01 | 311 | 002 | Public safety | Public safety |  |  | Yes |  | European Commission c/o | #VALUE! | 171183 | #VALUE! | -171183 | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | [7 empty] | Works orders issued for work to be done. | May 2012 | Funding withdrawn as per Budget Adjustment | 725/010/6/83/1105
Computer & Globe Surfer - A10/113 | 710020 | 5 | 05 | 1217 | 05 | 02 | 01 | 01 | 270 | 001 | Community and social services | Health Services |  | Yes |  | N/A | Own Funds | #VALUE! | 9500 | #VALUE! |  | 9246 | 9245.95 | 0 | 9245.95 |  | 0.05 | #VALUE! | #VALUE! | 100% | [7 empty] | MIS in process of procurring computer and globe surfer for Zanempilo Clinic | February 2012 | Project Completed. | 710/020/5/05/1217
3 x Fridges - A10/106 | 710020 | 5 | 05 | 1222 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Health Services |  | Yes |  | N/A | Own Funds | #VALUE! | 9500 | #VALUE! |  | 7103 | 7102.63 | 0 | 7102.63 |  | 0.37 | #VALUE! | #VALUE! | 99.99% | [7 empty] | Fridges have been received by Gompo C | January 2012 | Project Completed. | 710/020/5/05/1222
Clinics | 710020 | 6 | 36 | 1001 | 05 | 04 | 01 | 01 | 200 | 001 | Health | Health Services | Renewal-200 |  | Yes | N/A | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2100000 | 3354.24 | -3354.24 | 0 |  | 2100000 | #VALUE! | #VALUE! | 0% | JUNE 2011 | Ward 46 | BCMM | BIA |  | N/A |  | Appointment letter signed on 6-12-2011. Waiting for construction guarantee from contractor | End June 2012 | Contract cancelled due to contractor not providing construction guarantee certificate. PHC taken over by Province from July 2012. | 710/020/6/36/1001
Air quality monitoring station equipment | 710040 | 6 | 01 | 1031 | 05 | 04 | 01 | 01 | 270 | 001 | Community and social services | Environmental Services | New-270 | Yes |  | All Wards | Own Funds c/o | #VALUE! | -311895 | #VALUE! |  | 100268 | 0 | 83600 | 83600 |  | 16668 | #VALUE! | #VALUE! | 83.38% | MAY 2010 | All wards | BCMM | Yes | N/A | Non |  | MIS to process requisition in order for SCM to procure computer. | End March 2012 | Awaiting delivery of laptop and printer ordered by MIS costing R10 414 - 63. | 710/040/6/01/1031
Mobile Clinics Equipment | 710020 | 6 | 01 | 1032 | 05 | 04 | 01 | 01 | 200 | 001 | Health | Health Services | New-260 | Yes |  | All Wards | Own Funds c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 235495 | 219641.91 | 11339.25 | 230981.16 |  | 4513.84 | #VALUE! | #VALUE! | 98.08% | JUNE 2011 | Ward 31;44 | BCMM | N/A | N/A | N/A |  | SCM is updating BCMM Suppliers Database | 2012-05-01 | Project Completed | 710/020/6/01/1032
Upgrading of Clinics - Ginsberg | 710020 | 6 | 01 | 1033 | 05 | 04 | 01 | 01 | 200 | 001 | Health | Health Services | Renewal-200 |  | Yes | 42 | Own Funds c/o | #VALUE! | 100000 | #VALUE! |  | 698124 | 404287.12 | 94370 | 498657.12 |  | 199466.88 | #VALUE! | #VALUE! | 71.43% | MAY 2010 | Ward 39 | BCMM | BIA | N/A | N/A |  | Orders have been placed with Service Providers and some equipment already received. Requisitions to be submitted to SCM for balance of equipment. | Mid March 2012 | Project Completed | 710/020/6/01/1033
Desktop computer - A10/56 | 710020 | 5 | 05 | 1233 | 05 | 02 | 01 | 01 | 270 | 001 | Community and social services | Health Services |  | Yes |  | N/A | Own Funds | #VALUE! | 9500 | #VALUE! |  | 7235 | 7234.21 | 0 | 7234.21 |  | 0.79 | #VALUE! | #VALUE! | 99.99% | MAY 2010 | Ward 39 | BCMM | BIA | N/A | N/A |  | Total expenditure is R370,348 | End February 2012 | Project Completed. | 710/020/5/05/1233
KWT Fire Station | 725010 | 6 | 1 | 1105 | 05 | 07 | 01 | 01 | 311 | 002 | Public safety | Public safety |  |  | Yes | 42 | Own Funds c/o |  |  |  |  | 1999999 |  | 401971 | 401971 |  | 1598028 |  |  | 0%
Fire Engine R/O | 725010 | 6 | 82 | 1103 | 05 | 07 | 02 | 01 | 360 | 002 | Public safety | Public safety | New-360 | Yes |  | All Wards | DBSA Phase 4 |  |  |  |  | 11651923 |  | 11651923 | 11651923 |  | 0 |  |  | 0%
Insurance vehicle replacement - M10/189 | 725015 | 5 | 05 | 1212 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | All Wards | Own Funds | #VALUE! | 265000 | #VALUE! |  | 265000 | 0 | 0 | 0 |  | 265000 | #VALUE! | #VALUE! | 0% | [7 empty] | Request for advertising of tender submitted to Fleet Mang. | May 2012 | Fleet requested to purchase vehicles - project to be rolled over | 725/015/5/05/1212
Insurance vehicle replacement- M10/27 | 725020 | 5 | 05 | 1213 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | All Wards | Own Funds | #VALUE! | 265000 | #VALUE! |  | 265000 | 0 | 0 | 0 |  | 265000 | #VALUE! | #VALUE! | 0% | [7 empty] | Request for advertising of tender submitted to Fleet Mang. | May 2012 | Fleet requested to purchase vehicles - project to be rolled over | 725/020/5/05/1213
Law Enforcement Equipment | 725015 | 6 | 01 | 1034 | 05 | 07 | 02 | 01 | 270 | 001 | Corporate Services | Public safety | New-260 | Yes |  | All Wards | Own Funds c/o | #VALUE! | -161398 | #VALUE! |  | 18602 | 18186.67 | 0 | 18186.67 |  | 415.33 | #VALUE! | #VALUE! | 97.77% |  | 27 & 41 | n/a | n/a | n/a | n/a |  | Project completed. | December 2011 | Project completed. | 725/015/6/01/1034
Traffic Vehicles | 725020 | 4 | 01 | 1021 | 05 | 07 | 02 | 01 | 250 | 001 | Public safety | Public safety | New-250 | Yes |  | All Wards | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 450000 | 0 | 42607.82 | 42607.82 |  | 407392.18 | #VALUE! | #VALUE! | 9.468% |  | All | n/a | n/a | n/a | n/a |  | Tender for M/cycles closed on 20 Dec. 2011. Tender for mini bus to be advertised. | March 2012 | Fleet requested to purchase vehicles - project to be rolled over | 725/020/4/01/1021
Insurance vehicle replacement - M09/131 | 725020 | 5 | 05 | 1210 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | All Wards | Own Funds | #VALUE! | 220000 | #VALUE! |  | 220000 | 0 | 0 | 0 |  | 220000 | #VALUE! | #VALUE! | 0% | [7 empty] | Request for advertising of tender submitted to Fleet Mang. | May 2012 | Fleet requested to purchase vehicles - project to be rolled over | 725/020/5/05/1210
Learners Licence Centre - Mdantsane | 725035 | 4 | 01 | 1022 | 05 | 07 | 02 | 01 | 312 | 001 | Public safety | Public safety | New-312 | Yes |  | All Wards | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 3298.68 | -3298.68 | 0 |  | 1000000 | #VALUE! | #VALUE! | 0% |  | All | n/a | n/a | n/a | n/a |  | Land identified, plans approved, awaiting further funding as R 2.5m will be required for completion | 2012-06-30 | Tender closed on 30 March 2012, in evaluation stage. Project to be rolled over | 725/035/4/01/1022
Fire Engines Roll 0ver | 725010 | 6 | 01 | 1035 | 05 | 07 | 02 | 01 | 360 | 002 | Public safety | Public safety | New-360 | Yes |  | All Wards | Own Funds c/o | #VALUE! | 4456705 | #VALUE! |  | 4106923 | 11911338.36 | -10623800.12 | 1287538.24 |  | 2819384.76 | #VALUE! | #VALUE! | 31.35% |  | All | n/a | n/a | Waiting delivery | n/a |  | 2 x Aerial Appiances have been delivered. Delivery of Urban Rescue vehicle due in February 2012. | End February 2012 | Project completed. | 725/010/6/01/1035
Fire Engine Equipment | 725010 | 6 | 01 | 1036 | 05 | 07 | 02 | 01 | 360 | 002 | Public safety | Public safety | New-360 | Yes |  | All Wards | Own Funds c/o | #VALUE! | -503399 | #VALUE! |  | 2371404 | 1575941.33 | 364836.76 | 1940778.09 |  | 430625.91 | #VALUE! | #VALUE! | 81.84% |  | All | n/a | n/a | Waiting delivery | n/a |  | Procurement in progress. | May 2012 | Project completed. | 725/010/6/01/1036
KWT Fire Station | 725010 | 6 | 82 | 1102 | 05 | 07 | 01 | 01 | 311 | 002 | Public safety | Public safety |  |  | Yes | 37 | DBSA Phase 4 & 5 c/o | #VALUE! | 2000000 | #VALUE! |  | 1 | 401971.16 | -401971 | 0.16 |  | 0.84 | #VALUE! | #VALUE! | 16% | [7 empty] | As per line 186/Vote 725/010/4/36/1053 above. | June 2012 | To be used in conjunction with the R6m provided for KWT Fire Station. Funding to be rolled over, completion date January 2013. | 725/010/6/82/1102
Flood Relocation (DM Structures) | 725055 | 6 | 89 | 1100 | 05 | 07 | 01 | 01 | 311 | 002 | Public safety | Public safety |  |  | Yes | All Wards | Disaster Management Fund c/o | #VALUE! | 41025 | #VALUE! |  | 41025 | 0 | 0 | 0 |  | 41025 | #VALUE! | #VALUE! | 0% | [9 empty] | Development Planning requested to utilise funding as per D.V.R.I. Roll over required | 725/055/6/89/1100
Disaster Management Capacity | 725055 | 6 | 89 | 1001 | 05 | 07 | 04 | 01 | 320 | 002 | Public Safety | Public safety | New-320 |  | Yes | All Wards | Disaster Management Fund c/o | #VALUE! | -7150 | #VALUE! |  | 36790 | 23729.76 | 0 | 23729.76 |  | 13060.24 | #VALUE! | #VALUE! | 64.5% | 2006/7 | All | n/a | n/a | n/a | n/a |  | Purchase of equipment in progress. | March 2012 | Balance to be rolled over. | 725/055/6/89/1001
Disaster Management Centres | 725055 | 6 | 89 | 1002 | 05 | 07 | 04 | 01 | 320 | 002 | Public Safety | Public safety | New-320 | Yes |  | All Wards | Disaster Management Fund c/o | #VALUE! | 0 | #VALUE! |  | 84779 | 84779 | 0 | 84779 |  | 0 | #VALUE! | #VALUE! | 100% | 2005/6 | All | n/a | n/a | n/a | n/a |  | Tender awarded to Sidiki Trading for supply & installation of Automatic Fire detection & Inhert Gas Extinguishing System. | February 2012 | Project Completed | 725/055/6/89/1002
TOTAL : DIRECTORATE OF HEALTH AND PUBLIC SAFETY | [10 empty] | 8 | [6 empty] | #VALUE! | 6563571 | #VALUE! | #VALUE! | 31905370 | 16205120.17 | 3108460.77 | 19313580.94 | 0 | 12591789.06 | #VALUE! | #VALUE! | 60.53%
DIRECTORATE OF COMMUNITY SERVICES
Development of Community Parks(Mdantsane, Potsdam, Reeston) | 755010 | 4 | 36 | 1048 | 05 | 03 | 01 | 01 | 150 | 001 | Community and social services | Amenities | New-150 | Yes |  | 23,20,21,22,17 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 1016303 | 101904.99 | 441500 | 543404.99 |  | 472898.01 | #VALUE! | #VALUE! | 53.47% | 2011-07-01 | 20,23 | BCMM | Not required | Consultation complete, land identified. | None |  | SCM busy with adjudication of the tenders received |  | Play park equipment has been ordered and await installation by the Service Provider. To re advertise for informal tender for the fencing of 3 parks and purchasing of park furniture, trees and signage. A roll over will be required to complete the project. | 755/010/4/36/1048
Brushcutter - A10/102 | 755010 | 5 | 05 | 1203 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Environmental Services |  | Yes |  | N/A | Own Funds | #VALUE! | 9600 | #VALUE! |  | 8373 | 8372.5 | 0 | 8372.5 |  | 0.5 | #VALUE! | #VALUE! | 99.99% | [7 empty] | Order created by SCM for the service provider |  | Machine received in January 2012 | 755/010/5/05/1203
3 x Brushcutters - A11/15 | 755010 | 5 | 05 | 1205 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Environmental Services |  | Yes |  | N/A | Own Funds | #VALUE! | 30000 | #VALUE! |  | 25602 | 25601.97 | 0 | 25601.97 |  | 0.03 | #VALUE! | #VALUE! | 100% | [7 empty] | Awaiting SCM to process the order |  | Machines received. | 755/010/5/05/1205
Development of 3 New Cemetries(Inland, Midland and Coastal) | 755025 | 4 | 36 | 1049 | 05 | 05 | 04 | 01 | 320 | 001 | Community and social services | Environmental Services | New-220 | Yes |  | 34,39,11,12,14,20,21,22,23,30,42,48,50 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 3000000 | 372906.58 | 184273.01 | 557179.59 |  | 2442820.41 | #VALUE! | #VALUE! | 18.57% | 2011-07-01 | 36, 22, 37 | BCMM | BIA | Work instruction submitted to Engineering for the design, plan and tarring of roads and ablutions facilities at KWT and Dimbaza. | None |  | Consultants Ages (PTY, LTD) appointed to conduct feasibility studies in the Midland and Inland area as well as the feasibility study for the construction of an access bridge at the King Williams Town Extension Cemetery. |  | The construction branch have appointed a service provider to deveop and establish road in Dimbaza and KWT Cemeteries but according to the construction branch the project was delayed due to the fact that SCM onlyprocessed Works orders on 21 June and the work will be completed in the new financial year therefore a roll over is required. | 755/025/4/36/1049
Insurance vehicle replacement - M07/212 | 755025 | 5 | 05 | 1239 | 05 | 02 | 01 | 01 | 250 | 001 | Environmental Protection | Environmental Services |  | Yes |  |  | Own Funds |  |  |  | 298224 | 0 | 0 |  | 0 |  | 0 |  |  | #DIV/0! | [9 empty] | Insurance replacement | 755/025/5/05/1239
Desktop Computer - A10/127 | 760010 | 5 | 05 | 1204 | 05 | 02 | 01 | 01 | 270 | 001 | Corporate Services | Support Services |  | Yes |  | N/A | Own Funds | #VALUE! | 8500 | #VALUE! |  | 7328 | 7327.78 | 0 | 7327.78 |  | 0.22 | #VALUE! | #VALUE! | 100% | [9 empty] | Computer purchased and commissioned into use. | 760/010/5/05/1204
Scenery Park Community Hall | 760025 | 4 | 36 | 1050 | 05 | 05 | 03 | 01 | 170 | 001 | Community and social services | Amenities | New-170 | Yes |  | 5,13 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2000000 | 1908763.29 | 25739.86 | 1934503.15 |  | 65496.85 | #VALUE! | #VALUE! | 96.73% | 2011-09-10 | 5 | BCM | n/a | n/a | n/a |  | Complete | 16 January 2012 | Project completed. Balance of the funding to be spent on sewer/water connections in 2012/2013. Roll over requested. | 760/025/4/36/1050
Viper Polisher - A09/105 | 760025 | 5 | 05 | 1211 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Amenities |  | Yes |  | N/A | Own Funds | #VALUE! | 10000 | #VALUE! |  | 8500 | 8500 |  | 8500 |  | 0 | #VALUE! | #VALUE! | 100% | [7 empty] | To be determined by SCM processes. |  | The polisher has been received and commissioned into use. | 760/025/5/05/1211
Insurance vehicle replacemen - M11/55 | 760025 | 5 | 05 | 1232 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  | All Wards | Own Funds | #VALUE! | 285000 | #VALUE! |  | 285000 | 0 |  | 0 |  | 285000 | #VALUE! | #VALUE! | 0% | [7 empty] | To be determined by Mechanical Workshops & SCM processes | To be determined by SCM processes | Insurance Claim - Mechanical Workshops (Mr Gijana) confirmed to Mr Mahomed 06/07/2012 that the vehicle tender was still with the Bid Committee. Vehicle expected to be replaced by end of July 2012. | 760/025/5/05/1232
Insurance vehicle replacement - M09/153 | 765030 | 5 | 05 | 1219 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet |  | Yes |  |  | Own Funds | #VALUE! | 350000 | #VALUE! |  | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | [7 empty] | Vehicle was handed over to Beaches | Completed: insurance claim | Vehicle has been delivered, handed over to beaches. | 765/030/5/05/1219
Solid waste management | 770030 | 4 | 36 | 1051 | 05 | 10 | 01 | 01 | 100 | 001 | Waste Management | Cleansing |  | Yes |  | All Wards | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2800000 | 1284893.77 | 450300.99 | 1735194.76 |  | 1064805.24 | #VALUE! | #REF! | 61.97% | 2011-06-30 |  | BCMM | n/a | n/a | n/a |  | Construction of Drop Off Points (R2.8 million) - Project at Bid Evaluation Stage | To be determined by SCM processes | Project completed. Balance declared as savings | 770/030/4/36/1051
Planning of designs of Third Cell | 770030 | 4 | 36 | 1135 | 05 | 05 | 04 | 01 | 100 | 001 | Environmental Protection | Environmental Services | New-220 | Yes |  | All Wards | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 500000 | 0 | 88334.71 | 88334.71 |  | 411665.29 | #VALUE! | #VALUE! | 17.67% | 2011-07-01 | 36, 22, 37 | BCMM | BIA | Work instruction submitted to Engineering for the design, plan and tarring of roads and ablutions facilities at KWT and Dimbaza. | None |  | Consultants Ages (PTY, LTD) appointed to conduct feasibility studies in the Midland and Inland area as well as the feasibility study for the construction of an access bridge at the King Williams Town Extension Cemetery. |  | Contractor is on site doing bush clearing. A request has been submitted for the balance to be rolled over to complete the project. | 770/030/4/36/1135
Sport Facilities | 765010 | 4 | 36 | 1052 | 05 | 10 | 01 | 01 | 160 | 001 | Sports and Recreation | Cleansing | Renewal-160 |  | Yes | 7,12,13,28,29,35,37,38,41,44 | Urban Settlement Development Grant | #VALUE! | 0 | #VALUE! | #VALUE! | 2000000 | 289497.13 | -7973.23 | 281523.9 |  | 1718476.1 | #VALUE! | #VALUE! | 14.08% | 2011-10-11 | 7,12,13,28,29,35,37,38,44 | BCM | N/A | Specifications submitted to SCM | n/a |  | Projects will be handled as informal tenders. Informal tender forms are being drafted | 30/06/2012 | Bid specification documents was on the agenda of the BSC meeting on 24/2/12.BSC requested that the PMU must assist in the finalisation of the Bill of Quantities which will form part of the bid spec document. PMU indicated that that they do not have capacity to assist.The Community Services Directorate attempted to meet the BSC to clarify that the Bill of Quantities may not be needed for purposes of the specification document. The Director Community Services did not obtain confirmation from chairperson of the BSC for a date of the meeting. There is no committment for the project, therefore it cannot be rolled over. | 765/010/4/36/1052
Insurance vehicle replacement - M11/02 | 770005 | 5 | 05 | 1226 | 05 | 02 | 01 | 01 | 250 | 001 | Other | Other - BCM Fleet | Renewal-250 | Yes |  | All Wards | Own Funds | #VALUE! | 160000 | #VALUE! |  | 160000 | 0 | 0 | 0 |  | 160000 | #VALUE! | #VALUE! | 0% | [9 empty] | Tender awarded. Awaiting delivery | 770/005/5/05/1226
Purchase of 7 Refuse Compactor Trucks - Mdantsane | 770010 | 4 | 01 | 1007 | 05 | 05 | 01 | 01 | 350 | 001 | Waste Management | Cleansing | New-350 | Yes |  | All Wards | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 10500000 | 2913.6 | 8666291.64 | 8669205.24 |  | 1830794.76 | #VALUE! | #VALUE! | 82.56% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | To be submitted to BEC |  | Tender awarded. Awaiting delivery | 770/010/4/01/1007
Purchase of 3 Refuse Compactor Trucks (Mdantsane) | 770010 | 4 | 01 | 1008 | 05 | 05 | 01 | 01 | 350 | 001 | Waste Management | Cleansing | New-350 | Yes |  | All Wards | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 4500000 | 0 | 0 | 0 |  | 4500000 | #VALUE! | #VALUE! | 0% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | To be submitted to BEC |  | Tender awarded. Awaiting delivery | 770/010/4/01/1008
Purchase of 2 x LDV Bakkie's | 770010 | 4 | 01 | 1009 | 05 | 05 | 01 | 01 | 250 | 001 | Waste Management | Cleansing | New-350 | Yes |  | All Wards | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 460000 | 0 |  | 0 |  | 460000 | #VALUE! | #VALUE! | 0% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | To be submitted to BEC |  | Tender awarded. Awaiting delivery | 770/010/4/01/1009
Purchase of 1 X Load lugger | 770010 | 4 | 01 | 1010 | 05 | 05 | 01 | 01 | 250 | 001 | Waste Management | Cleansing | New-350 | Yes |  | All Wards | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 800000 | 0 |  | 0 |  | 800000 | #VALUE! | #VALUE! | 0% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | To be seubmitted to BEC |  | Tender awarded. Awaiting delivery | 770/010/4/01/1010
Refuse 5 Compactor Trucks - Coastal Region | 750005 | 4 | 01 | 1011 | 05 | 05 | 01 | 01 | 350 | 001 | Community and social services | Cleansing | New-350 | Yes |  | All Wards | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 10000000 | 8013649.82 | 0 | 8013649.82 |  | 1986350.18 | #VALUE! | #VALUE! | 80.14% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | All trucks delivered | Completed | Tender awarded. Awaiting delivery | 750/005/4/01/1011
Vehicles for Solid Waste Supervisors, Safety Officers, District Cleansing Officers and Superintendents -(9 X Sedans, 8 LDV's, 3 X Double Cabs, 2X3 Ton Trucks (Inland,Midlands and Coastal Areas) | 750005 | 4 | 01 | 1012 | 05 | 10 | 11 | 01 | 250 | 001 | Waste Management | Cleansing | New-250 | Yes |  | All Wards | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 4000000 | 3104.7 | 2463368.07 | 2466472.77 |  | 1533527.23 | #VALUE! | #VALUE! | 61.66% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | To be submitted to BEC |  | Tender awarded. | 750/005/4/01/1012
Miscallaneous Bins | 750005 | 6 | 01 | 1023 | 05 | 10 | 11 | 01 | 100 | 002 | Waste Management | Cleansing | New-100 | Yes |  |  | Own Funds c/o | #VALUE! | -58000 | #VALUE! |  | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | Complete, balance declared as savings |  | Completed | 750/005/6/01/1023
9 x Brushcutters - A10/117 | 755010 | 5 | 05 | 1215 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Environmental Services |  | Yes |  | N/A | Own Funds | #VALUE! | 87000 | #VALUE! |  | 76005 | 76005 | 0 | 76005 |  | 0 | #VALUE! | #VALUE! | 100% | [9 empty] | 9x Brushcutters purchased and delivered to Workshop | 755/010/5/05/1215
6 x Brushcutters, Pruner, Chainsaw - A11/22 | 755010 | 5 | 05 | 1216 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Environmental Services |  | Yes |  | N/A | Own Funds | #VALUE! | 78000 | #VALUE! |  | 78000 | 70822 |  | 70822 |  | 7178 | #VALUE! | #VALUE! | 90.8% | [9 empty] | Machines received and currently at Meadow Road depot | 755/010/5/05/1216
Rotovor - A11/30 | 755010 | 5 | 05 | 1234 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Environmental Services |  | Yes |  | N/A | Own Funds | #VALUE! | 15000 | #VALUE! |  | 15000 | 11841.23 |  | 11841.23 |  | 3158.77 | #VALUE! | #VALUE! | 78.94% | [8 empty] | Completed | Rotovator received and sent to the Nursery | 755/010/5/05/1234
3xBrushcutters & 1 x Blower -A11/30 | 755010 | 5 | 05 | 1236 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Environmental Services |  | Yes |  | N/A | Own Funds |  |  |  | 35000 | 35000 | 30035.77 | 0 | 30035.77 |  | 4964.23 |  |  | 85.82% | [9 empty] | Machines received | 755/010/5/05/1236
Insurance vehicle replacement - M07/212 | 755025 | 4 | 01 | 1013 | 05 | 05 | 04 | 01 | 250 | 001 | Environmental Protection | Other - BCM Fleet | New-260 | Yes |  | All Wards | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 298224 | 0 |  | 0 |  | 298224 | #VALUE! | #VALUE! | 0% | 2011-07-01 | 7 | Insurance Claim | N/A | N/A | None |  | N/A | Completed | Completed | 755/025/4/01/1013
Fencing of Rural Cemeteries Upgrade | 755025 | 6 | 01 | 1024 | 05 | 05 | 04 | 01 | 320 | 002 | Community and social services | Environmental Services | Renewal-320 |  | Yes |  | Own Funds c/o | #VALUE! | 154956 | #VALUE! |  | 314956 | 69100 | 142210 | 211310 |  | 103646 | #VALUE! | #VALUE! | 67.09% | 2011-07-01 | 41 | BCMM | BIA | N/A | None |  | None | March 2012 | Pallisade fencing 30meters completed in needs camp cemetery. The contractor appointed for the kuni village cemtery is near completion. A further R79 000 will be utilised to fence one of the rural cemeteries and a roll over is required. | 755/025/6/01/1024
3x Brushcutters - A11/105 | 755025 | 5 | 05 | 1239 | 05 | 02 | 01 | 01 | 250 | 001 | Community and social services | Amenities |  | Yes |  | N/A | Own Funds |  |  |  |  | 33000 | 0 | 0 | 0 |  | 33000 |  |  | 0% | [9 empty] | Machines have been ordered and will be delivered in June 2012. | 755/025/5/05/1239
9x Brushcutters - A11/95 | 755025 | 5 | 05 | 1258 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Amenities |  | Yes |  | N/A | Own Funds |  |  |  |  | 88000 |  | 76726.89 | 76726.89 |  | 11273.11 |  |  | 87.19% | [9 empty] | Machines delivered | 755/025/5/05/1258
Dry Sanitation & Greywater Recycling | 755035 | 6 | 63 | 1100 | 05 | 09 | 01 | 01 | 320 | 002 | Waste Water Management | Waste Water |  |  | Yes | All Wards | Department of Science & Technology c/o (DST) | #VALUE! | 173830 | #VALUE! |  | 173830 | 0 | 0 | 0 |  | 173830 | #VALUE! | #VALUE! | 0% | [9 empty] | Project has been transferred to Sanitation Department by IED' office | 755/035/6/63/1100
Waste Minimisation | 755035 | 6 | 63 | 1101 | 05 | 09 | 01 | 01 | 320 | 002 | Community and social services | Cleansing |  |  | Yes | All Wards | Department of Science & Technology c/o (DST) | #VALUE! | 160317 | #VALUE! |  | 160317 | 0 | 150000 | 150000 |  | 10317 | #VALUE! | #VALUE! | 93.56% | [9 empty] | Waste Minimisation infrasturture being procudred through informal tender | 755/035/6/63/1101
Egerton Railway Station Massacre Memorail Site | 760005 | 6 | 78 | 1100 | 05 | 03 | 01 | 01 | 190 | 002 | Sports and Recreation | Amenities |  |  | Yes | 9 | Office of the Premier c/o | #VALUE! | 500000 | #VALUE! |  | 500000 | 145538.39 | 287041 | 432579.39 |  | 67420.61 | #VALUE! | #VALUE! | 86.52% | [7 empty] | Service provider appointed. | 2012-03-01 | Project complete | 760/005/6/78/1100
Continuation of refurbishment of KWT Hall / Cambridge | 760025 | 4 | 01 | 1014 | 05 | 08 | 01 | 01 | 170 | 001 | Community and social services | Amenities | Renewal-170 |  | Yes | 42 | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 2792507 | 1114241.49 | 600431.97 | 1714673.46 |  | 1077833.54 | #VALUE! | #VALUE! | 61.4% | 2011-09-10 | 42 | BCM | n/a | Complete | n/a |  | Tender closed 05/08/2011 |  | KWT Town Hall - validity period expired. To be resubmitted to BAC in the new financial year. Roll over requested. Cambridge Town Hall - Phase 1: complete. Phase 2 has commenced and project to be complete by the end of August 2012. | 760/025/4/01/1014
Upgrading of Beacon Bay Library | 760025 | 4 | 01 | 1015 | 05 | 08 | 01 | 01 | 170 | 001 | Community and social services | Amenities | Renewal-180 |  | Yes | 4 | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 363795 | 333656.82 | 23512.79 | 357169.61 |  | 6625.39 | #VALUE! | #VALUE! | 98.18% | 2011-11-12 | 29 | BCM | n/a | Complete | n/a |  | Tender closed 05/08/2011 | May 2012 | Project complete and balance of funds requested to be rolled over and to be utilised for the refurbishment of the kitchen. | 760/025/4/01/1015
Rural Communit Halls Rehabilitation ( Airport St Mary) | 760025 | 6 | 61 | 1106 | 05 | 08 | 01 | 01 | 170 | 001 | Community and social services | Amenities | Renewal-180 |  | Yes | 46 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 625764 | 312280.7 | 111948.79 | 424229.49 |  | 201534.51 | #VALUE! | #VALUE! | 67.79% | 2011-11-12 | 29 | BCM | n/a | Complete | n/a |  | Tender closed 05/08/2011 | May 2012 | Rehabilitation of both halls have been completed. Released the retention payments. Roll over requested. | 760/025/6/61/1106
1X Lawnmower & 1 X Brushcutter -A11/59 | 765010 | 5 | 05 | 1242 | 05 | 02 | 01 | 01 | 260 | 002 | Community and social services | Support Services | renewal-320 | Yes |  | N/A | Own Funds | #VALUE! | 4890900 | #VALUE! |  | 36000 | 0 | 24931.48 | 24931.48 |  | 11068.52 | #VALUE! | #VALUE! | 69.25% | [9 empty] | Equipment replaced as per insurance claim. Project complete. | 765/010/5/05/1242
1xBlower, Pole Pruner, Microphone - A11/88 | 765010 | 5 | 05 | 1248 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Amenities |  | Yes |  | N/A | Own Funds |  |  |  |  | 56000 | 0 | 45832.57 | 45832.57 |  | 10167.43 |  |  | 81.84% | [9 empty] | Equipment replaced as per insurance claim. Project complete. | 765/010/5/05/1248
Rural Sports Facilities | 765010 | 6 | 61 | 1107 | 05 | 08 | 01 | 01 | 180 | 001 | Sports and Recreation | Amenities | Renewal-180 |  | Yes | 24 | Municipal Infrastructure Grant c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 406901 | 406901 | 0 | 406901 |  | 0 | #VALUE! | #VALUE! | 100% | 2011-11-12 | 29 | BCM | n/a | Complete | n/a |  | Tender closed 05/08/2011 | May 2012 | The amount R406, 901 was journalized into the Sports Facilities USDG vote 7650104361052 as the funds from the sports facilities project was utilized to pay service providers for the MIG funded project of Rural Sports Facilities due to MIG funding not being rolled over at that stage of the financial year (July 2011). | 765/010/6/61/1107
CCTV Camera System - A10/30 | 765010 | 5 | 05 | 1209 | 05 | 02 | 01 | 01 | 270 | 001 | Community and social services | Amenities |  | Yes |  | N/A | Own Funds | #VALUE! | 17100 | #VALUE! |  | 17100 | 14933.96 | 0 | 14933.96 |  | 2166.04 | #VALUE! | #VALUE! | 87.33% | [9 empty] | CCTV system was replaced at BC Stadium as per insurance claim. Project complete. | 765/010/5/05/1209
Upgrading of Needs Camp Sportfield | 765010 | 6 | 01 | 1025 | 05 | 08 | 01 | 01 | 160 | 001 | Sports and Recreation | Amenities | Renewal-160 |  | Yes | 33 | Own Funds c/o | #VALUE! | 149123 | #VALUE! |  | 2500000 | 3104.64 | -3104.64 | 0 |  | 2500000 | #VALUE! | #VALUE! | 0% | 9/10 | 33 | BCM | Bulk Infstructure needed | Bid documents for the appoitnment of a professional service provider submitted to SCM | n/a |  | Waiting for item to be placed on BSC agenda |  | Tender advert closed on the 04 April 2012. SCM have finalized price/ HDI Ranking. There is no committment for this project, therefore the project cannot proceed. | 765/010/6/01/1025
Upgrading of Rural Sportsfields | 765010 | 6 | 01 | 1026 | 05 | 08 | 01 | 01 | 160 | 001 | Sports and Recreation | Amenities | Renewal-160 |  | Yes | 24 | Own Funds c/o | #VALUE! | -203783 | #VALUE! |  | 72038 | 71759.17 | -13462.68 | 58296.49 |  | 13741.51 | #VALUE! | #VALUE! | 80.92% | 09/10 | 45 | BCM | Bulk Infstructure needed | n/a | n/a |  | Orders awarded for phases 1, 2 and 3 | 31/03/2012 | Perimeter fencing at Nkqonkweni has been done. Phase 1 completed. Phase 2 grass seeding to be done. Phase 3 which involves maintenance of the field to follow there after. Orders for phase 2 and phase 3 have been issued by SCM in the last financial year. | 765/010/6/01/1026
Ruth Belonsky Swimming Pool | 765015 | 4 | 01 | 1016 | 05 | 03 | 01 | 01 | 160 | 001 | Community and social services | Amenities | New-160 | Yes |  | 1 | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 12720 | 12719.3 | -12719.3 | 0 |  | 12720 | #VALUE! | #VALUE! | 0% | 10/11 | 5 | BCM | n/a | n/a | n/a |  | Project complete |  | Project was Completed in September 2011 | 765/015/4/01/1016
Zoo CCTV Camera System - A11/84 | 765025 | 5 | 05 | 1250 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Amenities |  | Yes |  | All Wards | Own Funds |  |  |  |  | 46000 | 45984 | 0 | 45984 |  | 16 |  |  | 99.97% | [9 empty] | Project Completed | 765/025/5/05/1250
3X Brushcutters - A11/112 | 760025 | 5 | 05 | 1257 | 05 | 02 | 01 | 01 | 260 | 001 | Community and social services | Amenities |  | Yes |  | N/A | Own Funds |  |  |  |  | 33000 |  | 28860 | 28860 |  | 4140 |  |  | 87.45% | [9 empty] | Completed | 760/025/5/05/1257
Upgrading Of Zoo Offices & Ablution Blocks | 765025 | 6 | 01 | 1027 | 05 | 03 | 01 | 01 | 190 | 001 | Sports and Recreation | Amenities | Renewal-190 |  | Yes | All Wards | Own Funds c/o | #VALUE! | -197247 | #VALUE! |  | 723254 | 83600 | 89276.18 | 172876.18 |  | 550377.82 | #VALUE! | #VALUE! | 23.9% | 9/10 | 22 | BCM | n/a | Planning and specifications done by Architects division | n/a |  | N/A |  | The service provider that was appointed by the tender process has made very little progress on site as he has indicated that he is experiencing cash flow problems. The Architects Division who are Project Managers has issued the service provider with 3 letters instructing him to show due diligence. Due to slow progress contractor working to penalties of R750.00 a day from 25 May 2012 until completion. A roll over has been requested | 765/025/6/01/1027
Fencing Of Zoo c/o | 765025 | 6 | 01 | 1028 | 05 | 03 | 01 | 01 | 190 | 001 | Sports and Recreation | Amenities | Renewal-190 |  | Yes | All Wards | Own Funds c/o | #VALUE! | 0 | #VALUE! | #VALUE! | 606481 | 238111.2 | 546.49 | 238657.69 |  | 367823.31 | #VALUE! | #VALUE! | 39.35% | 09/10 | 22 | BCM | n/a | Planning and specifications done by Architects division | n/a |  | N/A |  | The service provider that was appointed by the tender process has made very little progress on site as he has indicated that he is experiencing cash flow problems. The Architects Division who are Project Managers has issued the service provider with 3 letters instructing him to show due diligence. Due to slow progress contractor working to penalties of R750.00 a day from 25 May 2012 until completion.A roll over has been requested | 765/025/6/01/1028
Intergrated Beach Front hub | 765035 | 4 | 01 | 1017 | 05 | 09 | 01 | 01 | 220 | 001 | Community and social services | Amenities | New-220 | Yes |  | All Wards | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 500000 | 460.53 | -460.53 | 0 |  | 500000 | #VALUE! | #VALUE! | 0% | 9/10 | 5 | BCM | n/a | n/a | n/a |  | N/A |  | Vote number has been given to Director of Engineering Services to utilize for for Engineering related projects in Marina Glen as per Top Management decision. A roll over has been requested. | 765/035/4/01/1017
Isuzu NQR 500 Cage Tipper - M09/153 | 765030 | 6 | 01 | 1029 | 05 | 08 | 01 | 01 | 250 | 001 | Community and social services | Other - BCM Fleet | New-260 | Yes |  |  | Own Funds c/o | #VALUE! | -348765 | #VALUE! |  | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 9/10 | N/A | BCM | N/A | Planning and specifications done by Mechanical Services | n/a |  | Vehicle was handed over to Beaches | Completed: insurance claim | Project completed | 765/030/6/01/1029
Grass Cutting Equipment | 770005 | 4 | 01 | 1018 | 05 | 08 | 01 | 01 | 260 | 001 | Community and social services | Cleansing | New-260 | Yes |  | All Wards | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 1300000 | 146711.14 | 415649.78 | 562360.92 |  | 737639.08 | #VALUE! | #VALUE! | 43.26% | 2011-07-01 | All | BCMM | BIA | n/a | None |  | Specs submitted to SCM |  | Orders for the grass mowing equipment is with SCM and the machines will be delivered in July 2012. Second phase purchasing is to be submitted to SCM for re-advertisement. | 770/005/4/01/1018
Insurance vehicle replacement : M09/198 | 770005 | 5 | 05 | 1235 | 05 | 08 | 01 | 01 | 260 | 001 | Other | Cleansing | New-260 | Yes |  | All Wards | Own Funds | #VALUE! | 1700000 | #VALUE! |  | 1700000 | 0 | 0 | 0 |  | 1700000 | #VALUE! | #VALUE! | 0% | [9 empty] | Tender process in place - Replacement vehicle | 770/005/5/05/1235
Refuse removal Skips | 770015 | 4 | 01 | 1019 | 05 | 10 | 01 | 01 | 100 | 001 | Waste Management | Cleansing | New-100 | Yes |  | All Wards | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 684204 | 0 | 684204 |  | 315796 | #VALUE! | #VALUE! | 68.42% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | Tender awarded by the Bid Adjudication Committee in October 2011 | Completed | Project completed, savings identified. | 770/015/4/01/1019
Drop Off Points - Solid Waste | 770030 | 6 | 01 | 1030 | 05 | 10 | 01 | 01 | 100 | 001 | Waste Management | Cleansing | New-100 |  | Yes |  | Own Funds c/o | #VALUE! | -210479 | #VALUE! |  | 0 | 0 |  | 0 |  | 0 | #VALUE! | #VALUE! | #DIV/0! | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | Funding spent | 2011-05-01 | Completed | 770/030/6/01/1030
Regional Waste Disposal Site | 770030 | 4 | 01 | 1020 | 05 | 10 | 01 | 01 | 100 | 001 | Waste Management | Cleansing | New- 100 | Yes |  |  | Own Funds | #VALUE! | 0 | #VALUE! | #VALUE! | 1000000 | 8644.7 | -8644.7 | 0 |  | 1000000 | #VALUE! | #VALUE! | 0% | 2011-06-30 |  | n/a | n/a | n/a | n/a |  | Project to be implemented by Engineering - Roads Department | June 2012 | Engineering Roads Department confirmed that Tender for Contract 26 has been awarded and all processes of construction will take place. | 770/030/4/01/1020
TOTAL : DIRECTORATE OF COMMUNITY SERVICES | [10 empty] | 9 | [6 empty] | #VALUE! | 7761052 | #VALUE! | #VALUE! | 57634998 | 15762552.78 | 14270411.14 | 30178502.31 | 0 | 27456495.69 | #VALUE! | #VALUE! | 52.36%
TOTAL: CAPITAL PROJECTS - ALL DIRECTORATES | [19 empty] | #REF! | #REF! | 729035035 | 172660158.23 | 106227539.1 | 278887697.33 | 225212.1 | 450147337.67 | #REF! |  | 38.25%
Insurance Asset Replacement | 320005 | 5 | 05 | 1200 | 05 | 02 | 01 | 01 | 320 | 002 | Budget & Treasury | Support Services | renewal-320 | Yes |  | N/A | Own Funds | #VALUE! | 4890900 | #VALUE! |  | 2506349 | 0 | 0 | 0 |  | 2506349 | #VALUE! | #VALUE! | 0% | [9 empty] | This contingent vote( institutional) is in respect of those assets that are replaced due to insurance claims. When ever an insurance loss occurrs and an asset is to be replaced , an equivalent amount of the asset is transferred from this budget to the relevant department in oder to capitalise the asset. | 320/005/5/05/1200
TOTAL: CAPITAL PROJECTS - GRAND TOTAL | [17 empty] | #REF! | #REF! | #REF! | #REF! | 731541384 | 172660158.23 | 106227539.1 | 278887697.33 | 225212.1 | 452653686.67 | #REF! | #REF! | 38.12%
[18 empty] | #VALUE! | #VALUE! | #VALUE! |  |  | 0 |  |  |  |  | #VALUE!
[18 empty] | #VALUE! | #VALUE! | #VALUE! |  |  | 0 |  |  |  |  | #VALUE!
[18 empty] | #VALUE! | #VALUE! | #VALUE! |  |  | 0 |  |  |  |  | #VALUE!
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%
[23 empty] | 0 |  |  |  |  | 0%

## Appendix S
APPENDIX S
DECLARATION OF RETURNS NOT MADE IN DUE TIME UNDER MFMA S71
NB: All S71 reports are submitted timeously to the Executive Mayor within 10 working days of the following month and the report is sent simultaneously to all stakeholders.