## 2014-2017 Projects
ANNEXURE "E"
BUFFALO CITY METROPOLITAN MUNICIPALITY
CAPITAL EXPENDITURE REPORT AS AT 30 NOVEMBER 2014
Directorate | Cost centre name | C5C | USDG Service | Cost Centre No. |  |  |  | A5 | Service | V1 | V1 | V1 | VT | VT | VT | VT | VT | VT | 34a & 34b | New Asset | Renewal | A9 | Asset Sub Class- SA36 | KPA'S | Ward No. | Project Name | Funding Source | 2013/2014 Approved Budget | Adjustment | 2013/2014 Rollover Adjustment Budget | Adjustments | 2013/14 Conditional Grants Rollover Adjustment Budget | Mid-Year Adjustments | 2013/2014 Mid-Year Adjusted Budget | Savings | 2014/2015 Approved Capital Budget | Adjustment | 2014/2015 Rollover Adjustment Budget | July 2014 | Vat | July 2014 (VAT incl) | August 2014 | Vat | August 2014 (VAT incl) | September 2014 | Vat | September 2014 (VAT incl) | October 2014 | Vat | October 2014 (VAT incl) | November 2014 | Vat | November 2014 (VAT incl) | December 2014 | Vat | December 2014 (VAT incl) | January 2015 | Vat | January 2015 (VAT incl) | February 2015 | Vat | February 2015 (VAT incl) | March 2015 | Vat | March 2015 (VAT incl) | April 2015 | Vat | April 2015 (VAT incl) | May 2015 | Vat | May 2015 (VAT incl) | June 2015 | Vat | June 2015 (VAT incl) | Commitments as per Venus | YTD Expenditure | YTD Expenditure (VAT incl) | Commitments (Outstanding invoices for work done not yet paid) | Available Budget | Available Budget ( Budget -Expenditure including VAT) | % Expenditue | % Expenditure (including VAT) | Comments | 2015/2016 Draft Capital Budget | 2016/2017 Draft Capital Budget | 2017/2018 Draft Capital Budget | 2018/2019 Draft Capital Budget | July Expenditure | July Expenditure(VAT inc.) | August Expenditure | August Expenditure ( VAT inc.) | September Expenditure | Vat | September Expenditure (VAT inc.) | 1st Quarter Expenditure (Exc. VAT) | 1st Quarter Expenditure (incl. VAT) | October Expenditure | Vat | October Expenditure (VAT inc.) | November Expenditure | Vat | November Expenditure (VAT inc.) | December Expenditure | Vat | December Expenditure (VAT inc.) | January Expenditure | January Expenditure (VAT inc.) | February Expenditure | February Expenditure (VAT inc.) | March Expenditure | March Expenditure (VAT inc.) | April Expenditure | April Expenditure (VAT inc.) | May Expenditure | May Expenditure ( VAT inc.) | June Expenditure | June Expenditure ( VAT inc.) | Commitments as per Venus | YTD Expenditure | YTD Expenditure ( VAT inc.) | Commitments (Outstanding invoices for work done not yet paid) | Available Budget | Available Budget ( Budget -Expenditure including VAT) | % Expenditue | % Expenditue including VAT) | 2017/2018 Draft Capital Budget | 2018/2019 Draft Capital Budget | 2017/2018 Draft Capital Budget | Comments
EXECUTIVE SUPPORT SERVICES | [25 empty] | DIRECTORATE OF EXECUTIVE SUPPORT SERVICES
Executive Support Services | Office of the Director of Executive Support Services | 1.1 - Office of The Director of Executive Support |  | 105005 | 4 | 01 | 1501 | Executive and council | Support Services | 4 | 01 |  | 05 | 01 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA5 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 278508.77 |  | 278508.77 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 10235.22 | 278508.77 | 278508.77 |  | 221491.23 | 221491.23 | 55.7% | 55.7% | Loudhailers were delivered and distributed to the Ward Councillors. Service Provider was paid in October 2014 the monies will be spent by year end. | 500000 | 500000
Executive Support Services | Office of the Director of Executive Support Services | 4.4 - Asset Risk & Financial Services |  | 105005 | 5 | 05 | 1518 | Budget and treasury | Support Services |  |  |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of Laptop - LT Sikhinzi - A13/116 | Own Funds | [10 empty] | 13000 | [8 empty] | 0 |  |  | 0 |  |  | 0 | [21 empty] | 10826 | 0 | 0 |  | 13000 | 13000 | 0% | 0% | Order generated, awaiting for service provider to receive stock.
Executive Support Services | Office of the Director of Executive Support | 4.4 - Asset Risk & Financial Services |  | 105005 | 5 | 05 | 1527 | Budget and treasury | Support Services | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of Laptop J.A. Benneck - A14/30 | Own Funds | [10 empty] | 13000 | [11 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 13000 | 13000 | 0% | 0% | Order generated, awaiting for service provider to receive stock.
Executive Support Services | Office of the Director of Executive Support Services | 1.1 - Office of The Director of Executive Support |  | 105005 | 6 | 01 | 1501 | Executive and council | Support Services |  |  |  | 05 | 01 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other assets |  |  | All Wards | Office Furniture and Equipment (Councillors) | Own Funds c/o | [9 empty] | 1284326 | 1284326 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1284326 | 1284326 | 0% | 0% | Tender process to be initiated.
Executive Support Services | Office of the Director of Executive Support Services | 1.1 - Office of The Director of Executive Support |  | 105005 | 6 | 01 | 1502 | Executive and council | Support Services |  |  |  | 05 | 01 | 01 | 01 | 271 | 002 | New-270 | Yes |  | Other assets |  |  | All Wards | Back up Generator | Own Funds c/o | [9 empty] | 1489573 | 1489573 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 1489573 | 1489573 | 0% | 0% | Consultation has been done with Heritage informing them of the intention of installing the generator. Pins for the stand of the generator will be installed during the month of December the project is underway
Executive Support Services | Office of the Director of Executive Support Services | 1.1 - Office of The Director of Executive Support |  | 105005 | 6 | 01 | 1503 | Executive and council | Support Services |  |  |  | 05 | 01 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other assets |  |  | All Wards | Councillors Office Accomodation | Own Funds c/o | [9 empty] | 2996498 | 2996498 | [5 empty] | 0 |  |  | 0 | 1325.34 |  | 1325.34 |  |  | 0 | [22 empty] | 1325.34 | 1325.34 |  | 2995172.66 | 2995172.66 | 0.04423% | 0.04423% | Tender process to be initiated for the park homes.
Executive Support Services | Counsillors | 4.4 - Asset Risk & Financial Services |  | 105012 | 5 | 05 | 1504 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Asset Replacements - Insurance | Own Funds |  |  |  |  | 0 |  | 0 |  |  | 14000 | 14000 |  |  | 0 |  |  | 0 |  |  | 0 | 7619 |  | 7619 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 7619 | 7619 |  | 6381 | 6381 | 54.42% | 54.42% | Laptop replaced.
Executive Support Services | Development Co-Oeration | 1.11 - Development Co-Operation |  | 120005 | 6 | 83 | 1501 | Executive and council | Housing |  |  |  | 05 | 01 | 01 | 01 | 312 | 002 | New-312 | Yes |  | Other assets |  |  |  | Garcia Flats | Leiden c/o | [9 empty] | 458860 | 458860 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 458860 | 458860 | 0% | 0% | Still under procurement process.
Executive Support Services | Public Relations & International Events | 4.4 - Asset Risk & Financial Services |  | 120010 | 5 | 05 | 1528 | Budget and treasury | Support Services | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of 2 x Cameras - A14/29 | Own Funds | [10 empty] | 22500 | [11 empty] | 0 |  |  | 0 | [21 empty] | 19575.96 | 0 | 0 |  | 22500 | 22500 | 0% | 0% | Procurement process underway
Executive Support Services | Research Policy & Knowledge Management Unit | 4.4 - Asset Risk & Financial Services |  | 130005 | 5 | 05 | 1514 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 55000 | 55000 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 55000 | 55000 | 0% | 0% | Procurement Process Underway
[26 empty] | TOTAL: EXECUTIVE SUPPORT SERVICES |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 500000 | 6298257 | 6846757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287453.11 | 0 | 287453.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40637.18 | 287453.11 | 287453.11 | 0 | 6559303.89 | 6559303.89 | 4.198% | 4.198% |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0
[32 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
MUNICIPAL MANAGER'S OFFICE | [25 empty] | MUNICIPAL MANAGERS 'OFFICE | [5 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Municipal Manager's Office | Municipal Manager's Office | 2.1 - Office of The Municipal Manager & Support Services |  | 205005 | 4 | 67 | 1501 | Executive and council | Support Services | 4 | 67 |  | 05 | 02 | 01 | 01 | 320 | 001 | New-320 | Yes |  | Other | Other | KPA2 | All Wards | Neighbourhood Development Partnership | NDPG | 10000000 |  | 10000000 |  | 10000000 | -10000000 | 0 |  | 5000000 |  | 5000000 | 0 | 0 | 0 |  |  | 0 | 107792 | 0 | 107792 | 2583366.68 | 376762.21 | 2960128.89 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1267878.34 | 2691158.68 | 3067920.89 |  | 2308841.32 | 1932079.11 | 53.82% | 61.36% | 800m x 5.5 Road Refurbishment has been completed at Sandile Road, Mdantsane. Project near completion | 16878000 | 17744000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 10000000 | 10000000 | 0% | 0%
Municipal Manager's Office | Municipal Manager's Office | 2.1 - Office of The Municipal Manager & Support Services |  | 205005 | 4 | 01 | 1502 | Executive and council | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Furniture | KPA5 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds | 250000 |  | 250000 |  | 250000 |  | 250000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 9824.6 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Procurement process underway | 500000 | 500000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 171173.4 | 0 | 0 |  | 250000 | 250000 | 0% | 0%
Municipal Manager's Office | Municipal Manager's Office | 2.1 - Office of The Municipal Manager & Support Services | Support Services | 205005 | 4 | 36 | 1501 | Executive and council | Support Services | 4 | 36 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other |  | KPA2 | All Wards | Furniture and Equipment - Project Management Office | USDG |  |  | 0 | 2500000 | 2500000 |  | 2500000 |  | 1500000 |  | 1500000 | 0 | 0 | 0 | 170805 | 23912.7 | 194717.7 |  |  | 0 | 129259.3 |  | 129259.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 300064.3 | 323977 |  | 1199935.7 | 1176023 | 20% | 21.6% | Awaiting delivery of vehicles and delivery of Laptops for new EPMO staff. | 1500000 | 1500000 | [19 empty] | 0 | [14 empty] | 0 |  | 2500000 | 2500000 | 0% | 0%
Municipal Manager's Office | Internal Audit | 4.4 - Asset Risk & Financial Services |  | 215005 | 5 | 05 | 1515 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 8500 | 8500 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [21 empty] | 5916.19 | 0 | 0 |  | 8500 | 8500 | 0% | 0% | CPU has been purchased, awaiting SCM to process the payment.
[26 empty] | TOTAL: MUNICIPAL MANAGERS 'OFFICE |  | 10250000 | 0 | 10250000 | 2500000 | 12750000 | -10000000 | 2750000 | 0 | 7000000 | 8500 | 7008500 | 0 | 0 | 0 | 170805 | 23912.7 | 194717.7 | 107792 | 0 | 107792 | 2712625.98 | 376762.21 | 3089388.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1283619.13 | 2991222.98 | 3391897.89 | 0 | 4017277.02 | 3616602.11 | 42.68% | 48.4% |  | 18878000 | 19744000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171173.4 | 0 | 0 | 0 | 12750000 | 12750000 | 0% | 0% |  |  | 0
[32 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
HUMAN SETTLEMENTS | [25 empty] | DIRECTORATE OF HUMAN SETTLEMENTS | [5 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Human Settlements |  | 3.2 - Office of The Chief Operations Officer |  | 250005 | 4 | 01 | 1503 | Housing | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other | Housing | KPA2 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 | 0 | 0 | 0 | 14706.1 |  | 14706.1 |  |  | 0 | 45043.26 |  | 45043.26 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 52121.81 | 59749.36 | 59749.36 |  | 440250.64 | 440250.64 | 11.95% | 11.95% | Some office furniture has been received. Service provider has promised that more furniture will be delivered by the end of January 2015. | 500000 | 500000
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 01 | 1504 | Housing | Housing | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other | Housing | KPA2 |  | Beneficiary Administration (Procure GPS Devices) | Own Funds | 200000 |  | 200000 |  | 200000 | 200000 | 400000 |  | 100000 |  | 100000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 100000 | 100000 | 0% | 0% | Project is at procurement stage for the procurement of the devices. | 150000 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 01 | 1504 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other | Housing | KPA3 |  | Beneficiary Administration (Procure GPS Devices) | Own Funds c/o | [9 empty] | 102199 | 102199 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 102199 | 102199 | 0% | 0% | Project at procurement stage for the procurement of the devices.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 01 | 1505 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other | Housing | KPA4 |  | Refurbishment of all Rental Stock | Own Funds c/o | [9 empty] | 200000 | 200000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 200000 | 200000 | 0% | 0% | The project is in process. Service provider has been appointed with the help of building maintenance.
Human Settlements | DVRI | 3.1 - Mdantsane Urban Renewal Unit |  | 250005 | 4 | 35 | 1501 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | Reeston MPCC - DVRI | HSDG-(MPCC) | 2100000 |  | 2100000 |  | 2100000 |  | 2100000 |  | 10068500 | -10068500 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 13068500 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 33675 |  | 33675 | 53800 |  | 53800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 87475 | 87475 |  | 2012525 | 2012525 | 4.165% | 4.165%
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1502 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3: Stage 2 | HSDG | 11684600 |  | 11684600 |  | 11684600 |  | 11684600 |  | 7000000 |  | 7000000 | 0 | 0 | 0 |  |  | 0 | 1519732.96 |  | 1519732.96 | 3175774.64 |  | 3175774.64 | -4555.42 |  | -4555.42 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 4690952.18 | 4690952.18 |  | 2309047.82 | 2309047.82 | 67.01% | 67.01% | First phase of 951 engineering services have been complete and handed over to BCMM, the remainder of 1549 will be constructed by the implementing agent. | 15000000 | 20000000 | 10000000 | 10000000 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8771929.82 | 0 | 0 |  | 11684600 | 11684600 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1502 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA3 | 13 | Reeston Phase 3: Stage 2 - P1 & P3 | HSDG c/o | [9 empty] | 5104919 | 5104919 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 5035371.4 |  | 5035371.4 | [22 empty] | 5035371.4 | 5035371.4 |  | 69547.6 | 69547.6 | 98.64% | 98.64% | First phase of 951 engineering services have been complete and handed over to BCMM, the remainder of 1549 will be constructed by the implementing agent.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1503 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 3 | HSDG | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 7000000 |  | 7000000 | 2245000.06 | 0 | 2245000.06 | 3355847.36 |  | 3355847.36 | 492390.71 |  | 492390.71 | 173475.74 |  | 173475.74 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 6266713.87 | 6266713.87 |  | 733286.13 | 733286.13 | 89.52% | 89.52% | The contractor is on site progressing very well with the works. | 15000000 | 12000000 | 10000000 | 7590000 |  | 0 | 48240 | 48240 |  |  | 0 | 48240 | 48240 |  |  | 0 |  |  | 0 | 18152.9 |  | 18152.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 66392.9 | 66392.9 |  | 9933607.1 | 9933607.1 | 0.6639% | 0.6639% |  |  |  |  | 44000000
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1503 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 3 - P1 & P3 | HSDG c/o | [9 empty] | 6922271 | 6922271 |  |  | 0 |  |  | 0 | 21421.49 |  | 21421.49 | 6168337.19 |  | 6168337.19 | 542889.77 |  | 542889.77 | [22 empty] | 6732648.45 | 6732648.45 |  | 189622.55 | 189622.55 | 97.26% | 97.26% | The contractor is on site progressing very well with the works.
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1502 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 2 | USDG | 6815400 |  | 6815400 |  | 6815400 | 5000000 | 11815400 |  | 2970400 | 1306712 | 4277112 | 0 | 0 | 0 |  |  | 0 | 183604.45 | 25704.63 | 209309.08 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 183604.45 | 209309.08 |  | 4093507.55 | 4067802.92 | 4.293% | 4.894% | First phase of 951 engineering services have been complete and handed over to BCMM, the remainder of 1549 will be constructed by the implementing agent. | 5000000 | 10000000 |  |  |  | 0 | 4119.6 | 4119.6 | -4119.6 | 0 | -4119.6 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3614075.5 | 0 | 0 |  | 6815400 | 6815400 | 0% | 0% | 55265000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1551 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 3 | USDG |  |  |  |  | 0 |  | 0 |  | 2000000 |  | 2000000 | 2000000 | 280000 | 2280000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 2000000 | 2280000 |  | 0 | -280000 | 100% | 114% | The contractor is on site progressing very well with the works. | 5000000 | 10000000 | [44 empty] | 17000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1503 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam Ikhwezi Block 1 | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 56248 | 7874.72 | 64122.72 | 148135 | 20738.9 | 168873.9 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 204383 | 232996.62 |  | 295617 | 267003.38 | 40.88% | 46.6% | Preliminary designs submitted to service branches, awaiting comments. | 5900000 | 13000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 175438.6 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1504 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam Ikhwezi Block 2 | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 71570 | 10019.8 | 81589.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 71570 | 81589.8 |  | 428430 | 418410.2 | 14.31% | 16.32% | Consultant busy with geotechnical investigation | 200000 | 200000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1505 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam North Kanana | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Consultants are busy with preliminary designs | 200000 | 200000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1506 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 36 | Dimbaza Destitute 27 Units | USDG | 2500000 |  | 2500000 | -2300000 | 200000 |  | 200000 |  | 200000 |  | 200000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0% | The land to be developed is under dispute by Amahleke traditional council and this matter is being addressed by MEC office for local government | 0 |  |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 169290 | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1507 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 45 | Ilitha North 177 Units | USDG | 700000 |  | 700000 |  | 700000 |  | 700000 |  | 1500000 |  | 1500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1500000 | 1500000 | 0% | 0% | Designs are completed and submitted to service departments for comments | 4000000 | 6800000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 700000 | 700000 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1508 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | DVRI Pilot Project (Mekeni, Haven Hills, Competition Site) | USDG | 2500000 |  | 2500000 | 1000000 | 3500000 |  | 3500000 |  | 775000 |  | 775000 | 0 | 0 | 0 | 23366.2 | 3271.27 | 26637.47 | 45833.96 | 6416.75 | 52250.71 | 425949.5 | 59632.93 | 485582.43 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 495149.66 | 564470.61 |  | 279850.34 | 210529.39 | 63.89% | 72.83% | The contractor is on site, progressing with the works. | 0 |  |  |  |  | 0 |  | 0 | 81590 | 11422.6 | 93012.6 | 81590 | 93012.6 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 81590 | 93012.6 |  | 3418410 | 3406987.4 | 2.331% | 2.658%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1506 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | DVRI Pilot Project (Mekeni, Haven Hills, Competition Site) P1 & P3 | HSDG c/o | [9 empty] | 5687069 | 5687069 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 4874483.92 |  | 4874483.92 | [22 empty] | 4874483.92 | 4874483.92 |  | 812585.08 | 812585.08 | 85.71% | 85.71% | The contractor is on site, progressing with the works.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1505 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 15 | Duncan Village Proper | HSDG | 350000 |  | 350000 |  | 350000 |  | 350000 |  | 700000 |  | 700000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 700000 | 700000 | 0% | 0% | The project is at design stage. | 1300000 | 3300000 | 10000000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 350000 | 350000 | 0% | 0%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1501 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 15 | Duncan Village Proper | HSDG c/o | [9 empty] | 350000 | 350000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 350000 | 350000 | 0% | 0% | The project is at design stage.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1506 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | C Section and Triangular Site | HSDG | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 700000 |  | 700000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 700000 | 700000 | 0% | 0% | The project is at design stage. | 1300000 | 2000000 | 10000000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 3707.64 |  | 3707.64 | -3707.64 |  | -3707.64 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1504 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | C Section and Triangular Site P1-P3 | HSDG c/o | [9 empty] | 770420 | 770420 |  |  | 0 |  |  | 0 |  |  | 0 | 21703 |  | 21703 | 93121.16 |  | 93121.16 | [22 empty] | 114824.16 | 114824.16 |  | 655595.84 | 655595.84 | 14.9% | 14.9% | The project is at design stage.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1507 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | D Hostel | HSDG | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 700000 |  | 700000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 700000 | 700000 | 0% | 0% | The project is at design stage. | 1300000 | 2000000 | 10000000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1505 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | D Hostel P1 & P3 | HSDG c/o | [9 empty] | 600000 | 600000 |  |  | 0 |  |  | 0 |  |  | 0 | 45990.01 |  | 45990.01 |  |  | 0 | [22 empty] | 45990.01 | 45990.01 |  | 554009.99 | 554009.99 | 7.665% | 7.665% | The project is at design stage.
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1509 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 23 | Mdantsane Zone 18 CC Phase 2 | USDG | 3000000 |  | 3000000 |  | 3000000 | -1000000 | 2000000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | Contractor appointed, will commence with site establishment in January 2015 | 8500000 | 18500000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 382.04 | 382.04 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 382.04 |  | 3000000 | 2999617.96 | 0% | 0.01273% | 16500000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1510 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1 | Block Yard TRA | USDG | 500000 |  | 500000 | 1831500 | 2331500 |  | 2331500 |  | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | The contractor is temporally out of site due to financial issue of the project engineer and the municipality. | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 295.58 | 295.58 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 175180.32 | 0 | 295.58 |  | 2331500 | 2331204.42 | 0% | 0.01268%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1508 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 1 | Block Yard TRA | HSDG c/o | [9 empty] | 608785 | 608785 |  |  | 0 |  |  | 0 |  |  | 0 | 307405.79 |  | 307405.79 |  |  | 0 | [21 empty] | 226959.32 | 307405.79 | 307405.79 |  | 301379.21 | 301379.21 | 50.49% | 50.49% | The contractor is temporally out of site due to financial issue of the project engineer and the municipality.
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1511 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 19 | Second Creek (Turn Key) | USDG | 8000000 |  | 8000000 | 1800000 | 9800000 |  | 9800000 |  | 100000 |  | 100000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 100000 | 100000 | 0% | 0% | The project is complete, awaiting for the final claim from the contractor prior the final inspection | 0 | 0 |  |  |  | 0 | 149203.55 | 170092.05 | 761056.68 | 106547.93 | 867604.61 | 910260.23 | 1037696.66 |  |  | 0 | 340800.89 | 47712.12 | 388513.01 | 751461.26 |  | 751461.26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2002522.38 | 2177670.93 |  | 7797477.62 | 7622329.07 | 20.43% | 22.22%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1512 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 9 | Amalinda Co- Op | USDG | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 2200000 | -180000 | 2020000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 99250 | 99520 | 198770 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 248728.6 | 99250 | 198770 |  | 1920750 | 1821230 | 4.913% | 9.84% | The project is on design stage. | 4800000 | 100000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0% | 6000000
Human Settlements |  | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1513 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 |  | Amalinda Fairlands | USDG | 0 |  | 0 |  | 0 |  | 0 |  | 300000 |  | 300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 300000 | 300000 | 0% | 0% | Project is still on planning stage. | 300000 | 500000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1514 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 48,12,21,11,17,11,20 | Cluster 1 (Masibambane; Masibulele; Velwano; Ilinge and Dacawa) | USDG | 3500000 |  | 3500000 |  | 3500000 |  | 3500000 |  | 15000000 | -1306712 | 13693288 | 92322.33 | 12925.13 | 105247.46 | 2636185.49 | 335267.91 | 2971453.4 | 4404470.01 | 555616.39 | 4960086.4 | 4033709.64 | 512671.78 | 4546381.42 | 547961.1 | 76714.55 | 624675.65 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 11714648.57 | 13207844.33 |  | 1978639.43 | 485443.67 | 85.55% | 96.45% | Contractor is on site, progressing with installation of internal services and construction of top structures. | 19000000 | 76000000 |  |  |  | 0 | 4737.54 | 4737.54 | -4737.54 | 0 | -4737.54 | 0 | 0 |  |  | 0 |  |  | 0 | 9997.5 | 1399.65 | 11397.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 9997.5 | 11397.15 |  | 3490002.5 | 3488602.85 | 0.2856% | 0.3256% | 73047792 |  |  |  | 113500000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1515 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 17,14, | Cluster 2 (Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe) | USDG | 3500000 |  | 3500000 |  | 3500000 | -2500000 | 1000000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | Contractor is on site, completed site establishment, to commence with installation of internal services. | 10000000 | 36464685 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | -3707.64 |  | -3707.64 | 3707.64 |  | 3707.64 | 2574.75 | 360.46 | 2935.21 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2574.75 | 2935.21 |  | 3497425.25 | 3497064.79 | 0.07356% | 0.08386% | 46000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1516 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 10 | Cluster 3 (Fynbos Informal 1, Fynbos Informal 2, Ndancama) P1 & P3 | USDG | 5524440 |  | 5524440 | -1300000 | 4224440 | -2000000 | 2224440 |  | 7775000 |  | 7775000 | 0 | 0 | 0 |  |  | 0 | 825710.32 | 115599.44 | 941309.76 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 825710.32 | 941309.76 |  | 6949289.68 | 6833690.24 | 10.62% | 12.11% | The contractor has commenced with the works of construction for both internal services and top structure. | 25350000 | 20100000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 417514 | 58451.96 | 475965.96 | 168266.6 | 23557.32 | 191823.92 | 13864.37 | 1941.01 | 15805.38 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 599644.97 | 683595.26 |  | 3624795.03 | 3540844.74 | 14.19% | 16.18% | 68000000
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1508 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 9 | Braelyn ext 10 | HSDG | 500000 |  | 500000 |  | 500000 | -500000 | 0 |  | 2000000 | 0 | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Project s on design stage. | 10000000 | 20000000 | 8000000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1509 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 9 | Braelyn ext 10 - P1 & P3 | HSDG c/o | [9 empty] | 118812 | 118812 |  |  | 0 |  |  | 0 |  |  | 0 | 89302.5 |  | 89302.5 |  |  | 0 | [22 empty] | 89302.5 | 89302.5 |  | 29509.5 | 29509.5 | 75.16% | 75.16% | Project s on design stage.
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1517 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 31 | Sunny South | USDG | 10000000 |  | 10000000 | 4000000 | 14000000 |  | 14000000 |  | 2000000 | 180000 | 2180000 | 82100.88 | 11494.12 | 93595 | 126676.4 | 17734.7 | 144411.1 | 1347611.08 | 11494.12 | 1359105.2 | 135369.1 | 11494.12 | 146863.22 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1691757.46 | 1743974.52 |  | 488242.54 | 436025.48 | 77.6% | 80% | Contractor on site, there are delays on the project, project will be completed in March 2015. | 100000 | 0 |  |  |  | 0 |  | 0 | 312750 |  | 312750 | 312750 | 312750 | 34750 | 43785 | 78535 | 793348.34 | 107369.96 | 900718.3 | 439562.11 | 61538.7 | 501100.81 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1580410.45 | 1793104.11 |  | 12419589.55 | 12206895.89 | 11.29% | 12.81%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1518 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 43 | Tyutyu Phase 3 | USDG | 200000 |  | 200000 | 0 | 200000 |  | 200000 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 100000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1519 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 46 | Westbank Restitution | USDG | 2000000 |  | 2000000 | 0 | 2000000 |  | 2000000 |  | 3547208 |  | 3547208 | 0 | 0 | 0 | 1372549.25 | 192156.89 | 1564706.14 | 409895.51 | 57385.38 | 467280.89 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1782444.76 | 2031987.03 |  | 1764763.24 | 1515220.97 | 50.25% | 57.28% | The project is still on bulk implementation stage. | 16000000 | 15000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | 140000000 |  | R70mill from 15/16
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1507 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | Housing Needs Database and Accreditation (Capacity Enhancement) | HSDG c/o | [9 empty] | 273172 | 273172 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 273172 | 273172 | 0% | 0% | Budget reserved for procurement of office requirements for additional person to be acquired through the Capacity Enhancement Grant, much dependant on availability of additional office space.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1509 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | Housing Needs Database and Accreditation (Capacity Enhancement) | HSDG | 390000 |  | 390000 |  | 390000 |  | 390000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Budget reserved for procurement of office requirements for additional person to be acquired through the Capacity Enhancement Grant, much dependant on availability of additional office space. | 1000000 |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 60641.08 |  | 60641.08 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 60641.08 | 60641.08 |  | 329358.92 | 329358.92 | 15.55% | 15.55%
Human Settlements | Housing Department | 4.4 - Asset Risk & Financial Services |  | 255005 | 5 | 05 | 1525 | Housing | Housing | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of CPU & Monitor - A14/32 | Own Funds | [10 empty] | 12000 | [11 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 12000 | 12000 | 0% | 0% | Project at procurement stage.
Human Settlements | Mdantsane Urban Renuwal Unit | 4.4 - Asset Risk & Financial Services |  | 255010 | 5 | 05 | 1524 | Budget and treasury | Support Services | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Laptop F. Melane - A14/25 | Own Funds | [10 empty] | 13000 | [11 empty] | 0 | 10826 |  | 10826 | [22 empty] | 10826 | 10826 |  | 2174 | 2174 | 83.28% | 83.28% | IT Department is still installing software in the laptop
[26 empty] | TOTAL : HUMAN SETTLEMENTS |  | 75564440 | 0 | 75564440 | 5931500 | 81495940 | -800000 | 80695940 | 0 | 90136108 | 10669147 | 100830255 | 4419423.27 | 304419.25 | 4723842.52 | 7529330.8 | 548430.77 | 8077761.57 | 9250670.49 | 772216.71 | 10022887.2 | 14777558.37 | 691193.55 | 15468751.92 | 11319802.93 | 107473.25 | 11427276.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 527809.73 | 47296785.86 | 49720519.39 | 0 | 53533469.14 | 51109735.61 | 46.91% | 49.31% |  | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 206300.69 | 227189.19 | 1146539.54 | 117970.53 | 1264510.07 | 1352840.23 | 1491699.26 | 452264 | 102236.96 | 554500.96 | 1396731.91 | 179317.02 | 1576048.93 | 1289412.89 | 65239.82 | 1354652.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12905914.24 | 4491249.03 | 4976901.86 | 0 | 77004690.97 | 76519038.14 | 5.511% | 6.107% |  |  | 0
[32 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF FINANCIAL SERVICES | [25 empty] | DIRECTORATE OF FINANCIAL SERVICES | [5 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Financial Services |  | 4.1 - Office of The Director of Finance |  | 305005 | 4 | 01 | 1505 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 | 19074.32 | 0 | 19074.32 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 117610.12 | 19074.32 | 19074.32 |  | 480925.68 | 480925.68 | 3.815% | 3.815% | Procurement process underway. | 500000 | 500000
Financial Services |  | 4.1 - Office of The Director of Finance |  | 305005 | 6 | 01 | 1506 | Budget and treasury | Support Services |  |  |  | 05 | 03 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Office Furniture and Equipment | Own Funds c/o | [9 empty] | 431902 | 431902 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 431902 | 431902 | 0% | 0% | Procurement process underway.
Financial Services |  | 4.9 - Consolidated Billing & Miscellaneous Revenue Office |  | 330010 | 4 | 01 | 1507 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Partitioning of Offices for SCM | Own Funds |  |  |  |  | 0 |  | 0 |  | 350000 |  | 350000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 166000 | 0 | 0 |  | 350000 | 350000 | 0% | 0% | Service provider is on site and work to be completed by 18th December 2014, first payments of R200 000 to be made by month end. | 0 | 0
Financial Services | Consolidated Billing and Miscellaneous Revenue Office | 4.4 - Asset Risk & Financial Services |  | 330010 | 5 | 05 | 1519 | Budget and treasury | Support Services |  |  |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Laptop S. Peter - A14/15 | Own Funds | [10 empty] | 18500 | [8 empty] | 0 |  |  | 0 | 14773.5 |  | 14773.5 | [22 empty] | 14773.5 | 14773.5 |  | 3726.5 | 3726.5 | 79.86% | 79.86% | Procurement process underway
Financial Services | Consolidated Billing and Miscellaneous Revenue Office | 4.4 - Asset Risk & Financial Services |  | 330010 | 5 | 05 | 1521 | Budget and treasury | Support Services | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Laptop P. Dawethi - A14/14 | Own Funds | [10 empty] | 12500 | [11 empty] | 0 | 10140 |  | 10140 | [22 empty] | 10140 | 10140 |  | 2360 | 2360 | 81.12% | 81.12% | Procurement process underway
Financial Services | Debtors Management Office | 4.4 - Asset Risk & Financial Services |  | 330015 | 5 | 05 | 1517 | Budget and treasury | Support Services | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Laptop - Z. Mjali - A14/12 | Own Funds | [10 empty] | 13000 | 0 |  | 0 |  |  | 0 |  |  | 0 | 10251 |  | 10251 |  |  | 0 | [22 empty] | 10251 | 10251 |  | 2749 | 2749 | 78.85% | 78.85% | The laptop has been replaced.
Financial Services |  | 4.11 - Customer Care Office |  | 330020 | 4 | 01 | 1508 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 260 | 001 | New-260 | Yes |  |  |  | KPA4 | All Wards | CCTV Cameras for BCMM Cash Offices | Own Funds |  |  |  |  | 0 |  | 0 |  | 1500000 |  | 1500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1500000 | 1500000 | 0% | 0% | Funding is to be reallocated to DHPS | 1500000
[26 empty] | TOTAL : FINANCIAL SERVICES |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 2350000 | 431902 | 2825902 | 19074.32 | 0 | 19074.32 | 0 | 0 | 0 | 0 | 0 | 0 | 10251 | 0 | 10251 | 24913.5 | 0 | 24913.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283610.12 | 54238.82 | 54238.82 | 0 | 2771663.18 | 2771663.18 | 1.919% | 1.919% |  | 2000000 | 500000 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0
[32 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF CORPORATE SERVICES | [25 empty] | DIRECTORATE OF CORPORATE SERVICES | [5 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Corporate services |  | 5.1 - Office of The Director of Corporate Services |  | 405005 | 4 | 01 | 1509 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA1 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Procurement process underway | 500000 | 500000
Corporate services |  | 4.4 - Asset Risk & Financial Services |  | 415010 | 5 | 05 | 1516 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 150000 | 150000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 150000 | 150000 | 0% | 0% | Procurement process underway
Corporate services |  | 5.4 - Auxilliary & Telecommunication Support |  | 415010 | 6 | 01 | 1510 | Corporate Services | Support Services |  |  |  | 05 | 04 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Vehicle | Own Funds c/o | [9 empty] | 150000 | 150000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 150000 | 150000 | 0% | 0% | Procurement process underway
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1510 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Procurement of Pre-Payment Vending Machines | Own Funds | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 | 168270 |  | 168270 |  |  | 0 | 1728 |  | 1728 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1728 | 169998 | 169998 |  | 330002 | 330002 | 34% | 34% | The delivery have delayed and expected by end of April 2014. | 0 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 23472.6 |  | 23472.6 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23472.6 | 23472.6 |  | 476527.4 | 476527.4 | 4.695% | 4.695%
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1511 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Systems Intergration - (Process Implementation) | Own Funds | 5250000 | -250000 | 5000000 |  | 5000000 |  | 5000000 |  | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | The procurement process shall commence for the period of 3 years for the total amount of R25 million in February / March 2014. | 12000000 | 12000000 |  |  |  | 0 |  | 0 | 581900 |  | 581900 | 581900 | 581900 | 1191020 |  | 1191020 | 574780.65 |  | 574780.65 | 553836.65 |  | 553836.65 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1548136.26 | 2901537.3 | 2901537.3 |  | 2098462.7 | 2098462.7 | 58.03% | 58.03%
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1512 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Security Software | Own Funds |  |  |  |  | 0 |  | 0 |  | 2400000 |  | 2400000 | 0 | 0 | 0 |  |  | 0 | 2135.27 |  | 2135.27 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 2135.27 | 2135.27 |  | 2397864.73 | 2397864.73 | 0.08897% | 0.08897% | Procurement process underway | 0 | 0
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1513 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Infrastructure Network Upgrade | Own Funds | 0 |  | 0 |  | 0 |  | 0 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Procurement process underway | 4000000 | 4000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 6 | 01 | 1507 | Corporate Services | Support Services |  |  |  | 05 | 04 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Infrastructure Upgrade | Own Funds c/o | [9 empty] | 7154862 | 7154862 |  |  | 0 |  |  | 0 | 362979.88 |  | 362979.88 |  |  | 0 | 1703875.87 |  | 1703875.87 | [21 empty] | 131720.82 | 2066855.75 | 2066855.75 |  | 5088006.25 | 5088006.25 | 28.89% | 28.89% | Procurement process underway
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 6 | 01 | 1508 | Corporate Services | Support Services |  |  |  | 05 | 04 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Duncan Village ICT Centre - DVRI | Own Funds c/o | [9 empty] | 137926 | 137926 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [21 empty] | 114824.56 | 0 | 0 |  | 137926 | 137926 | 0% | 0% | Procurement process underway
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 6 | 01 | 1509 | Corporate Services | Support Services |  |  |  | 05 | 04 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Systerms - ( Anti Virus) | Own Funds c/o | [9 empty] | 723345 | 723345 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 122807.83 |  | 122807.83 | [22 empty] | 122807.83 | 122807.83 |  | 600537.17 | 600537.17 | 16.98% | 16.98% | Procurement process underway
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1514 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Computer Equipment - BCMM | Own Funds | 1000000 |  | 1000000 |  | 1000000 |  | 1000000 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 | 53630.52 |  | 53630.52 | 353865.69 |  | 353865.69 | 171700.95 |  | 171700.95 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 427979.87 | 579197.16 | 579197.16 |  | 1420802.84 | 1420802.84 | 28.96% | 28.96% | Procurement process underway | 0 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 491628.54 |  | 491628.54 | 295850.02 |  | 295850.02 | 110520 |  | 110520 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 82826.35 | 897998.56 | 897998.56 |  | 102001.44 | 102001.44 | 89.8% | 89.8%
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1515 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Infrastructure Servers | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Procurement process underway | 2000000 | 2000000
Corporate services | Management Information Services | 5.7 - H.R. Administration |  | 420005 | 4 | 28 | 1501 | Corporate Services | Support Services | 4 | 28 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Office Furniture and Equipment and Computers | ISDG | 100000 |  | 100000 |  | 100000 |  | 100000 |  | 100000 |  | 100000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 100000 | 100000 | 0% | 0% | Procure of computers and other equipment underway, the expenditure is expected to show by end of October 2014.. IT is assisting with procurement | 100000 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 19673.6 | 2754.3 | 22427.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 65646.91 | 19673.6 | 22427.9 |  | 80326.4 | 77572.1 | 19.67% | 22.43%
Corporate services | H.R. Administration | 5.7 - H.R. Administration |  | 420005 | 4 | 01 | 1518 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Electronic Attandance Control System | Own Funds | 0 |  | 0 |  | 0 |  | 0 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Procurement process underway | 1500000 | 1000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Corporate services | H.R. Administration | 4.4 - Asset Risk & Financial Services |  | 420005 | 5 | 05 | 1507 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 8500 | 8500 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [21 empty] | 5916.19 | 0 | 0 |  | 8500 | 8500 | 0% | 0% | Procurement process underway
Corporate services | H.R. Administration | 4.4 - Asset Risk & Financial Services |  | 420005 | 5 | 05 | 1520 | Budget and treasury | Support Services |  |  |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Laptop V. Forosi - A13/78 | Own Funds | [10 empty] | 13000 | [8 empty] | 0 |  |  | 0 | 10707 |  | 10707 | [22 empty] | 10707 | 10707 |  | 2293 | 2293 | 82.36% | 82.36% | Procurement process underway
Corporate services | Occupational Risk Mnagement | 5.8 - Occupational Risk Management |  | 420010 | 4 | 01 | 1519 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other assets | Land & Buildings | KPA1 | All Wards | Extensions to Employee Wellness Centre | Own Funds | 0 |  | 0 |  | 0 |  | 0 |  | 2500000 |  | 2500000 | 0 | 0 | 0 |  |  | 0 | 2761.12 |  | 2761.12 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 2761.12 | 2761.12 |  | 2497238.88 | 2497238.88 | 0.1104% | 0.1104% | Procurement process underway | 0 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1516 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Land & Buildings | KPA1 | All Wards | ICT Networks and Communications for Call Centre | Own Funds |  |  |  |  | 0 |  | 0 |  | 800000 |  | 800000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 800000 | 800000 | 0% | 0% | Procurement process underway | 500000 | 200000
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1517 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Land & Buildings | KPA1 | All Wards | IT Hardware for Call Centre | Own Funds |  |  |  |  | 0 |  | 0 |  | 800000 |  | 800000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 800000 | 800000 | 0% | 0% | Procurement process underway | 1500000 | 500000
[26 empty] | TOTAL : CORPORATE SERVICES |  | 6850000 | -250000 | 6600000 | 0 | 6600000 | 0 | 6600000 | 0 | 15100000 | 8324633 | 23437633 | 0 | 0 | 0 | 0 | 0 | 0 | 589776.79 | 0 | 589776.79 | 353865.69 | 0 | 353865.69 | 2010819.65 | 0 | 2010819.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682169.44 | 2954462.13 | 2954462.13 | 0 | 20483170.87 | 20483170.87 | 12.61% | 12.61% |  | 22100000 | 20200000 | 0 | 0 | 0 | 0 | 0 | 0 | 581900 | 0 | 581900 | 581900 | 581900 | 1682648.54 | 0 | 1682648.54 | 894103.27 | 0 | 894103.27 | 684030.25 | 2754.3 | 686784.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1696609.52 | 3842682.06 | 3845436.36 | 0 | 2757317.94 | 2754563.64 | 58.22% | 58.26% |  |  | 0
[32 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF ENGINEERING SERVICES | [25 empty] | DIRECTORATE OF ENGINEERING SERVICES | [5 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Engineering Services | Office of the Director of Engineering Services | 6.1 - Office of The Director of Engineering Services |  | 505005 | 4 | 01 | 1520 | Other | Support Services | 4 | 01 |  | 05 | 05 |  |  | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA2 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 133843.34 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Procurement process underway | 500000 | 500000
Engineering Services | Scientific Services | 6.9 - Sewerage Admin |  | 510005 | 4 | 01 | 1559 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Water |  | KPA2 | All Wards | Upgrading of Laboratory Infrastructure | Own Funds | [9 empty] | 2000000 | 2000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Procurement process underway
Engineering Services | Scientific Services | 6.9 - Sewerage Admin |  | 510005 | 6 | 01 | 1511 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 002 | Renewal-70 |  | Yes | Water |  | KPA2 | All Wards | Upgrading of Laboratory Infrastructure | Own Funds c/o | [9 empty] | 1574513 | 1574513 |  |  | 0 |  |  | 0 |  |  | 0 | 8580 |  | 8580 |  |  | 0 | [21 empty] | 295591.66 | 8580 | 8580 |  | 1565933 | 1565933 | 0.5449% | 0.5449% | Procurement process underway
Engineering Services | Sewerage Admin | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1520 | Waste Water Management | Waste Water | 4 | 36 |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Bulk Sanitation Provision - Programme | USDG | 37854000 |  | 37854000 | 20000000 | 57854000 |  | 57854000 |  | 176507892 | -175507892 | 1000000 | 76820 | 0 | 76820 | 555847.54 | 74348.55 | 630196.09 | -138617.26 | 0 | -138617.26 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 494050.28 | 568398.83 |  | 505949.72 | 431601.17 | 49.41% | 56.84% | Projects on going. Annual contractor has been appointed and is implementing project-Multi year ongoing project. | 190000000 | 97000000 |  |  |  | 0 | 3961956.8 | 4516630.75 | 7810659.85 | 1250665.11 | 9061324.96 | 11772616.65 | 13577955.71 | 8848276.78 | 1132017.03 | 9980293.81 | 9756441.29 | 1265741.02 | 11022182.31 | 16134838.1 | 1207170.73 | 17342008.83 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 46512172.82 | 51922440.66 | 625034.64 | 11341827.18 | 5931559.34 | 80.4% | 89.75% | 120000000
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1552 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Waste Water Infrastructure Capacity (KWT Reg Scheme) | USDG | [9 empty] | 54507892 | 22857892 |  |  | 0 |  |  | 0 | 543944.88 | 76152.28 | 620097.16 |  |  | 0 |  |  | 0 | [22 empty] | 543944.88 | 620097.16 |  | 22313947.12 | 22237794.84 | 2.38% | 2.713% | Mechanical & Electrical Works contract awarded. Civil Works contract was awarded but another bidder appealed the award to preferred bidder.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1553 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Reeston Phase 3 Bulk Services Sewer | USDG | [9 empty] | 50000000 | 50000000 |  |  | 0 | 2978423.71 | 372528.8 | 3350952.51 | 3869608.52 | 481925.25 | 4351533.77 | 2840418.79 | 364233.26 | 3204652.05 | 3173219.13 | 444250.67 | 3617469.8 | [22 empty] | 12861670.15 | 14524608.13 |  | 37138329.85 | 35475391.87 | 25.72% | 29.05% | Civil works on going, 48% complete. Mechanical & Electrical Works contract awarded but another bidder appealed the award to preferred bidder.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1554 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Mdantsane Infrastructure- Refurbishment/ Augmentation | USDG | [9 empty] | 20000000 | 20000000 |  |  | 0 | 5202755.74 | 663036.59 | 5865792.33 | -2086248.95 | 414183.12 | -1672065.83 | 1281854.55 | 179459.64 | 1461314.19 | 1111763.54 | 155646.89 | 1267410.43 | [22 empty] | 5510124.88 | 6922451.12 |  | 14489875.12 | 13077548.88 | 27.55% | 34.61% | Project progressing well, 70% complete.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1555 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Diversion of Amalinda & Wilsonia Effluent | USDG | [9 empty] | 1000000 | 1017458 |  |  | 0 |  |  | 0 | 439435.42 | 61520.96 | 500956.38 | 55372.69 | 7752.18 | 63124.87 | 510710.62 | 71499.49 | 582210.11 | [22 empty] | 1005518.73 | 1146291.36 |  | 11939.27 | -128833.36 | 98.83% | 112.7% | Phase 1A complete. Design for phase 2 completed-Tunnel option, awaiting for funds to go out to tender.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1556 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Sanitation Backlog Eradication - (Coastal) | USDG | [9 empty] | 40000000 | 40000000 |  |  | 0 | 940264.83 | 153505.26 | 1093770.09 | 3422872.13 | 445761.59 | 3868633.72 | 320973.21 | 31374.86 | 352348.07 | 1367811.75 | 191493.65 | 1559305.4 | [22 empty] | 6051921.92 | 6874057.28 |  | 33948078.08 | 33125942.72 | 15.13% | 17.19% | 23 consortiums had been appointed,work progressing, 95% complete.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1557 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Eastern Beach Sewers | USDG | [9 empty] | 1000000 | 1056888 |  |  | 0 |  |  | 0 | 927094.74 | 129793.26 | 1056888 |  |  | 0 |  |  | 0 | [22 empty] | 927094.74 | 1056888 |  | 129793.26 | 0 | 87.72% | 100% | Procurement process underway
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1558 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Sludge Handling & Chlorination Facilities | USDG | [9 empty] | 1000000 | 1729909 |  |  | 0 | 180844.29 | 25318.2 | 206162.49 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 180844.29 | 206162.49 |  | 1549064.71 | 1523746.51 | 10.45% | 11.92% | PSP appointed 95 % complete.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1559 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Ablution Blocks | USDG | [9 empty] | 3000000 | 3949029 | -276650.91 |  | -276650.91 | 101276.44 | 10634.59 | 111911.03 |  |  | 0 | 278866.52 | 39041.31 | 317907.83 | 359721.22 | 50360.97 | 410082.19 | [21 empty] | 1651666.43 | 463213.27 | 563250.14 |  | 3485815.73 | 3385778.86 | 11.73% | 14.26% | The Ablution Blocks project on going. Annual contractors have been appointed for provision of Ablution Facilities and fencing
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1560 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Berlin Sewers | USDG | [9 empty] | 5000000 | 5029611 |  |  | 0 | 116918.57 | 16368.59 | 133287.16 | 593257.87 | 83056.1 | 676313.97 | 468158.58 | 65542.2 | 533700.78 |  |  | 0 | [21 empty] | 1058214.13 | 1178335.02 | 1343301.91 |  | 3851275.98 | 3686309.09 | 23.43% | 26.71% | Procurement process underway
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1568 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes |  |  |  |  | West Bank Restitution Sewer Infrastructure | USDG | [10 empty] | 10000000 | [8 empty] | 0 |  |  | 0 |  |  | 0 | [21 empty] | 10000000 | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | Annual contractor on site to complete the outstanding works.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1569 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes |  |  |  |  | Quinera WWTW | USDG | [10 empty] | 12440860 | [8 empty] | 0 | 2575489.78 | 360568.57 | 2936058.35 |  |  | 0 | [22 empty] | 2575489.78 | 2936058.35 |  | 9865370.22 | 9504801.65 | 20.7% | 23.6% | Project complete, expenditure to reflect by November 2014
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1570 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes |  |  |  |  | Gqozo Village Phase 2 | USDG | [10 empty] | 10000000 | [8 empty] | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | Procurement process underway
Engineering Services | Sewerage Admin | 6.9 - Sewerage Admin |  | 515010 | 4 | 01 | 1521 | Waste Water Management | Waste Water | 4 | 01 |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Bulk Sanitation Provision - Replacing Existing Infrastructure | Own Funds |  |  |  |  | 0 |  | 0 |  | 40000000 | -2000000 | 38000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 38000000 | 38000000 | 0% | 0% | Procurement process underway | 40000000 | 40000000
Engineering Services | Water Treatment Works | 6.20 - Water Administration | Water | 520005 | 4 | 36 | 1521 | Water | Water | 4 | 36 |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes | Road Transport | Roads | KPA2 | 34,37,38,39,40,41,43,44,49,35,11,12,13,14,42,48,50,17,20,23,1-25 & 28,29,30,31, & 33,27,31,33,36,1,2,7,14,17,20,21,22,23,30,2,8,25,34,44,41 | Bulk Water Provision - Programme | USDG | 0 |  |  |  | 0 |  | 0 |  | 52500000 |  | 49926245 | 0 | 0 | 0 | 1511048.24 | 195288.57 | 1706336.81 | 929320.16 | 125133.92 | 1054454.08 | 2521923.71 | 187200.94 | 2709124.65 | 2471176.03 | 529175 | 3000351.03 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2944256.85 | 7433468.14 | 8470266.57 |  | 42492776.86 | 41455978.43 | 14.89% | 16.97% | PSP for the design of Kei Road Treatment plant is busy with the design report. Relocation of Midblock mains in Dimbaza & Ilitha will commence on the first week of November 2014. PSP for the Design & Implementation of Amahleke Water regional storage is currently busy with the Preliminary report. Tenders for Bulk water supply to coastal areas are at procurement stage and Water supply to Komashini is practically completed. Contractor implementing the upgrading of BRPS manifolds is underway and the upgrading of UWTW is underway. | 51000000 | 51000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [13 empty] | 0 |  |  | 0 |  | 0% |  | 73000000
Engineering Services | Water Treatment Works | 6.20 - Water Administration |  | 520005 | 4 | 01 | 1522 | Water | Water | 4 | 01 |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes | Road Transport | Roads | KPA2 | 34,37,38,39,40,41,43,44,49,35,11,12,13,14,42,48,50,17,20,23,1-25 & 28,29,30,31, & 33,27,31,33,36,1,2,7,14,17,20,21,22,23,30,2,8,25,34,44,41 | Bulk Water Provision Replacing of Existing Infrastructure | Own Funds |  |  |  |  | 0 |  | 0 |  | 40000000 |  | 40000000 | 0 | 0 | 0 | 268846.57 |  | 268846.57 | 1115607.01 |  | 1115607.01 | 240444.21 |  | 240444.21 | 3167217.07 |  | 3167217.07 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 9878447.46 | 4792114.86 | 4792114.86 |  | 35207885.14 | 35207885.14 | 11.98% | 11.98% | Replacement of old water mains & water meters and installation of zonal & new domestic water meters is progressing well. | 40000000 | 40000000
Engineering Services | Water Admin | 6.20 - Water Administration | Water | 520005 | 4 | 36 | 1522 | Water | Water | 4 | 36 |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes | Road Transport | Roads | KPA2 | 34,37,38,39,40,41,43,44,49,35,11,12,13,14,42,48,50,17,20,23,1-25 & 28,29,30,31, & 33,27,31,33,36,1,2,7,14,17,20,21,22,23,30,2,8,25,34,44,41 | West Bank Restitution - Water | USDG | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 5000000 |  | 5000000 | 0 | 0 | 0 | 67797.4 | 9491.64 | 77289.04 |  |  | 0 | 235705.26 | 32998.73 | 268703.99 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 303502.66 | 345993.03 |  | 4696497.34 | 4654006.97 | 6.07% | 6.92% | Project under litigation, institution looking at finalizing the matter before re-advertising . | 0 | 0 |  |  |  | 0 | -1849660.37 | -1849660.37 |  |  | 0 | -1849660.37 | -1849660.37 |  |  | 0 |  |  | 0 | 3541740.65 |  | 3541740.65 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1692080.28 | 1692080.28 |  | 8307919.72 | 8307919.72 | 16.92% | 16.92%
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1523 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Urban Roads - Programme | USDG | 30000000 |  |  |  | 0 |  | 0 |  | 110000000 | -110000000 | 1581556 | -47814.16 | 0 | -47814.16 | 75959.59 |  | 75959.59 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1125142.64 | 28145.43 | 28145.43 |  | 1553410.57 | 1553410.57 | 1.78% | 1.78% | Budget will need to be adjusted to adress short-fall | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1562 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Upgrade Mdantsane Roads | USDG | 30000000 |  |  |  | 0 |  | 0 |  |  | 30000000 | 29000000 |  | 0 | 0 |  |  | 0 |  |  | 0 | 791918.6 | 110868.6 | 902787.2 | 302105.26 | 42294.74 | 344400 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1922547.34 | 1094023.86 | 1247187.2 |  | 27905976.14 | 27752812.8 | 3.772% | 4.301% | Work is progressing well on site | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1563 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Quinera Arterial Road | USDG | 30000000 |  |  |  | 0 |  | 0 |  |  | 30000000 | 31325132 |  | 0 | 0 | 1370589 | 175671.96 | 1546260.96 | 279125.87 | 39077.62 | 318203.49 | 4769537.59 | 612733.41 | 5382271 | 2589616.25 | 362546.28 | 2952162.53 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 9008868.71 | 10198897.98 |  | 22316263.29 | 21126234.02 | 28.76% | 32.56% | Work progressing well. | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1564 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Fleet Street | USDG | 30000000 |  |  |  | 0 |  | 0 |  |  | 20000000 | 20463013 |  | 0 | 0 | 1170655.39 | 163891.76 | 1334547.15 | 318205.64 | 44548.79 | 362754.43 | 322430.4 | 45140.26 | 367570.66 | -1157661.74 | 162072.63 | -995589.11 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3450277.8 | 653629.69 | 1069283.13 |  | 19809383.31 | 19393729.87 | 3.194% | 5.225% | Project delayed, institution to utilize other implementation mechanisms. | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1565 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Gonubie Main Road | USDG | 30000000 |  |  |  | 0 |  | 0 |  |  | 30000000 | 19689137 |  | 0 | 0 | 153007.76 | 21421.09 | 174428.85 | 209352.69 | 29309.38 | 238662.07 | 694059.61 | 97168.35 | 791227.96 | 963730.12 | 134922.22 | 1098652.34 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 2020150.18 | 2302971.22 |  | 17668986.82 | 17386165.78 | 10.26% | 11.7% | Work progressing well, though minor delays due to weather.Additional funding will be required for completion of the project. | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services |  | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1567 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 |  | RDP Houses- Roads Refurbishment | USDG | [10 empty] | 4431601 | [11 empty] | 0 | 1033346.59 | 144668.52 | 1178015.11 | [21 empty] | 3656006.32 | 1033346.59 | 1178015.11 |  | 3398254.41 | 3253585.89 | 23.32% | 26.58% | Orders have been issued. Expenditure expected to be reflect by end November 2014.
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1524 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 11, 12, 14, 17, 20, 20, 21, 22, 23, 30, 42,48 50 | Upgading of Mdantsane Roads | USDG | 0 |  |  |  | 0 |  | 0 |  | 53000000 |  | 56063757 | 0 | 0 | 0 | 5803174.76 | 783490.07 | 6586664.83 | 16914156.71 | 1582124.54 | 18496281.25 | 15681456.24 | 2086278.72 | 17767734.96 | 9592832.52 | 1342996.56 | 10935829.08 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1961765.07 | 47991620.23 | 53786510.12 |  | 8072136.77 | 2277246.88 | 85.6% | 95.94% | Work is progressing well | 60000000 | 60000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [13 empty] | 0 |  |  | 0 |  | 0%
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1525 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 46 | Rehabilitation of BCMM Bridges | USDG | 0 |  |  |  | 0 |  | 0 |  | 8000000 |  | 8000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 161349.81 | 22588.97 | 183938.78 | 1974608.25 | 276445.15 | 2251053.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 4377412.13 | 2135958.06 | 2434992.18 |  | 5864041.94 | 5565007.82 | 26.7% | 30.44% | Project ongoing, Settlers Pedestrian Bridge repaired, expenditure to reflect by end November 2014. | 5000000 | 10000000 | [16 empty] | 0 |  |  | 0 | [16 empty] | 0 |  |  |  | 80000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1526 | Road transport | Other - BCM Fleet | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 24,26,31, 33, 35,36, 37, 38, 39, 40, 41, 49, 44, 43, 45, | Procurement of Graders for Rural Roads | USDG | 25000000 |  | 25000000 | 8000000 | 33000000 | 3500000 | 36500000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | Procurement process underway | 30000000 | 30000000 |  |  |  | 0 | 2916096.53 | 3323571.44 | 5902572.57 | 533811.63 | 6436384.2 | 8818669.1 | 9759955.64 | 4676639.56 | 948056.69 | 5624696.25 | 4623433.85 | 647280.74 | 5270714.59 | 4357834.3 | 610096.82 | 4967931.12 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2038718.1 | 22476576.81 | 25623297.6 |  | 10523423.19 | 7376702.4 | 68.11% | 77.65% | 110000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1527 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 24,26,31, 33, 35,36, 37, 38, 39, 40, 41, 49, 44, 43, 45, | Rehabilitation of Rural Roads | USDG |  |  |  |  | 0 |  | 0 |  | 15000000 |  | 15445804 | 0 | 0 | 0 | 1400662.06 | 196092.69 | 1596754.75 | 1662796.5 | 232791.49 | 1895587.99 | 1857472.2 | 260046.1 | 2117518.3 | 981726.02 | 137441.64 | 1119167.66 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 9492648.48 | 5902656.78 | 6729028.7 |  | 9543147.22 | 8716775.3 | 38.22% | 43.57% | Work progressing well, more invoices submitted for processing | 0 | 0
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1528 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Quinera Arterial Road | USDG | 15000000 |  | 15000000 | -6000000 | 9000000 |  | 9000000 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Project delayed, institution to utilize other implementation mechanisms. | 0 | 0 |  |  |  | 0 |  | 0 | 90883.71 |  | 90883.71 | 90883.71 | 90883.71 |  |  | 0 |  |  | 0 | 7999784.83 |  | 7999784.83 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 8090668.54 | 8090668.54 |  | 909331.46 | 909331.46 | 89.9% | 89.9%
Engineering Services | Roads and Stormwater Drainage | 4.4 - Asset Risk & Financial Services |  | 525025 | 5 | 05 | 1531 | Budget and treasury | Roads | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of 2 x Computers & Furniture - A13/70 | Own Funds | [10 empty] | 45000 | [14 empty] | 0 | [22 empty] | 0 | 0 |  | 45000 | 45000 | 0% | 0%
Engineering Services | Fleet management - Braelyn | 6.43 - Fleet Management - Braelyn |  | 530020 | 4 | 01 | 1523 | Electricity | Other - BCM Fleet | 4 | 01 |  | 05 | 05 | 01 | 01 | 250 | 001 | New-250 | Yes |  | Other assets | Vehicles | KPA2 | All Wards | BCMM Fleet, Plant and Specialised Equipment and Specialised Solid Waste Vehicles | Own Funds | 0 |  | 0 |  | 0 |  | 0 |  | 18300000 |  | 18300000 | 0 | 0 | 0 | 1888532.64 |  | 1888532.64 | 10484165.53 |  | 10484165.53 | 4549898.98 |  | 4549898.98 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 16922597.15 | 16922597.15 |  | 1377402.85 | 1377402.85 | 92.47% | 92.47% | the 8% will be spent using transvesal contract RT57 | 18000000 | 18000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Engineering Services |  | 6.43 - Fleet Management - Braelyn |  | 530020 | 6 | 01 | 1512 | Electricity | Other - BCM Fleet |  |  |  | 05 | 05 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Other assets | Vehicles | KPA2 | All Wards | BCMM Fleet | Own Funds c/o | [9 empty] | 3997668 | 3997668 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 3997668 | 3997668 | 0% | 0% | This vote will be used on contract RT 57
Engineering Services |  | 6.43 - Fleet Management - Braelyn |  | 530020 | 6 | 01 | 1513 | Electricity | Electricity |  |  |  | 05 | 05 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Other assets | Vehicles | KPA2 | All Wards | Electricity Dept. - Specialised Plant and Equipment | Own Funds c/o | [9 empty] | 3000000 | 3000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 3000000 | 3000000 | 0% | 0% | Buy crane mechanism for two trucks and the balance will also be used on contract RT57
Engineering Services | Electricity Administration | 4.4 - Asset Risk & Financial Services |  | 535005 | 5 | 05 | 1509 | Budget and treasury | Electricity | 4 | 01 |  | 05 | 05 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 8500 | 8500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 8500 | 8500 | 0% | 0% | Waiting for information from Operations on Claims
Engineering Services |  | 4.4 - Asset Risk & Financial Services |  | 535010 | 5 | 05 | 1513 | Budget and treasury | Electricity | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 39900 | 39900 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 39900 | 39900 | 0% | 0% | Waiting for information from Operations on Claims
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design |  | 535025 | 4 | 01 | 1524 | Electricity | Electricity | 4 | 01 |  | 05 | 05 | 01 | 01 | 060 | 001 | Renewal-60 |  | Yes | Electricity | Electricity reticulation | KPA2 | 16, 18,29,35 | Bulk Electricity Infrastructure Upgrade(Ring-Fenced 4% of the Total Electricity Revenue) | Own Funds | 5285700 |  | 438631.88 |  | 438631.88 | 29084305 | 29522936.88 |  | 40000000 |  | 40000000 | 0 | 0 | 0 | 153718.89 |  | 153718.89 | 531767.37 |  | 531767.37 | 2301904.56 |  | 2301904.56 | 536394.46 |  | 536394.46 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 5529980.27 | 3523785.28 | 3523785.28 |  | 36476214.72 | 36476214.72 | 8.809% | 8.809% | 50% of Electrical projects prepared and at various installation stages - balance project at design & planning stage - long delivery items; orders submitted to SCM expected delivery first batch 3 Nov 14 - switchboard panels ordered delivery 2015 | 50000000 | 60000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 438631.88 | 438631.88 | 0% | 0%
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design |  | 535025 | 4 | 01 | 1525 | Electricity | Electricity | 4 | 01 |  | 05 | 05 | 01 | 01 | 060 | 001 | Renewal-60 |  | Yes | Electricity | Electricity reticulation | KPA2 | 16, 18,29,35 | Bulk Electricity Infrastructure Upgrade - Replacing Existing Infrastructure | Own Funds |  |  |  |  | 0 |  | 0 |  | 40000000 |  | 40000000 | 0 | 0 | 0 | 551972.49 |  | 551972.49 | 4746762.37 |  | 4746762.37 | 5945207.95 |  | 5945207.95 | 1926827.29 |  | 1926827.29 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 6603202.97 | 13170770.1 | 13170770.1 |  | 26829229.9 | 26829229.9 | 32.93% | 32.93% | 75 % Electrical projects prepared and at various installation stages - 25% identified @ design & planning stage - long delivery items; orders submitted to SCM expected delivery first batch 3 Nov 14 - RMU request submitted to contact delivery week of the 8th Sept 14 | 40000000 | 40000000
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design |  | 535025 | 4 | 56 | 1533 | Electricity | Electricity | 4 | 56 |  | 05 | 05 | 01 | 01 | 060 | 001 | New-60 | Yes |  | Electricity | Electricity reticulation | KPA2 | 1,3,19, | INEP Electrification Programme | DoE(Intergrated National Electrification Programme) | 1329000 |  | 1329000 | -1329000 | 0 |  | 0 |  | 27000000 |  | 27000000 | 34346 | 0 | 34346 | 128806.07 |  | 128806.07 | 2895383.81 | 423386.58 | 3318770.39 | 9399037.37 | 702294.26 | 10101331.63 | 2741800.57 | 997423.06 | 3739223.63 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 15199373.82 | 17322477.72 |  | 11800626.18 | 9677522.28 | 56.29% | 64.16% | DoE has advise on revised allocation, waiting for confirmation - Completion of ED329 & ED373 Queenspark Projects / Installation of Queenspark Cable / Electrification Duncan Village, Second Creek, Infills BCMM area | 27000000 | 12000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design | Electricity | 535025 | 4 | 36 | 1529 | Electricity | Electricity | 4 | 36 |  | 05 | 05 | 01 | 01 | 060 | 001 | New-60 | Yes |  | Electricity | Electricity reticulation | KPA2 | 1,2, 7, 8, 9,10 | INEP Electrification Programme - Counterfunding | USDG | 1600000 |  | 1600000 |  | 1600000 |  | 1600000 |  | 5000000 |  | 5000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 5000000 | 5000000 | 0% | 0% | Procurement process underway | 5000000 | 5000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 1600000 | 1600000 | 0% | 0% | 5000000
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design | Electricity | 535025 | 4 | 36 | 1530 | Electricity | Electricity | 4 | 36 |  | 05 | 05 | 01 | 01 | 060 | 001 | New-60 | Yes |  | Electricity | Electricity reticulation | KPA2 | 2,7,8,9,11,12 | Electrification of Informal Dwelling Areas within BCMM | USDG | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 | 131675.29 | 18434.54 | 150109.83 | 374455.86 | 52423.82 | 426879.68 | 1598235.55 | 209410.26 | 1807645.81 | 582021.35 | 78536.07 | 660557.42 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 2686388.05 | 3045192.74 |  | 7313611.95 | 6954807.26 | 26.86% | 30.45% | Electrification projects Duncan Village / Mdantsane Zone 1 & 3 / Phakamisa to be cancelled | 15000000 | 20000000 |  |  |  | 0 | 799580.21 | 911521.46 |  |  | 0 | 799580.21 | 911521.46 | 4082.92 | 571.61 | 4654.53 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 803663.13 | 916175.99 |  | 9196336.87 | 9083824.01 | 8.037% | 9.162% | 25000000
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design | Electricity | 535025 | 4 | 36 | 1531 | Electricity | Electricity | 4 | 36 |  | 05 | 05 | 01 | 01 | 060 | 001 | New-60 | Yes |  | Electricity | Electricity reticulation | KPA2 | 10,15,29,28,36,46 | Street Lighting and Highmasts within BCMM Areas of Supply - Informal Settlements | USDG | 853700 |  | 853700 |  | 853700 |  | 853700 |  | 3500000 |  | 3500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 194085.28 | 27171.94 | 221257.22 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 194085.28 | 221257.22 |  | 3305914.72 | 3278742.78 | 5.545% | 6.322% | Procurement process underway | 3500000 | 3500000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 853700 | 853700 | 0% | 0% | 3500000
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design | Electricity | 535025 | 4 | 36 | 1532 | Electricity | Electricity | 4 | 36 |  | 05 | 05 | 01 | 01 | 060 | 001 | Renewal-60 |  | Yes | Electricity | Electricity reticulation | KPA2 | 10,15,29,28,36,46 | Replacement and Refurbishment of Bulk ELECT Infrastructure | USDG |  |  |  |  | 0 |  | 0 |  | 9199000 |  | 9199000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 9199000 | 9199000 | 0% | 0% | As per DES - funds to be transferred to Roads Dept - next Adjustment Budget | 2000000 | 8000000
Engineering Services | Water Admin | 6.20 - Water Administration |  | 520005 | 4 | 75 | 1501 | Water | Water | 4 |  |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes | Road Transport | Roads | KPA2 | 34,37,38,39,40,41,43,44,49,35,11,12,13,14,42,48,50,17,20,23,1-25 & 28,29,30,31, & 33,27,31,33,36,1,2,7,14,17,20,21,22,23,30,2,8,25,34,44,41 | Upgrade Water Supply in Rural Areas | LGTH |  |  |  |  | 0 |  | 0 |  | 188726 |  | 188726 | 0 | 0 | 0 |  |  | 0 | 178585.49 |  | 178585.49 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 178585.49 | 178585.49 |  | 10140.51 | 10140.51 | 94.63% | 94.63% | 95% of the budget has been spent
[26 empty] | TOTAL : ENGINEERING SERVICES |  | 256922400 | 0 | 102075331.88 | 20671000 | 122746331.88 | 32584305 | 155330636.88 | 0 | 665695618 | 8620581 | 674361199 | -213299.07 | 0 | -213299.07 | 24752777.27 | 2879522.9 | 27632300.17 | 48211032.36 | 4221188.7 | 52432221.06 | 59094381.44 | 5441872.56 | 64536254 | 34228966.3 | 5121773.54 | 39350739.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64081002.89 | 166073858.3 | 183738216 | 0 | 508287340.7 | 490622983 | 24.63% | 27.25% |  | 1027000000 | 895000000 | 0 | 0 | 0 | 0 | 5827973.17 | 6902063.28 | 13804116.13 | 1784476.74 | 15588592.87 | 19632089.3 | 22490656.15 | 13528999.26 | 2080645.33 | 15609644.59 | 14379875.14 | 1913021.76 | 16292896.9 | 32034197.88 | 1817267.55 | 33851465.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038718.1 | 79575161.58 | 88244663.07 | 625034.64 | 43171170.3 | 34501668.81 | 64.83% | 71.89% |  |  | 0
[32 empty] | 0 |  | 0 | [18 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [32 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF DEVELOPMENT PLANNING | [25 empty] | DIRECTORATE OF DEVELOPMENT PLANNING | [5 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Directorate of Development Planning | Director's Office | 7.1 - Office of The Director of Planning & Economic Dev. |  | 605005 | 4 | 01 | 1526 | Planning and Development | Planning and development | 4 | 01 |  | 05 | 06 | 01 | 01 | 270 | 001 | New-270 | Yes |  |  |  | KPA2 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 5100 |  | 5100 | 2418 |  | 2418 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 98256.89 | 7518 | 7518 |  | 492482 | 492482 | 1.504% | 1.504% | Procurement Processes are underway. | 500000 | 500000
Directorate of Development Planning |  | 7.11 - City Planning |  | 615070 | 6 | 01 | 1514 | Planning and Development | Planning and development |  |  |  | 05 | 06 | 01 | 01 | 312 | 002 | Renewal-312 |  | Yes | Other assets | Other Assets | KPA2 | All Wards | Upgrading of the City Hall | Own Funds c/o | [9 empty] | 5395309 | 5395309 |  |  | 0 |  |  | 0 | 1609065.89 |  | 1609065.89 | 478955.34 |  | 478955.34 | 571594.05 |  | 571594.05 | [21 empty] | 2553658.2 | 2659615.28 | 2659615.28 |  | 2735693.72 | 2735693.72 | 49.29% | 49.29% | Replacement of the City Hall roof project underway (works = 95% complete)
Directorate of Development Planning | Architecture | 7.12 - Architecture | Development & Transport Planning | 615075 | 4 | 36 | 1534 | Planning and Development | Planning and development | 4 | 36 |  | 05 | 06 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other assets | Other Assets | KPA2 | All Wards | Upgrade KWT Payments Hall | USDG | 2800000 |  | 2800000 | -2800000 | 0 |  | 0 |  | 5000000 |  | 5000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 797099.25 | 0 | 0 |  | 5000000 | 5000000 | 0% | 0% | Professional service provider signed acceptance of appointment letter on 4 August 2014. Designs and specifications are now underway. Due to restarting theproject, the majority of the 2014/15 budget will not be spent before the financial year-end - balance of budget to be adjusted into 2015/16 financial year for completion of consultancy services and construction costs. | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0%
Directorate of Development Planning | Architecture | 4.4 - Asset Risk & Financial Services |  | 615075 | 5 | 05 | 1530 | Budget and treasury | Planning and development | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of CPU - A12/118 | Own Funds | [10 empty] | 8500 | [14 empty] | 0 | [22 empty] | 0 | 0 |  | 8500 | 8500 | 0% | 0% | Replacement of CPU will be processed through the ICT Department.
Directorate of Development Planning |  | 7.12 - Architecture |  | 615075 | 6 | 01 | 1515 | Planning and Development | Planning and development |  |  |  | 05 | 06 | 01 | 01 | 312 | 002 | Renewal-312 |  | Yes | Other assets | Other Assets | KPA2 | All Wards | Upgrade KWT Payments Hall | Own Funds c/o | [9 empty] | 477792 | 477792 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 477792 | 477792 | 0% | 0% | Due to restarting the project, this budget will not be spent before the 2014/15 financial year-end. Budget to be adjusted into 2015/16 financial year for construction costs.
Directorate of Development Planning | Land Administration | 7.13 - Land Administration | Development & Transport Planning | 615080 | 4 | 36 | 1535 | Planning and Development | Planning and development | 4 | 36 |  | 05 | 06 | 01 | 01 | 311 | 001 | New-311 | Yes |  | Other assets | Land & Buildings | KPA2 | All Wards | Land Acquisition | USDG | 20000000 |  | 20000000 | -11000000 | 9000000 |  | 9000000 |  | 5500000 |  | 5500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 5500000 | 5500000 | 0% | 0% | Matter referred to the Office of the MEC COGTA. Independent valuer to be appointed by agreement by parties concerned. Terms of Reference for the appointment of Independent Valuer has been finalised by DOF (Rates & Valutations) in consultation with the office of the MEC - Mr Tau and BID Specification approved on the 1st October 2014 and sent to SCM on the 2nd October 2014 to advertise.Acquisition of land parcel valued at R2.7m will be discussed with CS Consulting before 15 th December 2014 for road purposes. | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 295925.4 | 23537.64 | 319463.04 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 295925.4 | 319463.04 | 0 | 8704074.6 | 8680536.96 | 3.288% | 3.55%
Directorate of Development Planning | Transport Planning & Operations Admin | 7.30 - Transport Planning & Operations Admin | Development & Transport Planning | 620005 | 4 | 36 | 1536 | Planning and development | Planning and development | 4 | 36 |  | 05 | 06 | 01 | 01 | 050 | 001 | New-50 | Yes |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 | All Wards | Integrated Transport Plan Implementation Programme | USDG | 3000000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 24000000 |  | 24000000 | 52995 | 1576.4 | 54571.4 | 1754959.43 | 276099.8 | 2031059.23 | 1633771.02 | 228727.97 | 1862498.99 | 922399.1 | 1576.4 | 923975.5 | 1878949.14 | 260598.37 | 2139547.51 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 4534744.42 | 6243073.69 | 7011652.63 |  | 17756926.31 | 16988347.37 | 26.01% | 29.22% | Traffic calming measures have been completed in Beacon Bay, Cambridge, Braelyn, Duncan Village, Amalinda, Sweetwaters, KWT CBD, Willow Park, Mzamomhle and Sunnyridge.Work is in progress in Zwelitsha and construction in Mdantsane will commence in mid-January 2015. Construction of sidewalks have commenced in Phakamisa and Potsdam and they are nearing completion. The project is still on the early stages in Scenery Park and the project in Mdantsane will commence after the completion of Phakamisa in mid-January 2015. Traffic Signage programme has commenced and is at design stage.Traffic signals have been identified on NEX, Robbie de Lange, Potters Pass and Gullsway and the work is in progress and one cable informal tender has been advertised. Guidance signs have been designed for the rural areas and an order for the manufacture is being processed by SCM. Needs Camp / Potsdam Bridge progressing through detailed designs stage. Guardrails have been idfentified and installed in Mdantsane, Braelyn, Zwelitsha and Phakamisa. KwaTshatshu Bridge awarded 1 August 2014, inception stage complete,feasibility study report approved and detailed design stage has commenced. Construction of Taxi/Bus embayments in Scenery Park, Cambridge and Mdantsane is in progress. Amalinda, Ginsberg, Dimbaza embayments and Bonza Bay main road taxi rank construction will start in mid-January 2015. Works instruction requested. | 30000000 | 59500000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 162616.91 | 22766.37 | 185383.28 | 234124.03 | 32777.36 | 266901.39 | 866586.58 | 121322.12 | 987908.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 853992.67 | 1263327.52 | 1440193.37 | 0 | 1736672.48 | 1559806.63 | 42.11% | 48.01% |  |  |  |  | 109500000
Directorate of Development Planning |  | 7.30 - Transport Planning & Operations Admin |  | 620005 | 6 | 81 | 1501 | Planning and development | Planning and development |  |  |  | 05 | 06 | 01 | 01 | 050 | 002 | New-50 | Yes |  | Other |  | KPA2 | All Wards | BCMET Roads | BCMET c/o | [9 empty] | 256818 | 256818 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 122174.32 |  | 122174.32 | [22 empty] | 122174.32 | 122174.32 |  | 134643.68 | 134643.68 | 47.57% | 47.57% | Work to be continued on Amalinda Main Road sidewalk project.
Directorate of Development Planning |  | 7.16 - Building Maintenance - Coastal / Central |  | 615095 | 4 | 01 | 1527 | Planning and Development | Planning and development | 4 | 01 |  | 05 | 06 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Rehabilitation of Midland Existing Municipal Buildings and Old Mutual Building (Finance) | Own Funds |  |  |  |  | 0 |  | 0 |  | 2471000 |  | 2471000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2471000 | 2471000 | 0% | 0% | BMS is waiting for the 5 anuual maintenance tender to go through as it was aggreed with CFO that these tender would be used to carry out this project . | 10000000 | 5000000
Directorate of Development Planning |  | 7.16 - Building Maintenance - Coastal / Central |  | 615095 | 4 | 01 | 1528 | Planning and Development | Planning and development | 4 | 01 |  | 05 | 06 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Building Refurbishments and Upgrading of Lifts for BCMM Buildings | Own Funds |  |  |  |  | 0 | 400000 | 400000 |  | 1424288 |  | 1424288 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1424288 | 1424288 | 0% | 0% | Consultants to undertake this project are currently being procured through the informal tender process. Due to the vacant Facilities Assessment Section and possible lengthy lead times caused by having to import components, the majority of the budget may not be spent before the 2014/15 financial year-end. Budget to be adjusted into 2015/16 fiancial year for completion of consultancy services and construction costs. | 820661 | 7755051 | [40 empty] | 8000000
Directorate of Development Planning |  | 7.16 - Building Maintenance - Coastal / Central |  | 615095 | 4 | 01 | 1529 | Planning and Development | Planning and development | 4 | 01 |  | 05 | 06 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 | All Wards | SCM Inventory Warehousing and Fencing | Own Funds |  |  |  |  | 0 | 400000 | 400000 |  | 6000000 | -4500000 | 1500000 | 0 | 0 | 0 | 1146359.07 |  | 1146359.07 | -1146359.07 |  | -1146359.07 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1500000 | 1500000 | 0% | 0% | Consultants to undertake this project are to be procured through the informal tender process, as previous drawings and specifications can be re-used. Budget to be adjusted into 2015/16 fiancial year for construction costs. | 900000 | 900000 | [40 empty] | 8000000
[26 empty] | TOTAL : DEVELOPMENT PLANNING |  | 25800000 | 0 | 25800000 | -13800000 | 12000000 | 800000 | 12800000 | 0 | 44895288 | 1629919 | 46533707 | 52995 | 1576.4 | 54571.4 | 2901318.5 | 276099.8 | 3177418.3 | 2096477.84 | 228727.97 | 2325205.81 | 1406454.44 | 1576.4 | 1408030.84 | 2575135.51 | 260598.37 | 2835733.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7983758.76 | 9032381.29 | 9800960.23 | 0 | 37501325.71 | 36732746.77 | 19.41% | 21.06% |  | 42220661 | 73655051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162616.91 | 22766.37 | 185383.28 | 234124.03 | 32777.36 | 266901.39 | 1162511.98 | 144859.76 | 1307371.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 853992.67 | 1559252.92 | 1759656.41 | 0 | 10440747.08 | 10240343.59 | 12.99% | 14.66%
[32 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF ECONOMIC DEVELOPMENT | [25 empty] | DIRECTORATE OF ECONOMIC DEVELOPMENT | [5 empty] | 0 |  | 0
Directorate of Economic Development | Local Economic Development | 4.4 - Asset Risk & Financial Services |  | 635005 | 5 | 05 | 1523 | Budget and treasury | Planning and development | 5 | 05 |  | 05 | 03 | 03 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of 2 x Laptops - LED A13/86 | Own Funds | [10 empty] | 26000 | [11 empty] | 0 |  |  | 0 | [21 empty] | 20802 | 0 | 0 |  | 26000 | 26000 | 0% | 0% | Procurement process underway.
Directorate of Economic Development |  | 7.35 - Local Economic Development | Development & Transport Planning | 635005 | 4 | 36 | 1537 | Planning and Development | Planning and development | 4 | 36 |  | 05 | 07 | 01 | 01 | 120 | 001 | New-120 | Yes |  |  |  | KPA3 |  | Enabling Infrastructure Programme - LED | USDG | 10000000 | 10000000 | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | Procurement process underway. | 10000000 | 10000000
[26 empty] | TOTAL : ECONOMIC DEVELOPMENT | [5 empty] | 0 |  | 0 |  | 10000000 | 0 | 10026000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | 0 | 0 | 10026000 | 10026000 | 0% | 0% |  | 10000000 | 10000000
[32 empty] | 0 |  | 0
DIRECTORATE OF HEALTH AND PUBLIC SAFETY | [25 empty] | DIRECTORATE OF HEALTH AND PUBLIC SAFETY | [5 empty] | 0 |  | 0 | [15 empty] | 0 | [56 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Health and Public Safety | Office of the Director of Health & Public Safety | 8.1 - Office of The Director of Health & Public Safety |  | 705005 | 4 | 01 | 1530 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 30000 |  | 30000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 30000 | 30000 | 0% | 0% | Procurement process underway. Requistion submitted to SCM. | 500000 | 500000
Health and Public Safety | Health Administration | 8.1 - Office of The Director of Health & Public Safety |  | 710005 | 4 | 01 | 1553 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Health) | Own Funds |  |  |  |  | 0 |  | 0 |  | 70000 |  | 70000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 17468.46 | 0 | 0 |  | 70000 | 70000 | 0% | 0% | Procurement process underway. Requisitions have been submitted to SCM
Health and Public Safety |  | 8.4 - Health Support |  | 710010 | 6 | 01 | 1517 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 271 | 002 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Municipal Health Services - IT & Database Development | Own Funds c/o | [9 empty] | 216000 | 216000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 216000 | 216000 | 0% | 0% | Amount is to be transferred to IT for the maintanance and support of the MHS Software.
Health and Public Safety | Public Safety Administration | 8.1 - Office of The Director of Health & Public Safety |  | 725005 | 4 | 01 | 1554 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (GM Public Safety) | Own Funds |  |  |  |  | 0 |  | 0 |  | 21000 |  | 21000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 21000 |  | 21000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 21000 | 21000 |  | 0 | 0 | 100% | 100% | Project completed.
Health and Public Safety | Fire & Rescue Services | 8.13 - Fire and Rescue Services |  | 725010 | 4 | 01 | 1533 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 360 | 001 | New-360 | Yes |  | Community |  | KPA2 | 1 to 50 | Fire Engine | Own Funds |  |  |  |  | 0 |  | 0 |  | 4000000 |  | 4000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 4000000 | 4000000 | 0% | 0% | Project was recommended for BAC. | 4000000 | 4000000
Health and Public Safety | Fire & Rescue Services | 8.1 - Office of The Director of Health & Public Safety |  | 725010 | 4 | 01 | 1555 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Fire & Rescue Sercices) | Own Funds |  |  |  |  | 0 |  | 0 |  | 80000 |  | 80000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 42999 |  | 42999 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 30701.75 | 42999 | 42999 |  | 37001 | 37001 | 53.75% | 53.75% | Dinning Teak Elkana Table and 10 x Chairs, 28L Microwave, 600 SSU Defy Stove with Hob, Cooker and Oven and 430 L Metalic Fridge were delivered. Order 0001404909 for Informal Tender IT/DPHS/2014-15/128 to Supply and Delivery of Office Furniture was raised waiting for delivery.
Health and Public Safety | Fire & Rescue Services | 4.4 - Asset Risk & Financial Services |  | 725010 | 5 | 05 | 1526 | Budget and treasury | Public safety | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of V3030 & V3018 - Written off - M12/203 & M12/233 | Own Funds | [10 empty] | 600000 | [11 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 600000 | 600000 | 0% | 0% | Procurement will be done by Fleet Management Section, Specification submitted at Fleet Management Section.
Health and Public Safety | Fire & Rescue Services | 4.4 - Asset Risk & Financial Services |  | 725010 | 5 | 05 | 1529 | Budget and treasury | Public safety | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of V3029 - FLN384EC - M13/232 | Own Funds | [10 empty] | 600000 | [14 empty] | 0 | [22 empty] | 0 | 0 |  | 600000 | 600000 | 0% | 0% | Procurement will be done by Fleet Management Section, Specification submitted at Fleet Management Section.
Health and Public Safety |  | 8.13 - Fire and Rescue Services |  | 725010 | 6 | 01 | 1518 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 312 | 002 | New-312 | Yes |  | Other assets | Land & Buildings | KPA2 | All Wards | KWT Fire Station | Own Funds c/o | [9 empty] | 353709 | 353709 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 353709 | 353709 | 0% | 0% | KWT Station completed. Generator installed and need to be connected. Entrance gate delivered and installed need to be electrified.
Health and Public Safety |  | 8.13 - Fire and Rescue Services |  | 725010 | 6 | 01 | 1521 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Community |  |  | All Wards | Replacement of 2X Bush Fire Vehicles written off | Own Funds c/o | [9 empty] | 532200 | 532200 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 532200 | 532200 | 0% | 0% | Procurement will be done by Fleet Management Section, Specification submitted at Fleet Management Section.
Health and Public Safety |  | 8.13 - Fire and Rescue Services |  | 725010 | 6 | 01 | 1522 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Community |  |  | All Wards | Replacement of 5X Air Conditioners | Own Funds c/o | [9 empty] | 80000 | 80000 |  |  | 0 |  |  | 0 | 79776.8 |  | 79776.8 |  |  | 0 |  |  | 0 | [22 empty] | 79776.8 | 79776.8 |  | 223.2 | 223.2 | 99.72% | 99.72% | Project completed.
Health and Public Safety |  | 8.14 - Security Services |  | 725015 | 4 | 01 | 1534 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  |  | All Wards | Closed Circuit Television Network - CCTV | Own Funds | [8 empty] | 2000000 |  | 2000000 |  |  | 0 | 761505.76 |  | 761505.76 | -761455.82 |  | -761455.82 |  |  | 0 |  |  | 0 | [22 empty] | 49.94 | 49.94 |  | 1999950.06 | 1999950.06 | 0.002497% | 0.002497% | Tender as advertised 4 November 2014, closed 18 November 2014. Compulsory briefing session held 11 November 2014.
Health and Public Safety |  | 8.14 - Security Services |  | 725015 | 6 | 01 | 1516 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 271 | 002 | New-260 | Yes |  | Community |  |  | All Wards | Closed Circuit Television Network - CCTV c/o | Own Funds c/o | [9 empty] | 1196101 | 1196101 |  |  | 0 |  |  | 0 | 316911.22 |  | 316911.22 | 177174.39 |  | 177174.39 | 30168.27 |  | 30168.27 | [22 empty] | 524253.88 | 524253.88 |  | 671847.12 | 671847.12 | 43.83% | 43.83% | Land Administration (Geomatics) to do a reconnaissance of suitable high site for repeater site.
Health and Public Safety | Law Enforcement Services | 8.14 - Security Services |  | 725015 | 4 | 01 | 1535 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 250 | 001 | New-250 | Yes |  | Community | Other Assets | KPA2 | 1 to 50 | Fire Arms - Traffic and Law Enforcement | Own Funds | 50000 |  | 50000 |  | 50000 |  | 50000 |  | 100000 |  | 100000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 86850 |  | 86850 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 86850 | 86850 |  | 13150 | 13150 | 86.85% | 86.85% | Stock purchased, awaiting delivery once SAPS clearance is received. | 0 | 200000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 43280 |  | 43280 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 43280 | 43280 |  | 6720 | 6720 | 86.56% | 86.56%
Health and Public Safety | Law Enforcement Services | 8.1 - Office of The Director of Health & Public Safety |  | 725015 | 4 | 01 | 1557 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Law Enforcement) | Own Funds |  |  |  |  | 0 |  | 0 |  | 14110 |  | 14110 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 14110 | 14110 | 0% | 0% | Procurement process underway.
Health and Public Safety |  | 8.14 - Security Services |  | 725015 | 6 | 01 | 1520 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Community |  |  | All Wards | Security Equipment - DVRI | Own Funds c/o | [9 empty] | 40000 | 40000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 40000 | 40000 | 0% | 0% | Meetings with DVRI to be arranged in order obtain security equipment requirements.
Health and Public Safety | Traffic Administration | 8.1 - Office of The Director of Health & Public Safety |  | 725020 | 4 | 01 | 1556 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Traffic Services) | Own Funds |  |  |  |  | 0 |  | 0 |  | 211190 |  | 211190 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 211190 | 211190 | 0% | 0% | Procurement process underway. Informal tender submitted
Health and Public Safety | Traffic Administration | 4.4 - Asset Risk & Financial Services |  | 725020 | 5 | 05 | 1511 | Budget and treasury | Public safety | 4 | 01 |  | 05 | 03 | 03 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 145000 | 145000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 145000 | 145000 | 0% | 0% | Procurement process underway.
Health and Public Safety | Traffic Administration | 4.4 - Asset Risk & Financial Services |  | 725020 | 5 | 05 | 1522 | Budget and treasury | Public safety | 5 | 05 |  | 05 | 03 | 03 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of CPU & Monitor - A12/110 | Own Funds | [10 empty] | 10000 | [11 empty] | 0 |  |  | 0 | [21 empty] | 7569.32 | 0 | 0 |  | 10000 | 10000 | 0% | 0% | Requisition submitted to IT for the replacement of the CPU & Monitor
Health and Public Safety | Traffic Control | 8.16 - Traffic Control | Public Safety | 725025 | 4 | 36 | 1538 | Public safety | Public safety | 4 | 36 |  | 05 | 07 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Community | Land & Buildings/ Fire Stations | KPA2 | 35 | KWT Traffic Building | USDG | 1500000 |  | 1500000 | 500000 | 2000000 | -2000000 | 0 | 2000000 | 3000000 |  | 3000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2069735 | 0 | 0 |  | 3000000 | 3000000 | 0% | 0% | Service provider being professional planning team has been appointed and letter signed. Meetings with service provider & client held and draft plans being prepared based on requirements of clients. | 6000000 | 6000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0%
Health and Public Safety | Traffic Control | 8.16 - Traffic Control |  | 725025 | 4 | 01 | 1536 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 250 | 001 | New-250 | Yes |  | Community | Other Assets | KPA2 | 20 | Mdantsane Testing Station - Equipment | Own Funds | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 200000 | 1102.63 | 0 | 1102.63 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 12622.5 | 1102.63 | 1102.63 |  | 198897.37 | 198897.37 | 0.5513% | 0.5513% | PC's have been procurred and arrived at ICT on the 30 October 2014, waiting for confirmation of installation. | 0 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Health and Public Safety | Environmental Health |  |  | 710030 | 4 | 01 | 1531 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Air Monitoring Station | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 1800000
Health and Public Safety | Disaster Management |  |  | 725055 | 4 | 01 | 1542 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Tactic Radio Network | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 800000
Health and Public Safety | Disaster Management |  |  | 725055 | 4 | 01 | 1543 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Early Warning Systems | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 500000
Health and Public Safety | Traffic Control |  |  | 725025 | 4 | 01 | 1537 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Road Closure and Events Equipment | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 200000
Health and Public Safety | Traffic Control |  |  | 725025 | 4 | 01 | 1538 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Traffic Enforcement Equipment | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 1000000
Health and Public Safety | Fire & Rescue Services |  |  | 725010 | 4 | 01 | 1532 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Fire Equipment | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 2000000
Health and Public Safety | Traffic Control |  |  | 725025 | 4 | 01 | 1539 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 250 | 001 | New-250 | Yes |  | Community |  | KPA2 | 27 | Vehicle Pound | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 200000
Health and Public Safety | Vehicle Test Station / Examination |  |  | 725035 | 4 | 01 | 1540 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 27,1,41 | Vehicle Test Station Equipment | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 2000000
Health and Public Safety | Vehicle Test Station / Examination |  |  | 725035 | 4 | 01 | 1541 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Community |  | KPA2 | 27,1,41 | Upgrade Vehicle Test Station | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 2000000
Health and Public Safety |  | 8.18 - Vehicle Test Station / Examination |  | 725035 | 6 | 01 | 1519 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 312 | 002 | New-312 | Yes |  |  |  |  | All Wards | Learners Licence Centre - Mdantsane | Own Funds c/o | [9 empty] | 798970 | 798970 |  |  | 0 |  |  | 0 | 366421.75 |  | 366421.75 |  |  | 0 | 44666.78 |  | 44666.78 | [21 empty] | 155061.1 | 411088.53 | 411088.53 |  | 387881.47 | 387881.47 | 51.45% | 51.45% | The unspent balance will be paid out soon as project is completed. This amount is the final payment for the project and for the fencing of the project.
Health and Public Safety | Disaster Management | 8.1 - Office of The Director of Health & Public Safety |  | 725055 | 4 | 01 | 1558 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Disaster Management) | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 73700 |  | 73700 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 73700 | 73700 | 0% | 0% | Procurement process underway.
Health and Public Safety | Disaster Management | 4.4 - Asset Risk & Financial Services |  | 725055 | 5 | 05 | 1506 | Budget and treasury | Public safety | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Asset Replacements - Insurance | Own Funds |  |  | 0 |  | 0 |  | 0 |  |  | 95000 | 95000 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 9792.6 |  | 9792.6 | [21 empty] | 61630.7 | 9792.6 | 9792.6 |  | 85207.4 | 85207.4 | 10.31% | 10.31% | Procurement process underway. ITC equipment has been supplied and installed. A follow up is being undertaken to establish why the costs have not been deducted.
[26 empty] | TOTAL : HEALTH AND PUBLIC SAFETY |  | 1750000 | 0 | 1750000 | 500000 | 2250000 | -2000000 | 250000 | 2000000 | 9800000 | 3456980 | 14466980 | 1102.63 | 0 | 1102.63 | 761505.76 | 0 | 761505.76 | 1653.95 | 0 | 1653.95 | 177174.39 | 0 | 177174.39 | 235476.65 | 0 | 235476.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2354788.83 | 1176913.38 | 1176913.38 | 0 | 13290066.62 | 13290066.62 | 8.135% | 8.135% |  | 10500000 | 21200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43280 | 0 | 43280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43280 | 43280 | 0 | 2206720 | 2206720 | 1.924% | 1.924% |  |  | 0
[30 empty] | 0 |  | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF COMMUNITY SERVICES | [25 empty] | DIRECTORATE OF COMMUNITY SERVICES |  |  |  | 0 |  | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Community Services | Environmental Administration Support | 9.1 - Office of The Director of Community Services |  | 755005 | 4 | 01 | 1544 | Community and social services | Support Services | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 200000 |  | 200000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 24411.1 |  | 24411.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 27600.63 | 24411.1 | 24411.1 |  | 175588.9 | 175588.9 | 12.21% | 12.21% | The department is in the process of procuring furniture | 500000 | 500000
Community Services | Environmental Services | 9.4 - Environmental Services | Environmental Services | 755010 | 4 | 36 | 1539 | Community and social services | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 150 | 001 | New-150 | Yes |  | Community | Recreational Facilities | KPA2 | 13, 21,23 | Development of Community Parks(Inland, Midlands and Coastal) | USDG | 3000000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 4196.91 |  | 4196.91 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 908140.14 | 4196.91 | 4196.91 |  | 1995803.09 | 1995803.09 | 0.2098% | 0.2098% | Orders for installation of palisade fencing amounting to R658 023 has been generated by Supply Chain Management. | 0 | 0 |  |  |  | 0 |  | 0 | 4531.56 | 634.41 | 5165.97 | 4531.56 | 5165.97 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4531.56 | 5165.97 |  | 2995468.44 | 2994834.03 | 0.1511% | 0.1722%
Community Services | Cleansing Administration Support | 4.4 - Asset Risk & Financial Services |  | 755010 | 5 | 05 | 1505 | Budget and treasury | Amenities | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Asset Replacements - Insurance | Own Funds |  |  | 0 |  | 0 |  | 0 |  |  | 14000 | 14000 |  |  | 0 |  |  | 0 | 13675.44 |  | 13675.44 |  |  | 0 |  |  | 0 | [22 empty] | 13675.44 | 13675.44 |  | 324.56 | 324.56 | 97.68% | 97.68% | Assets have been replaced
Community Services | Interments | 9.7 - Interments | Environmental Services | 755025 | 4 | 36 | 1540 | Environmental Protection | Environmental Services | 4 | 36 |  | 05 | 07 | 01 | 01 | 220 | 001 | New-220 | Yes |  | Community | Cemeteries | KPA2 | All Wards | Development and Upgrading of Cemeteries(Inland, Midland and Coastal) | USDG | 12040943 |  | 8040943 | 3000000 | 11040943 | 7500000 | 18540943 |  | 10000000 |  | 10000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 284773.45 | 39868.28 | 324641.73 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 4740432.19 | 284773.45 | 324641.73 |  | 9715226.55 | 9675358.27 | 2.848% | 3.246% | An amount of R5 415 228 has been committed for the upgrading of road infrastructure. | 8000000 | 8000000 |  |  |  | 0 | 91583.2 | 94326.92 | 581732.54 | 8018.19 | 589750.73 | 673315.74 | 684077.65 | 660644.36 | 88006.48 | 748650.84 | 1691335.57 | 212536.29 | 1903871.86 | 3734448.25 | 432675.81 | 4167124.06 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4981912.06 | 6759743.92 | 7503724.41 |  | 4281199.08 | 3537218.59 | 61.22% | 67.96% | 10000000
Community Services |  | 9.7 - Interments |  | 755025 | 6 | 01 | 1523 | Environmental Protection | Amenities |  |  |  | 05 | 07 | 01 | 01 | 250 | 002 | New-250 | Yes | [5 empty] | Cemetery Vehicles | Own Funds c/o | [9 empty] | 1700000 | 1700000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 1700000 | 1700000 | 0% | 0% | Funds are to be transferred to Solid Waste
Community Services | Interments | 4.4 - Asset Risk & Financial Services |  | 755025 | 5 | 05 | 1512 | Budget and treasury | Amenities | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  |  |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 57250 | 57250 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 57250 | 57250 | 0% | 0% | The paperwork has been sent to Mechanical Workshop to procure.
Community Services | Libraries | 4.4 - Asset Risk & Financial Services |  | 760010 | 5 | 05 | 1508 | Budget and treasury | Amenities | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  |  |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 1700 | 1700 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [21 empty] | 1341 | 0 | 0 | 1341 | 1700 | 1700 | 0% | 0% | Project complete
Community Services | Halls | 9.14 - Halls | Amenities | 760025 | 4 | 36 | 1541 | Community and social services | Amenities |  |  |  | 05 | 07 | 01 | 01 | 170 | 001 | New-170 | Yes |  | Community |  | KPA2 |  | Construction of Nompumelelo Halls | USDG |  |  | 4000000 |  | 4000000 | -3000000 | 1000000 |  | 7000000 |  | 7000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | -5964.03 | 0 | 0 | 0 | 7000000 | 7000000 | 0% | 0% | Site briefing was held on 2/12/2014, closing date for tenders is 9/12/2014. Evaluation report will be drafted and submitted to BEC in January 2015. | 0 | 0 | [19 empty] | 0 | [14 empty] | 0 |  | 4000000 | 4000000 | 0% | 0%
Community Services | Halls | 9.14 - Halls | Amenities | 760025 | 4 | 36 | 1542 | Community and social services | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 170 | 001 | New-170 | Yes |  | Community | Halls | KPA2 | 42,39,13,33,5 | Development and Upgrading of Community Halls - War Memorial Hall Upgrade of Parking Area, O.R.Tambo Hall Upgrade of Parking Area, Egoli Community Hall( New Hall), Needs Camp Community Hall Upgrade, Orient Theatre Upgrade, Continuation of KWT Town Hall and NU 5 Hall Mdantsane | USDG | 10000000 |  | 10000000 | -4000000 | 6000000 | -5000000 | 1000000 |  | 3000000 |  | 3000000 | 0 | 0 | 0 | 47492.13 | 5262.9 | 52755.03 | 121503.65 | 17010.51 | 138514.16 |  |  | 0 | 502484.64 | 21527.67 | 524012.31 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1658218.53 | 671480.42 | 715281.5 | 1813396 | 2328519.58 | 2284718.5 | 22.38% | 23.84% | OR Tambo hall: contract 26 approved (tarring of parking area), contractor appointed, to commence work mid January 2015. Needs Camp Hall: work in progress, 70% complete (Replace Roof/floor, new windows & doors/installation of burglar proofing & revamp of ablutions). | 9000000 | 9000000 |  |  |  | 0 | 123401.18 | 126631 | 485376.34 | 65891.88 | 551268.22 | 608777.52 | 677899.22 | 295837.21 | 8054.91 | 303892.12 | 132480 |  | 132480 | 727758.62 | 16971.31 | 744729.93 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1574808.82 | 1764853.35 | 1859001.27 |  | 4235146.65 | 4140998.73 | 29.41% | 30.98% | 20000000
Community Services |  | 9.14 - Halls |  | 760025 | 6 | 01 | 1524 | Community and social services | Amenities |  |  |  | 05 | 07 | 01 | 01 | 170 | 002 | New-170 | Yes | [5 empty] | Reeston Community Hall Renovations | Own Funds c/o | [9 empty] | 100000 | 100000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 | 0 | 100000 | 100000 | 0% | 0% | Await authorisation to utilise funds on non-municipal property. This budget is not sufficient to renovate the community hall
Community Services |  | 9.14 - Halls |  | 760025 | 6 | 01 | 1525 | Community and social services | Amenities |  |  |  | 05 | 07 | 01 | 01 | 170 | 002 | New-170 | Yes | [5 empty] | Continuation of Refurbishment of KWT Hall / Cambridge | Own Funds c/o | [9 empty] | 1075698 | 1075698 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 | 0 | 1075698 | 1075698 | 0% | 0% | Works to be identified and to commence in January 2015.
Community Services |  | 9.14 - Halls |  | 760025 | 6 | 01 | 1534 | Community and social services | Support Services |  |  |  | 05 | 07 | 01 | 01 | 271 | 002 | New-260 | Yes | [5 empty] | Replacement of 2 X Hifgh back chairs, 1 X Piano and 2 X Bar Stools | Own Funds c/o | [9 empty] | 51000 | 51000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 | 0 | 51000 | 51000 | 0% | 0% | Supply Chain Management have indicated that the replacement of the items must go out to informal tender.
Community Services |  | 9.14 - Halls |  | 760025 | 6 | 01 | 1535 | Community and social services | Support Services |  |  |  | 05 | 07 | 01 | 01 | 271 | 002 | New-260 | Yes | [5 empty] | Replacement of Stove and Fridge | Own Funds c/o | [9 empty] | 12000 | 12000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 | 0 | 12000 | 12000 | 0% | 0% | Requisition completed & sent to Supply Chain Management. Awaiting order.
Community Services |  | 9.14 - Halls |  | 760025 | 4 | 35 | 1510 | Community and social services | Amenities |  |  |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes | [5 empty] | Reeston MPCC - DVRI | HSDG-(MPCC) | [9 empty] | 10068500 | 10068500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [21 empty] | 2245300 | 0 | 0 | 2245300 | 10068500 | 10068500 | 0% | 0% | Awaiting authorisation to utilise funds on non municipal property
Community Services | Sportsfields | 9.16 - Sportsfields |  | 765010 | 4 | 01 | 1545 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes |  |  | KPA2 |  | Sports equipment and structures | Own Funds | [8 empty] | 1500000 |  | 1500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 335950 |  | 335950 | 28620 |  | 28620 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 78000 | 364570 | 364570 |  | 1135430 | 1135430 | 24.3% | 24.3% | Cricket covers and goal posts received. Awaiting delivery of Trailer. Pedestrian roller informal tender advertised. Specifications for Kudu Mowers and Brushcutters was finalized, signed and submitted to Supply Chain Management and returned by Supply Chain Management to the Division as Supply Chain Management is closed and to be re-submitted in January 2014. | 0 | 0
Community Services | Sportsfields | 9.16 - Sportsfields |  | 765010 | 4 | 01 | 1546 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Community | Sportsfields | KPA2 | 42,33,47,36,41,43,37,43,19,3 | Equipment for Jan Smuts Stadium | Own Funds | [8 empty] | 41907 |  | 41907 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 28997.54 |  | 28997.54 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 28997.54 | 28997.54 |  | 12909.46 | 12909.46 | 69.19% | 69.19% | Two marking machines were received by Sportsfields.
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1543 | Sport and recreation | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Community | Swimming Pool | KPA2 | 20, 46 | Redevelopment of Mdantsane NU 2 Swimming Pool and Upgrading of Waterworld | USDG | 5000000 |  | 5000000 | -5000000 | 0 |  | 0 |  | 15000000 | -5000000 | 10000000 | 0 | 0 | 0 |  |  | 0 | 2024.82 | 283.48 | 2308.3 | 2540.24 |  | 2540.24 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 4565.06 | 4848.54 |  | 9995434.94 | 9995151.46 | 0.04565% | 0.04849% | Tenders closed. Specification document submitted to Bid Evaluation Committee. | 5000000 | 5000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  | 10000000
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1544 | Sport and recreation | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Community | Sportsfields | KPA2 | 42,33,47,36,41,43,37,43,19,3 | Upgrading of Dimbaza and Zwelitsha Stadium | USDG | 4000000 |  | 4000000 | 1800000 | 5800000 | -5384413 | 415587 |  | 2250000 |  | 2250000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2250000 | 2250000 | 0% | 0% | Cancellation report for last financial year tender was submitted on the 22/09/2014. Formal tender will be advertised when last financial year tender is cancelled. | 4750000 | 4750000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 2111.29 | 295.58 | 2406.87 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2111.29 | 2406.87 |  | 5797888.71 | 5797593.13 | 0.0364% | 0.0415%
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1545 | Sport and recreation | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Community | Sportsfields | KPA2 | 42,33,47,36,41,43,37,43,19,3 | Upgrading of Floodlights at Victoria Grounds, Bhisho Stadium, Ginsberg stadium, Sisa Dukashe Stadium, Alfred Schoeman Stadium, North End Stadium, Jan Smuts Stadium, Amalinda Stadium, and Gompo Stadium | USDG | 5000000 |  | 5000000 | -1000000 | 4000000 | -2500000 | 1500000 |  | 3000000 |  | 3000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 978025.7 | 136923.61 | 1114949.31 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 978025.7 | 1114949.31 |  | 2021974.3 | 1885050.69 | 32.6% | 37.16% | Remedial work is done by Electricity Department. Electricity Department will not continue working on this project. Informal tender for appointment of Eletrical Engeneers has been drafted and will be submitted to Supply Chain Management in January 2015 to be advertised. | 0 | 0 |  |  |  | 0 |  | 0 | 7827.24 | 1095.81 | 8923.05 | 7827.24 | 8923.05 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7827.24 | 8923.05 |  | 3992172.76 | 3991076.95 | 0.1957% | 0.2231%
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1546 | Sport and recreation | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes |  |  | KPA2 |  | Upgrading of Phakamisa and Mount Coke sports fields | USDG | [8 empty] | 1000000 |  | 1000000 | 0 | 0 | 0 | 190000 |  | 190000 | 746098.5 | 0 | 746098.5 | -91626.13 |  | -91626.13 | 29500 |  | 29500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 28980 | 873972.37 | 873972.37 |  | 126027.63 | 126027.63 | 87.4% | 87.4% | Councillor's and Sport Committee delivered the letter for top soil and palisade fence at Phakamisa Sportsfields. Annual contract for top soil will be utilized and requisition for poles and refurbishment of fence for Mount Coke and Phakamisa submitted to Supply Chain Management. | 1500000 | 0
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1566 | Sport and recreation | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Community | Swimming Pool | KPA2 | 20, 46 | Upgrading of Waterworld | USDG | [9 empty] | 5000000 | 5000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 5000000 | 5000000 | 0% | 0% | Assesment report submitted to Supply Chain Management for HDI pricing.
Community Services |  | 9.16 - Sportsfields |  | 765010 | 6 | 36 | 1501 | Sport and recreation | Amenities |  |  |  | 05 | 07 | 01 | 01 | 160 | 002 | Renewal-160 |  | Yes |  |  |  |  | Completion of Upgrading of 2010 Stadium | DSRAC c/o | [9 empty] | 2686285 | 2686285 |  |  | 0 |  |  | 0 | 180000 |  | 180000 | 68800 |  | 68800 | 137600 |  | 137600 | [22 empty] | 386400 | 386400 |  | 2299885 | 2299885 | 14.38% | 14.38% | Planting of the grass has been done, portable stands have been installed and fencing of the play surface has been done at Dimbaza, Ndevana, Peelton, Newlands and lower Mngqisha sportsfiels.
Community Services |  | 9.16 - Sportsfields |  | 765010 | 6 | 01 | 1526 | Sport and recreation | Amenities |  |  |  | 05 | 07 | 01 | 01 | 160 | 002 | Renewal-160 |  | Yes |  |  |  |  | Upgrading of Resort and Purchase of Equipment | Own Funds c/o | [9 empty] | 384660 | 384660 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [21 empty] | 19340 | 0 | 0 |  | 384660 | 384660 | 0% | 0% | Awaiting Service Provider to Deliver equipment as per order given. Delivery is expected in January 2015.
Community Services | Swimming Pools | 9.17 - Swimming Pools |  | 765015 | 4 | 01 | 1547 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes |  |  | KPA2 |  | Refurbishment of Swimming Pools | Own Funds | [8 empty] | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Tender specification document for heating system at Joan Harrison Pool finalized and will be delivered to Supply Chain before being submitted to the Bid Specification Committee. | 2500000 | 0
Community Services | Aquarium | 9.18 - Aquarium | Amenities | 765020 | 4 | 36 | 1547 | Sport and recreation | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 190 | 001 | Renewal-190 |  | Yes |  |  | KPA2 |  | Relocation of Aquarium | USDG | [8 empty] | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Specification for formal tender finalized and to submit for signature. Awaiting approval of deviation report for remedial work. | 5000000 | 10000000
Community Services | Zoo | 9.19 - Zoo |  | 765025 | 4 | 01 | 1548 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 190 | 001 | Renewal-190 |  | Yes |  |  | KPA2 |  | Upgrading of Zoo Facilities | Own Funds | [8 empty] | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Specification document submitted to Bid Specification Committee on 4/11/2014. | 1500000 | 0
Community Services | Zoo | 9.16 - Sportsfields |  | 765025 | 4 | 01 | 1549 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 190 | 001 | Renewal-190 |  | Yes |  |  | KPA2 |  | FEL Zoo - Aquarium | Own Funds | [8 empty] | 238502 |  | 238502 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 238502 | 238502 | 0% | 0% | Specification document submitted to Bid Specification Committee on 4/11/2014.
Community Services | Beaches | 9.20 - Beaches |  | 765030 | 4 | 01 | 1550 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 190 | 001 | Renewal-190 |  | Yes |  |  | KPA2 |  | Upgrading of Beaches Facilities | Own Funds | [8 empty] | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Awaiting Supply Chain Management to advertise informal tenders for appointment of Qauntity Survyor and refurbishment of ablution blocs. | 1500000 | 0
Community Services | Cleansing Administration Support | 9.1 - Office of The Director of Community Services |  | 770005 | 4 | 01 | 1552 | Community and social services | Waste Management | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 |  | Office Furniture and Equipment (Solid Waste Management) | Own Funds | [8 empty] | 300000 |  | 300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 26265.65 | 0 | 0 |  | 300000 | 300000 | 0% | 0% | Procurement process underway
Community Services | Cleansing Administration Support | 4.4 - Asset Risk & Financial Services |  | 770005 | 5 | 05 | 1510 | Budget and treasury | Amenities | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 1700000 | 1700000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [21 empty] | 1700000 | 0 | 0 |  | 1700000 | 1700000 | 0% | 0% | Replacement of vehicles done at mechanical workshops
Community Services |  | 9.17 - Swimming Pools |  | 770005 | 6 | 01 | 1527 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 271 | 002 | New-260 | Yes | [5 empty] | Grass Cutting Equipment | Own Funds c/o | [9 empty] | 668126 | 668126 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 128560 |  | 128560 | [21 empty] | 37129 | 128560 | 128560 |  | 539566 | 539566 | 19.24% | 19.24% | The tender for grass cutting equipment was advertised on the 2 December 2014
Community Services |  | 9.23 - Refuse Removal |  | 770010 | 6 | 01 | 1533 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes |  | Community | Refuse | KPA2 | All Wards | Acquisition of Solid Waste Plant | Own Funds c/o | [9 empty] | 8804587 | 8804587 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [21 empty] | 7288444.3 | 0 | 0 |  | 8804587 | 8804587 | 0% | 0% | Tender has been awarded awaiting delivery
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1528 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Upgrade & Refurbishment Disposal Sites - Phase 2 - Design & Construction of 3rd and 4th Cell and Ancillary Works | Own Funds c/o | [9 empty] | 1774658 | 1774658 |  |  | 0 |  |  | 0 | 1488773.47 |  | 1488773.47 |  |  | 0 | 189188.75 |  | 189188.75 | [22 empty] | 1677962.22 | 1677962.22 |  | 96695.78 | 96695.78 | 94.55% | 94.55% | Project in progress
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1529 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Solid Waste Programme- Weigh Bridge KWT | Own Funds c/o | [9 empty] | 2000000 | 2000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Enterprise Project Management Office (EPMO) is assisting the department in connection with this project
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1530 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Waste Management Programme - Plant and Equipment | Own Funds c/o | [9 empty] | 1268845 | 1268845 |  |  | 0 |  |  | 0 |  |  | 0 | 3201.75 |  | 3201.75 | 1258179 |  | 1258179 | [22 empty] | 1261380.75 | 1261380.75 |  | 7464.25 | 7464.25 | 99.41% | 99.41% | Project complete
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1531 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Counterfunding - Leiden Twinning - Solid Waste Drop-Off Points | Own Funds c/o | [9 empty] | 967405 | 967405 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 967405 | 967405 | 0% | 0% | Awaiting delivery from the service provider
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1532 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Specialised Solid Waste Vehicles | Own Funds c/o | [9 empty] | 4000000 | 4000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [21 empty] | 3595377.72 | 0 | 0 |  | 4000000 | 4000000 | 0% | 0% | Awaiting delivery
Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 9.27 - E.L Regional Waste Disposal Site & Transfer Station | Waste Management | 770030 | 4 | 36 | 1548 | Waste Management | Waste Management | 4 | 36 |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes |  | Community | Refuse | KPA2 | Will provide ward no, as soon as land is availed/identified | Construction of Transfer Stations - 3 x Sites | USDG | 0 |  | 0 |  | 0 |  | 0 |  | 5000000 |  | 5000000 | 0 | 0 | 0 | 3976.02 | 556.64 | 4532.66 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 3976.02 | 4532.66 |  | 4996023.98 | 4995467.34 | 0.07952% | 0.09065% | Procurement process underway | 5000000 | 5000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0%
Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 9.27 - E.L Regional Waste Disposal Site & Transfer Station | Waste Management | 770030 | 4 | 36 | 1549 | Waste Management | Waste Management | 4 | 36 |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes |  |  |  | KPA2 |  | KWT Tanery Site | USDG | [8 empty] | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Procurement process underway | 1000000 | 1000000
Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 9.27 - E.L Regional Waste Disposal Site & Transfer Station | Waste Management | 770030 | 4 | 36 | 1550 | Waste Management | Waste Management | 4 | 36 |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes |  | Community | Refuse | KPA2 | 25 | Construction and Rehabilitation of Waste Cells | USDG | 0 |  | 0 |  | 0 |  | 0 |  | 20000000 |  | 20000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 20000000 | 20000000 | 0% | 0% | Procurement process underway | 20710100 | 14412415 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0%
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 4 | 01 | 1560 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes | [5 empty] | Solid Waste Mechanical Plant and Vehicles | Own Funds | [9 empty] | 40000000 | 40000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [21 empty] | 17777957 | 0 | 0 |  | 40000000 | 40000000 | 0% | 0% | 8 Compactor Trucks and 2 x TLB's have been delivered
Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 4 | 01 | 1551 | Waste Management | Waste Management | 4 | 01 |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes |  | Community |  | KPA2 |  | 17800 X240 Litre Wheelie Bins | Own Funds |  |  | 0 | 51990000 | 14240000 |  | 14240000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 | 641246.4 |  | 641246.4 | 961869.6 |  | 961869.6 | 2235456.2 |  | 2235456.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3009600 | 3838572.2 | 3838572.2 |  | 6161427.8 | 6161427.8 | 38.39% | 38.39% | Wheelie Bins of contract C3041 have been delivered and paid ; C3046 Bins have been delivered . | 10000000 | 10000000 | [19 empty] | 0 | [13 empty] | 0 | 0 |  | 14240000 | 14240000 | 0% | 0%
[26 empty] | TOTAL : COMMUNITY SERVICES |  | 39040943 | 0 | 39040943 | 46790000 | 48080943 | -8384413 | 39696530 | 0 | 86530409 | 77334714 | 163865123 | 0 | 0 | 0 | 882714.55 | 5819.54 | 888534.09 | 3513945.48 | 17293.99 | 3531239.47 | 3565542.21 | 136923.61 | 3702465.82 | 2583316.94 | 61395.95 | 2644712.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43136162.13 | 10545519.18 | 10766952.27 | 4060037 | 153319603.82 | 153098170.73 | 6.435% | 6.571% |  | 75960100 | 67662415 | 0 | 0 | 0 | 0 | 214984.38 | 220957.92 | 1079467.68 | 75640.29 | 1155107.97 | 1294452.06 | 1376065.89 | 956481.57 | 96061.39 | 1052542.96 | 1825926.86 | 212831.87 | 2038758.73 | 4462206.87 | 449647.12 | 4911853.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6556720.88 | 8539067.36 | 9379221.57 | 0 | 39541875.64 | 38701721.43 | 17.76% | 19.51%
[26 empty] | TOTAL : CAPITAL PROJECTS - ALL DIRECTORATES | [9 empty] | 932007423 | 116774633 | 1050202056 | 4279296.15 | 305995.65 | 4585291.8 | 36998451.88 | 3733785.71 | 40732237.59 | 63771348.91 | 5239427.37 | 69010776.28 | 82385306.63 | 6648328.33 | 89033634.96 | 52978431.48 | 5551241.11 | 58529672.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120394360.21 | 240412835.05 | 261891613.22 | 4060037 | 809789220.95 | 788310442.78 | 22.89% | 24.94%
Asset Replacement |  | 4.4 - Asset Risk & Financial Services |  | 320005 | 5 | 05 | 1501 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds |  |  |  |  | 0 |  | 0 |  | 10000000 |  | 6282650 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 6282650 | 6282650 | 0% | 0% | This is to be used to replace assets iro insurance claims. | 10000000 | 10000000
0
[26 empty] | TOTAL : BCMM CAPITAL BUDGET |  | #REF! | #REF! | #REF! | #REF! | #REF! | 12199892 | #REF! | 2000000 | 942007423 | 116774633 | 1056484706 | 4279296.15 | 305995.65 | 4585291.8 | 36998451.88 | 3733785.71 | 40732237.59 | 63771348.91 | 5239427.37 | 69010776.28 | 82385306.63 | 6648328.33 | 89033634.96 | 52978431.48 | 5551241.11 | 58529672.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120394360.21 | 240412835.05 | 261891613.22 | 4060037 | 816071870.95 | 794593092.78 | 22.76% | 24.79% |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
91458961
106541039
[26 empty] | Projects Deleted from the list |  | #REF!
Directorate of Development Planning |  |  |  | 620005 | [14 empty] | Renewal-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks |  |  | Public Transport Facilities | PTISG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 50000000 | [42 empty] | 50000000
Directorate of Development Planning |  |  |  | 615095 | [14 empty] | Renewal-312 |  |  | Other | Car Parks,Bus termonals & Taxi ranks |  |  | Replacement of Lift Shoprite Building | Own Funds |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 3500000
[36 empty] | 0 | [47 empty] | 0 | 3500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Oxford Street Mall (Pedestrianisation/Public Transport Zone) | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 6000000 | [42 empty] | 6000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Northwest Expressway widening and extension to Amalinda Main Road | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 5000000 | [42 empty] | 5000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Fitzpatrick Road/Currie Street Link Road (Sleeper Site) | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 4000000 | [42 empty] | 4000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Non-Motorised Transport Facilities Implementation | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 5000000 | [42 empty] | 5000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Traffic congestion improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 2000000 | [42 empty] | 2000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Bonza Bay Road LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 1500000 | [42 empty] | 1500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Vincent and Berea LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 1500000 | [42 empty] | 1500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | KWT LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 1500000 | [42 empty] | 1500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Mdantsane LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 1500000 | [42 empty] | 1500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Bhisho LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 1500000 | [42 empty] | 1500000
[36 empty] | 86530409 | [47 empty] | 75960100
[36 empty] | 86530409 | [47 empty] | 75960100
[36 empty] | 0 | [47 empty] | 0
[38 empty] | 507185871 | [6 empty] | 549298835
[38 empty] | 507135271 | [6 empty] | 549349435
[38 empty] | 50600 | [6 empty] | -50600
17000000

## Summaries
2014/2015 - 2016/2017 CAPITAL BUDGET PER FUNDING SOURCE
| M |  |  | AE | AF |  | AH | [32 empty] | AI | Aj |  | Aj
Funding | 2013/2014 Approved Budget | 2013/2014 Rollover Adjustment Budget | 2013/2014 Conditional Grants Rollover Adjustment Budget | Mid-Year Adjustments | 2013/2014 Mid-Year Adjusted Budget | 2014/2015 DoRA | 2014/2015 Approved Capital Budget | 2014/2015 Rollover Adjustment Budget | July 2014 | July 2014 (VAT incl) | August 2014 | August 2014 (VAT incl) | September 2014 | September 2014 (VAT incl) | October 2014 | October 2014 (VAT incl) | November 2014 | November 2014 (VAT incl) | December 2014 | December 2014 (VAT incl) | January 2015 | January 2015 (VAT incl) | February 2015 | February 2015 (VAT incl) | March 2015 | March 2015 (VAT incl) | April 2015 | April 2015 (VAT incl) | May 2015 | May 2015 (VAT incl) | June 2015 | June 2015 (VAT incl) | YTD Expenditure | YTD Expenditure (VAT) incl) | Commitments as per Venus | Variance | Variance ( VAT incl) | % Expenditure | % Expenditure (VAT incl) | 2015/2016 Draft Capital Budget | 2016/2017 Draft Capital Budget | NT | DoRA
Own Funds | 21878631.88 | 21878631.88 | 21878631.88 | 30084305 | 51962936.88 |  | 241225697 | 276725697 | 20176.95 | 20176.95 | 5426887.92 | 5426887.92 | 16172829.34 | 16172829.34 | 16338247.16 | 16338247.16 | 6066404.97 | 6066404.97 | [14 empty] | 44024546.34 | 44024546.34 | 45843023.9 | 232701150.66 | 232701150.66 | 15.91% | 15.91% | 256870661 | 270555051 | Own funds |  |  | Own Funds | 255845288 | 261320661 | 276905051
Own Funds c/o | [6 empty] | 0 | 55139872 |  |  | 0 | 0 | 4223929.01 | 4223929.01 | 669236.82 | 669236.82 | 4049040.55 | 4049040.55 | [14 empty] | 8942206.38 | 8942206.38 | 14191147.36 | 46197665.62 | 46197665.62 | 16.22% | 16.22%
Total Own Funding |  |  | 21878631.88 | 30084305 | 51962936.88 | 0 | 241225697 | 331865569 | 20176.95 | 20176.95 | 5426887.92 | 5426887.92 | 20396758.35 | 20396758.35 | 17007483.98 | 17007483.98 | 10115445.52 | 10115445.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52966752.72 | 52966752.72 | 60034171.26 | 278898816.28 | 278898816.28 | 15.96% | 15.96% | 256870661 | 270555051 |  |  |  |  | -14619591 | -4450000 | -6350000
DoE(Intergrated National Electrification Programme) | 0 | 0 | 0 | 0 | 0 |  | 27000000 | 27000000 | 34346 | 34346 | 128806.07 | 128806.07 | 2895383.81 | 3318770.39 | 9399037.37 | 10101331.63 | 2741800.57 | 3739223.63 | [14 empty] | 15199373.82 | 17322477.72 | 0 | 11800626.18 | 9677522.28 | 56.29% | 64.16% | 27000000 | 12000000 | N |  |  | N
Department of Sports, Recreation, Arts and Culture c/o | [7 empty] | 2686285 |  |  | 0 | 0 | 180000 | 180000 | 68800 | 68800 | 137600 | 137600 | [14 empty] | 386400 | 386400 | 0 | 2299885 | 2299885 | 14.38% | 14.38% |  |  | P |  |  | P
Local Government, Traditional Affairs and Housing | [6 empty] | 188726 | 188726 | 0 | 0 | 0 | 0 | 178585.49 | 178585.49 | 0 | 0 | 0 | 0 | [14 empty] | 178585.49 | 178585.49 | 0 | 10140.51 | 10140.51 | 94.63% | 94.63% | 0 | 0 | P |  |  | P
Infrastructure Skills Development Grant | 100000 | 100000 | 100000 | 0 | 100000 |  | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 100000 | 100000 | 0% | 0% | 100000 | 0 | N |  |  | N
BCMET c/o | [7 empty] | 256818 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 122174.32 | 122174.32 | [14 empty] | 122174.32 | 122174.32 | 0 | 134643.68 | 134643.68 | 47.57% | 47.57% | [5 empty] | P
Leiden c/o | [6 empty] | 0 | 458860 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 458860 | 458860 | 0% | 0%
Neigbourhood Development Partnership Grant | 10000000 | 10000000 | 10000000 | -10000000 | 0 |  | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 107792 | 107792 | 2583366.68 | 2960128.89 | 0 | 0 | [14 empty] | 2691158.68 | 3067920.89 | 1267878.34 | 2308841.32 | 1932079.11 | 53.82% | 61.36% | 16878000 | 17744000 | N |  |  | N
Urban Settlement Development Grant | 238119983 | 238119983 | 238119983 | -7384413 | 230735570 |  | 639824500 | 639824500 | 1979773.14 | 2285768.79 | 28086910.53 | 31820696.24 | 37979284.1 | 42795324.89 | 43344629.73 | 48913901.59 | 29320100.24 | 33873918.29 | [14 empty] | 140710697.74 | 159689609.8 | 56620051.29 | 499113802.26 | 480134890.2 | 21.99% | 24.96% | 1023310100 | 1025627100 | N |  | #REF! | N | 33464500 | 37147900 | 38147900 | OPEX
Human Settlement Development Grant | 23924600 | 23924600 | 23924600 | -500000 | 23424600 |  | 18600000 | 18600000 | 2245000.06 | 2245000.06 | 3355847.36 | 3355847.36 | 2012123.67 | 2012123.67 | 3349250.38 | 3349250.38 | -4555.42 | -4555.42 | [14 empty] | 10957666.05 | 10957666.05 | 0 | 7642333.95 | 7642333.95 | 58.91% | 58.91% | 44900000 | 59300000 | P |  |  | P
Human Settlement Development Grant c/o | [6 empty] | 0 | 20435448 |  |  | 0 | 0 | 21421.49 | 21421.49 | 6632738.49 | 6632738.49 | 10545866.25 | 10545866.25 | [14 empty] | 17200026.23 | 17200026.23 | 226959.32 | 3235421.77 | 3235421.77 | 84.17% | 84.17% |  |  | P |  |  | P
Human Settlement Development Grant-MPCC | 0 | 0 | 0 | 0 | 0 |  | 10068500 | 10068500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 2245300 | 10068500 | 10068500 | 0% | 0% | 13068500 | 0 | P |  |  | P
Total Grants | 272144583 | 272144583 | 272144583 | -17884413 | 254260170 | 0 | 700781726 | 724619137 | 4259119.2 | 4565114.85 | 31571563.96 | 35305349.67 | 43374590.56 | 48614017.93 | 65377822.65 | 72026150.98 | 42862985.96 | 48414227.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187446082.33 | 208924860.5 | 60360188.95 | 537173054.67 | 515694276.5 | 25.87% | 28.83% | 1125256600 | 1114671100
TOTAL PER FUNDING | 272144583 | 272144583 | 294023214.88 | 12199892 | 306223106.88 | 0 | 942007423 | 1056484706 | 4279296.15 | 4585291.8 | 36998451.88 | 40732237.59 | 63771348.91 | 69010776.28 | 82385306.63 | 89033634.96 | 52978431.48 | 58529672.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240412835.05 | 261891613.22 | 120394360.21 | 816071870.95 | 794593092.78 | 22.76% | 24.79% | 1382127261 | 1385226151 | 0 | 0 | 0 |  | 673289000 | 1060458000 | 1063775000
C5C | 2013/2014 Approved Budget | 2013/2014 Rollover Adjustment Budget | 2013/2014 Conditional Grants Rollover Adjustment Budget | Mid-Year Adjustments | 2013/2014 Mid-Year Adjusted Budget | 2014/2015 DoRA | 2014/2015 Approved Capital Budget | 2014/2015 Rollover Adjustment Budget | July 2014 | July 2014 (VAT incl) | August 2014 | August 2014 (VAT incl) | September 2014 | September 2014 (VAT incl) | October 2014 | October 2014 (VAT incl) | November 2014 | November 2014 (VAT incl) | December 2014 | December 2014 (VAT incl) | January 2015 | January 2015 (VAT incl) | February 2015 | February 2015 (VAT incl) | March 2015 | March 2015 (VAT incl) | April 2015 | April 2015 (VAT incl) | May 2015 | May 2015 (VAT incl) | June 2015 | June 2015 (VAT incl) | YTD Expenditure | YTD Expenditure (VAT) incl) | Commitments as per Venus | Variance | Variance ( VAT incl) | % Expenditure | % Expenditure (VAT incl)
1.1 - Office of The Director of Executive Support | 0 | 12750000 | 12750000 | -10000000 | 2750000 |  | 500000 | 6270397 | 0 | 0 | 0 | 0 | 0 | 0 | 279834.11 | 279834.11 | 0 | 0 | [14 empty] | 279834.11 | 279834.11 | 10235.22 | 5990562.89 | 5990562.89 | 55.97% | 55.97%
1.11 - Development Co-Operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 458860 | 458860 | #DIV/0! | #DIV/0!
1.2 - Executive Mayor, Speaker & Mayoral Committee | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
1.8 - City Hall | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2.1 - Office of The Municipal Manager & Support Services | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 7000000 | 7000000 | 0 | 0 | 170805 | 194717.7 | 107792 | 107792 | 2712625.98 | 3089388.19 | 0 | 0 | [14 empty] | 2991222.98 | 3391897.89 | 1277702.94 | 4008777.02 | 3608102.11 | 42.73% | 48.46%
3.1 - Mdantsane Urban Renewal Unit | [6 empty] | 10068500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0%
3.2 - Office of The Chief Operations Officer | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 0 | 0 | 14706.1 | 14706.1 | 0 | 0 | 45043.26 | 45043.26 | 0 | 0 | [14 empty] | 59749.36 | 59749.36 | 52121.81 | 440250.64 | 440250.64 | 11.95% | 11.95%
3.3 - Housing Department | 0 | 0 | 0 | 0 | 0 |  | 79567608 | 100305255 | 4419423.27 | 4723842.52 | 7514624.7 | 8063055.47 | 9250670.49 | 10022887.2 | 14732515.11 | 15423708.66 | 11308976.93 | 11416450.18 | [14 empty] | 47226210.5 | 49649944.03 | 475687.92 | 53079044.5 | 50655310.97 | 59.35% | 62.4%
4.1 - Office of The Director of Finance | [6 empty] | 500000 | 931902 | 19074.32 | 19074.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 19074.32 | 19074.32 | 117610.12 | 912827.68 | 912827.68 | 3.815% | 3.815%
4.4 - Asset Risk & Financial Services | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 13675.44 | 13675.44 | 17870 | 17870 | 56239.1 | 56239.1 | [14 empty] | 87784.54 | 87784.54 | 1833577.36 | 9912215.46 | 9912215.46 | 0.8778% | 0.8778%
4.3 - Budget Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
4.7 - Salary Office | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
4.9 - Consolidated Billing & Miscellaneous Revenue Office | [6 empty] | 350000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 166000 | 350000 | 350000 | 0% | 0%
4.10 - Debtors Management Office | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
4.11 - Customer Care Office | [6 empty] | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 1500000 | 1500000 | 0% | 0%
5.1 - Office of The Director of Corporate Services | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 500000 | 500000 | 0% | 0%
5.4 - Auxilliary & Telecommunication Support | [6 empty] | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 150000 | 150000 | #DIV/0! | #DIV/0!
5.6 - Management Information Services | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 18016133 | 0 | 0 | 0 | 0 | 587015.67 | 587015.67 | 353865.69 | 353865.69 | 2000112.65 | 2000112.65 | [14 empty] | 2940994.01 | 2940994.01 | 676253.25 | 15075138.99 | 15075138.99 | 29.41% | 29.41%
5.7 - H.R. Administration | 0 | 0 | 0 | 0 | 0 |  | 2100000 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 2100000 | 2100000 | 0% | 0%
5.8 - Occupational Risk Management | [6 empty] | 2500000 | 2500000 | 0 | 0 | 0 | 0 | 2761.12 | 2761.12 | 0 | 0 | 0 | 0 | [14 empty] | 2761.12 | 2761.12 | 0 | 2497238.88 | 2497238.88 | 0.1104% | 0.1104%
5.9 - Labour Relations | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
5.10 - Organisational Development | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
6.1 - Office of The Director of Engineering Services | [6 empty] | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 133843.34 | 500000 | 500000 | 0% | 0%
6.9 - Sewerage Admin | 0 | 0 | 0 | 0 | 0 | 0 | 216507892 | 220656160 | -199830.91 | -199830.91 | 10076331.12 | 11392071.7 | 7571347.35 | 9263739.91 | 7829714.12 | 8877686.14 | 6523226.26 | 7436477.93 | [14 empty] | 31800787.94 | 36770144.77 | 13005472.22 | 188855372.06 | 183886015.23 | 14.69% | 16.98%
6.20 - Water Administration | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 97688726 | 95114971 | 0 | 0 | 1847692.21 | 2052472.42 | 2223512.66 | 2348646.58 | 2998073.18 | 3218272.85 | 5638393.1 | 6167568.1 | [14 empty] | 12707671.15 | 13786959.95 | 12822704.31 | 82407299.85 | 81328011.05 | 13.01% | 14.11%
6.25 - Water Treatment Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
6.34 - Roads Administration | [6 empty] | 198000000 | 198000000 | -47814.16 | -47814.16 | 9974048.56 | 11314616.13 | 19383637.41 | 21311489.23 | 24278224.45 | 27513048.86 | 16280303.27 | 18883691.01 | [14 empty] | 69868399.53 | 78975031.07 | 25985799.78 | 128131600.47 | 119024968.93 | 35.29% | 39.89%
6.36 - Roads and Stormwater Drainage | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
6.43 - Fleet Management - Braelyn | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 18300000 | 25297668 | 0 | 0 | 1888532.64 | 1888532.64 | 10484165.53 | 10484165.53 | 4549898.98 | 4549898.98 | 0 | 0 | [14 empty] | 16922597.15 | 16922597.15 | 0 | 8375070.85 | 8375070.85 | 92.47% | 92.47%
6.46 - Electricity Planning & Design | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 134699000 | 134699000 | 34346 | 34346 | 966172.74 | 984607.28 | 8548369.41 | 9024179.81 | 19438470.71 | 20377347.17 | 5787043.67 | 6863002.8 | [14 empty] | 34774402.53 | 37283483.06 | 12133183.24 | 99924597.47 | 97415516.94 | 25.82% | 27.68%
7.1 - Office of The Director of Planning & Economic Dev. | [6 empty] | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 5100 | 5100 | 2418 | 2418 | [14 empty] | 7518 | 7518 | 98256.89 | 492482 | 492482 | 1.504% | 1.504%
7.11 - City Planning | [6 empty] | 0 | 5395309 | 0 | 0 | 0 | 0 | 1609065.89 | 1609065.89 | 478955.34 | 478955.34 | 571594.05 | 571594.05 | [14 empty] | 2659615.28 | 2659615.28 | 2553658.2 | 2735693.72 | 2735693.72 | #DIV/0! | #DIV/0!
7.12 - Architecture | 0 | 0 | 0 | 0 | 0 |  | 5000000 | 5477792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 797099.25 | 5477792 | 5477792 | 0% | 0%
7.13 - Land Administration | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 5500000 | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 5500000 | 5500000 | 0% | 0%
7.16 - Building Maintenance - Coastal / Central | [6 empty] | 9895288 | 5395288 | 0 | 0 | 1146359.07 | 1146359.07 | -1146359.07 | -1146359.07 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 5395288 | 5395288 | 0% | 0%
7.30 - Transport Planning & Operations Admin | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 24000000 | 24256818 | 52995 | 54571.4 | 1754959.43 | 2031059.23 | 1633771.02 | 1862498.99 | 922399.1 | 923975.5 | 2001123.46 | 2261721.83 | [14 empty] | 6365248.01 | 7133826.95 | 4534744.42 | 17891569.99 | 17122991.05 | 26.52% | 29.72%
7.35 - Local Economic Development | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 10000000 | 10000000 | 0% | 0%
7.36 - Market | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
8.1 - Office of The Director of Health & Public Safety | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63999 | 63999 | [14 empty] | 63999 | 63999 | 48170.21 | 436001 | 436001 | 12.8% | 12.8%
8.3 - Health Administration | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
8.4 - Health Support | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 0 | 216000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 216000 | 216000 | #DIV/0! | #DIV/0!
8.12 - Public Safety Administration | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
8.13 - Fire and Rescue Services | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 4000000 | 4965909 | 0 | 0 | 0 | 0 | 79776.8 | 79776.8 | 0 | 0 | 0 | 0 | [14 empty] | 79776.8 | 79776.8 | 0 | 4886132.2 | 4886132.2 | 1.994% | 1.994%
8.14 - Security Services | 0 | 0 | 0 | 0 | 0 | 0 | 2100000 | 3336101 | 0 | 0 | 761505.76 | 761505.76 | -444544.6 | -444544.6 | 177174.39 | 177174.39 | 117018.27 | 117018.27 | [14 empty] | 611153.82 | 611153.82 | 0 | 2724947.18 | 2724947.18 | 29.1% | 29.1%
8.15 - Traffic Administration | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
8.16 - Traffic Control | [6 empty] | 3200000 | 3200000 | 1102.63 | 1102.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 1102.63 | 1102.63 | 2082357.5 | 3198897.37 | 3198897.37 | 0.03446% | 0.03446%
8.18 - Vehicle Test Station / Examination | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 0 | 798970 | 0 | 0 | 0 | 0 | 366421.75 | 366421.75 | 0 | 0 | 44666.78 | 44666.78 | [14 empty] | 411088.53 | 411088.53 | 155061.1 | 387881.47 | 387881.47 | #DIV/0! | #DIV/0!
8.23 - Disaster Management | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
9.1 - Office of The Director of Community Services | [6 empty] | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24411.1 | 24411.1 | [14 empty] | 24411.1 | 24411.1 | 53866.28 | 475588.9 | 475588.9 | 4.882% | 4.882%
9.2 - Cleansing Administration Support | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
9.4 - Environmental Services | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 4196.91 | 4196.91 | 0 | 0 | [14 empty] | 4196.91 | 4196.91 | 908140.14 | 1995803.09 | 1995803.09 | 0.2098% | 0.2098%
9.7 - Interments | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 10000000 | 11700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284773.45 | 324641.73 | [14 empty] | 284773.45 | 324641.73 | 4740432.19 | 11415226.55 | 11375358.27 | 2.848% | 3.246%
9.14 - Halls | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 21307198 | 0 | 0 | 47492.13 | 52755.03 | 121503.65 | 138514.16 | 0 | 0 | 502484.64 | 524012.31 | [14 empty] | 671480.42 | 715281.5 | 3897554.5 | 20635717.58 | 20591916.5 | 6.715% | 7.153%
9.16 - Sportsfields | 0 | 0 | 0 | 0 | 0 |  | 23030409 | 26101354 | 0 | 0 | 190000 | 190000 | 928123.32 | 928406.8 | 1322687.35 | 1459610.96 | 195720 | 195720 | [14 empty] | 2636530.67 | 2773737.76 | 126320 | 23464823.33 | 23327616.24 | 11.45% | 12.04%
9.17 - Swimming Pools | [6 empty] | 2000000 | 2668126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128560 | 128560 | [14 empty] | 128560 | 128560 | 37129 | 2539566 | 2539566 | 6.428% | 6.428%
9.18 - Aquarium | [6 empty] | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 1000000 | 1000000 | 0% | 0%
9.19 - Zoo | [6 empty] | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 1000000 | 1000000 | 0% | 0%
9.20 - Beaches | [6 empty] | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 1000000 | 1000000 | 0% | 0%
9.22 - Cleansing Administration Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
9.23 - Refuse Removal | 0 | 0 | 0 | 0 | 0 |  | 0 | 8804587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 7288444.3 | 8804587 | 8804587 | #DIV/0! | #DIV/0!
9.27 - E.L Regional Waste Disposal Site & Transfer Station | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 36000000 | 86010908 | 0 | 0 | 645222.42 | 645779.06 | 2450643.07 | 2450643.07 | 2238657.95 | 2238657.95 | 1447367.75 | 1447367.75 | [14 empty] | 6781891.19 | 6782447.83 | 24382934.72 | 79229016.81 | 79228460.17 | 18.84% | 18.84%
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 942007423 | 1056484706 | 4279296.15 | 4585291.8 | 36998451.88 | 40732237.59 | 63771348.91 | 69010776.28 | 82385306.63 | 89033634.96 | 52978431.48 | 58529672.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240412835.05 | 261891613.22 | 120394360.21 | 816071870.95 | 794593092.78 | 25.52% | 27.8%
1056484706
942007423
0
0
C5 | 2013/2014 Approved Budget | 2013/2014 Rollover Adjustment Budget | 2013/2014 Conditional Grants Rollover Adjustment Budget | Mid-Year Adjustments | 2013/2014 Mid-Year Adjusted Budget | 2014/2015 DoRA | 2014/2015 Approved Capital Budget | 2014/2015 Rollover Adjustment Budget | July 2014 | July 2014 (VAT incl) | August 2014 | August 2014 (VAT incl) | September 2014 | September 2014 (VAT incl) | October 2014 | October 2014 (VAT incl) | November 2014 | November 2014 (VAT incl) | December 2014 | December 2014 (VAT incl) | January 2015 | January 2015 (VAT incl) | February 2015 | February 2015 (VAT incl) | March 2015 | March 2015 (VAT incl) | April 2015 | April 2015 (VAT incl) | May 2015 | May 2015 (VAT incl) | June 2015 | June 2015 (VAT incl) | YTD Expenditure | YTD Expenditure (VAT) incl) | Commitments as per Venus | Variance | Variance ( VAT incl) | % Expenditure | % Expenditure (VAT incl)
Capital Expenditure - Standard
Governance and administration | #REF! | #REF! | #REF! | #REF! | #REF! |  | 34950000 | 49765292 | 19074.32 | 19074.32 | 170805 | 194717.7 | 711244.23 | 711244.23 | 3364195.78 | 3740957.99 | 2056351.75 | 2056351.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6321671.08 | 6722345.99 | 4081378.89 | 43443620.92 | 43042946.01 | 18.09% | 19.23% | 53478000 | 50944000
Executive and council | #REF! | #REF! | #REF! | #REF! | #REF! |  | 7500000 | 13729257 | 0 | 0 | 170805 | 194717.7 | 107792 | 107792 | 2992460.09 | 3369222.3 | 0 | 0 | [14 empty] | 3271057.09 | 3671732 | 1287938.16 | 10458199.91 | 10057525 | 43.61% | 48.96% | 19378000 | 20244000
Budget and treasury office | #REF! | #REF! | #REF! | #REF! | #REF! |  | 12350000 | 12769902 | 19074.32 | 19074.32 | 0 | 0 | 13675.44 | 13675.44 | 17870 | 17870 | 56239.1 | 56239.1 | [14 empty] | 106858.86 | 106858.86 | 2117187.48 | 12663043.14 | 12663043.14 | 0.8653% | 0.8653% | 12000000 | 10500000
Corporate services | #REF! | #REF! | #REF! | #REF! | #REF! |  | 15100000 | 23266133 | 0 | 0 | 0 | 0 | 589776.79 | 589776.79 | 353865.69 | 353865.69 | 2000112.65 | 2000112.65 | [14 empty] | 2943755.13 | 2943755.13 | 676253.25 | 20322377.87 | 20322377.87 | 19.5% | 19.5% | 22100000 | 20200000
Community and public safety | #REF! | #REF! | #REF! | #REF! | #REF! |  | 140466517 | 168742787 | 4420525.9 | 4724945.15 | 8528328.69 | 9082022.36 | 10301951.41 | 11091462.11 | 16281617.02 | 17109734.18 | 12257276.72 | 12386277.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51789699.74 | 54394441.44 | 7799279.46 | 116953087.26 | 114348345.56 | 36.87% | 38.72% | 204718500 | 317214685
Community and social services | #REF! | #REF! | #REF! | #REF! | #REF! |  | 12500000 | 23807198 | 0 | 0 | 47492.13 | 52755.03 | 121503.65 | 138514.16 | 4196.91 | 4196.91 | 526895.74 | 548423.41 | [14 empty] | 700088.43 | 743889.51 | 4859560.92 | 23107109.57 | 23063308.49 | 5.601% | 5.951% | 9500000 | 9500000
Sport and recreation | #REF! | #REF! | #REF! | #REF! | #REF! |  | 28030409 | 31101354 | 0 | 0 | 190000 | 190000 | 928123.32 | 928406.8 | 1322687.35 | 1459610.96 | 195720 | 195720 | [14 empty] | 2636530.67 | 2773737.76 | 126320 | 28464823.33 | 28327616.24 | 9.406% | 9.895% | 21750000 | 19750000
Public safety | #REF! | #REF! | #REF! | #REF! | #REF! |  | 9800000 | 13016980 | 1102.63 | 1102.63 | 761505.76 | 761505.76 | 1653.95 | 1653.95 | 177174.39 | 177174.39 | 225684.05 | 225684.05 | [14 empty] | 1167120.78 | 1167120.78 | 2285588.81 | 11849859.22 | 11849859.22 | 11.91% | 11.91% | 10500000 | 21200000
Housing | #REF! | #REF! | #REF! | #REF! | #REF! |  | 90136108 | 100817255 | 4419423.27 | 4723842.52 | 7529330.8 | 8077761.57 | 9250670.49 | 10022887.2 | 14777558.37 | 15468751.92 | 11308976.93 | 11416450.18 | [14 empty] | 47285959.86 | 49709693.39 | 527809.73 | 53531295.14 | 51107561.61 | 52.46% | 55.15% | 162968500 | 266764685
Health | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
Economic and environmental services | #REF! | #REF! | #REF! | #REF! | #REF! |  | 262895288 | 266225207 | 5180.84 | 6757.24 | 12875367.06 | 14492034.43 | 21480115.25 | 23636695.04 | 25684678.89 | 28921079.7 | 19140212.23 | 22044066.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79185554.27 | 89100633.03 | 38709990.73 | 187039652.73 | 177124573.97 | 30.12% | 33.89% | 605220661 | 591655051
Planning and development | #REF! | #REF! | #REF! | #REF! | #REF! |  | 54895288 | 56525207 | 52995 | 54571.4 | 2901318.5 | 3177418.3 | 2096477.84 | 2325205.81 | 1406454.44 | 1408030.84 | 2575135.51 | 2835733.88 | [14 empty] | 9032381.29 | 9800960.23 | 7983758.76 | 47492825.71 | 46724246.77 | 16.45% | 17.85% | 52220661 | 83655051
Road transport | #REF! | #REF! | #REF! | #REF! | #REF! |  | 198000000 | 198000000 | -47814.16 | -47814.16 | 9974048.56 | 11314616.13 | 19383637.41 | 21311489.23 | 24278224.45 | 27513048.86 | 16280303.27 | 18883691.01 | [14 empty] | 69868399.53 | 78975031.07 | 25985799.78 | 128131600.47 | 119024968.93 | 35.29% | 39.89% | 545000000 | 500000000
Environmental protection | #REF! | #REF! | #REF! | #REF! | #REF! |  | 10000000 | 11700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284773.45 | 324641.73 | [14 empty] | 284773.45 | 324641.73 | 4740432.19 | 11415226.55 | 11375358.27 | 2.848% | 3.246% | 8000000 | 8000000
Trading services | #REF! | #REF! | #REF! | #REF! | #REF! |  | 503195618 | 571251420 | -165484.91 | -165484.91 | 15423951.13 | 16963463.1 | 31278038.02 | 33571374.9 | 37054814.94 | 39261863.09 | 19524590.78 | 22042976.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103115909.96 | 111674192.76 | 69669867.79 | 468135510.04 | 459577227.24 | 20.49% | 22.19% | 518210100 | 424912415
Electricity | #REF! | #REF! | #REF! | #REF! | #REF! |  | 152999000 | 159996668 | 34346 | 34346 | 2854705.38 | 2873139.92 | 19032534.94 | 19508345.34 | 23988369.69 | 24927246.15 | 5787043.67 | 6863002.8 | [14 empty] | 51696999.68 | 54206080.21 | 12133183.24 | 108299668.32 | 105790587.79 | 33.79% | 35.43% | 160500000 | 166500000
Water | #REF! | #REF! | #REF! | #REF! | #REF! |  | 97688726 | 95114971 | 0 | 0 | 1847692.21 | 2052472.42 | 2223512.66 | 2348646.58 | 2998073.18 | 3218272.85 | 5638393.1 | 6167568.1 | [14 empty] | 12707671.15 | 13786959.95 | 12822704.31 | 82407299.85 | 81328011.05 | 13.01% | 14.11% | 91000000 | 91000000
Waste water management | #REF! | #REF! | #REF! | #REF! | #REF! |  | 216507892 | 220656160 | -199830.91 | -199830.91 | 10076331.12 | 11392071.7 | 7571347.35 | 9263739.91 | 7829714.12 | 8877686.14 | 6523226.26 | 7436477.93 | [14 empty] | 31800787.94 | 36770144.77 | 13005472.22 | 188855372.06 | 183886015.23 | 14.69% | 16.98% | 230000000 | 137000000
Waste management | #REF! | #REF! | #REF! | #REF! | #REF! |  | 36000000 | 95483621 | 0 | 0 | 645222.42 | 645779.06 | 2450643.07 | 2450643.07 | 2238657.95 | 2238657.95 | 1575927.75 | 1575927.75 | [14 empty] | 6910451.19 | 6911007.83 | 31708508.02 | 88573169.81 | 88572613.17 | 19.2% | 19.2% | 36710100 | 30412415
Other | #REF! | #REF! | #REF! | #REF! | #REF! |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 133843.34 | 500000 | 500000 | 0% | 0% | 500000 | 500000
Total Capital Expenditure - Standard | #REF! | #REF! | #REF! | #REF! | #REF! |  | 942007423 | 1056484706 | 4279296.15 | 4585291.8 | 36998451.88 | 40732237.59 | 63771348.91 | 69010776.28 | 82385306.63 | 89033634.96 | 52978431.48 | 58529672.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240412835.05 | 261891613.22 | 120394360.21 | 816071870.95 | 794593092.78 | 25.52% | 27.8% | 1382127261 | 1385226151
[7 empty] | 942007423 | 1056484706
[7 empty] | 0 | 0
[41 empty] | DoRA |  |  |  |  | 673289000 | 700458000 | 743775000
[41 empty] | Diff |  |  |  |  | 0 | -360000000 | -320000000 | USD
|  |  |  | 189271546 |  | 230735570 | 667025500 | [32 empty] | 690810100
[6 empty] | 21156250 | 31264500 | [32 empty] | 32147900
|  |  |  | 189271546 | 0 | 251891820 | 698290000 | [32 empty] | 722958000
|  |  |  | 176071546 |  | 613305000 | 698290000 | [32 empty] | 722958000
|  |  |  | 803061 |  | 361413180 | 0 | [32 empty] | 0
12396939
2014/2015 - 2016/2017 CAPITAL BUDGET PER DIRECTORATE
Directorate | 2013/2014 Approved Budget | 2013/2014 Rollover Adjustment Budget | 2013/2014 Conditional Grants Rollover Adjustment Budget | Mid-Year Adjustments | 2013/2014 Mid-Year Adjusted Budget | 2014/2015 DoRA | 2014/2015 Approved Capital Budget | 2014/2015 Rollover Adjustment Budget | July 2014 | July 2014 (VAT incl) | August 2014 | August 2014 (VAT incl) | September 2014 | September 2014 (VAT incl) | October 2014 | October 2014 (VAT incl) | November 2014 | November 2014 (VAT incl) | December 2014 | December 2014 (VAT incl) | January 2015 | January 2015 (VAT incl) | February 2015 | February 2015 (VAT incl) | March 2015 | March 2015 (VAT incl) | April 2015 | April 2015 (VAT incl) | May 2015 | May 2015 (VAT incl) | June 2015 | June 2015 (VAT incl) | YTD Expenditure | YTD Expenditure (VAT) incl) | Commitments as per Venus | Variance | Variance ( VAT incl) | % Expenditure | % Expenditure (VAT incl) | 2015/2016 Capital Budget | 2016/2017 Capital Budget |  | 2016/2017 Capital Budget
1. Executive Support Services | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 6846757 | 0 | 0 | 0 | 0 | 0 | 0 | 287453.11 | 287453.11 | 0 | 0 | [14 empty] | 287453.11 | 287453.11 | 40637.18 | 6559303.89 | 6559303.89 | 4.198% | 4.198% | 500000 | 500000 |  | 500000
2. Municipal Manager's Office | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 7000000 | 7008500 | 0 | 0 | 170805 | 194717.7 | 107792 | 107792 | 2712625.98 | 3089388.19 | 0 | 0 | [14 empty] | 2991222.98 | 3391897.89 | 1283619.13 | 4017277.02 | 3616602.11 | 42.68% | 48.4% | 18878000 | 19744000 |  | 19744000 |  |  |  | 77950000
3. Human Settlements | 0 | 0 | 0 | 0 | 0 | 0 | 90136108 | 100830255 | 4419423.27 | 4723842.52 | 7529330.8 | 8077761.57 | 9250670.49 | 10022887.2 | 14777558.37 | 15468751.92 | 11319802.93 | 11427276.18 | [14 empty] | 47296785.86 | 49720519.39 | 527809.73 | 53533469.14 | 51109735.61 | 46.91% | 49.31% | 162968500 | 266764685 |  | 0 |  |  |  | 321031108
4. Directorate of Financial Services | 0 | 0 | 0 | 0 | 0 |  | 2350000 | 2825902 | 19074.32 | 19074.32 | 0 | 0 | 0 | 0 | 10251 | 10251 | 24913.5 | 24913.5 | [14 empty] | 54238.82 | 54238.82 | 283610.12 | 2771663.18 | 2771663.18 | 1.919% | 1.919% | 2000000 | 500000 |  | 500000 |  |  |  | 398981108
5. Directorate of Corporate Services | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 15100000 | 23437633 | 0 | 0 | 0 | 0 | 589776.79 | 589776.79 | 353865.69 | 353865.69 | 2010819.65 | 2010819.65 | [14 empty] | 2954462.13 | 2954462.13 | 682169.44 | 20483170.87 | 20483170.87 | 12.61% | 12.61% | 22100000 | 20200000 |  | 20200000
6. Directorate of Engineering Services |  |  | 122746331.88 | 32584305 | 155330636.88 |  | 665695618 | 674361199 | -213299.07 | -213299.07 | 24752777.27 | 27632300.17 | 48211032.36 | 52432221.06 | 59094381.44 | 64536254 | 34228966.3 | 39350739.84 | [14 empty] | 166073858.3 | 183738216 | 64081002.89 | 508287340.7 | 490622983 | 24.63% | 27.25% | 1027000000 | 895000000 |  | 895000000 |  |  |  | 255845288
7. Directorate of Development Planning |  |  | 12000000 | 800000 | 12800000 | 12000000 | 44895288 | 46533707 | 52995 | 54571.4 | 2901318.5 | 3177418.3 | 2096477.84 | 2325205.81 | 1406454.44 | 1408030.84 | 2575135.51 | 2835733.88 | [14 empty] | 9032381.29 | 9800960.23 | 7983758.76 | 37501325.71 | 36732746.77 | 19.41% | 21.06% | 42220661 | 73655051 |  | 156655051 |  |  |  | 673289000
8. Directorate of Economic Development | [6 empty] | 10000000 | 10026000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 20802 | 10026000 | 10026000 | 0% | 0% | 10000000 | 10000000
9. Directorate of Health & Public Safety |  |  | 2250000 | -2000000 | 250000 | 2250000 | 9800000 | 14466980 | 1102.63 | 1102.63 | 761505.76 | 761505.76 | 1653.95 | 1653.95 | 177174.39 | 177174.39 | 235476.65 | 235476.65 | [14 empty] | 1176913.38 | 1176913.38 | 2354788.83 | 13290066.62 | 13290066.62 | 8.135% | 8.135% | 10500000 | 21200000 |  | 21200000 |  |  |  | 929134288
10 .Directorate of Community Services | 48080943 | 48080943 | 48080943 | -8384413 | 39696530 | 48080943 | 86530409 | 163865123 | 0 | 0 | 882714.55 | 888534.09 | 3513945.48 | 3531239.47 | 3565542.21 | 3702465.82 | 2583316.94 | 2644712.89 | [14 empty] | 10545519.18 | 10766952.27 | 43136162.13 | 153319603.82 | 153098170.73 | 6.435% | 6.571% | 75960100 | 67662415 |  | 67662415
TOTAL DIRECTORATES | 67430943 | 67430943 | 204427274.88 | 12999892 | 217427166.88 | 62330943 | 932007423 | 1050202056 | 4279296.15 | 4585291.8 | 36998451.88 | 40732237.59 | 63771348.91 | 69010776.28 | 82385306.63 | 89033634.96 | 52978431.48 | 58529672.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240412835.05 | 261891613.22 | 120394360.21 | 809789220.95 | 788310442.78 | 22.89% | 24.94% | 1372127261 | 1375226151 |  | 1181461466 |  |  |  | 0.42941
Asset Replacement | 0 | 0 | 0 | 0 | 0 |  | 10000000 | 6282650 | 0 | 0 | [25 empty] | 6282650 | 6282650 | 0% | 0% | 10000000 | 10000000 |  | 10000000
GRAND - TOTAL | 67430943 | 67430943 | 204427274.88 | 12999892 | 217427166.88 | 62330943 | 942007423 | 1056484706 | 4279296.15 | 4585291.8 | 36998451.88 | 40732237.59 | 63771348.91 | 69010776.28 | 82385306.63 | 89033634.96 | 52978431.48 | 58529672.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240412835.05 | 261891613.22 | 120394360.21 | 816071870.95 | 794593092.78 | 22.76% | 24.79% | 1382127261 | 1385226151 |  | 1191461466 |  | 942007423 |  | #REF! |  | 1024127261 | #REF! | #REF! | #REF! | 1069226151
F
A5 - Schedule | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 |  | Budget Year 2014/15 | [32 empty] | Budget Year 2014/15 | Budget Year 2014/15
Capital Expenditure - Standard
Governance and administration | #REF! | #REF! | #REF! | #REF! | #REF! |  | 34950000 | [32 empty] | 53478000 | 50944000
Executive and council | #REF! | #REF! | #REF! | #REF! | #REF! |  | 7500000 | [32 empty] | 19378000 | 20244000
Budget and treasury office | #REF! | #REF! | #REF! | #REF! | #REF! |  | 12350000 | [32 empty] | 12000000 | 10500000
Corporate services | #REF! | #REF! | #REF! | #REF! | #REF! |  | 15100000 | [32 empty] | 22100000 | 20200000
Community and public safety | #REF! | #REF! | #REF! | #REF! | #REF! |  | 140466517 | [32 empty] | 204718500 | 317214685
Community and social services | #REF! | #REF! | #REF! | #REF! | #REF! |  | 12500000 | [32 empty] | 9500000 | 9500000
Sport and recreation | #REF! | #REF! | #REF! | #REF! | #REF! |  | 28030409 | [32 empty] | 21750000 | 19750000
Public safety | #REF! | #REF! | #REF! | #REF! | #REF! |  | 9800000 | [32 empty] | 10500000 | 21200000
Housing | #REF! | #REF! | #REF! | #REF! | #REF! |  | 90136108 | [32 empty] | 162968500 | 266764685
Health | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Economic and environmental services | #REF! | #REF! | #REF! | #REF! | #REF! |  | 262895288 | [32 empty] | 605220661 | 591655051
Planning and development | #REF! | #REF! | #REF! | #REF! | #REF! |  | 54895288 | [32 empty] | 52220661 | 83655051
Road transport | #REF! | #REF! | #REF! | #REF! | #REF! |  | 198000000 | [32 empty] | 545000000 | 500000000
Environmental protection | #REF! | #REF! | #REF! | #REF! | #REF! |  | 10000000 | [32 empty] | 8000000 | 8000000
Trading services | #REF! | #REF! | #REF! | #REF! | #REF! |  | 503195618 | [32 empty] | 518210100 | 424912415
Electricity | #REF! | #REF! | #REF! | #REF! | #REF! |  | 152999000 | [32 empty] | 160500000 | 166500000
Water | #REF! | #REF! | #REF! | #REF! | #REF! |  | 97688726 | [32 empty] | 91000000 | 91000000
Waste water management | #REF! | #REF! | #REF! | #REF! | #REF! |  | 216507892 | [32 empty] | 230000000 | 137000000
Waste management | #REF! | #REF! | #REF! | #REF! | #REF! |  | 36000000 | [32 empty] | 36710100 | 30412415
Other | #REF! | #REF! | #REF! | #REF! | #REF! |  | 500000 | [32 empty] | 500000 | 500000
Total Capital Expenditure - Standard | #REF! | #REF! | #REF! | #REF! | #REF! |  | 942007423 | [32 empty] | 1382127261 | 1385226151
Funded by:
National Government | #REF! | #REF! | #REF! | #REF! | #REF! |  | 671924500 | [32 empty] | 1067288100 | 1055371100
Provincial Government | #REF! | #REF! | #REF! | #REF! | #REF! |  | 28857226 | [32 empty] | 57968500 | 59300000
District Municipality | 0 | 0 | 0 | 0 | 0 |  | 0 | [32 empty] | 0 | 0
Other transfers and grants | 0 | 0 | 0 | 0 | 0 |  | 0 | [32 empty] | 0 | 0
Transfers recognised - capital | #REF! | #REF! | #REF! | #REF! | #REF! |  | 700781726 | [32 empty] | 1125256600 | 1114671100
Public contributions & donations | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Borrowing | 0 | 0 | 0 | 0 | 0 |  | 0 | [32 empty] | 0 | 0
Internally generated funds | #REF! | #REF! | #REF! | #REF! | #REF! |  | 241225697 | [32 empty] | 256870661 | 270555051
Total Capital Funding | #REF! | #REF! | #REF! | #REF! | #REF! |  | 942007423 | [32 empty] | 1382127261 | 1385226151
Q
SA - 34a - Schedule | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 |  | Budget Year 2014/15 | [32 empty] | Budget Year 2014/15 | Budget Year 2014/15
Capital expenditure on NEW ASSETS by Asset Class/Sub-class
Infrastructure | #REF! | #REF! | #REF! | #REF! | #REF! |  | 225500000 | [32 empty] | 577210100 | 540412415
Infrastructure - Road transport | #REF! | #REF! | #REF! | #REF! | #REF! |  | 110000000 | [32 empty] | 450000000 | 400000000
Roads, Pavements & Bridges | #REF! | #REF! | #REF! | #REF! | #REF! |  | 110000000 | [32 empty] | 450000000 | 400000000
Storm water
Infrastructure - Electricity | #REF! | #REF! | #REF! | #REF! | #REF! |  | 45500000 | [32 empty] | 50500000 | 40500000
Generation
Transmission & Reticulation | #REF! | #REF! | #REF! | #REF! | #REF! |  | 45500000 | [32 empty] | 50500000 | 40500000
Street Lighting | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Infrastructure - Water | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Dams & Reservoirs
Water purification
Reticulation | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Infrastructure - Sanitation | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Reticulation | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Sewerage purification
Infrastructure - Other | #REF! | #REF! | #REF! | #REF! | #REF! |  | 70000000 | [32 empty] | 76710100 | 99912415
Waste Management | #REF! | #REF! | #REF! | #REF! | #REF! |  | 36000000 | [32 empty] | 36710100 | 30412415
Transportation | #REF! | #REF! | #REF! | #REF! | #REF! |  | 24000000 | [32 empty] | 30000000 | 59500000
Gas
Other | #REF! | #REF! | #REF! | #REF! | #REF! |  | 10000000 | [32 empty] | 10000000 | 10000000
Community | #REF! | #REF! | #REF! | #REF! | #REF! |  | 22000000 | [32 empty] | 17000000 | 17000000
Parks & gardens | #REF! | #REF! | #REF! | #REF! | #REF! |  | 2000000 | [32 empty] | 0 | 0
Sportsfields & stadia | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Swimming pools | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Community halls | #REF! | #REF! | #REF! | #REF! | #REF! |  | 10000000 | [32 empty] | 9000000 | 9000000
Libraries | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Recreational facilities | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Fire, safety & emergency
Security and policing
Buses | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Clinics | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Museums & Art Galleries
Cemeteries | 0 | 0 | 0 | 0 | 0 |  | 10000000 | [32 empty] | 8000000 | 8000000
Social rental housing
Other | #REF! | #REF! | #REF! | #REF! | #REF!
Heritage assets | 0 | 0 | 0 | 0 | 0 |  | 0 | [32 empty] | 0 | 0
Buildings
Other
Investment properties | #REF! | #REF! | #REF! | #REF! | #REF! |  | 89536108 | [32 empty] | 162318500 | 266264685
Housing development | #REF! | #REF! | #REF! | #REF! | #REF! |  | 89536108 | [32 empty] | 162318500 | 266264685
Other
Other assets | #REF! | #REF! | #REF! | #REF! | #REF! |  | 59650000 | [32 empty] | 78128000 | 84144000
General vehicles | #REF! | #REF! | #REF! | #REF! | #REF! |  | 18600000 | [32 empty] | 18000000 | 18400000
Specialised vehicles | #REF! | #REF! | #REF! | #REF! | #REF! |  | 4000000 | [32 empty] | 4000000 | 4000000
Plant & equipment | #REF! | #REF! | #REF! | #REF! | #REF! |  | 3500000 | [32 empty] | 1500000 | 8300000
Computers - hardware/equipment | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Furniture and other office equipment | #REF! | #REF! | #REF! | #REF! | #REF! |  | 28550000 | [32 empty] | 37750000 | 35700000
Abattoirs
Markets | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Civic Land and Buildings | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Other Buildings
Other Land
Surplus Assets - (Investment or Inventory)
Other | #REF! | #REF! | #REF! | #REF! | #REF! |  | 5000000 | [32 empty] | 16878000 | 17744000
Agricultural assets | 0 | 0 | 0 | 0 | 0 |  | 0 | [32 empty] | 0 | 0
List sub-class
Biological assets | 0 | 0 | 0 | 0 | 0 |  | 0 | [32 empty] | 0 | 0
List sub-class
Intangibles | 0 | 0 | 0 | 0 | 0 |  | 0 | [32 empty] | 0 | 0
Computers - software & programming
Other (list sub-class)
Total Capital Expenditure on new assets | #REF! | #REF! | #REF! | #REF! | #REF! |  | 396686108 | [32 empty] | 834656600 | 907821100
Specialised vehicles | #REF! | #REF! | #REF! | #REF! | #REF! |  | 4000000 | [32 empty] | 4000000 | 4000000
Refuse | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Fire | #REF! | #REF! | #REF! | #REF! | #REF! |  | 4000000 | [32 empty] | 4000000 | 4000000
Conservancy | [6 empty] | 0 | [32 empty] | 0 | 0
Ambulances
SA - 34b - Schedule | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 |  | Budget Year 2014/15 | [32 empty] | Budget Year 2014/15 | Budget Year 2014/15
Capital expenditure on RENEWAL OF EXISTING ASSETS by Asset Class/Sub-class
Infrastructure | #REF! | #REF! | #REF! | #REF! | #REF! |  | 491395618 | [32 empty] | 508000000 | 436000000
Infrastructure - Road transport | #REF! | #REF! | #REF! | #REF! | #REF! |  | 88000000 | [32 empty] | 95000000 | 100000000
Roads, Pavements & Bridges | #REF! | #REF! | #REF! | #REF! | #REF! |  | 88000000 | [32 empty] | 95000000 | 100000000
Storm water | 0 | 0 | 0 | 0 | 0
Infrastructure - Electricity | #REF! | #REF! | #REF! | #REF! | #REF! |  | 89199000 | [32 empty] | 92000000 | 108000000
Generation | 0 | 0 | 0 | 0 | 0
Transmission & Reticulation | #REF! | #REF! | #REF! | #REF! | #REF! |  | 89199000 | [32 empty] | 92000000 | 108000000
Street Lighting | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Infrastructure - Water | #REF! | #REF! | #REF! | #REF! | #REF! |  | 97688726 | [32 empty] | 91000000 | 91000000
Dams & Reservoirs
Water purification
Reticulation | #REF! | #REF! | #REF! | #REF! | #REF! |  | 97688726 | [32 empty] | 91000000 | 91000000
Infrastructure - Sanitation | #REF! | #REF! | #REF! | #REF! | #REF! |  | 216507892 | [32 empty] | 230000000 | 137000000
Reticulation | #REF! | #REF! | #REF! | #REF! | #REF! |  | 216507892 | [32 empty] | 230000000 | 137000000
Sewerage purification
Infrastructure - Other | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Waste Management | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Transportation | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Gas
Other | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Community | #REF! | #REF! | #REF! | #REF! | #REF! |  | 28030409 | [32 empty] | 21750000 | 19750000
Parks & gardens | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Sportsfields & stadia | #REF! | #REF! | #REF! | #REF! | #REF! |  | 24791907 | [32 empty] | 13750000 | 9750000
Swimming pools | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Community halls | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Libraries | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Recreational facilities | #REF! | #REF! | #REF! | #REF! | #REF! |  | 3238502 | [32 empty] | 8000000 | 10000000
Fire, safety & emergency
Security and policing
Buses | [6 empty] | 0 | [32 empty] | 0 | 0
Clinics | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Museums & Art Galleries | #REF! | #REF! | #REF! | #REF! | #REF!
Cemeteries | 0 | 0 | 0 | 0 | 0 |  | 0 | [32 empty] | 0 | 0
Social rental housing
Other | #REF! | #REF! | #REF! | #REF! | #REF!
Heritage assets | 0 | 0 | 0 | 0 | 0 |  | 0 | [32 empty] | 0 | 0
Buildings
Other
Investment properties | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Housing development | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Other
Other assets | #REF! | #REF! | #REF! | #REF! | #REF! |  | 20395288 | [32 empty] | 17720661 | 21655051
General vehicles | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Specialised vehicles | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Plant & equipment | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Computers - hardware/equipment | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Furniture and other office equipment | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Abattoirs
Markets | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Civic Land and Buildings | #REF! | #REF! | #REF! | #REF! | #REF! |  | 20395288 | [32 empty] | 17720661 | 21655051
Other Buildings
Other Land
Surplus Assets - (Investment or Inventory)
Other | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [32 empty] | 0 | 0
Agricultural assets | 0 | 0 | 0 | 0 | 0 |  | 0 | [32 empty] | 0 | 0
List sub-class
Biological assets | 0 | 0 | 0 | 0 | 0 |  | 0 | [32 empty] | 0 | 0
List sub-class
Intangibles | 0 | 0 | 0 | 0 | 0 |  | 0 | [32 empty] | 0 | 0
Computers - software & programming
Other (list sub-class)
Total Capital Expenditure on renewal of assets | #REF! | #REF! | #REF! | #REF! | #REF! |  | 539821315 | [32 empty] | 547470661 | 477405051 |  |  |  |  | 936507423 | -5500000
Specialised vehicles | 0 | 0 | 0 | 0 | 0 |  | 0 | [32 empty] | 0 | 0
Refuse | [6 empty] | 0 | [32 empty] | 0 | 0
Fire | [6 empty] | 0 | [32 empty] | 0 | 0
Conservancy | [6 empty] | 0 | [32 empty] | 0 | 0
Ambulances
2014/2015 - 2016/2017 CAPITAL BUDGET PER SERVICE
Services | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget |  | 2014/2015 Approved Capital Budget | 2014/2015 Rollover Adjustment Budget | July 2014 | July 2014 (VAT incl) | August 2014 | August 2014 (VAT incl) | September 2014 | September 2014 (VAT incl) | October 2014 | October 2014 (VAT incl) | November 2014 | November 2014 (VAT incl) | December 2014 | December 2014 (VAT incl) | January 2015 | January 2015 (VAT incl) | February 2015 | February 2015 (VAT incl) | March 2015 | March 2015 (VAT incl) | April 2015 | April 2015 (VAT incl) | May 2015 | May 2015 (VAT incl) | June 2015 | June 2015 (VAT incl) | YTD Expenditure | YTD Expenditure (VAT) incl) | Commitments as per Venus | Variance | Variance ( VAT incl) | % Expenditure | % Expenditure (VAT incl) | 2015/2016 Draft Capital Budget | 2016/2017 Draft Capital Budget
Water | #REF! | #REF! | 10000000 | 0 | 10000000 |  | 97688726 | 95114971 | 0 | 0 | 1847692.21 | 2052472.42 | 2223512.66 | 2348646.58 | 2998073.18 | 3218272.85 | 5638393.1 | 6167568.1 | [14 empty] | 12707671.15 | 13786959.95 | 12822704.31 | 82407299.85 | 81328011.05 | 13.36% | 14.5% | 91000000 | 91000000
Waste Water | #REF! | #REF! | 57854000 | 0 | 57854000 |  | 216507892 | 220656160 | -199830.91 | -199830.91 | 10076331.12 | 11392071.7 | 7571347.35 | 9263739.91 | 7829714.12 | 8877686.14 | 6523226.26 | 7436477.93 | [14 empty] | 31800787.94 | 36770144.77 | 13005472.22 | 188855372.06 | 183886015.23 | 14.41% | 16.66% | 230000000 | 137000000
Electricity | #REF! | #REF! | 12892331.88 | 29084305 | 41976636.88 |  | 134699000 | 137747400 | 34346 | 34346 | 966172.74 | 984607.28 | 8548369.41 | 9024179.81 | 19438470.71 | 20377347.17 | 5787043.67 | 6863002.8 | [14 empty] | 34774402.53 | 37283483.06 | 12133183.24 | 102972997.47 | 100463916.94 | 25.25% | 27.07% | 142500000 | 148500000
Roads and Stormwater | #REF! | #REF! | 9000000 | 0 | 9000000 |  | 188000000 | 188045000 | -47814.16 | -47814.16 | 9974048.56 | 11314616.13 | 19383637.41 | 21311489.23 | 24278224.45 | 27513048.86 | 16280303.27 | 18883691.01 | [14 empty] | 69868399.53 | 78975031.07 | 25985799.78 | 118176600.47 | 109069968.93 | 37.16% | 42% | 515000000 | 470000000
Housing | #REF! | #REF! | 81695940 | -800000 | 80895940 |  | 89636108 | 100776115 | 4419423.27 | 4723842.52 | 7514624.7 | 8063055.47 | 9250670.49 | 10022887.2 | 14732515.11 | 15423708.66 | 11308976.93 | 11416450.18 | [14 empty] | 47226210.5 | 49649944.03 | 475687.92 | 53549904.5 | 51126170.97 | 46.86% | 49.27% | 162468500 | 266264685
Transport Planning | #REF! | #REF! | 22000000 | 800000 | 22800000 |  | 54895288 | 56559707 | 52995 | 54571.4 | 2901318.5 | 3177418.3 | 2096477.84 | 2325205.81 | 1406454.44 | 1408030.84 | 2575135.51 | 2835733.88 | [14 empty] | 9032381.29 | 9800960.23 | 8004560.76 | 47527325.71 | 46758746.77 | 15.97% | 17.33% | 52220661 | 83655051
Waste Management / Refuse | #REF! | #REF! | 14240000 | 0 | 14240000 | 14240000 | 36300000 | 95783621 | 0 | 0 | 645222.42 | 645779.06 | 2450643.07 | 2450643.07 | 2238657.95 | 2238657.95 | 1575927.75 | 1575927.75 | [14 empty] | 6910451.19 | 6911007.83 | 31734773.67 | 88873169.81 | 88872613.17 | 7.215% | 7.215% | 36710100 | 30412415
Amenities | #REF! | #REF! | 22800000 | -15884413 | 6915587 | 14240000 | 40030409 | 57818502 | 0 | 0 | 237492.13 | 242755.03 | 1063302.41 | 1080596.4 | 1326884.26 | 1463807.87 | 698204.64 | 719732.31 | [14 empty] | 3325883.44 | 3506891.61 | 6633355.64 | 54492618.56 | 54311610.39 | 5.752% | 6.065% | 30750000 | 28750000
Environmental Services | #REF! | #REF! | 11040943 | 7500000 | 18540943 | 14240000 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284773.45 | 324641.73 | [14 empty] | 284773.45 | 324641.73 | 4740432.19 | 9715226.55 | 9675358.27 | 2.848% | 3.246% | 8000000 | 8000000
Health Services | #REF! | #REF! | 0 | 0 | 0 | 14240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
Public Safety | #REF! | #REF! | 2250000 | -2000000 | 250000 | 14240000 | 9800000 | 14466980 | 1102.63 | 1102.63 | 761505.76 | 761505.76 | 1653.95 | 1653.95 | 177174.39 | 177174.39 | 235476.65 | 235476.65 | [14 empty] | 1176913.38 | 1176913.38 | 2354788.83 | 13290066.62 | 13290066.62 | 8.135% | 8.135% | 10500000 | 21200000
Support Services | #REF! | #REF! | 19350000 | -10000000 | 9350000 | 14240000 | 36150000 | 47218582 | 19074.32 | 19074.32 | 185511.1 | 209423.8 | 697568.79 | 697568.79 | 3409239.04 | 3786001.25 | 2070970.25 | 2070970.25 | [14 empty] | 6382363.5 | 6783038.41 | 2503601.65 | 40836218.5 | 40435543.59 | 13.52% | 14.37% | 54978000 | 52444000
Other - BCM Fleet | #REF! | #REF! | 33000000 | 3500000 | 36500000 | 33000000 | 28300000 | 32297668 | 0 | 0 | 1888532.64 | 1888532.64 | 10484165.53 | 10484165.53 | 4549898.98 | 4549898.98 | 0 | 0 | [14 empty] | 16922597.15 | 16922597.15 | 0 | 15375070.85 | 15375070.85 | 52.4% | 52.4% | 48000000 | 48000000
| #REF! | #REF! | 296123214.88 | 12199892 | 308323106.88 |  | 942007423 | 1056484706 | 4279296.15 | 4585291.8 | 36998451.88 | 40732237.59 | 63771348.91 | 69010776.28 | 82385306.63 | 89033634.96 | 52978431.48 | 58529672.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240412835.05 | 261891613.22 | 120394360.21 | 816071870.95 | 794593092.78 | 22.76% | 24.79% | 1382127261 | 1385226151
|  |  | 91695940 | -800000 | 90895940 | -62330943 | 0 | [30 empty] | #DIV/0! | #DIV/0! | 0 | 0 | 0 | -1191461466
KEY OBJECTIVES | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget |  | 2014/2015 Approved Capital Budget | 2014/2015 Rollover Adjustment Budget | July 2014 | July 2014 (VAT incl) | August 2014 | August 2014 (VAT incl) | September 2014 | September 2014 (VAT incl) | October 2014 | October 2014 (VAT incl) | November 2014 | November 2014 (VAT incl) | December 2014 | December 2014 (VAT incl) | January 2015 | January 2015 (VAT incl) | February 2015 | February 2015 (VAT incl) | March 2015 | March 2015 (VAT incl) | April 2015 | April 2015 (VAT incl) | May 2015 | May 2015 (VAT incl) | June 2015 | June 2015 (VAT incl) | YTD Expenditure | YTD Expenditure (VAT) incl) | Commitments as per Venus | Variance | Variance ( VAT incl) | % Expenditure | % Expenditure (VAT incl) | 2015/2016 Capital Budget | 2016/2017 Capital Budget
1.Municipal Transformation and Organisational Development | #REF! | #REF! | #REF! | #REF! | #REF! |  | 15100000 | [30 empty] | 0% | 0% | 22100000 | 20200000
2.Service Delivery and Basic Infrastructure | #REF! | #REF! | #REF! | #REF! | #REF! |  | 901557423 | [30 empty] | 0% | 0% | 1337027261 | 1343526151
3.Local Economic Development | #REF! | #REF! | #REF! | #REF! | #REF! |  | 10000000 | [30 empty] | 0% | 0% | 10000000 | 10000000
4.Municipal Financial Viability and Management | #REF! | #REF! | #REF! | #REF! | #REF! |  | 12350000 | [30 empty] | 0% | 0% | 12000000 | 10500000
5.Good Governance and public Participation | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1000000 | [30 empty] | 0% | 0% | 1000000 | 1000000
TOTAL | #REF! | #REF! | #REF! | #REF! | #REF! |  | 940007423 | [30 empty] | 0% | 0% | 1382127261 | 1385226151
USDG CAPITAL BUDGET PER SERVICE
Services | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget |  | 2014/2015 Approved Capital Budget | 2014/2015 Rollover Adjustment Budget | July 2014 | July 2014 (VAT incl) | August 2014 | August 2014 (VAT incl) | September 2014 | September 2014 (VAT incl) | October 2014 | October 2014 (VAT incl) | November 2014 | November 2014 (VAT incl) | December 2014 | December 2014 (VAT incl) | January 2015 | January 2015 (VAT incl) | February 2015 | February 2015 (VAT incl) | March 2015 | March 2015 (VAT incl) | April 2015 | April 2015 (VAT incl) | May 2015 | May 2015 (VAT incl) | June 2015 | June 2015 (VAT incl) | YTD Expenditure | YTD Expenditure (VAT) incl) | Commitments as per Venus | Variance | Variance ( VAT incl) | % Expenditure | % Expenditure (VAT incl)
Water | #REF! | #REF! | 10000000 | 0 | 10000000 |  | 57500000 | 54926245 | 0 | 0 | 1578845.64 | 1783625.85 | 929320.16 | 1054454.08 | 2757628.97 | 2977828.64 | 2471176.03 | 3000351.03 | [14 empty] | 7736970.8 | 8816259.6 | 12822704.31 | 47189274.2 | 46109985.4 | 14.09% | 16.05%
Waste Water | #REF! | #REF! | 57854000 | 0 | 57854000 |  | 176507892 | 179081647 | -199830.91 | -199830.91 | 10076331.12 | 11392071.7 | 7571347.35 | 9263739.91 | 7821134.12 | 8869106.14 | 6523226.26 | 7436477.93 | [14 empty] | 31792207.94 | 36761564.77 | 13005472.22 | 147289439.06 | 142320082.23 | 17.75% | 20.53%
Electricity | #REF! | #REF! | 12892331.88 | 29084305 | 41976636.88 |  | 27699000 | 27699000 | 0 | 0 | 131675.29 | 150109.83 | 374455.86 | 426879.68 | 1792320.83 | 2028903.03 | 582021.35 | 660557.42 | [14 empty] | 2880473.33 | 3266449.96 | 12133183.24 | 24818526.67 | 24432550.04 | 10.4% | 11.79%
Roads and Stormwater | #REF! | #REF! | 9000000 | 0 | 9000000 |  | 198000000 | 198000000 | -47814.16 | -47814.16 | 9974048.56 | 11314616.13 | 19383637.41 | 21311489.23 | 24278224.45 | 27513048.86 | 16280303.27 | 18883691.01 | [14 empty] | 69868399.53 | 78975031.07 | 25985799.78 | 128131600.47 | 119024968.93 | 35.29% | 39.89%
Housing | #REF! | #REF! | 81695940 | -800000 | 80895940 |  | 60867608 | 60867608 | 2174423.21 | 2478842.46 | 4158777.34 | 4707208.11 | 7217125.33 | 7989342.04 | 4750526.24 | 5441719.79 | 767666.1 | 875139.35 | [14 empty] | 19068518.22 | 21492251.75 | 475687.92 | 41799089.78 | 39375356.25 | 31.33% | 35.31%
Transport Planning | #REF! | #REF! | 22000000 | 800000 | 22800000 |  | 44500000 | 44500000 | 52995 | 54571.4 | 1754959.43 | 2031059.23 | 1633771.02 | 1862498.99 | 922399.1 | 923975.5 | 1878949.14 | 2139547.51 | [14 empty] | 6243073.69 | 7011652.63 | 8004560.76 | 38256926.31 | 37488347.37 | 14.03% | 15.76%
Waste Management / Refuse | #REF! | #REF! | 14240000 | 0 | 14240000 | 14240000 | 26000000 | 26000000 | 0 | 0 | 3976.02 | 4532.66 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 3976.02 | 4532.66 | 31734773.67 | 25996023.98 | 25995467.34 | 0.01529% | 0.01743%
Amenities | #REF! | #REF! | 22800000 | -15884413 | 6915587 | 14240000 | 32250000 | 32250000 | 0 | 0 | 237492.13 | 242755.03 | 869626.97 | 886920.96 | 888939.81 | 1025863.42 | 531984.64 | 553512.31 | [14 empty] | 2528043.55 | 2709051.72 | 6633355.64 | 29721956.45 | 29540948.28 | 7.839% | 8.4%
Environmental Services | #REF! | #REF! | 11040943 | 7500000 | 18540943 | 14240000 | 12000000 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 4196.91 | 4196.91 | 284773.45 | 324641.73 | [14 empty] | 288970.36 | 328838.64 | 4740432.19 | 11711029.64 | 11671161.36 | 2.408% | 2.74%
Health Services | #REF! | #REF! | 0 | 0 | 0 | 14240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
Public Safety | #REF! | #REF! | 2250000 | -2000000 | 250000 | 14240000 | 3000000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 2354788.83 | 3000000 | 3000000 | 0% | 0%
Support Services | #REF! | #REF! | 19350000 | -10000000 | 9350000 | 14240000 | 1500000 | 1500000 | 0 | 0 | 170805 | 194717.7 | 0 | 0 | 129259.3 | 129259.3 | 0 | 0 | [14 empty] | 300064.3 | 323977 | 2503601.65 | 1199935.7 | 1176023 | 20% | 21.6%
Other - BCM Fleet | #REF! | #REF! | 33000000 | 3500000 | 36500000 | 33000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
| #REF! | #REF! | 296123214.88 | 12199892 | 308323106.88 |  | 639824500 | 639824500 | 1979773.14 | 2285768.79 | 28086910.53 | 31820696.24 | 37979284.1 | 42795324.89 | 43344629.73 | 48913901.59 | 29320100.24 | 33873918.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140710697.74 | 159689609.8 | 120394360.21 | 499113802.26 | 480134890.2 | 21.99% | 24.96%

## Housing
BUFFALO CITY METROPOLITAN MUNICIPALITY
2014-2017 DRAFT CAPITAL BUDGET
Directorate | Cost centre name | C5C | USDG Service | Cost Centre No. | A5 | Service | V1 | V1 | V1 | VT | VT | VT | VT | VT | VT | 34a & 34b | New Asset | Renewal | A9 | Asset Sub Class- SA36 | KPA'S | Ward No. | Project Name | Funding Source | 2013/2014 Approved Budget | Adjustment | 2013/2014 Rollover Adjustment Budget | Adjustments | 2013/14 Conditional Grants Rollover Adjustment Budget | Mid-Year Adjustments | 2013/2014 Mid-Year Adjusted Budget | Savings | 2014/2015 Draft Capital Budget | 2015/2016 Draft Capital Budget | 2016/2017 Draft Capital Budget | July Expenditure | July Expenditure(VAT inc.) | August Expenditure | August Expenditure ( VAT inc.) | September Expenditure | Vat | September Expenditure (VAT inc.) | 1st Quarter Expenditure (Exc. VAT) | 1st Quarter Expenditure (incl. VAT) | October Expenditure | Vat | October Expenditure (VAT inc.) | November Expenditure | Vat | November Expenditure (VAT inc.) | December Expenditure | Vat | December Expenditure (VAT inc.) | January Expenditure | January Expenditure (VAT inc.) | February Expenditure | February Expenditure (VAT inc.) | March Expenditure | March Expenditure (VAT inc.) | April Expenditure | April Expenditure (VAT inc.) | May Expenditure | May Expenditure ( VAT inc.) | June Expenditure | June Expenditure ( VAT inc.) | Commitments as per Venus | YTD Expenditure | YTD Expenditure ( VAT inc.) | Commitments (Outstanding invoices for work done not yet paid) | Available Budget | Available Budget ( Budget -Expenditure including VAT) | % Expenditue | % Expenditue including VAT) | 2017/2018 Draft Capital Budget | 2018/2019 Draft Capital Budget | 2017/2018 Draft Capital Budget | Comments
[55 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
CHIEF OPERATIONS OFFICER | [22 empty] | CHIEF OPERATIONS OFFICE | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Chief Operations Officer |  |  |  | 250005 | Housing | Support Services | [9 empty] | New-270 |  |  | Other | Housing | KPA2 |  | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 | 500000 | 500000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 01 | 1407 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 |  | Beneficiary Administration (Procure GPS Devices) | Own Funds | 200000 |  | 200000 |  | 200000 | 200000 | 400000 |  | 100000 | 150000 | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Beneficiary Registration DVRI Projects (Reeston, Cambridge, DVRI Pilot, Braelyn ext 10, C Section and Triangular Site, D Hostel) | HSDG - Opex | [8 empty] | 500000 | 100000 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Beneficiary Registration (Potsdam Unit V, Cluster 3, Orange Groove, Mdantsane Zone CC, Cluster 1, Cluster 2, Peelton Cluster, Hanover, Skobeni, Sunny South, Ilitha North, Dimbaza 110, Dimbaza Phase 3,Potsdam Village; North Kanana, Ikhwezi Block 1 & 2, Amalinda Co-op, Eradication of Wooden Houses to Formal Houses | HSDG - Opex | [8 empty] | 1350000 | 1000000 | 1000000
[33 empty] | 1950000 | 1250000 | 1000000
Chief Operations Officer | DVRI | 3.2 - Office of The Chief Operations Officer |  | 250005 | Housing | Housing | 4 | 39 | 1401 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | Reeston MPCC - DVRI | HSDG-Special Fund | 2100000 |  | 2100000 |  | 2100000 |  | 2100000 |  | 10068500 | 13068500 | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 33675 |  | 33675 | 53800 |  | 53800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 87475 | 87475 |  | 2012525 | 2012525 | 4.165% | 4.165%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1403 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3: Stage 2 - P1 & P3 | HSDG | 11684600 |  | 11684600 |  | 11684600 |  | 11684600 |  | 7000000 | 9000000 | 55265000 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8771929.82 | 0 | 0 |  | 11684600 | 11684600 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Reeston Phase 3: Stage 2 - P5 | HSDG | [8 empty] | 30000000 | 30000000 | 100000000
[33 empty] | 47068500 | 52068500 | 155265000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1404 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 3 - P1 & P3 | HSDG | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 8722000 | 19134500 | 36795436 |  | 0 | 48240 | 48240 |  |  | 0 | 48240 | 48240 |  |  | 0 |  |  | 0 | 18152.9 |  | 18152.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 66392.9 | 66392.9 |  | 9933607.1 | 9933607.1 | 0.6639% | 0.6639% |  |  |  |  | 74651936
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Reeston Phase 3 Stage 3 P5 | HSDG | [8 empty] | 14965387 | 59804569 | 30000000
[33 empty] | 23687387 | 78939069 | 66795436
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1401 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 2 -P1 & P3 | USDG | 6815400 |  | 6815400 |  | 6815400 | 5000000 | 11815400 |  | 6815400 | 100000 | 100000 |  | 0 | 4119.6 | 4119.6 | -4119.6 | 0 | -4119.6 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3614075.5 | 0 | 0 |  | 6815400 | 6815400 | 0% | 0% | 55265000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1404 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 3 - P1 & P3 | USDG | [8 empty] | 0 | 10000000 | 62923951.73 | [42 empty] | 72923951.73
[33 empty] | 6815400 | 10100000 | 63023951.73
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Potsdam Village Phase 1 & 2 - P5 | HSDG - Opex | [8 empty] | 50000 | 200000 | 36000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1409 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam Ikhwezi Block 1 - P1 & P3 | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 | 1600000 | 1600000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 175438.6 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1410 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam Ikhwezi Block 2 - P1 & P3 | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 | 2000000 | 2000000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1411 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 23 | Potsdam Village- P1 & P3 | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 | 2000000 | 2000000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1412 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam North Kanana - P1 | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 | 2300000 | 2300000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Potsdam Ikhwezi Block 1 - P5 | HSDG - Opex | [8 empty] | 500000 | 500000 | 10000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Potsdam Ikhwezi Block 2- P5 | HSDG - Opex | [8 empty] | 500000 | 500000 | 10000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Potsdam North Kanana - P5 | HSDG - Opex | [8 empty] | 500000 | 500000 | 10000000
[33 empty] | 3550000 | 9600000 | 73900000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1414 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 36 | Dimbaza Destitute 27 Units - P1 & P3 | USDG | 2500000 |  | 2500000 | -2300000 | 200000 |  | 200000 |  | 200000 | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 169290 | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Dimbaza 110 -P 5 (Top Structure) | HSDG - Opex | [8 empty] | 7100000 | 0 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Dimbaza Destitute 27 Units - P5 | HSDG - Opex | [8 empty] | 500000 | 500000 | 0
[33 empty] | 7800000 | 500000 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1416 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 36 | Disaster Project | USDG | 500000 |  | 500000 | -500000 | 0 |  | 0 |  | 1000000 | 200000 | 200000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1415 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 45 | Ilitha North 177 Units | USDG | 700000 |  | 700000 |  | 700000 |  | 700000 |  | 1500000 | 1000000 | 1000000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 700000 | 700000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Ilitha North - 177 Units P5 | HSDG - Opex | [8 empty] | 0 | 500000 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Ilitha Eradication of Wooden Houses to Formal Houses | HSDG - Opex | [8 empty] | 18180294 | 6000000 | 0
[33 empty] | 19680294 | 7500000 | 1000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | DVRI Planning Budget (FROM 8.7MIL) | Dept of LGTH - Opex | [8 empty] | 5000000 | 0 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1420 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | DVRI Pilot Project (Mekeni, Haven Hills, Competition Site) P1 & P3 | USDG | 2500000 |  | 2500000 | 1000000 | 3500000 |  | 3500000 |  | 775000 | 0 | 0 |  | 0 |  | 0 | 81590 | 11422.6 | 93012.6 | 81590 | 93012.6 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 81590 | 93012.6 |  | 3418410 | 3406987.4 | 2.331% | 2.658%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | DVRI Pilot Project (Mekeni, Haven Hills, Competition Site) P5 | HSDG - Opex | [8 empty] | 5000000 | 0 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1402 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 15 | Duncan Village Proper | HSDG | 350000 |  | 350000 |  | 350000 |  | 350000 |  | 700000 | 3300000 | 10000000 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 350000 | 350000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1406 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | C Section and Triangular Site - P1 & P3 | HSDG | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 2000000 | 2000000 | 10000000 |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 3707.64 |  | 3707.64 | -3707.64 |  | -3707.64 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1407 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | D Hostel - P1 & P3 | HSDG | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 2000000 | 2000000 | 10000000 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | C Section and Triangular Site - P5 | HSDG - Opex | [8 empty] | 0 | 300000 | 30000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | D Hostel - P5 | HSDG - Opex | [8 empty] | 0 | 300000 | 30000000
[33 empty] | 15475000 | 7900000 | 90000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Mdantsane Zone 18CC - P5 | HSDG - Opex | [8 empty] | 3109500 | 2551000 | 65000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1402 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 23 | Mdantsane Zone 18 CC Phase 2 - P1 & P3 | USDG | 3000000 |  | 3000000 |  | 3000000 | -1000000 | 2000000 |  | 10000000 | 13500000 | 13500000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 382.04 | 382.04 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 382.04 |  | 3000000 | 2999617.96 | 0% | 0.01273% | 16500000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1410 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 |  | Mdantsane Zone CC Phase 2 P1 & P3 | HSDG | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8500000 | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
[33 empty] | 13109500 | 24551000 | 78500000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1419 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1 | Block Yard TRA - P1 & P3 | USDG | 500000 |  | 500000 | 1831500 | 2331500 |  | 2331500 |  | 100000 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 295.58 | 295.58 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 175180.32 | 0 | 295.58 |  | 2331500 | 2331204.42 | 0% | 0.01268%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1404 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 19 | Second Creek (Turn Key) - P1 & P3 | USDG | 8000000 |  | 8000000 | 1800000 | 9800000 |  | 9800000 |  | 100000 | 0 | 0 |  | 0 | 149203.55 | 170092.05 | 761056.68 | 106547.93 | 867604.61 | 910260.23 | 1037696.66 |  |  | 0 | 340800.89 | 47712.12 | 388513.01 | 751461.26 |  | 751461.26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2002522.38 | 2177670.93 |  | 7797477.62 | 7622329.07 | 20.43% | 22.22%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Second Creek - P5 | HSDG - Opex | [8 empty] | 1000000 | 0 | 0
[33 empty] | 1100000 | 0 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1421 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 9 | Amalinda Co- Op | USDG | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 1100000 | 1000000 | 1000000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0% | 6000000
Chief Operations Officer |  |  |  | 255005 | Housing | Housing | [9 empty] | New-80 |  |  | Other | Housing | KPA2 |  | Amalinda Fairlands Pi & P2 | USDG | 0 |  | 0 |  | 0 |  | 0 |  | 1250000 | 1300000 | 1300000
Chief Operations Officer |  |  |  | 255005 | [18 empty] | Amalinda Co - Op P5 | HSDG - Opex | [8 empty] | 0 | 500000 | 0
Chief Operations Officer |  |  |  | 255005 | [18 empty] | Amalinda Fairlands P5 | HSDG - Opex | [8 empty] | 500000 | 4000000 | 6000000
[33 empty] | 2850000 | 6800000 | 8300000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1405 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 48,12,21,11,17,11,20 | Cluster 1 (Masibambane; Masibulele; Velwano; Ilinge and Dacawa) | USDG | 3500000 |  | 3500000 |  | 3500000 |  | 3500000 |  | 12452208 | 34000000 | 94440733 |  | 0 | 4737.54 | 4737.54 | -4737.54 | 0 | -4737.54 | 0 | 0 |  |  | 0 |  |  | 0 | 9997.5 | 1399.65 | 11397.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 9997.5 | 11397.15 |  | 3490002.5 | 3488602.85 | 0.2856% | 0.3256% | 73047792 |  |  |  | 144392941
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1411 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 |  | Cluster 1 (Masibambane; Masibulele; Velwano; Ilinge and Dacawa) | HSDG | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6000000 | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Cluster 1 (Masibambane; Masibulele; Velwano; Ilinge and Dacawa) P5 | HSDG | [8 empty] | 1250000 | 100190955 | 33000000
[33 empty] | 13702208 | 140190955 | 127440733
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1412 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 |  | Cluster 2 (Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe) | HSDG | 0 |  | 0 |  | 0 |  | 0 |  | 6500000 | 10000000 | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1406 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 17,14, | Cluster 2 (Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe) | USDG | 3500000 |  | 3500000 |  | 3500000 | -2500000 | 1000000 |  | 5000000 | 10000000 | 10000000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | -3707.64 |  | -3707.64 | 3707.64 |  | 3707.64 | 2574.75 | 360.46 | 2935.21 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2574.75 | 2935.21 |  | 3497425.25 | 3497064.79 | 0.07356% | 0.08386% | 46000000
Chief Operations Officer |  | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 6 | 36 | 1417 | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes | [5 empty] | Cluster 2 (Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe) | USDG c/o |  |  | 0 | 9590 | 9590 |  | 9590 |  | 0 | 0 | 0 | [17 empty] | 0 | [14 empty] | 0 |  | 9590 | 9590 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Cluster 2 (Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe) P5 (Name Change) | HSDG - Opex | [8 empty] | 6000000 | 7000000 | 33000000
[33 empty] | 17500000 | 27000000 | 43000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1407 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 10 | Cluster 3 (Fynbos Informal 1, Fynbos Informal 2, Ndancama) P1 & P3 | USDG | 5524440 |  | 5524440 | -1300000 | 4224440 | -2000000 | 2224440 |  | 7275000 | 29650000 | 19900000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 417514 | 58451.96 | 475965.96 | 168266.6 | 23557.32 | 191823.92 | 13864.37 | 1941.01 | 15805.38 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 599644.97 | 683595.26 |  | 3624795.03 | 3540844.74 | 14.19% | 16.18% | 68000000
Chief Operations Officer |  | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 6 | 36 | 1418 | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes | [5 empty] | Cluster 3 (Fynbos Informal 1, Fynbos Informal 2, Ndancama) P1 & P3 | USDG c/o |  |  | 0 | 1344861 | 1344861 |  | 1344861 | [21 empty] | 0 | [14 empty] | 0 |  | 1344861 | 1344861 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Cluster 3 (Fynbos 1; Fynbos 2; Ndancama, ) P5 | HSDG - Opex | [8 empty] | 300000 | 100861424 | 26000000
[33 empty] | 7575000 | 130511424 | 45900000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1408 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 31 | Sunny South - P1 & P3 | USDG | 10000000 |  | 10000000 | 4000000 | 14000000 |  | 14000000 |  | 8000000 | 0 | 0 |  | 0 |  | 0 | 312750 |  | 312750 | 312750 | 312750 | 34750 | 43785 | 78535 | 793348.34 | 107369.96 | 900718.3 | 439562.11 | 61538.7 | 501100.81 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1580410.45 | 1793104.11 |  | 12419589.55 | 12206895.89 | 11.29% | 12.81%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1408 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes | [5 empty] | Sunny South -P5 | HSDG - Opex | [8 empty] | 11000000 | 10500000 | 0
[33 empty] | 19000000 | 10500000 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1405 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 9 | Braelyn ext 10 - P1 & P3 | HSDG | 500000 |  | 500000 |  | 500000 | -500000 | 0 |  | 2000000 | 2000000 | 69000000 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Braelyn Ext 10 North - P5 | HSDG - Opex | [8 empty] | 5000000 | 30000000 | 57000000
[33 empty] | 7000000 | 32000000 | 126000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1417 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 43 | Tyutyu Phase 3 P1 & P3 Units | USDG | 200000 |  | 200000 | 0 | 200000 |  | 200000 |  | 500000 | 200000 | 200000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Tyutyu Phase 2 - P 5 (Top Structure) | HSDG - Opex | [8 empty] | 1000000 | 0 | 0
[33 empty] | 1500000 | 200000 | 200000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1418 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 46 | Westbank Restitution - P1 & P3 | USDG | 2000000 |  | 2000000 | 0 | 2000000 |  | 2000000 |  | 5000000 | 500000 | 500000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | 140000000 |  | R70mill from 15/16
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1409 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | Housing Needs Database and Accreditation (Capacity Enhancement) | HSDG | 390000 |  | 390000 |  | 390000 |  | 390000 |  | 500000 | 1000000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 60641.08 |  | 60641.08 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 60641.08 | 60641.08 |  | 329358.92 | 329358.92 | 15.55% | 15.55%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Housing Needs Database and Accreditation | HSDG - Opex | [8 empty] | 10327914 | 10818705 | 0
[33 empty] | 10827914 | 11818705 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Reconstruction of Storm Damaged Houses
[33 empty] | 23000000 | 100000 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Peelton Cluster (Majali, Mdange, Kwatrain, Nkqonqweni, Drayini & Esixekweni) - P5 | [9 empty] | 1000000 | 1000000 | 5000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Hanover - P5 | [9 empty] | 1000000 | 1000000 | 5000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Skobeni - P5 | [9 empty] | 1000000 | 1000000 | 5000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Relocation of beneficiaries to formal houses for all housing programmes - All Projects | [9 empty] | 2140000 | 5350000 | 3000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Beneficiary Education ( All Projects) | [9 empty] | 150000 | 150000 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | MURP Sustainability Plan | [9 empty] | 500000 | 0 | 0
[23 empty] | TOTAL : CHIEF OPERATIONS OFFICE |  | 76264440 | 0 | 76264440 | 7085951 | 83550391 | -800000 | 82750391 | 0 | 255581203 | 561229653 | 899525120.73 | 0 | 0 | 206300.69 | 227189.19 | 1146539.54 | 117970.53 | 1264510.07 | 1352840.23 | 1491699.26 | 452264 | 102236.96 | 554500.96 | 1396731.91 | 179317.02 | 1576048.93 | 1289412.89 | 65239.82 | 1354652.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12905914.24 | 4491249.03 | 4976901.86 | 0 | 78859141.97 | 78373489.14 | 5.375% | 5.957% |  |  | 0
[33 empty] | 152423095 | 375226653 | 495000000
[33 empty] | 103158108 | 186003000 | 404525120.73
[33 empty] | 255581203 | 561229653 | 899525120.73
[33 empty] | 0 | 0 | 0