## Per Funding
ANNEXURE B
2011/2012 ROLL - 1ST ROLL-OVER ADJUSTMENT BUDGET - OPERATING PROJECTS
DIRECTORATE | COST CENTRE DESCRIPTION |  | PROJECT DESCRIPTION | 2011/2012 | 2011/2012 | 2011/2012 | COMMENTS
|  | COST |  | APPROVED | BUDGET | 1st ROLL-OVER |  | PROJECT STATUS phase as at 30 June 2010 (e.g. Contract not awarded, contract awarded, project on site, design phase, tender etc.) | REASONS why spending was not 100%: Name key challenges | TIME PERIOD to complete the rolled-over money
|  | CENTRE |  | BUDGET | ADJUSTMENTS | ADJ. BUDGET
1. BCMET c/o
Directorate of Development Planning | Transport Planning and Operations Admin | 620005 | Transport planning c/o | 0 | 204382.5 | 204382.5 |  | Consultant has been appointed and work has commenced | Progress stalled due to Councilors not being appointed to Project Steering Committee over period of Local Elections | Project to be completed by December 2011
Directorate of Development Planning | Transport Planning and Operations Admin | 620005 | Transport policy and by-law | 0 | 400000 | 400000 |  | New Funding | New Funding | New Funding
|  |  |  | 0 | 604382.5 | 604382.5 | 0
2. Department of Environmental Affairs and Tourism c/o
Directorate of Development Planning | Local Economic Development | 635005 | Intlanzi eKoloni (DEDEA Funds) | 140000 |  | 140000
|  |  |  | 140000 |  | 140000 | 0
3. Disaster Management Fund c/o
Directorate of Health and Public Safety | Fire and Rescue Services | 725010 | Risk & Vulnerability Assessment c/o | 96999 | -96999 | 0 |  | Correcting wrong Cost Centre | Correcting wrong Cost Centre | Correcting wrong Cost Centre
Directorate of Health and Public Safety | Fire and Rescue Services | 725055 | Risk & Vulnerability Assessment c/o | 0 | 96999 | 96999 |  | Evaluation phase, tender closed 24 June 2011 | Project in progress. | March 2012
|  |  |  | 96999 | 0 | 96999
4. Local Government and Traditional Affairs c/o
Directorate of Financial Services | Supply Chain Management | 320010 | Overview of Internal Controls - SCM | 0 | 12135 | 12135 |  | Design phase | Funds to be used in conjunction with SCM Turnaround project | Funds will be spent before FYE
Directorate of Development Planning | City Planning | 615070 | Informal Settlement Study & Implementation Programme c/o | 0 | 300000 | 300000 |  | Service Providers were appointed. The categorisation and classification of informal settlements has been completed. Project team in process of drafting draft report and implementation programme. Balance of project to be paid on completion of the project. | Project was delayed by more than 18 months due to the non-existence of Project Steering Committees due to political instability. | Project to be completed by February 2012 and submit to Council for approval in March of 2012.
Directorate of Development Planning | City Planning | 615070 | Mdantsane LSDF c/o | 0 | 414857 | 414857 |  | Service Provider appointed and Situation Analysis completed (Phase 1) and Key Spatial Development Proposals (Phase 2) developed and to be be presented to a Project Steering Committee and Stakeholders meeting in near future. | The project has been delayed due to the fact that no Project Steering Committee (chaired by the Portfolia Councillor) has taken place since scince October 2010. A PSC meeting and a stakeholders meeting was scheduled for March 2011 was cancelled due to the upcoming election and has not taken place since. | The project is intended to be completed by end of 2011/2012 FY
Directorate of Development Planning | City Planning | 615070 | Planning - Needscamp c/o | 0 | 58036 | 58036 |  | Service Providers appointed. Settlement Planning component completed. Awaiting MEC approval when land ownership i.e. Section 28 Certificate from Department of Land Affairs has been resolved before final payment can be made to Service Providers. Payments done in previuous financial years. | MEC approval is outstanding for a few yesrs | Will be completed once MEC has approved it
Directorate of Development Planning | City Planning | 615070 | Settlement upgrading of Yellowwood c/o | 0 | 471845 | 471845 |  | Service Providers appointed. Settlement Planning component completed. Awaiting MEC final approval which can only be given when land ownership has been resolved with Department of Land Affairs. Only when MECs approval has been given can final payment be made to Service Providers. Payments done in previous financial years. | MEC approval is outstanding for a few yesrs | Will be completed once MEC has approved it
|  |  |  | 0 | 1256873 | 1256873
5. Department of Water Affairs and Forestry - DoRA
Directorate of Engineering Services | Water, Sanitation and Scientific services | 520005 | Water Services Operating & Transfer Subsidy | 1680000 |  | 1680000 | Roll Overs from 2009/10
Directorate of Engineering Services | Water, Sanitation and Scientific services | 520005 | Water Services Capacity Building Business Plan | 1150000 |  | 1150000 | Roll Overs from 2009/10
|  |  |  | 2830000 | 0 | 2830000
6. Department of Water Affairs and Forestry- Provincial
Directorate of Engineering Services | Water, Sanitation and Scientific services | 520005 | East Bank WWTW | 6945000 |  | 6945000 | Roll Overs from 2009/10
Directorate of Engineering Services | Water, Sanitation and Scientific services | 520005 | Dimbaza WWTW | 450000 |  | 450000
Directorate of Engineering Services | Water, Sanitation and Scientific services | 520005 | Water Connservation & Demand Management | 5000000 |  | 5000000
|  |  |  | 12395000 | 0 | 12395000
7. DLGTA c/o
Municipal Manager's Office | Municipal Manager and Support Services | 205005 | Muncipal Manager and Support Services (Elections) | 0 | 201327.09 | 201327.09 | Roll Overs from 2009/10 | Unspent portion from the IEC still receiving invoices | Unspent portion from the IEC still receiving invoices | June 2012
Municipal Manager's Office | Municipal Manager and Support Services | 205005 | Local Government Elections Financial Assistance | 0 | 2367523.83 | 2367523.83 |  | Unspent portion from the IEC still receiving invoices | Unspent portion from the IEC still receiving invoices | June 2012
Chief Operations Officer | Mdantsane Urban Renewal Unit | 255010 | Mdantsane ICT Centre c/o | 0 | 391649.2 | 391649.2 |  | Contract awarded. | The project is ongoing and is implemented in phases. The project is in the fourth phase of its implementation. | The rolled-over funds will be completed
Chief Operations Officer | DVRI | 250005 | DV Stakeholder Mobilisation c/o | 0 | 81222.05 | 81222.05 |  | Project has been completed. The remaining funds will be utilised to cunduct Stakeholder's Forum meetings . | The appointment amount for the service provider as well as operating costs during project implementation period, were below the budget available. | 2012-06-01
Chief Operations Officer | DVRI | 250005 | DVRI Business Plan | 0 | 712313.51 | 712313.51 |  | The tender has been readvertised for the third time. | The procurement of a service provider has not been finalised due to readvertisement of the tender for three times based on the following reasons: 1). the recommended bidder had an invalid tax clearance certificate and couldnt provide a valid one. 2). The bids recieved quoted above the budget available. 3). The tender documents couldn't be accessed by bidders at SCM due to the internal strike action and that adversely affected the procurement process. 4). All bidders were non-responsive. | The tender will be cancelled and readvertised during the second quarter of the FY. Subsequently, the project will be implemented for a duration of 3 months and therefore the budget available will be utilised by end of June 2012
Chief Operations Officer | DVRI | 250005 | DV Quality of Life Survey c/o | 0 | 300000 | 300000 |  | The DVRI Steering Committee resolved that the budget must be reallocated to the DV ICT Center project as one of the priority issues for consideration. The request to reallocate funding has been submitted to the funder (DLGTA) for approval. | The funding reallocation request has only been approved in principle in 09 Sept 11 subject to submission of a council resolution on the matter. | During the current financial year it is envisaged that only 50% of the budget will be utilised, due to the council resolution required by DLGTA as well as procurement process to be undertaken once the funding has been fully reallocated, aligned with municipal budget adjustment processes.
Directorate of Financial Services | Office of the Director of Finance | 305005 | Internal Control | 0 | 500000 | 500000 |  | Discussion were undertaken with National Treasury to assist in enhancing SCM internal controls and capacity | Still awaiting National Treasury's response on their intervention in terms of the critical areas identified | 2012-06-01
Directorate of Development Planning | City Planning | 615070 | Mdantsane Infill Areas - Phase III | 0 | 228437.5 | 228437.5 |  | Service Providers appointed. Project Phase 1 completed and approved by Council end of 2010. Phase 2: "Land idendification study for the relocation of Infill in Mdantsane". Appointments where done in March 2011 and busy with stage 2 and draft report: "On -Site Verification of Land Parcels" has been submitted to BCMM for comments by BCMM. Invoice of R 38 688 has been submitted to BCMM for payment. Can only be paid once roll-overs have been approved. | As phase 1 was only approved by Council end of 2010 and phase 2 commenced only in 2011. No challenges | Project to be completed by end of December 2011
Directorate of Development Planning | Local Economic Development | 635005 | Mdantsane Skills Audit c/o | 0 | 322908.22 | 322908.22
|  |  |  | 0 | 5105381.4 | 5105381.4
8. European Commission c/o
Directorate of Community Services | Internments | 755025 | Clearing of Cemetries | 0 | 73242.14 | 73242.14 |  | A roll over has been requested to continue project | The project is ongoing . Participants to be engaged | The rolled over funds will be completed
Chief Operations Officer | Mdantsane Urban Renewal Unit | 255010 | ICT Centre c/o | 0 | 222180.84 | 222180.84 |  | Contract awarded. | The project is ongoing and is implemented in phases. The project is in the fourth phase of its implementation. | The rolled-over funds will be completed
Chief Operations Officer | Mdantsane Urban Renewal Unit | 255010 | Street Naming Phase 1 c/o | 0 | 209702.22 | 209702.22 |  | Database of names for neighbourhoods and higher order roads has been developed and is awating approval from the Project Steering Committee. | Phase three of the project has not been completed as a result of a meeting with neighbourhood 4 that could not convene. This resulted in the Service Provider not being paid the remaining amount for phase three. | The project is still on hold and the remaining funds for the project will be utilized once the project implementation has commenced.
Directorate of Development Planning | Local Economic Development | 635005 | Hydro-ponics - MDT | 0 | 119002.04 | 119002.04 |  | The funds are to be used to equip the packshed at NU 18 Mdantsane, which will be completed by End October 2011 | Currently in the process of completing the construction of the packshed and will therefore procure the operational equipment through informal tender | 1 month after budget Approval by Council
Directorate of Development Planning | Local Economic Development | 635005 | LIFE - Livelihoods and Innovation Fund Enhancement | 0 | 27355.55 | 27355.55
Directorate of Community Services | Internments | 755035 | Mdantsane Moss | 0 | 121632 | 121632 |  | Training of Councillors to be conducted | Training of Councillors to be conducted | Training of Councillors to be conducted
|  |  |  | 0 | 773114.79 | 773114.79
9. Finance Management Grant
Directorate of Financial Services | Budget Office | 315005 | Budget Reforms | 1450000 |  | 1450000 | Roll Overs from 2009/10
|  |  |  | 1450000 | 0 | 1450000
10. Galve c/o
Executive Support Services | Development Co-Operation | 120005 | Management Co-Ordination | 0 | 733636.2 | 733636.2 | Roll Overs from 2009/10 | Project not limited to our financial year | Project not limited to our financial year | Dec 2012
|  |  |  | 0 | 733636.2 | 733636.2
11. Glasgow Partnership
Executive Support Services | Development Co-Operation | 120005 | Management Co-Ordination | 0 | 264808 | 264808 | Roll Overs from 2009/10 | Project not limited to our financial year | Project not limited to our financial year | Dec 2012
|  |  |  | 0 | 264808 | 264808
12. Human Settlements Development Grant (HSDG)
Chief Operations Officer | Housing Projects | 255005 | Second Creek (Turn key)-P5 | 20914860 |  | 20914860
Chief Operations Officer | Housing Projects | 255005 | Potsdam Unit P,Stage 2-P5 | 67085400 |  | 67085400
Chief Operations Officer | Housing Projects | 255005 | Airport / Phase 2A Construction New units-P5 | 9802100 |  | 9802100
Chief Operations Officer | Housing Projects | 255005 | Storm damaged reconstruction project 988 Top structures and Rural sanitation (Emergency housing) | 8000000 |  | 8000000
Chief Operations Officer | Housing Projects | 255005 | Masibambane-P5 | 6156072 |  | 6156072
Chief Operations Officer | Housing Projects | 255005 | Masibulele-P5 | 6313920 |  | 6313920
Chief Operations Officer | Housing Projects | 255005 | Velwano-P5 | 7892400 |  | 7892400
Chief Operations Officer | Housing Projects | 255005 | Chris Hani Park Phase 3-P5 | 8287020 |  | 8287020
Chief Operations Officer | Housing Projects | 255005 | Ilinge-P5 | 3946200 |  | 3946200
Chief Operations Officer | Housing Projects | 255005 | Gwentshe Village-P5 | 986550 |  | 986550
Chief Operations Officer | Housing Projects | 255005 | Fynbos Informal 1-P5 | 4222434 |  | 4222434
Chief Operations Officer | Housing Projects | 255005 | Fynbos Informal 2-P5 | 3946200 |  | 3946200
Chief Operations Officer | Housing Projects | 255005 | Ndacama-P5 | 3946200 |  | 3946200
Chief Operations Officer | Housing Projects | 255005 | Ilitha wooden Houses-P5 | 16800000 |  | 16800000
Chief Operations Officer | Housing Projects | 255005 | Mathemba Vuso-P5 | 2959650 |  | 2959650
Chief Operations Officer | Housing Projects | 255005 | Deluxolo Village-P5 | 3472656 |  | 3472656
Chief Operations Officer | Housing Projects | 255005 | Francis Mei | 1341708 |  | 1341708
Chief Operations Officer | Housing Projects | 255005 | Mahlangu Village-P5 | 3591042 |  | 3591042
Chief Operations Officer | Housing Projects | 255005 | Sisulu Village-P5 | 3038574 |  | 3038574
Chief Operations Officer | Housing Projects | 255005 | Winnie Mandela -P5 | 2959650 |  | 2959650
Chief Operations Officer | Housing Projects | 255005 | Reeston Phase 3 Stage 2-P4 | 400000 |  | 400000
Chief Operations Officer | Housing Projects | 255005 | Reeston Phase 3 Stage 2-P5 | 39462000 |  | 39462000
Chief Operations Officer | Housing Projects | 255005 | DVRI Pilot Project, 323 units (Mekeni,Competition site ,Haven hills) -P5 | 22132000 |  | 22132000
Chief Operations Officer | Housing Projects | 255005 | Braelyn Ext 10 North -P2 | 1267200 |  | 1267200
Chief Operations Officer | Housing Projects | 255005 | C Section (690)-P2 | 222000 |  | 222000
Chief Operations Officer | Housing Projects | 255005 | Pilot C Section Triangle -P2 | 48000 |  | 48000
Chief Operations Officer | Housing Projects | 255005 | D Hostel-P2 | 199200 |  | 199200
Chief Operations Officer | Housing Projects | 255005 | Duncan Village Proper (746)-P2 | 222000 |  | 222000
Chief Operations Officer | Housing Projects | 255005 | LU Housing Nom.School-P1 | 835200 |  | 835200
Chief Operations Officer | Housing Projects | 255005 | LU Housing Nom.School-P2 | 278400 |  | 278400
Chief Operations Officer | Housing Projects | 255005 | Lu Housing II-P1 | 349200 |  | 349200
Chief Operations Officer | Housing Projects | 255005 | Lu Housing II-P2 | 116400 |  | 116400
Chief Operations Officer | Housing Projects | 255005 | N2 Road Reserve 1-P1 | 1746000 |  | 1746000
Chief Operations Officer | Housing Projects | 255005 | N2 Road Reserve 1-P2 | 582000 |  | 582000
Chief Operations Officer | Housing Projects | 255005 | Kei Road -Dawn-P1 | 1800000 |  | 1800000
Chief Operations Officer | Housing Projects | 255005 | Kei Road -Dawn-P2 | 600000 |  | 600000
Chief Operations Officer | Housing Projects | 255005 | Mdantsane Access/Buffalo-P5 | 7959053 |  | 7959053
Chief Operations Officer | Housing Projects | 255005 | Reeston Phase 3 Stage 3-P1 | 1123356 |  | 1123356
Chief Operations Officer | Housing Projects | 255005 | Reeston Phase 3 Stage 3-P4 | 127500 |  | 127500
Chief Operations Officer | Housing Projects | 255005 | Amalinda (Co-op) | 319153 |  | 319153
Chief Operations Officer | Housing Projects | 255005 | Amalinda (CNIP Projects) | 10852050 |  | 10852050
|  |  |  | 276303348 | 0 | 276303348
13. Dept of Human Settlements c/o
Chief Operations Officer | Housing Department | 255005 | Reeston Phase 3 - Stage 2 - P4 - Sales Admin & Conveyancers | 0 | 79840 | 79840 | Roll Overs from 2009/10 | Service Provider has been appointed | The access to the General Plan was delayed to be submitted to the Conveyancer to proceed with the transfer | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Reeston Phase 3 - Stage 2 - 1000 units: P1 | 0 | 266510 | 266510 | Roll Overs from 2009/10 | Service provider has been appointed, the appointment of the internal services contractor for construction is still on tender stage | The funding is for contract administration (project management) which will be used once the internal services project implementation has started | The project will be implemented over in three financial years
Chief Operations Officer | Housing Department | 255005 | 1440 Families Relocation From Duncan VIllage to Reeston | 0 | 467483.43 | 467483.43 | Roll Overs from 2009/10 | The service provider is appointed on adhoc basis when there is demand for relocation. No permanent appointment of service provider is made. | Currently experiencing challenges of illegal occupation and structural defects by PDoHS appointed Contractor (Thubelisha Homes) | Depend upon the completion of the completed units.
Chief Operations Officer | Housing Department | 255005 | Accreditation: Buffalo City Municipality: Housing | 0 | 798530.72 | 798530.72 | Roll Overs from 2009/10 | Not applicable | The funding is maily used for salary related costs | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Mdantsane Zone 18 CC - Phase 2 - Stage 1: P1 | 0 | 120074.08 | 120074.08 | Roll Overs from 2009/10 | Service provide has been appointed | Engineering design only completed for 500 units, available budget can only be spent in the current financial year. Have instructed the engineers to proceed with the engineering designs for the balance of 1,000 sites, will require budget adjustment in December 2011. Available budget to be rolled over. | The project will be implemented over in two financial years
Chief Operations Officer | Housing Department | 255005 | Potsdam Unit P: 500 Units - P5 Top Structure c/o | 0 | 396416 | 396416 | Roll Overs from 2009/10 | Contractor not yet awarded | Funding was held back from Thubelisha as part of rectictification and will be utilized in the current financial year on defective units. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Potsdam Unit P: 500 Units - P4 c/o | 0 | 83650 | 83650 | Roll Overs from 2009/10 | Service Provider has been appointed | Land Administration who processes property transfers experience a capacity challenge and the request for transfers of properties to individuals get delayed. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Potsdam Unit P: Stage 2: 2003 Units: P1: Engineering Design c/o | 0 | 107471.85 | 107471.85 | Roll Overs from 2009/10 | The project is almost complete | Awaiting finalization of close out report to make the final payments. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Reeston Phase 3: Stage 1: 800 Units:Conveyancing: P4 c/o | 0 | 50000 | 50000 | Roll Overs from 2009/10 | Service Provider has not been appointed | Land Administration who processes property transfers experiencing a capacity challenge and the request for transfers of properties to individuals get delayed. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Z Soga 171 Units: P4 c/o | 0 | 50000 | 50000 | Roll Overs from 2009/10 | Service Provider has been appointed | Land Administration who processes property transfers experience a capacity challenge and the request for transfers of properties to individuals get delayed. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Z Soga 171 Units: P5 c/o | 0 | 929760.01 | 929760.01 | Roll Overs from 2009/10 | Contractor was appointed | 166 Units of the 171 are complete. The contractor is off site due to 5 undevelopable sites. The department is in the process of doing the required turkey survey to develop the sites. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Mdantsane Zone 18 CC - Phase 2 - Stage 1 - P1 c/o | 0 | 51734 | 51734 | Roll Overs from 2009/10 | Service provide has been appointed | Engineering design only completed for 500 units, available budget can only be spent in the current financial year. Have instructed the engineers to proceed with the engineering designs for the balance of 1,000 sites, will require budget adjustment in December 2011. Available budget to be rolled over. | The project will be implemented over in two financial years
Chief Operations Officer | Housing Department | 255005 | Manyano & Tembeilihle - P1 c/o | 0 | 387013.2 | 387013.2 | Roll Overs from 2009/10 | Service provide has been appointed | The funding is for contract administration (project management) which was delayed by delayed appointment of internal services contractor | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Airport Phase 2A - 614 Units - P4 c/o | 0 | 20000 | 20000 | Roll Overs from 2009/10 | The service Provider has been appointed | There has been a delay in the opening of the Township register and the appointed service provider has also delayed. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Airport Phase 2A - 614 Units - Est. Grant c/o | 0 | 76986 | 76986 | Roll Overs from 2009/10 | Contract not awarded | The funding is for contract administration (project management) which will be used once the project implementation has started. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Amalinda Simanyene 93 Units P4 c/o | 0 | 3596.49 | 3596.49 | Roll Overs from 2009/10 | Service Provider has been appointed | Beneficiary registration completed, Land admin still busy with transfer of properties. Available budget to be rolled over. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Amalinde Simanyene 93 Units P5 c/o | 0 | 223613.27 | 223613.27 | Roll Overs from 2009/10 | Service Provider has been appointed | Project is practical complete, contractor is still busy with the snags, upon completion the money will be spent. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Second Creek Development: 300 Units- P1 c/o | 0 | 467097.39 | 467097.39 | Roll Overs from 2009/10 | Service provider appointed and engineering designs are complete. Project management still to commence. | The funding will be utilised during project implementation of both internal services and top structures for project management. The appointment of the contractor is delayed. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Reeston Phase 1 & 2 Stage 1B: P4 - Conveyancers c/o | 0 | 10000 | 10000 | Roll Overs from 2009/10 | Service Provider has been appointed | Land Administration who processes property transfers is experiencing capacity challenges and the request for transfers of properties to individuals get delayed. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Reeston Phase 1&2 stage 1B: 1000 Units: P5 (606 units) c/o | 0 | 1283583.47 | 1283583.47 | Roll Overs from 2009/10 | Contractor on site | Payment to the contractor was held back due slow progress on signing of happy letters by beneficiaries as some of the houses are occupied by illegal occupants. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Reeston Phase 1 & 2 Stage 1B:400 - Est Grant | 0 | 97933 | 97933 | Roll Overs from 2009/10 | Contractor on site | Work completed, however the payment of the service provider depends upon signing of happy letters by beneficiaries. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | 1440 Families Relocation From Duncan VIllage to Reeston c/o | 0 | 339187 | 339187 | Roll Overs from 2009/10 | The service provider is appointed on adhoc basis when there is demand for relocation. No permanent appointment of service provider is made. | Currently experiencing challenges of illegal occupation and structural defects by PDoHS appointed Contractor (Thubelisha Homes) | Depend upon the completion of the completed units.
Chief Operations Officer | Housing Department | 255005 | Haven HillsSouth Pilot Project: P4 c/o | 0 | 10000 | 10000 | Roll Overs from 2009/10 | Service Provider has not been appointed | Registration is underway, done in house. Land Admin was unable to proceed with the transfers because the general plans that were outstanding have only been received recently. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | TyuTyu Phase 1 : 300 units : P5 : Top Structure c/o | 0 | 2493861.58 | 2493861.58 | Roll Overs from 2009/10 | Contractor on site | Delays were experienced in the signing of the subsidy agreement which affected contractors progress claim. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | TyuTyu Phase 2 : 373 units : P4 :Conv & Sales Admin c/o | 0 | 10000 | 10000 | Roll Overs from 2009/10 | Service provider is on site | Land Administration who processes property transfers is experiencing capacity challenges and the request for transfers of properties to individuals get delayed. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | TyuTyu Phase 2 : 373 units : P5 : Top Structure c/o | 0 | 822000 | 822000 | Roll Overs from 2009/10 | Currently stagnant | BCMM housing is busy with the tender document for the appointment of the contractor to construct the remaining 100 top structures, also a letter has been sent to the Department of Human Settlement for additional funding application. | Budget should be spent within the current financial year.
Chief Operations Officer | Housing Department | 255005 | Ilitha South : 439 units : P5 : Top Structure c/o | 0 | 767687.84 | 767687.84 | Roll Overs from 2009/10 | Contractor on site | Delays were experienced in the signing of the subsidy agreement which affected contractors progress claims. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Dimbaza Phase 2: 1720 Units P5 Top Structure | 0 | 1112586.36 | 1112586.36 | Roll Overs from 2009/10 | Contractor on site | Delays were experienced in the signing of the subsidy agreement which affected contractors progress claims. | Budget will be spent in this current financial year
Chief Operations Officer | Housing Department | 255005 | Storm Damaged Reconstruction : 988 Units | 0 | 197484 | 197484 |  | Professional team is on site | There were delays on tender processes. Professional team has only been appointed in July 2011. | Budget should be spent within the current financial year.
|  |  |  | 0 | 11724099.69 | 11724099.69
14. Leiden Platform
Executive Support Services | Development Co-Operation | 120005 | BCM Speical Programmes Focal Areas Strategies Implementaion | 0 | 139648 | 139648 | Roll Overs from 2009/10 | Funding only received end FY10/11 for use FY11/12 | New Funding Received for FY11/12 | FY11/12
Executive Support Services | Development Co-Operation | 120005 | Management Coordination | 0 | 190732 | 190732 |  | New funding | New funding | DEC 2012
|  |  |  | 0 | 330380 | 330380
15. Leiden Platform c/o
Executive Support Services | Special Programmes | 105030 | Special Programmes Focal Areas Administrator Project | 0 | 295701.35 | 295701.35 | Roll Overs from 2009/10 | Ongoing project- does not require SCM processes | Monthly journal for Special Programmes Project Administrator FY11/12
Executive Support Services | Special Programmes | 105030 | BCM Speical Programmes Focal Areas Strategies Implementaion | 0 | 190350.01 | 190350.01 | Roll Overs from 2009/10 | Funding to support ongoing activities of SPU Forums | Funding to support activities of the Youth, Women's, Older Persons and Disability Forums and the Metro AIDS Council in FY11/12 | FY11/12
Executive Support Services | Development Co-Operation | 120005 | Leiden reimbursement | 0 | 100000 | 100000 | Roll Overs from 2009/10 | Project not limited to BCMM financial year | Project not limited to BCMM financial year | DEC 2012
Executive Support Services | Development Co-Operation | 120005 | Communication Solid Waste | 0 | 148782 | 148782 | Roll Overs from 2009/10 | Project not limited to BCMM financial year | Project not limited to BCMM financial year | DEC 2012
Executive Support Services | Development Co-Operation | 120005 | Data Collection/River Clean-Up | 0 | 99736.31 | 99736.31 | Roll Overs from 2009/10 | Project not limited to BCMM financial year | Project not limited to BCMM financial year | DEC 2012
Executive Support Services | Development Co-Operation | 120005 | Co-Ordination Leiden Projects | 0 | 203666.79 | 203666.79 | Roll Overs from 2009/10 | Project not limited to BCMM financial year | Project not limited to BCMM financial year | DEC 2012
Executive Support Services | Special Programmes | 105030 | HIV/AIDS Projects Leiden | 0 | 45612.31 | 45612.31 | Roll Overs from 2009/10 | Funding ring fenced printing HIV Strategy FY11/12 | Strategy only ready for printing FY11/12 | FY11/12
Executive Support Services | Development Co-Operation | 120005 | Communication Sanitation | 0 | 40000 | 40000 | Roll Overs from 2009/10 | Project not limited to BCMM financial year | Project not limited to BCMM financial year | DEC 2012
Executive Support Services | Special Programmes | 105030 | BCM Special Programme Focal Areas | 0 | 52007.75 | 52007.75 | Roll Overs from 2009/10 | Funding to support ongoing activities of SPU Forums | Funding to support activities of the Youth, Women's, Older Persons and Disability Forums and the Metro AIDS Council in FY11/12 | FY11/12
Executive Support Services | Development Co-Operation | 120005 | Leiden Flood Plain Project | 0 | 33316.55 | 33316.55 | Roll Overs from 2009/10 | Project not limited to BCMM financial year | Project not limited to BCMM financial year | DEC 2012
|  |  |  | 0 | 1209173.07 | 1209173.07
16. LGH (Local Government Housing) c/o
Directorate of Development Planning | City Planning | 615070 | Duncan Village Settlement Planning | 0 | 778452 | 778452 | Roll Overs from 2009/10 | Service Providers appointed. All three projects completed their feasibility study phase. In process with draft layouts, but cannot finalize them until final decision has been taken in terms of Housing Typology, densities and erf sizes. Delays experienced in regard to this during election period. DVRI is in process to organise a meeting with DV Councillors and stake holders to resolve issue. Meeting was also delayed due to strikes. Once the housing typology, densities and erf sizes has been resolved, can layout plans be submitted to PSC Mtg and to brief new councillors. | Challenge is the issue in regard to housing typology, densities and erf sizes has not been finalized and therefore draft layouts where not possible to be finalized by end of June 2011. | End of Finacial Year 2011/2012.
Directorate of Development Planning | Land Surveying | 615085 | Yellowwoods/ Kei Roads Subdivision c/o | 0 | 698133 | 698133 | Roll Overs from 2009/10 | BSC rejected specifications. Tenders have gone to the ACM for approval of specifications. | The Department of Rural Development and Land Reform funded the projects in the interim. | One year.
|  |  |  | 0 | 1476585 | 1476585
17. Own Funds
Executive Support Services | Development Co-Operation | 120005 | International Partnership | 300000 |  | 300000 | Roll Overs from 2009/10
Executive Support Services | Development Co-Operation | 120005 | African Partnership | 100000 |  | 100000
Executive Support Services | Communications | 120010 | Implementation of the Communication Strategy | 200000 |  | 200000
Executive Support Services | IGR | 120010 | IGR | 200000 |  | 200000
Executive Support Services | GIS | 110015 | GIS on the internet | 630000 |  | 630000
Executive Support Services | Public Participation | 120010 | PP Strategy Annual Plan | 300000 |  | 300000
Executive Support Services | Special Programmes | 105030 | Economic Empowerment for targeted groups (R100,000) | 100000 |  | 100000
Executive Support Services | Knowledge Management | 130005 | Capacity building | 598353 |  | 598353
Directorate of Financial Services | Debtors Management Office | 330010 | Data cleanup Project | 1000000 |  | 1000000
Directorate of Financial Services | Debtors Management Office | 330010 | Analysis of the Billing Debt book | 1000000 |  | 1000000
Directorate of Financial Services | GIS Unit | 330010 | Property data alignment and clean up | 500000 | -500000 | 0 |  | Funding wrongly allocated to Financial Service Budget and need to be transferred to GIS unit cost Centre | Bid Advertising closed on 23 September 2011 - the tender evaluation process in progress. Need to review one bidder for responsiveness;. | This is phase 1 of a 3 year contract Intergrated Property Information Management System and Business Process. To be completed at the end of June 2012.
Directorate of Financial Services | GIS Unit | 110015 | Property data alignment and clean up | 0 | 500000 | 500000 |  | New Project - funding misallocated under Financial Service Budget. Contract CE 102 - Bid Closing date 23 September 2011. In process of functionality Evaluation. | Bid Advertising closed on 23 September 2011 - the tender evaluation process in progress. Need to review one bidder for responsiveness;. | This is phase 1 of a 3 year contract Intergrated Property Information Management System and Business Process.Phase 1 to be completed at the end of June 2012.
Directorate of Financial Services | Asset and Risk | 320005 | Accounting Reforms | 720000 |  | 720000
Directorate of Financial Services | Supply Chain Management | 320010 | SCM turnaround Plan | 500000 |  | 500000
Directorate of Financial Services | Supply Chain Management | 320010 | SCM Intenda Project | 500000 |  | 500000
Directorate of Corporate Services | H.R. Administration | 420005 | Development of BCM Metropolitan Municipality organogram(UNDER MM'S budget) | 300000 |  | 300000
Directorate of Corporate Services | H.R. Administration | 420005 | Implementation of the EE Plan | 150000 |  | 150000
Directorate of Corporate Services | H.R. Administration | 420005 | Employee wellness programme | 400000 |  | 400000
Directorate of Corporate Services | Administration & Council Support Services | 415005 | Review BY-Law in Standing Rules of Order | 25000 |  | 25000
Directorate of Corporate Services | Administration & Council Support Services | 415005 | Policy on Closure of Council meetings | 25000 |  | 25000
Directorate of Development Planning | Transportation | 620005 | BCM ITP review | 1000000 |  | 1000000
Directorate of Development Planning | Spatial Planning | 615005 | Township Establishment Programme | 500000 |  | 500000
Directorate of Development Planning | SMME Development | 635005 | Business Management Training Program | 100000 |  | 100000
Directorate of Development Planning | SMME Development | 635005 | Emerging contractor Training Program | 400000 |  | 400000
Directorate of Development Planning | SMME Development | 635005 | Corporate governance Training Program | 100000 |  | 100000
Directorate of Development Planning | SMME Development | 635005 | Customer Training Program | 100000 |  | 100000
Directorate of Development Planning | SMME Development | 635005 | Tender Advise Training Program | 100000 |  | 100000
Directorate of Development Planning | SMME development | 635005 | Participation at International Trade Shows e.g Indaba, World Travel Market and ITB | 500000 |  | 500000
Directorate of Development Planning | SMME development | 635005 | Printing of marketing material for tourism SMME’s | 100000 |  | 100000
Directorate of Development Planning | SMME development | 635005 | Participation at Domestic Trade Shows e.g Kyalami Outdoor show in Johannesburg, Cape Town Getaway Show and Rand Easter Show | 300000 |  | 300000
Directorate of Development Planning | SMME development | 635005 | Management of business support centre’s e.g. Mdantsane One Stop Shop and Duncan Village Business Hives | 1000000 |  | 1000000
Directorate of Development Planning | SMME development | 635005 | Cooperatives Support | 1000000 |  | 1000000
Directorate of Development Planning | Tourism Development | 635005 | Health and Hygiene Training Program for the accommodation sector | 300000 |  | 300000
Directorate of Development Planning | Tourism Development | 635005 | Summer Season Program | 3000000 |  | 3000000
Directorate of Development Planning | Tourism Development | 635005 | Tourism Month Celebration | 500000 |  | 500000
Directorate of Development Planning | Tourism Development | 635005 | Easter Festival | 1000000 |  | 1000000
Directorate of Development Planning | Tourism Development | 635005 | Tourism Service Excellence Awards | 500000 |  | 500000
Directorate of Development Planning | Tourism Development | 635005 | Tourism SMME Support Programme | 100000 |  | 100000
Directorate of Development Planning | Agricultural Development | 635005 | Agriculture training and capacity building program | 500000 |  | 500000
Directorate of Development Planning | Agricultural Development | 635005 | Hydroponics Rollout Program | 3300000 |  | 3300000
Directorate of Development Planning | Agricultural Development | 635005 | Farmer Support Services | 500000 |  | 500000
Directorate of Development Planning | Trade and investment | 635005 | Participation at local and International Investment and Trade Shows | 500000 |  | 500000
Directorate of Development Planning | Trade and investment | 635005 | Promotion key sector investment programme | 600000 |  | 600000
Directorate of Development Planning | Trade and investment | 635005 | Export Support Programme | 500000 |  | 500000
Directorate of Development Planning | Local Economic Development | 635005 | Review of Agricultural Strategy | 350000 |  | 350000
Directorate of Health and Public Safety | Law enforcement | 725020 | Crime Prevention Strategy | 1000000 | -1000000 | 0 |  | Correcting wrong Cost Centre | Correcting wrong Cost Centre | Correcting wrong Cost Centre
Directorate of Health and Public Safety | Law enforcement | 725015 | Crime Prevention Strategy |  | 1000000 | 1000000 |  | Correcting wrong Cost Centre | Correcting wrong Cost Centre | Correcting wrong Cost Centre
Directorate of Health and Public Safety | Traffic Services | 725020 | Traffic Safety Plan | 1000000 |  | 1000000
Directorate of Health and Public Safety | Health Services | 710005 | Development & Implementation of an Air Quality Management Plan | 1000000 |  | 1000000
Directorate of Health and Public Safety | Health Services | 710005 | Develop & Implement Municipal Health Services Delivery Plan | 2000000 |  | 2000000
Directorate of Community Services | Environmental Management | 755010 | Eradication of Alien Vegetation | 200000 |  | 200000
Directorate of Community Services | Environmental Management | 755010 | BCM Climate Change Strategy | 350000 |  | 350000
Directorate of Community Services | Environmental Management | 755010 | Environmental Education Strategy | 200000 |  | 200000
Directorate of Community Services | Environmental Management | 755010 | Integrated Environmental Management Plan & Integrated Coastal Zone Management Plan | 350000 |  | 350000
|  |  |  | 30498353 | 0 | 30498353
18. Own Funds c/o
Executive Support Services | GIS | 110015 | Cadastral Clean up and Maintenance | 240000 | 172964 | 412964 | Roll Overs from 2009/10 | Contract 2701. 3rd Year of maintenance phase of contract. Require a Total of R240,000 for the final year of contract. July, Augus, September 2011 Invoices submitted and cadastral data received. October to June 2012 invoice to be submitted as data is received and review. | The total budget for 3 years was transferred during the 2009/2010 budget adjustment process therefore a carry over for subsequent years was needed. Contractor gets paid as data is received and reveiwed. Adequate funding is required for the final year of the contract. R240 000 or R20 000 per month. | 25 June 2012
Executive Support Services | Public Participation | 120010 | Customer satisfaction survey | 350000 |  | 350000
Executive Support Services | Development Co-Operation | 120005 | Logo South Projects Management and coordination | 37878.77 | 17718 | 55596.77 |  | Project not limited to BCMM financial year | Project not limited to BCMM financial year | DEC 2012
Executive Support Services | Executive Support Services | 105005 | Ducatts - Sewerage | 40000 | -40000 | 0 |  | Busy with DCS regarding the contracts for trained staff
Directorate of Financial Services | Debtors Management Office | 330015 | Billing Debt Book c/o | 2997237 | -174845 | 2822392 |  | Funds Carry Over. Project at design/processing Phase. | Delays in Contract/Bid assessment to final award | Project contract awared April 2011 and is continuing to 2011/12 Financial year end.
Directorate of Financial Services | Debtors Management Office | 330015 | Billing Data Clean Up c/o | 1495497 |  | 1495497
Directorate of Financial Services | Asset and Risk | 320005 | Grap Implementation Project | 150000 | 76379 | 226379 |  | Contract ongoing - to be finalized 31/12/11 | The reason for the roll-over is that the service provider who is paid on a time-input basis was utilized less than what was expected. R150 000 is still required until the project completion date of 31/12/11. | Project to be completed by 31/12/11
Directorate of Financial Services | Rates and Valuations Office | 330005 | General valuations | 4758821.9 | -729841 | 4028980.9 |  | Project to be advertised in the November 2011 and Appointment by March 2012 | Provision of Funding pre -adverrtising | Project life 18-mths. Funds to be utilised for Supplementary Valuations 05 & 06
Directorate of Financial Services | Rates and Valuations Office | 330005 | Supplementary Valuations | 241178.1 | -241178 | 0.1 |  | SV 04 performed internally | Fourth Supplementary Valuation withdrawn | Project withdrawal, SV04
Directorate of Engineering Services | Office of the Director of Engineering Services | 505005 | Maintain Ablution Blocks in Informal Areas (EPWP) | 2000000 | -2000000 | 0
Directorate of Development Planning | Local Economic Development | 635005 | Tourism Business Support | 600000 | 240889 | 840889 |  | The service provider has been appointed and has commenced . The first payment has been made to the service provider. | The votes were blocked in the first quarter and were only open in the third quarter. This caused a delay in appointing the service provider. | The project will be completed by end of march in 2012.
Directorate of Development Planning | Local Economic Development | 635005 | Heritage and Tourism Route | 594193 | -100510 | 493683 |  | The service provider to implement the project has been appointed and has commenced with the implementation. The first payment has already been made to the service provider. | The votes were blocked in the first quarter and were only open in the third quarter. This caused a delay in appointing the service provider. | The project will be completed by the end of May.
Directorate of Development Planning | Local Economic Development | 635005 | Economic Planning | 300000 | 23093 | 323093 |  | The service provider to implement the project has been appointed and has commenced with the implementation. The first payment has already been made to the service provider. | The votes were blocked in the first quarter and were only open in the third quarter. This caused a delay in appointing the service provider. | The project will be completed at the end of April 2012.
Directorate of Development Planning | Local Economic Development | 635005 | Urban Agriculture | 493614 | -419803 | 73811 |  | Project is on going, request for informal tender for Dimbaza Agric coops in in progress to provide agricultural infraSTRUCTURE. Service provider was asppointed who could not deliver the required services. | Informal tender request for inputs | 1 month after budget Approval by Council
Directorate of Development Planning | Local Economic Development | 635005 | Cooperative Support Fund | 412863 | -338600 | 74263 |  | Project in progrss for Poultry Cooperative, structure finalised towards end June and therefore remaining funds to be utilised for operational inputs | Informal tender request for inputs | 1 month after budget Approval by Council
Directorate of Development Planning | Local Economic Development | 635005 | Informal Traders Development Programme | 381821 | -262497 | 119324
Directorate of Development Planning | Local Economic Development | 635005 | Trade and Investment | 485000 |  | 485000
Directorate of Development Planning | Transport Planning | 620005 | SDF Review & Implementation | 250000 | 3684 | 253684 |  | Consultants are appointed and project is underway with data analysis. It has been requested on a number of occasions that this be moved to the City Planning Cost Centre. Invoices have been received and can only be paid once roll-overs have been implemented. | Apointments were only finalised in June 2011. Finance indicated that the money could be rolled over if the funding was committed before the end of the FY. Funding was committed and appointments were made. No challenges | Project will be completed December 2011
Directorate of Development Planning | Transport Planning | 620005 | Transport planning | 1497438 | -795776 | 701662 |  | ITP review at Bid Evaluation stage. Tender awarded for Non-motorised Transport study | ITP Review:Tender award has been made and project to commence. Delays were caused by key staff shortages and funding not being released until 3rd quarter. NMT Study: Delays in signing Service Level Agreement, delays in councilors being appointed on Project Steering Committee | ITP review: Project to be completed by 31 March 2011 NMT Study: May 2012
Directorate of Development Planning | Transport Planning | 620005 | Transport policy and by-law | 305464 | -35464 | 270000 |  | Tender was requested to be cancelled | Delays caused by tender validity not being extended. Extension was required due to KZN ruling and other procurement delays (Bid Evaluation Committee requested SCM to provide report on preferred supplier capacity). Tender has been re-advertised and closes on 21 October 2011. | Project to be completed by 30 April 2012
Directorate of Development Planning | City Planning | 615070 | Vincent Berea Riview | 0 | 306140 | 306140 |  | Consultants are appointed and project is underway with data analysis. Invoices have been received and can only be paid once the roll-overs have been implemented. This project has been left off the rollover budget and finance has been requested several times to put it back. Therefore the division has included it. | Apointments were only finalised in June 2011. Finance indicated that the money could be rolled over if the funding was committed before the end of the FY. Funding was committed and appointments were made. No challenges. | Project will be completed December 2011
Directorate of Health and Public Safety | Disaster Management | 725055 | Disaster Management Structures | 236218 | -1830 | 234388 |  | Service provider appointed | D.M. Structure funding utilised for D.M. Framework Policy | March 2012
Directorate of Community Services | E.L. Regional Waste Disposal Sites & Transfer Station | 770030 | Intergrated Waste Management Plan of Buffalo City | 747255 |  | 747255
Directorate of Community Services | Zoo | 765025 | Section 78 Studies for the Zoo, Aquarium | 179298 |  | 179298
Municipal Manager's Office | Municipal Manager and Support Services | 205005 | Metro Status Impact Analysis | 0 | 990765.56 | 990765.56 |  | Metro readiness is an ongoing process and we are still incurring expenditure | Metro readiness is an ongoing process and we are still incurring expenditure | June 2012
Roll Overs from 2009/10
|  |  |  | 18793776.77 | -3308711.44 | 15485065.33
19. Urban Settlement Development Grant (USDG)
Chief Operations Officer | Housing Projects | 255005 | Mdantsane Zone 18 CC Phase 2-P4 | 127500 |  | 127500 | Roll Overs from 2009/10
Chief Operations Officer | Housing Projects | 255005 | Manyano & Thembelihle Phase 2-P4 | 680000 |  | 680000
Chief Operations Officer | Housing Projects | 255005 | Second Creek (Turn key )-P4 | 212000 |  | 212000
Chief Operations Officer | Housing Projects | 255005 | Potsdam unit ,Stage 2 - P4 | 783265 |  | 783265
Chief Operations Officer | Housing Projects | 255005 | Airport / Phase 2A Construction of new units-P4 | 156570 |  | 156570
Chief Operations Officer | Housing Projects | 255005 | Masibambane-P4 | 19890 |  | 19890
Chief Operations Officer | Housing Projects | 255005 | Masibulele-P4 | 20655 |  | 20655
Chief Operations Officer | Housing Projects | 255005 | Velwano-P4 | 25500 |  | 25500
Chief Operations Officer | Housing Projects | 255005 | Chris Hani Park Phase 3-P4 | 26775 |  | 26775
Chief Operations Officer | Housing Projects | 255005 | Ilinge-P4 | 25500 |  | 25500
Chief Operations Officer | Housing Projects | 255005 | Gwentshe Village-P4 | 6375 |  | 6375
Chief Operations Officer | Housing Projects | 255005 | Westbank Restitution-P1 | 7293600 |  | 7293600
Chief Operations Officer | Housing Projects | 255005 | Westbank Restitution-P2 | 2431200 |  | 2431200
Chief Operations Officer | Housing Projects | 255005 | Fynbos Informal 1-P2 | 256800 |  | 256800
Chief Operations Officer | Housing Projects | 255005 | Fynbos Informal 1-P4 | 27285 |  | 27285
Chief Operations Officer | Housing Projects | 255005 | Fynbos Informal 2-P2 | 1105200 |  | 1105200
Chief Operations Officer | Housing Projects | 255005 | Fynbos Informal 2-P4 | 25500 |  | 25500
Chief Operations Officer | Housing Projects | 255005 | Ndacama-P2 | 768000 |  | 768000
Chief Operations Officer | Housing Projects | 255005 | Ndacama-P4 | 25500 |  | 25500
Chief Operations Officer | Housing Projects | 255005 | Mathemba Vuso-P4 | 19125 |  | 19125
Chief Operations Officer | Housing Projects | 255005 | Deluxolo Village-P4 | 22440 |  | 22440
Chief Operations Officer | Housing Projects | 255005 | Francis Mei-P4 | 8670 |  | 8670
Chief Operations Officer | Housing Projects | 255005 | Mahlangu Village-P4 | 23205 |  | 23205
Chief Operations Officer | Housing Projects | 255005 | Sisulu Village-P4 | 19636 |  | 19636
Chief Operations Officer | Housing Projects | 255005 | Winnie Mandela-P4 | 38250 |  | 38250
Chief Operations Officer | Housing Projects | 255005 | Dacawa | 38250 |  | 38250
Chief Operations Officer | Housing Projects | 255005 | Sunny South-P4 | 25500 |  | 25500
|  |  |  | 14212191 | 0 | 14212191
20. SALAIDA c/o
Executive Support Services | Development Co-Operation | 120005 | GAVLE Projects 2008-2009 | 0 | 738298.33 | 738298.33 | Roll Overs from 2009/10 | Project not limited to BCMM financial year | 10 year anniversary in February 2012 | Dec. 2012
|  |  |  | 0 | 738298.33 | 738298.33
21. SETA c/o
Directorate of Corporate Services | Organisational Development | 420020 | Training and Development | 0 | 10282.14 | 10282.14 | Roll Overs from 2009/10 | Preparations for local government elections negatively affected availability of targeted councilors | Preparations for local government elections negatively affected availability of targeted councilors | Preparations for local government elections negatively affected availability of targeted councilors
Executive Support Services | Councillors | 105012 | Councillor Training | 0 | 1145430.7 | 1145430.7 | Roll Overs from 2009/10 | Funding had to be reserved for orientation and induction of newly elected councillors | Funding had to be reserved for orientation and induction of newly elected councillors | Funding had to be reserved for orientation and induction of newly elected councillors
|  |  |  | 0 | 1155712.84 | 1155712.84
22. Trust Funds c/o
Directorate of Development Planning | City Planning | 615070 | Planning - Potsdam Unit V | 0 | 127492 | 127492 | Roll Overs from 2009/10 | Service Providers have been appointed. Final draft layout plans completed and circulated for comments to line departments. Extensive delays in project completion due to very slow or no response of receiving of comments from critical technical department. Various reminders and requests for comments have been unsuccesful to date. Once all comments have been received can layout be finalised and submitted to council for approval. | Challenge is that comments from key line departments are still outstanding in regard to the final draft layout which has been circulated beginnig of the year. | End of December 2011 and the to be submitted to Council beginning of 2012.
Directorate of Development Planning | City Planning | 615070 | Map Preparation | 0 | 127492 | 127492 | Roll Overs from 2009/10 | Project linked to the Informal Settlement Study & Implementation Programme for the printing of maps and documents of the final report once approved by Council | None | End of financial year 2011/2012
|  |  |  | 0 | 254984 | 254984
|  |  |  | 356719667.77 | 22318718.38 | 379038386.15 | #VALUE!