## Per Funding
[10 empty] | ANNEXURE A |  |  | "ANNEXURE D"
2011/2012 1ST ROLL-OVER ADJUSTMENT BUDGET - CAPITAL PROJECTS
DIRECTORATE | COST CENTRE DESCRIPTION |  | PROJECT DESCRIPTION | 2011/2012 | 2011/2012 | 2011/2012 | COMMENTS | PROJECT STATUS phase as at 31 December 2011 (e.g. Contract not awarded, contract awarded, project on site, design phase, tender etc.) | REASONS why spending was not 50%: Name key challenges | TIME PERIOD to complete the project | 2011/2012 | 2011/2012 | Comments
|  | COST |  | APPROVED | BUDGET | 1st ROLL-OVER | [5 empty] | MID YEAR
|  | CENTRE |  | BUDGET | ADJUSTMENTS | ADJ. BUDGET |  |  |  |  | ADJUSTMENTS | BUDGET
1. Buffalo City Metropolitan Transport c/o
Development Facilitation and Partnership | Transport Planning & Operations Admin | 620005 | Potsdam/Needs Camp Bridge Feasibility Study | 710630 |  | 710630 |  |  |  |  | -476843 | 233787 | Work in Progress. Awaiting first invoice from service provider. Savings of R476,843
|  |  |  | 710630 |  | 710630 | 0 |  |  |  | -476843 | 233787
2. Disaster Management Fund c/o
Municipal Services | Disaster Management | 725055 | Disaster Management Capacity | 43940 | -7150 | 36790 |  | Tender Phase | Tender withdrawn, re-advertise. | March 2012 |  | 36790
Municipal Services | Disaster Management | 725055 | Disaster Management Centres | 84779 |  | 84779 | [5 empty] | 84779
Municipal Services | Disaster Management | 725055 | Flood Relocation (DM Structures) | 0 | 41025 | 41025 |  | Funding transferred to City Planning for the calculation of Duncan Village floodlines |  |  |  | 41025
|  |  |  | 128719 | 33875 | 162594 |  |  |  |  | 0 | 162594
3. DBSA Phase 4 and 5 c/o
Municipal Services | Roads and Stormwater Drainage | 525025 | West Bank Restitution | 0 | 5577424 | 5577424 |  | Project in progress with some technical challenges (contractual dispute on project quantities and specifications), which are being addressed. | Project in progress with some technical challenges (contractual dispute on project quantities and specifications), which are being addressed. | June 2012 |  | 5577424
Municipal Services | Roads and Stormwater Drainage | 525025 | Rural and Urban Roads | 0 | 10000000 | 10000000 |  | Project awarded | Project phased into three stages, phase 1 & 2 completed | February 2012 |  | 10000000
Municipal Services | Fire and Rescure Services | 725010 | KWT Fire Station | 0 | 2000000 | 2000000 | [5 empty] | 2000000
|  |  |  | 0 | 17577424 | 17577424 |  |  |  |  | 0 | 17577424
4. DEDEAT c/o
Development Facilitation and Partnership | Local Economic Development | 635005 | Hydro-ponics - MDT (funded by DEDEAT) | 0 | 5239.19 | 5239.19 | Roll Overs from 2009/10 | Procuring of seeds for Mdantsane Hydroponics | Late issuing of order number | 1 month after budget Approval by Council |  | 5239.19
|  |  |  | 0 | 5239.19 | 5239.19 |  |  |  |  | 0 | 5239.19
5. Dept of Sports Arts and Culture c/o
Strategic Management | Executive Support Sevices Office | 105005 | Upgrading of Sisa Dukashe, New Lands, Ndevana Stadium & Gompo Stadium. | 0 | 2272302.94 | 2272302.94 |  | Other sub-projects within the cluster are complete with exception of Ndevana. | Delays with electric connection from Eskom | Nov-2011 |  | 2272302.94
Strategic Management | Executive Support Sevices Office | 105005 | Upgrading of Bisho, Dimbaza, Peelton, Madramini & Victoria Grounds Stadium | 0 | 6598469.31 | 6598469.31 |  | Project was in progress(Bhisho Stadium will utilize the internal contractor and portion with annual contractor to complete the outstanding works once the funds are available) | Contracts for Bisho, Peelton & Victoria Grounds were terminated due to contractor's perfomance & had to be re-advertised. Victoria Grounds has since been completed. | Jan-2012 |  | 6598469.31
Strategic Management | Executive Support Sevices Office | 105005 | Upgrading of Tsholomnqa, Parkside, Needs Camp & North End. | 0 | 2208934.68 | 2208934.68 |  | Other sub-projects within the cluster are complete with exception of Tsholomnqa which is awaiting eskom connection. | Delays with electric connection from Eskom | Nov-2011 |  | 2208934.68
|  |  |  | 0 | 11079706.93 | 11079706.93 |  |  |  |  | 0 | 11079706.93
6. Dept of Science and Technology c/o
Municipal Services | Integrated Enviromental Management | 755035 | Dry Sanitation & Greywater Recycling | 0 | 173830.13 | 173830.13 |  | Project incomplete. | There's a pending investigation on project implementation and current expenditure |  |  | 173830.13
Municipal Services | Integrated Enviromental Management | 755035 | Waste Minimisation | 0 | 160317 | 160317 |  | Ongoing process | Waste Minimisation is an ongoing process as the institution is faced with a huge challenge around waste management | Ongoing process |  | 160317
|  |  |  | 0 | 334147.13 | 334147.13 |  |  |  |  | 0 | 334147.13
7. Dept of Land Affairs c/o
Development Planning & Management | Land Administration | 615080 | West Bank Restitution Project | 0 | 4141302.75 | 4141302.75 |  | 80% of Titles have been registered. | Process of registration is protracted. | 01 June 2012 |  | 4141302.75
Development Planning & Management | Land Administration | 615080 | West Bank Land Restitution | 0 | 243551.48 | 243551.48 |  | 80% of Titles have been registered. | Process of registration is protracted. | 01 June 2012 |  | 243551.48
|  |  |  | 0 | 4384854.23 | 4384854.23 |  |  |  |  | 0 | 4384854.23
8. DLGTA c/o
Finance and Support Services | Supply Chain Management | 320010 | Implementation of Intenda Electronic Software System | 0 | 10642.88 | 10642.88 | Roll Overs from 2009/10 | Project on site | Ongoing project | FYE |  | 10642.88
|  |  |  | 0 | 10642.88 | 10642.88 |  |  |  |  | 0 | 10642.88
9. Eastern Cape Development Co-Operation c/o
Municipal Services | Sewerage Interceptors | 515035 | Bulk Sanitation | 0 | 67358.44 | 67358.44 | Roll Overs from 2009/10 | Roll Over from 2010/2011 Fin Year. Project to be completed this financial year 2011/2012 | Roll Over from 2010/2011 Fin Year. Project to be completed this financial year 2011/2012 | Roll Over from 2010/2011 Fin Year. Project to be completed this financial year 2011/2012 |  | 67358.44
|  |  |  | 0 | 67358.44 | 67358.44 |  |  |  |  | 0 | 67358.44
10. European Commission c/o
Municipal Services | Fire and Rescure Services | 725010 | Upgrade Mdantsane Fire Stations | 0 | 171183.39 | 171183.39 |  | Design Phase | Delays with appointment of service providers. | June 2012 | -171183 | 0.39 | Declared as savings
|  |  |  | 0 | 171183.39 | 171183.39 |  |  |  |  | -171183 | 0.39
11. Electricity Demand Side Management
Municipal Services | Electricity Planning & Design | 535025 | Replacement of Street Lights | 4000000 |  | 4000000 | Roll Overs from 2009/10 |  |  |  |  | 4000000
|  |  |  | 4000000 | 0 | 4000000 |  |  |  |  | 0 | 4000000
11. Electricity Demand Side Management c/o
Municipal Services | Electricity Planning & Design | 535025 | Replacement of Street Lights | 0 |  | 0 | Roll Overs from 2009/10 |  |  |  | 1724 | 1724 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
|  |  |  | 0 | 0 | 0 |  |  |  |  | 1724 | 1724
12. Human Settlements Development Grant (HSDG)
Municipal Services | Housing Department | 255005 | Reeston Phase 3 Stage 2-P3 | 22418000 |  | 22418000 | Roll Overs from 2009/10 |  |  |  | -7418000 | 15000000 | Expenditure to be incurred from end March 2012.
Municipal Services | Housing Department | 255005 | DVRI Pilot project 323 units (Mekeni ,Competition site,Haven Hills) | 7241014 |  | 7241014 | Roll Overs from 2009/10 |  |  |  |  | 7241014 | Contractor on site, funding to be used before end of financial year.
Municipal Services | Housing Department | 255005 | Mdantsane Access/Buffalo | 1412820 |  | 1412820 | Roll Overs from 2009/10 |  |  |  | -1412820 | 0 | BCMM has received reservation of PDoHS funding for the project in the 2011 /2012 financial year.
Municipal Services | Housing Department | 255005 | Reeston Phase 3 Stage 3 | 5604500 |  | 5604500 | Roll Overs from 2009/10 |  |  |  | -5604500 | 0 | Calling for bids for the provision of internal services and top structures will be done in the last quarter of the financial year.
Municipal Services | Housing Department | 255005 | Block yard TRA-P3 | 2668500 |  | 2668500 | Roll Overs from 2009/10 |  |  |  | -2000000 | 668500 | Contractor has been appointed.
|  |  |  | 39344834 | 0 | 39344834 |  |  |  |  | -16435320 | 22909514
13. Intergrated National Electricity Programme (INEP)
Municipal Services | Electricity Planning & Design | 535025 | Electrification | 21000000 |  | 21000000 | Roll Overs from 2009/10 |  |  |  |  | 21000000
|  |  |  | 21000000 | 0 | 21000000 |  |  |  |  | 0 | 21000000
14. Leiden Platform c/o
Strategic Management | Development Co-Operation | 120005 | Leiden Twinning - Floodplain | 0 | 488000 | 488000 |  | Work continuation of past financial year | Work continuation of past financial year | Dec. 2012 |  | 488000
Strategic Management | Development Co-Operation | 120005 | Leiden Twinning - Solid Waste Drop-off Points | 0 | 974717.59 | 974717.59 |  | SCM processes are in place to draft a memo to the Bid Adjudication for the appointment of the Secon Lowest Bidder | Service provider submitted a withdrawal letter | June 2012 |  | 974717.59
Strategic Management | Development Co-Operation | 120005 | Leiden Twinning - Sanitation | 0 | 746896.53 | 746896.53 |  | Construction of ablution blocks in Nompumelelo -Project lifecycle different to BCMM financial year | Work continuation of past financial year | Dec. 2012 |  | 746896.53
Strategic Management | Development Co-Operation | 120005 | Leiden Twinning Project - Solid Waste | 0 | 512605.52 | 512605.52 |  | Work continuation of past financial year | Capacity issues with Solid waste department | Dec. 2012 |  | 512605.52
|  |  |  | 0 | 2722219.64 | 2722219.64 |  |  |  |  | 0 | 2722219.64
15. Local Government and Housing c/o
Municipal Services | Housing Department | 255005 | Potsdam Unit P : Stage 2 : 1000 units : P3 : Infrastructure | 0 | 336462.15 | 336462.15 |  | Contractor on site | Work practically completed on site payments will held till end retention period. | Budget will be spent in this current financial year |  | 336462.15 | Construction monitoring
Municipal Services | Housing Department | 255005 | Accreditation | 0 | 33903 | 33903 |  | Ongoing | The funding is for office requirements for the demand database programme. | Budget will be spent in this current financial year |  | 33903
Municipal Services | Housing Department | 255005 | Z. Soga: P3: Infrastructure | 0 | 274096.84 | 274096.84 |  | Almost complete. (Practical complete) | Awaiting the approval of additional funding by the PDoHS to pay the final payment of the service provider.The project should be closed off in 2011/2012 financial year. | On approval of additional funding by PDoHS and roll over budget by the Council. | -274097 | -0.16 | The project is complete.
|  |  |  | 0 | 644461.99 | 644461.99 |  |  |  |  | -274097 | 370364.99
15. Municipal Infrastructure Grant c/o
Municipal Services | Sewerage Admin | 515010 | Quinera Treatment Works | 0 |  | 0 |  |  |  |  | 8508421 | 8508421 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Sewerage Admin | 515010 | Bufferstrip Sanitition - Mdantsane | 0 |  | 0 |  |  |  |  | 201328 | 201328 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Water Ops and Maint.-Inland | 520025 | Amahleke Water Supply | 0 |  | 0 |  |  |  |  | 961009 | 961009 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Water Ops and Maint.-Inland | 520025 | Bulk Water Supply Newlands and other Areas | 0 |  | 0 |  |  |  |  | 47927 | 47927 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Sewerage Admin | 515010 | Construction of high level Reservoirs Breidbach | 0 |  | 0 |  |  |  |  | 100000 | 100000 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Roads and Stormwater Drainage | 525025 | Rehabilitation of Rural Roads Upgrade | 0 |  | 0 |  |  |  |  | 856328 | 856328 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Halls | 760025 | Rural Community Halls Rehabilitation (Airport & St Mary) | 0 |  | 0 |  |  |  |  | 625764 | 625764 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Sportsfields | 765010 | Rural Sports Facilities | 0 |  | 0 |  |  |  |  | 406901 | 406901 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Sewerage Admin | 515010 | Bulk Water Supply - Needscamp | 0 |  | 0 |  |  |  |  | 5300000 | 5300000 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Sewerage Admin | 515010 | Rural sanitation | 0 |  | 0 |  |  |  |  | 15000000 | 15000000 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Roads and Stormwater Drainage | 525025 | Upgrading and Rehabilitation of BCMM Roads-Nomgwadla | 0 |  | 0 |  |  |  |  | 600000 | 600000 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Roads and Stormwater Drainage | 525025 | Upgrading and Rehabilitation of BCMM Roads-Ngxwalana | 0 |  | 0 |  |  |  |  | 600000 | 600000 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Roads and Stormwater Drainage | 525025 | Upgrading and Rehabilitation of BCMM Roads-Msintsini | 0 |  | 0 |  |  |  |  | 600000 | 600000 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Roads and Stormwater Drainage | 525025 | Upgrading and Rehabilitation of BCMM Roads-Kwelera | 0 |  | 0 |  |  |  |  | 600000 | 600000 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Roads and Stormwater Drainage | 525025 | Upgrading and Rehabilitation of BCMM Roads-Balasi | 0 |  | 0 |  |  |  |  | 600000 | 600000 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Roads and Stormwater Drainage | 525025 | Upgrading and Rehabilitation of BCMM Roads-Ncera villages 5-9 | 0 |  | 0 |  |  |  |  | 1000000 | 1000000 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Roads and Stormwater Drainage | 525025 | Upgrading and Rehabilitation of BCMM Roads-Kuni,Needscamp | 0 |  | 0 |  |  |  |  | 1000000 | 1000000 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
Municipal Services | Roads and Stormwater Drainage | 525025 | Upgrading and Rehabilitation of BCMM Roads-Tsholomnqa | 0 |  | 0 |  |  |  |  | 493211 | 493211 | Roll Over from 10/11 Conditional Grants Approved by National Treasury in Feb 2012
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 37500889 | 37500889
16. Office of the Premier
Municipal Services | Arts & Cultural Services Admin | 760005 | Egerton Railway Station Massacre Memorial Site | 0 | 500000 | 500000 | Roll Overs from 2009/10 | Not awarded | The project has been delayed, due to an unclear mandate and also not having received the necessary approvals timeously from the Donor.This funding is urgently required for the contruction of the Egerton Memorial.Bids have been received and the funding is now required for the BAC report, in order to appoint a contractor to begin the work. | June 2012 |  | 500000
|  |  |  | 0 | 500000 | 500000 |  |  |  |  | 0 | 500000
17. Own Funds
Strategic Management | Office of the Municipal Manager & Support Services | 205005 | Councillor's IT requirements (Laptops) | 1000000 |  | 1000000 | [5 empty] | 1000000
Finance and Support Services | Asset and Risk | 320005 | Asset Replacements | 0 | 10000000 | 10000000 |  | R10 million is for the Asset Replacements in respect of Insurance Claims for the entire BCM for 2011/2012 financial year | R10 million is for the Asset Replacements in respect of Insurance Claims for the entire BCM for 2011/2012 financial year | June 2012 |  | 10000000
Finance and Support Services | General Admin & Telecomm Services | 415015 | BCM IT Requirements (All Directorates) | 5000000 |  | 5000000 | [5 empty] | 5000000
Finance and Support Services | Management Information Services | 415025 | Integrated Enterprise Resource planning System | 2000000 |  | 2000000 | [5 empty] | 2000000
Municipal Services | Sewerage Pump Station - Coastal | 515021 | Ablution Blocks Duncan Village | 2095378 |  | 2095378 | [5 empty] | 2095378
Municipal Services | Fleet management - Braelyn | 530020 | BCM Fleet | 7500000 |  | 7500000 | [5 empty] | 7500000
Development Facilitation and Partnership | Market | 635010 | Extension of Sales Hall | 2000000 |  | 2000000 | [5 empty] | 2000000
Municipal Services | Refuse Removal | 770010 | Purchase of 7 Refuse Compactor Trucks - Mdantsane | 10500000 |  | 10500000 | [5 empty] | 10500000
Municipal Services | Refuse Removal | 770010 | Purchase of 3 Refuse Compactor Trucks (Mdantsane) | 4500000 |  | 4500000 | [5 empty] | 4500000
Municipal Services | Refuse Removal | 770010 | Purchase of 2 x LDV Bakkie's | 460000 |  | 460000 | [5 empty] | 460000
Municipal Services | Refuse Removal | 770010 | Purchase of 1 X Load lugger | 800000 |  | 800000 | [5 empty] | 800000
Municipal Services | Office of the Director of Community Services | 750005 | Refuse 5 Compactor Trucks - Coastal Region | 10000000 |  | 10000000 | [5 empty] | 10000000
Municipal Services | Office of the Director of Community Services | 750005 | Vehicles for Solid Waste Supervisors, Safety Officers, District Cleansing Officers and Superintendents -(9 X Sedans, 8 LDV's, 3 X Double Cabs, 2X3 Ton Trucks (Inland,Midlands and Coastal Areas) | 4000000 |  | 4000000 | [5 empty] | 4000000
Municipal Services | Interments | 755025 | Vehicle | 385000 |  | 385000 |  |  |  |  | -86776 | 298224 | Balance of R125 782 removed by directorate of finance. As such expenditure is completed. Challenges & remedial action: funding of R180 00 reflected on 2011/12 budget, funding later removed by finance directorate.
Municipal Services | Halls | 760025 | Continuation of refurbishment of KWT Hall | 2792507 |  | 2792507 | [5 empty] | 2792507
Municipal Services | Halls | 760025 | Upgrading of Beacon Bay Library | 363795 |  | 363795 | [5 empty] | 363795
Municipal Services | Swimming Pools | 765015 | Ruth Belonsky Swimming Pool | 137822 |  | 137822 |  |  |  |  | -125102 | 12720 | Project completed in September 2011.
Municipal Services | Resorts | 765035 | Intergrated Beach Front hub | 500000 |  | 500000 | [5 empty] | 500000
Municipal Services | Cleansing Administration Support | 770005 | Grass Cutting Equipment | 1300000 |  | 1300000 | [5 empty] | 1300000
Municipal Services | Waste Disposal Sites | 770015 | Refuse removal Skips | 1000000 |  | 1000000 | [5 empty] | 1000000
Municipal Services | E.L.Regional Waste Disposal Site & Transfer Station | 770030 | Regional Waste Disposal Site | 1000000 |  | 1000000 | [5 empty] | 1000000
Municipal Services | Traffic Administration | 725020 | Traffic Vehicles | 450000 |  | 450000 | [5 empty] | 450000
Municipal Services | Vehicle Test Station / Examination | 725035 | Learners Licence Centre - Mdantsane | 800000 |  | 800000 | [5 empty] | 800000
Strategic Management | Office of the Municipal Manager & Support Services | 205005 | Furniture | 0 |  | 0 |  |  |  |  | 50000 | 50000 | Establishment costs for Council Committees- MPAC
Municipal Services | Electricity Planning & Design | 535025 | High Mast Lighting - Sweetwaters | 0 |  | 0 |  |  |  |  | 900000 | 900000 | New project - Sweetwaters . At award stage.
Development Facilitation and Partnership | Transport Planning & Operations Admin | 620005 | Yellowwoods River Bridge | 0 |  | 0 |  |  |  |  | 200000 | 200000 | R200,000 required to complete the construction of the Yellowwoods river Bridge project (Consultants fees)
Finance and Support Services | Debtors Management Office | 330015 | Meter reading handheld machines | 0 |  | 0 |  |  |  |  | 2856000 | 2856000 | Meter reading handheld machines required for additional meter readers appointed in order to avoid averaging of water consumption.
Municipal Services | Electricity Planning & Design | 535025 | Electrification - Counterfunding Reeston & Other Areas | 0 |  | 0 |  |  |  |  | 2000000 | 2000000 | In terms of the DoE conditional grant agreement BCMM to provide 40% counter funding.
Municipal Services | Electricity Planning & Design | 535025 | Upgrade of Bulk Electricity Infrastructure | 0 |  | 0 |  |  |  |  | 7900000 | 7900000 | Upgrading and recapitalisation of bulk electricity infrastructure to conter deferred maintenance and maintain a sustainable supply of energy.
Municipal Services | Electricity Planning & Design | 535025 | Streetlighting | 0 |  | 0 |  |  |  |  | 300000 | 300000 | Street lighting requests from different wards are received continuosly. Street lighting is good for crime prevention.
Development Planning & Management | Land Administration | 615080 | Land Acquisition - Construction of Wesbank Restitution Reservoir) | 0 |  | 0 |  |  |  |  | 600000 | 600000 | Land has been identified on Farm 922 for the construction of a Reservoir. The subdivision and registration of the diagram in respect of portion 2 of Farm 922 East London by the Surveyor General necessitates that funds be made available for payment of the purchase price of R450 000. Additional Funds of up to R150 000 need to be availed for the purpose of conveyancing fees re Tenure Upgrading transactions.
|  |  |  | 58584502 | 10000000 | 68584502 | 0 | 0 | 0 | 13994122 | 14594122 | 83178624
18. Own Funds c/o
Finance and Support Services | Customer Care | 330020 | KWT civic Centre Payments Hall upgrade | 1998597 |  | 1998597 | Roll Overs from 2009/10 |  |  |  | -1298597 | 700000 | Tender awarded on 17/05/2011 for the amount of R340,000 at 82sqm & the consultants were officially appointed on 13/06/2011. However, based on the increased scope of work, consultants fee was increased to R700 000.00 for 320 sqm .Since July 2011, the following have been completed: • On-site investigation • Final sketch plans and estimating costs of upgrading amounting to R4,2 million and will be budgeted for in the 2012/13 financial year.
Finance and Support Services | Customer Care | 330020 | Upgrading of all Zone Offices -Mdantsane | 3498597 |  | 3498597 |  |  |  |  | -3498597 | 0 | Project will not be implemented in the current financial year due to land disputes and unspent funds have been re-diredted to other project.s
Finance and Support Services | Management Information Services | 415025 | Telecommunication network system | 107884.68 | 94390 | 202274.68 |  | Informal tender was awarded but the service provider could not deliver. | The service provider appointed could not deliver the service. | 2011-11-30 |  | 202274.68
Finance and Support Services | Management Information Services | 415025 | Conferencing system | 598941.28 | -338911 | 260030.28 |  | Contract not awarded. | We were awaiting the award of network support tender. | 2011-03-31 |  | 260030.28
Finance and Support Services | Management Information Services | 415025 | Radio Data Network - Mdantsane | 166469.24 | 8762 | 175231.24 |  | Informal tender was awarded but the service provider could not deliver. | The service provider appointed could not deliver the service. | 2011-11-30 |  | 175231.24
Municipal Services | Office of the Director of Engineering Services | 505005 | Building Security | 300000 | -174341 | 125659 | [5 empty] | 125659
Municipal Services | Electricity Administration | 535005 | Electrification - Counterfunding Reeston & Other Areas | 2800000 | -2800000 | 0 | [5 empty] | 0
Municipal Services | Electricity Planning & Design | 535025 | Electricity Building Upgrade- Ablution Blocks | 145000 | 20923 | 165923 |  | Design Phase | Delays in compiling tender documents | 30 June 2012 |  | 165923
Municipal Services | Electricity Planning & Design | 535025 | Upgrade Electricity Reticulation (KWT and Coastal) | 3500000 | -3448826 | 51174 |  | Ongoing Project | Insufficient Funding | Insufficient Funding |  | 51174
Municipal Services | Roads and Stormwater Drainage | 525025 | Rehabilitation of BCM bridges and culverts( Breidbach, Dimbaza, Quigney) | 1992904 | -19908 | 1972996 |  | Project at bid specification stage | Funding was not available | April 2012 |  | 1972996
Municipal Services | Sewerage Pump Station - Coastal | 515021 | Upgrade Augmentation | 110220 | 415030 | 525250 |  | Will be completed this financial year | Will be completed this financial year | Will be completed this financial year |  | 525250
Municipal Services | Scientific Services | 510005 | Upgrading of the Laboratory infrastructure and equipment | 757856 | 150732 | 908588 |  | Funding for 2 tenders awarded in 2010/11 financial year. 1st tender awarded and awaiting equipment delivery. 2nd tender awarded and configuration in progress. | 1st tender - equipment shipped from overseas. 2nd tender - configuration requires input of large volume of laboratory data. | 1st tender - October 2011. 2nd tender - February 2012. |  | 908588
Development Facilitation and Partnership | Local Economic Development | 635005 | Tourism infrastructure development | 1000000 | 797478 | 1797478 | [5 empty] | 1797478
Development Facilitation and Partnership | Local Economic Development | 635005 | Roll – Out Hydroponics | 3500000 | 130503 | 3630503 |  | Was in the process of Bid Committess because the contract had to be readvertised due to non response to previous advert | Contract awarded in September 2011 | 4 months from the date of Budget Approval by Council |  | 3630503
Development Facilitation and Partnership | Local Economic Development | 635005 | Buffalo City Agric & Rural Development Infrastructure | 2992741 | -199740 | 2793001 |  | In the bid committees, validity period expired. Still awaiting approval for cancellation of bids and readvertising | Still awaiting approval for cancellation of bids and readvertising of bids | 6 months from the date of Budget Approval by Council |  | 2793001
Development Facilitation and Partnership | Local Economic Development | 635005 | Cooperative Support Programme | 1449188 | -1202733 | 246455 | [5 empty] | 246455
Development Facilitation and Partnership | Market | 635010 | Upgrade of Market | 1320000 | -360105 | 959895 |  | Phase one of the project was complete. Planning for phase 2 was underway. | Project implementation relied on completion of Phase One (Extension of sales hall). Phase one was only completed at the end of April 2011. | Project to be completed by June 2012 |  | 959895
Development Facilitation and Partnership | Transport Planning & Operations Admin | 620005 | Rural non Motorised Transport facilities | 494490.5 |  | 494490.5 |  |  |  |  | -163891 | 330599.5 | Work in Progress Awaiting first invoice from service provider to the value of R 174,224 being processed.
Development Facilitation and Partnership | Transport Planning & Operations Admin | 620005 | Traffic Management Measures | 1100000 | 714607 | 1814607 |  | Designs completed, moving to construction phase. | Project postponed as all contract 26 civil contractors had already been fully utilised by roads maintenance department. | Project to be completed by June 2012 |  | 1814607
Development Facilitation and Partnership | Transport Planning & Operations Admin | 620005 | Pedestrian facilities | 600000 | -256092 | 343908 |  | Annual milestones achieved, project ongoing | Sole supplier purchase issues with SCM. Informal tender process had to be used. | Project to be completed by June 2012 |  | 343908
Development Facilitation and Partnership | Transport Planning & Operations Admin | 620005 | Guidance Signage | 600000 | -13554 | 586446 |  | Annual milestones achieved, project ongoing | Funding only released in third quarter and delays with procurement processes due to tender not being minuted at Bid Specification meeting | Project to be completed by June 2012 |  | 586446
Development Facilitation and Partnership | Transport Planning & Operations Admin | 620005 | Yellowwoods River Bridge | 1900000 | 202612 | 2102612 |  | Contractor is on site and project is in the final stages of completion | This is a multi-year project and some delays were incurred due to rain | Project is complete |  | 2102612
Municipal Services | Office of the Director of Community Services | 750005 | Miscallaneous Bins | 58000 | -58000 | 0 |  | Project Complete | Project Complete | Project Complete |  | 0
Municipal Services | Interments | 755025 | Fencing of Rural Cemeteries Upgrade | 160000 | 154956 | 314956 |  | Order to Palisade fencing with SCM | Project initiated in 2010/11 financial year and thus a roll over | Dec 2011 |  | 314956
Municipal Services | Sportsfields | 765010 | Upgrading of Needs Camp Sportfield | 2350877 | 149123 | 2500000 |  | The terms of reference for the appointment of a professional service provider was forwarded to SCM on 30 June 2011. No feedback from SCM to date. | Lack of feedback from SCM | June 2012 |  | 2500000
Municipal Services | Sportsfields | 765010 | Upgrading of Rural Sportsfields | 275821 | -203783 | 72038 |  | Service Provider on site levelling the playing area at Nkqonkqweni as part of scope of work for phase 1. Stock fencing of sportsfields to follow | Project was initiated late in the 2010/11 financial year and thus was rolled over. Lack of feedback from SCM | June 2012 |  | 72038
Municipal Services | Zoo | 765025 | Upgrading Of Zoo Offices & Ablution Blocks | 920501 | -197247 | 723254 |  | The letter of appointment of service provider has been received. According to Architects Division, they are awaiting a construction guarantee from the service provider before proceeding with implementation of the project | Project was initiated late in the 2010/11 financial year and thus was rolled over. Competitive bidding process was followed for this project and thus took up a significant amount of time | June 2012 |  | 723254
Municipal Services | Zoo | 765025 | Fencing Of Zoo c/o | 606481 |  | 606481 |  | Chacma baboon, hamadrayas enclosure and tiger swimming pool completed. Jaguaur swimming pool not yet completed. | Jaguar pool was not yet completed, therefore payment was not done to the service provider. According to the Architects Division a portion of the funding from this project will be combined with the project of Upgrading of the zoo offices and ablution blocks. | June 2012 |  | 606481
Municipal Services | Beaches | 765030 | Vehicles | 348765 | -348765 | 0 |  | Tenders advertised by Mechanical Services | Awaiting feedback from Mechanical Services on progress with the tender | June 2012 |  | 0
Municipal Services | E.L.Regional Waste Disposal Site & Transfer Station | 770030 | Drop Off Points - Solid Waste | 210479 | -210479 | 0 |  | Project Complete | Project Complete | Project Complete |  | 0
Municipal Services | Pollution Control | 710040 | Air quality monitoring station equipment | 412163.49 | -311895 | 100268.49 |  | Informal requesition to be forwarded to SCM 18/10/11 |  |  |  | 100268.49
Municipal Services | Clinics | 710020 | Mobile Clinics Equipment | 235495 |  | 235495 | [5 empty] | 235495
Municipal Services | Clinics | 710020 | Upgrading of Clinics - Ginsberg | 598124 | 100000 | 698124 |  | An Amount of R73 659.79 has been paid to Life Connections Manufacturing & Supply. The progress of the construction is a bit slow. | The progress of the construction is a bit slow. |  |  | 698124
Municipal Services | Security Services | 725015 | Law Enforcement Equipment | 180000 | -161399 | 18601 |  | Contract awarded for licence plate recognition system - R161 399. | Tender prices were less than anticipated. | March 2012 |  | 18601
Municipal Services | Fire and Rescue Services | 725010 | Fire Engines Roll 0ver | 11502141 | 4456705 | 15958846 |  | Contract awarded. | Awaiting delivery & final invoice. | Nov. 2012 |  | 15958846
Municipal Services | Fire and Rescue Services | 725010 | Fire Engine Equipment | 2874803 | -503399 | 2371404 |  | Tender phase | Awaiting delivery & final invoice. | Rescue sets January 2012 B.A Sets x 100 January 2012 Urban Rescue Veh. Jun. 2012 |  | 2371404
Strategic Management | Executive Support Sevices Office | 105005 | Councillors Office | 0 | 2060844.76 | 2060844.76 | [5 empty] | 2060844.76
Municipal Services | Fleet Management - Braelyn | 530020 | Replacement of Bus Fleet | 0 | 5998398.75 | 5998398.75 |  | 5 solid waste trucks | The manufacture is still building the trucks | In 2months for the entire delivery |  | 5998398.75
Municipal Services | Fleet Management - Braelyn | 530020 | Traffic & Law Enforcement Fleet | 0 | 3000000 | 3000000 |  | 10 Traffic & Law enforcement sedans (2924) | The vehicles were delivered after the end of the financial year | Vehicles delivered & paid |  | 3000000
|  |  |  | 51666539.19 | 7645887.51 | 59312426.7 |  |  |  |  | -4961085 | 54351341.7
19. Provincial Treasury Office - LED Support Programme
Development Facilitation and Partnership | Local Economic Development | 635005 | Inner City regeneration - Pedestrian Priority Zone | 0 | 375269.23 | 375269.23 | Roll Overs from 2009/10 | Contract Awarded | Roll over is requested to do the final payment of R309,215-50 | Final payment as soon as the Report has been approved by Council |  | 375269.23
|  |  |  | 0 | 375269.23 | 375269.23 |  |  |  |  | 0 | 375269.23
20. Public Transport Infrastructure and Systems Grant (PTISG)
Development Facilitation and Partnership | Transport Planning & Operations Admin | 620005 | Construction of BRT lanes | 180000000 |  | 180000000 | Roll Overs from 2009/10 |  |  |  | -80000000 | 100000000 | Cash flow projections to be finalized after commencement of Business Plan project.
|  |  |  | 180000000 | 0 | 180000000 | 0 | 0 | 0 | 0 | -80000000 | 100000000
21. Public Transport Infrastructure and Systems Grant (PTISG) c/o
Development Facilitation and Partnership | Transport Planning & Operations Admin | 620005 | Implement Bus Rapid Transit System | 0 |  | 0 |  |  |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22. Urban Settlement Development Grant (USDG)
Municipal Services | Housing Department | 255005 | Mdantsane Zone 18 CC Phase 2-P3 | 11209000 |  | 11209000 | Roll Overs from 2009/10 |  |  |  | -11209000 | 0 | EIA has still to be completed.
Municipal Services | Housing Department | 255005 | Manyano & Thembelihle Phase 2-P3 | 19055300 |  | 19055300 | [5 empty] | 19055300 | Contractor currently working on site
Municipal Services | Housing Department | 255005 | Second Creek (Turn Key)-P3 | 5940770 |  | 5940770 |  |  |  |  | 8000000 | 13940770 | The project is being taken through bidding assessment.
Municipal Services | Housing Department | 255005 | Masibambane-P3 | 1748604 |  | 1748604 |  |  |  |  | -1498604 | 250000 | Whilst waiting for the completion of the EIA the Municipality has started to appoint professional teams that will complete the designs.
Municipal Services | Housing Department | 255005 | Masibulele-P3 | 1793440 |  | 1793440 |  |  |  |  | -1543440 | 250000 | Whilst waiting for the completion of the EIA the Municipality has started to appoint professional teams that will complete the designs.
Municipal Services | Housing Department | 255005 | Velwano | 2241800 |  | 2241800 |  |  |  |  | -1791800 | 450000 | Whilst waiting for the completion of the EIA the Municipality has started to appoint professional teams that will complete the designs.
Municipal Services | Housing Department | 255005 | Chris Hani Park Phase 3-P3 | 2353890 |  | 2353890 |  |  |  |  | -2153890 | 200000 | Tenders for the appointment of professional team are currently being assesed for evalaution. Appointment will be made in March 2012.
Municipal Services | Housing Department | 255005 | Ilinge -P 3 | 2241800 |  | 2241800 |  |  |  |  | -1641800 | 600000 | Tenders for the appointment of professional team are currently being assesed for evalaution. Appointment will be made in March 2012.
Municipal Services | Housing Department | 255005 | Gwentshe Village- P3 | 560450 |  | 560450 |  |  |  |  | -510450 | 50000 | Whilst waiting for the completion of the EIA the Municipality has started to appoint professional teams that will complete the designs.
Municipal Services | Housing Department | 255005 | Fynbos Informal 1-P3 | 2398726 |  | 2398726 |  |  |  |  | -1898726 | 500000 | Tenders for the appointment of professional team are currently being assesed for evalaution. Appointment will be made in March 2012.
Municipal Services | Housing Department | 255005 | Fynbos Informal 2-P3 | 2241800 |  | 2241800 |  |  |  |  | -1741800 | 500000 | Tenders for the appointment of professional team are currently being assesed for evalaution. Appointment will be made in March 2012.
Municipal Services | Housing Department | 255005 | Ndacama-P3 | 2241800 |  | 2241800 |  |  |  |  | -2241800 | 0 | Tenders for the appointment of professional team are currently being assesed for evalaution. Appointment will be made in March 2012.
Municipal Services | Housing Department | 255005 | Mathemba Vuso-P3 | 1681350 |  | 1681350 |  |  |  |  | -1381350 | 300000 | Whilst waiting for the completion of the EIA the Municipality has started to appoint professional teams that will complete the designs.
Municipal Services | Housing Department | 255005 | Deluxolo Village-P3 | 1972784 |  | 1972784 |  |  |  |  | -1772784 | 200000 | Tenders for the appointment of professional team are currently being assesed for evalaution. Appointment will be made in March 2012.
Municipal Services | Housing Department | 255005 | Francis Mei-P3 | 762212 |  | 762212 |  |  |  |  | -662121 | 100091 | Tenders for the appointment of professional team are currently being assesed for evalaution. Appointment will be made in March 2012.
Municipal Services | Housing Department | 255005 | Mahlangu Village-P3 | 2040038 |  | 2040038 |  |  |  |  | -1840038 | 200000 | Tenders for the appointment of professional team are currently being assesed for evalaution. Appointment will be made in March 2012.
Municipal Services | Housing Department | 255005 | Sisulu Village-P3 | 1726186 |  | 1726186 |  |  |  |  | -1426186 | 300000 | Tenders for the appointment of professional team are currently being assesed for evalaution. Appointment will be made in March 2012.
Municipal Services | Housing Department | 255005 | Winnie Mandela-P3 | 1681350 |  | 1681350 |  |  |  |  | -1281350 | 400000 | Tenders for the appointment of professional team are currently being assesed for evalaution. Appointment will be made in March 2012.
Municipal Services | Housing Department | 255005 | Dacawa-P3 | 1681350 |  | 1681350 |  |  |  |  | -1281350 | 400000 | Whilst waiting for the completion of the EIA the Municipality has started to appoint professional teams that will complete the designs.
Municipal Services | Housing Department | 255005 | Sunny South-P3 | 2241800 |  | 2241800 |  |  |  |  | -1641800 | 600000 | Whilst waiting for the completion of the EIA the Municipality has started to appoint professional teams that will complete the designs.
Municipal Services | Housing Projects | 255005 | Potsdam Unit P | 0 |  | 0 |  |  |  |  | 1360000 | 1360000 | Additional budget required for rectification of 115 affected sewer connections in Potsdam unit P
Municipal Services | Housing Department | 255005 | Block yard TRA-P3 | 0 |  | 0 | Roll Overs from 2009/10 |  |  |  | 2500000 | 2500000 | Additional budget is required for the implementation of the project
Municipal Services | Roads and Stormwater Drainage | 525025 | Mdantsane Roads | 42375700 |  | 42375700 | [5 empty] | 42375700
Municipal Services | Roads Design | 525020 | West Bank Restitution | 15000000 |  | 15000000 | [5 empty] | 15000000
Municipal Services | Roads Design | 525020 | Rural Roads Upgrade | 5000000 |  | 5000000 | [5 empty] | 5000000
Municipal Services | Roads and Stormwater Drainage | 525025 | Rehabilitation of Rural Roads Upgrade | 5000000 |  | 5000000 | [5 empty] | 5000000
Municipal Services | Sewerage Admin | 515010 | Nord Avenue Pump station | 8000000 |  | 8000000 |  |  |  |  | -4000000 | 4000000 | Project is delayed by changes in the specification to GCC 2010. Project advertised for construction in January 2012.
Municipal Services | Sewerage Admin | 515010 | Quinera Treatment Works | 50000000 |  | 50000000 |  |  |  |  | -11000000 | 39000000 | Project at award stage in Februry 2012. Anticipated cashflow will not be achieved.
Municipal Services | Sewerage Treatment- Coastal | 515026 | Waste Water Treatment Capacity (Zwelitsha) | 15000000 |  | 15000000 | [5 empty] | 15000000
Municipal Services | Sewerage Treatment- Central | 515027 | Reeston Phase 3 Bulk Services Sewer | 25000000 |  | 25000000 |  |  |  |  | -1500000 | 23500000
Municipal Services | Sewerage Treatment- Inland | 515028 | Bufferstrip Sanitation - Mdantsane | 15000000 |  | 15000000 | [5 empty] | 15000000
Municipal Services | Sewerage Reticulation -Coastal | 515031 | Mdantsane Sewers - Refurbishment | 5000000 |  | 5000000 | [5 empty] | 5000000
Municipal Services | Sewerage Admin | 515010 | Diversion of Amalinda and Wilsonia effluent to Reeston | 50000000 |  | 50000000 |  |  |  |  | -28000000 | 22000000 | Project at award stage in February 2012. 2nd phase drilling advertised in January 2012. Anticipated cashflow will not be achieved.
Municipal Services | Bulk pumping stations | 520015 | Augmentation of Water Treatment Capacity - Umzonyana/Raising Upper weir | 5000000 |  | 5000000 | [5 empty] | 5000000
Municipal Services | Sewerage Admin | 515010 | Inland Rural Sanitation (Dimbaza Villages,Ngxwalane and Kwalini) | 36000000 |  | 36000000 | [5 empty] | 36000000
Municipal Services | Umzonyana Water Treatment Works | 520021 | Bulk Water Supply Newlands and other areas | 1000000 |  | 1000000 | [5 empty] | 1000000
Municipal Services | Water Ops and Maint.-Inland | 520025 | Ward 33 Bulk Water Supply Scheme | 7000000 |  | 7000000 | [5 empty] | 7000000
Municipal Services | Water Ops and Maint.-Inland | 520025 | Bulk Water Supply Coastal Areas | 8000000 |  | 8000000 | [5 empty] | 8000000
Development Facilitation and Partnership | Local Economic Development | 635005 | BCM Urban Agriculture Infrastructure Development | 3000000 |  | 3000000 | [5 empty] | 3000000
Development Facilitation and Partnership | Transport Planning & Operations Admin | 620005 | Taxi Ranks | 5000000 |  | 5000000 |  |  |  |  | -1800000 | 3200000 | Awards still to be made for Architects and topographic surveys (est R800,000) balance to be Rolled Over to Supplement construction in outer years(multi year project).Tender awarded for design phase. Tender for implementation in 2012/13
Development Facilitation and Partnership | Transport Planning & Operations Admin | 620005 | Gonubie Main Road | 10000000 |  | 10000000 | [5 empty] | 10000000
Development Facilitation and Partnership | Local Economic Development | 635005 | Economic Infrastructure | 5000000 |  | 5000000 |  |  |  |  | 1000000 | 6000000 | Top up funding is needed due to unforseen increase in steel price and other materials related to the construction.
Municipal Services | Cleansing Administration Support | 755010 | Development of Community Parks(Mdantsane, Potsdam, Reeston) | 1016303 |  | 1016303 | [5 empty] | 1016303
Municipal Services | Interments | 755025 | Development of 3 New Cemetries(Inland, Midland and Coastal) | 3000000 |  | 3000000 | [5 empty] | 3000000
Municipal Services | Halls | 760025 | Scenery Park Community Hall | 2000000 |  | 2000000 | [5 empty] | 2000000
Municipal Services | E.L.Regional Waste Disposal Site & Transfer Station | 770030 | Solid waste management | 8800000 |  | 8800000 |  |  |  |  | -8800000 | 0 | (R3,3mill trf to Drop off Points & Third cell) Planning and Design of third cell by the Service Provider is in progress.
Municipal Services | E.L.Regional Waste Disposal Site & Transfer Station | 770030 | Construction of Drop Points |  |  | 0 |  |  |  |  | 2800000 | 2800000 | Planning and Design of third cell by the Service Provider is in progress.
Municipal Services | E.L.Regional Waste Disposal Site & Transfer Station | 770030 | Planning of Designs of Third Cell |  |  | 0 |  |  |  |  | 500000 | 500000 | Planning and Design of third cell by the Service Provider is in progress.
Municipal Services | Sportsfields | 765010 | Sport Facilities | 2000000 |  | 2000000 | [5 empty] | 2000000
Municipal Services | Fire and Rescue Services | 725010 | Fire and Clinics | 6227453 |  | 6227453 | [5 empty] | 6227453
Municipal Services | Clinics | 710020 | Clinics | 3000000 |  | 3000000 |  |  |  |  | -900000 | 2100000 | Report approved at BAC on 15/11/2011 BAC 380/11
Municipal Services | Sewerage Admin | 515010 | Eastern Beach Sewers | 0 |  | 0 |  |  |  |  | 2000000 | 2000000 | This infrastructure is in an absolute state of disrepair. The project has been on and off the budget for previous years.
Municipal Services | Sewerage Admin | 515010 | Ablution Blocks Duncan Village | 0 |  | 0 |  |  |  |  | 2000000 | 2000000 | The amount to eradicate chemical toilets iin Duncan Village. To be used for the provision of bases for the ablutions.
Municipal Services | Sewerage Admin | 515010 | Sludge Handling Facility | 0 |  | 0 |  |  |  |  | 2800000 | 2800000 | Consulting Engineers are in place to undertake this project. It is linked to the Leiden twinning project.
Municipal Services | Water Ops and Maint.-Inland | 520025 | Winterstrand Water Supply | 0 |  | 0 |  |  |  |  | 2000000 | 2000000 | Materials have been purchased. This is to implement the project before end of this financial year to address the water quality problem in Winterstrand.
Municipal Services | Sewerage Admin | 515010 | KWT and Bisho Infrastructure(Water) | 0 |  | 0 |  |  |  |  | 2500000 | 2500000 | This is for replacement of critical failing water infrastructure in the KWT area.
Municipal Services | Sewerage Admin | 515010 | Relocation of Midblocks in Mdantsane | 0 |  | 0 |  |  |  |  | 3000000 | 3000000 | Water mains that are mid-block are to be decommissioned and new mains with fire fighting capacity placed in road reserves to improve accessibility for maintenance.
Municipal Services | Sewerage Admin | 515010 | Augmentation of Water Treatment Capacity - Umzoniana / Raising Upper Weir | 0 |  | 0 |  |  |  |  | 2000000 | 2000000 | Refurbishment of filter blocks and appurtenant infrastructure and improve capacity of the treatment plant.
Municipal Services | Sewerage Admin | 515010 | Amahleke | 0 |  | 0 |  |  |  |  | 1000000 | 1000000 | Ongoing project unfunded in this year. Augmentation of infratructure capacity in the reagion.
Municipal Services | Sewerage Admin | 515010 | Coastal and Midland Infrastructure | 0 |  | 0 |  |  |  |  | 1500000 | 1500000 | This is for replacement of critical failing infrastructure due to deferred maintenance.
Municipal Services | Roads and Stormwater Drainage | 525025 | Rehabilitation of underground stormwater-Stormwater management system | 0 |  | 0 |  |  |  |  | 1100000 | 1100000 | No funds allocated for the rehabilitation of Stormwater structures.
Municipal Services | Roads and Stormwater Drainage | 525025 | Rehabilitation of underground stormwater-Amalinda forest | 0 |  | 0 |  |  |  |  | 1000000 | 1000000 | No funds allocated for the rehabilitation of Stormwater structures
Municipal Services | Roads and Stormwater Drainage | 525025 | Rehabilitation of underground stormwater-Duncan village | 0 |  | 0 |  |  |  |  | 1000000 | 1000000 | No funds allocated for the rehabilitation of Stormwater structures
Municipal Services | Roads and Stormwater Drainage | 525025 | Rehabilitation of underground stormwater-Dimbaza | 0 |  | 0 |  |  |  |  | 1000000 | 1000000 | No funds allocated for the rehabilitation of Stormwater structures
Municipal Services | Roads and Stormwater Drainage | 525025 | Rehabilitation of underground stormwater-West bank | 0 |  | 0 |  |  |  |  | 1100000 | 1100000 | No funds allocated for the rehabilitation of Stormwater structures
Municipal Services | Roads Design | 525020 | Upgrading and Rehabilitation of BCMM Roads-Duncan Village | 0 |  | 0 |  |  |  |  | 1000000 | 1000000 | Insufficient funds for roads rehabilitation on original budget
Municipal Services | Roads Design | 525020 | Upgrading and Rehabilitation of BCMM Roads-Ducats | 0 |  | 0 |  |  |  |  | 1250000 | 1250000 | Insufficient funds for roads rehabilitation on original budget
Municipal Services | Roads Design | 525020 | Upgrading and Rehabilitation of BCMM Roads-Zwelitsha | 0 |  | 0 |  |  |  |  | 1000000 | 1000000 | Insufficient funds for roads rehabilitation on original budget
Municipal Services | Roads Design | 525020 | Upgrading and Rehabilitation of BCMM Roads-Dimbaza | 0 |  | 0 |  |  |  |  | 1000000 | 1000000 | Insufficient funds for roads rehabilitation on original budget
Municipal Services | Roads Design | 525020 | Upgrading and Rehabilitation of BCMM Roads-Phakamisa | 0 |  | 0 |  |  |  |  | 1250000 | 1250000 | Insufficient funds for roads rehabilitation on original budget
Municipal Services | Roads Design | 525020 | Upgrading and Rehabilitation of BCMM Roads-Scenary park/Reeston | 0 |  | 0 |  |  |  |  | 1000000 | 1000000 | Insufficient funds for roads rehabilitation on original budget
Municipal Services | Roads Design | 525020 | Upgrading and Rehabilitation of BCMM Roads-Nonkcampa | 0 |  | 0 |  |  |  |  | 600000 | 600000 | Insufficient funds for roads rehabilitation on original budget
Municipal Services | Roads Design | 525020 | Upgrading and Rehabilitation of BCMM Roads-Ndileka | 0 |  | 0 |  |  |  |  | 600000 | 600000 | Insufficient funds for roads rehabilitation on original budget
Municipal Services | Roads Design | 525020 | Upgrading and Rehabilitation of BCMM Roads-Zabalaza | 0 |  | 0 |  |  |  |  | 600000 | 600000 | Insufficient funds for roads rehabilitation on original budget
Municipal Services | Roads Design | 525020 | Upgrading and Rehabilitation of BCMM Roads-Upper Mngqesha | 0 |  | 0 |  |  |  |  | 600000 | 600000 | Insufficient funds for roads rehabilitation on original budget
Municipal Services | Roads Design | 525020 | Upgrading and Rehabilitation of BCMM Roads-Tsholomnqa | 0 |  | 0 |  |  |  |  | 106789 | 106789 | Insufficient funds for roads rehabilitation on original budget
|  |  |  | 409233906 | 0 | 409233906 |  |  |  |  | -44351500 | 364882406
|  |  |  | 764669130.19 | 55552269.56 | 820221399.75 | 0 | 0 | 0 | 13994122 | -94575017 | 725646382.75

## Summary
CAPEX PER FUNDING SOURCE | 2011/2012 | 2011/2012 | 2011/2012 | 2011/2012 | 2011/2012
| APPROVED | BUDGET | 1st ROLL-OVER | BUDGET | MID YEAR
| BUDGET | ADJUSTMENTS | ADJ. BUDGET | ADJUSTMENTS | ADJ. BUDGET
NEW PROJECTS
Own Funds | 58584502 | 10000000 | 68584502 | 14594122 | 83178624
Electricity Demand Side Management | 4000000 | 0 | 4000000 | 0 | 4000000
Human Settlement Development Grant | 39344834 | 0 | 39344834 | -16435320 | 22909514
Intergrated National Electricity Programme | 21000000 | 0 | 21000000 | 0 | 21000000
Urban Settlement Development Grant | 409233906 | 0 | 409233906 | -44351500 | 364882406
Public Transport Infrastructure and Systems Grant | 180000000 | 0 | 180000000 | -80000000 | 100000000
TOTAL NEW CAPEX | 712163242 | 10000000 | 722163242 | -126192698 | 595970544
ROLLED-OVER PROJECTS
BCM Metropolitan Transport | 710630 | 0 | 710630 | -476843 | 233787
Own Funds | 51666539 | 7645887.51 | 59312426.51 | -4961085 | 54351341.51
Disaster Management Grant | 128719 | 33875 | 162594 | 0 | 162594
DBSA Phase 4 and 5 | 0 | 17577424 | 17577424 | 0 | 17577424
DEDEAT | 0 | 5239.19 | 5239.19 | 0 | 5239.19
Dept of Sports Arts and Culture | 0 | 11079706.93 | 11079706.93 | 0 | 11079706.93
Dept of Science and Technology | 0 | 334147.13 | 334147.13 | 0 | 334147.13
Dept of Land Affairs | 0 | 4384854.23 | 4384854.23 | 0 | 4384854.23
Dept of Local Government and Traditional Affairs | 0 | 10642.88 | 10642.88 | 0 | 10642.88
Eastern Cape Development Co-Operation | 0 | 67358.44 | 67358.44 | 0 | 67358.44
European Commission | 0 | 171183.39 | 171183.39 | -171183 | 0.39
Leiden Platform | 0 | 2722219.64 | 2722219.64 | 0 | 2722219.64
Municipal Infrastructure Grant | 0 | 0 | 0 | 37500889 | 37500889
Office of the Premier | 0 | 500000 | 500000 | 0 | 500000
Local Government and Housing | 0 | 644461.99 | 644461.99 | -274097 | 370364.99
Public Transport Infrastructure and Systems Grant | 0 | 0 | 0 | 0 | 0
Provincial Treasury Office - LED Support Programme | 0 | 375269.23 | 375269.23 | 0 | 375269.23
TOTAL ROLLED-OVER CAPEX | 52505888 | 45552269.56 | 98058157.56 | 31617681 | 129675838.56
TOTAL CAPEX PER FUNDING SOURCE | 764669130 | 55552269.56 | 820221399.56 | -94575017 | 725646382.56
CAPEX PER DIRECTORATE | 2011/2012 | 2011/2012 | 2011/2012 | 2011/2012 | 2011/2012
| APPROVED | BUDGET | ADJUSTMENT | BUDGET | MID YEAR
| BUDGET | ADJUSTMENTS | BUDGET | ADJUSTMENTS | ADJ. BUDGET
Strategic Management | 1000000 | 15862771 | 16862771 |  | 16862771
Municipal Services | 529631591 | 25336277 | 554967868 |  | 554967868
Finance and Support | 13370489 | 9774884 | 23145373 |  | 23145373
Development Facilitation and Partnership | 220667050 | 193484 | 220860534 |  | 220860534
Development Planning and Management | 0 | 4384854 | 4384854 |  | 4384854
| 764669130 | 55552270 | 820221400 | 0 | 820221400