## 2014-2017 Projects
BUFFALO CITY METROPOLITAN MUNICIPALITY | [65 empty] | Annexure D
2014-2015 OPERATING PROJECTS BUDGET
Directorate | Directorate | USDG Per Service | Vote Number | [8 empty] | Job Number | [6 empty] | Ward No. | PROJECT NAME | FUNDING SOURCE | 2014/2015 Approved Budget | 2013/2014 Approved Opex Budget | Adjustment | Rollover Budget Adjustment | Adjustments | 2014/2015 ADJUSTED BUDGET | Jul14 | VAT | Jul 14 inc. VAT | Aug 14 | VAT | Aug 14 (incl. VAT | Sept 14 | VAT | Sept 2014 (Incl. Vat) | Oct 14 | Vat | October Incl. VAT | Nov 14 | Vat | Nov 14 including VAT | Dec 14 | VAT | Dec (Inc. Vat) | Jan 15 | VAT | Feb 15 | VAT | Mar 15 | VAT | Apr 15 | VAT | May 15 | VAT | June 15 | VAT | Commitments | 2014/2015 TOTAL EXPENDITURE TO DATE (VENUS) | 2014/2015 TOTAL EXPENDITURE TO DATE (VAT) | Commitments (Outstanding invoices for work done not yet paid | 2014/2015 AVAILABLE BUDGET | 2014/2015 AVAILABLE BUDGET (VAT) | % EXPEND-TURE VS BUDGET | % EXPENDITURE VS BUDGET (VAT) | COMMENTS
EXECUTIVE SUPPORT SERVICES
DIRECTORATE OF EXECUTIVE SUPPORT SERVICES
Executive Support Services |  |  | 110005 | [5 empty] | 1 | 77 | 0025 | P | 1 | 5 | 0 | 0 | 15 | A2 |  | Millenium Development Goals Framework Rollout | Own Funds c/o | 0 |  |  |  | 100000 | 100000 |  |  |  | 0 |  | 0 | 50764.04 |  | 50764.04 | [22 empty] | 50764.04 | 50764.04 |  | 49235.96 | 49235.96 | 50.76% | 50.76% | Payment effected for invoice for first draft MDG Framework.
Executive Support Services |  |  | 120005 | [5 empty] | 1 | 77 | 0025 | P | 1 | 5 | 2 | 0 | 00 | D4 | All Wards | Community Support Centre | Leiden | 136315 |  |  |  |  | 136315 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 136315 | 136315 | 0% | 0% | Funds towards Jobs Summit linked to the Mdantsane Support Centre in October 2014
Executive Support Services |  |  | 120005 | [5 empty] | 1 | 77 | 0025 | P | 1 | 5 | 0 | 0 | 16 | D4 |  | Intergovernmental Relations | Own Funds c/o | 0 |  |  |  | 80000 | 80000 |  |  |  | 0 |  | 0 | 27850 |  | 27850 | [22 empty] | 27850 | 27850 |  | 52150 | 52150 | 34.81% | 34.81% | Funds for IR & IGR Forum meetings to be held 3 times a year . Next meeting to be held in November 2014.
Executive Support Services |  |  | 120010 | [5 empty] | 1 | 77 | 0125 | P | 1 | 5 | 3 | 0 | 00 | D4 | All Wards | Ward Committee Training | TRUST FUNDS | 132152 |  |  |  |  | 132152 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 132152 | 132152 | 0% | 0% | Awaiting for the appointment the service provider from SCM
Executive Support Services |  |  | 120005 | [5 empty] | 1 | 77 | 0025 | P | 1 | 5 | 4 | 0 | 00 | D4 | All Wards | Umsobomvu Youth Fund | Umsobomvu Youth Fund | 710406 |  |  |  |  | 710406 | 33130 | 0 | 33130 | 2976.31 |  | 2976.31 | 18090.18 |  | 18090.18 | [21 empty] | 0 | 54196.49 | 54196.49 |  | 656209.51 | 656209.51 | 7.629% | 7.629% | Ongoing expenditure in relation to BCMM Youth Centers and the Youth Council's Action Plan
Executive Support Services | Knowledge Management |  | 130005 | 1 | 77 | 0002 | KPA5 | N/A | 1 | 77 | 0002 | P | 1 | 5 | 1 | 0 | 00 | A2 | All Wards | Documentation of case studies | Own Funds | 300000 |  |  |  |  | 300000 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 300000 | 300000 | 0% | 0% | Bid specifications submitted to BSC on 3/9/2014, deferred by BSC on 19/9/2014 . BSC meeting of 26/9/14 postponed. Bid Specs to be considered by BSC on 3/10/14. First expenditure to be incurred in advertising of tender after approval of Bid Specifications by BSC
Executive Support Services |  |  | 130005 | [5 empty] | 1 | 77 | 0002 | P | 1 | 5 | 0 | 0 | 29 | A2 |  | Documentation of case studies c/o | Own Funds c/o | 0 |  |  |  | 296292 | 296292 |  |  |  | 0 |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 296292 | 296292 | 0% | 0% | Bid Specifications submitted to SCM for consideration by BSC on 12 September 2014, deferred by BSC on 19/9/2014. BSC meeting of 26/9/14 postponed . Bid Specs to be considered by BSC on 3/10/2014. First expenditure to be incurred in advertising of tender after approval of Bid Specifications by BSC
[20 empty] | TOTAL : EXECUTIVE SUPPORT SERVICES |  | 1278873 |  |  |  | 476292 | 1755165 | 33130 | 0 | 33130 | 2976.31 | 0 | 2976.31 | 96704.22 | 0 | 96704.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132810.53 | 132810.53 | 0 | 1622354.47 | 1622354.47 | 7.567% | 7.567%
MUNICIPAL MANAGER'S OFFICE | [19 empty] | MUNICIPAL MANAGER'S OFFICE
Municipal Manager's Office | Office of the Municipal Manager |  | 205005 |  |  | 0002 | KPA5 | N/A | 1 | 77 | 0002 | P | 2 | 5 | 0 | 0 | 01 | A2 | All Wards | Audit Improvement Plan | Own Funds | 3750000 |  |  |  |  | 3750000 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 3750000 | 3750000 | 0% | 0% | Ongoing multi-year project- invoices being processed
Municipal Manager's Office |  |  | 205005 |  |  | 0002 | KPA5 | N/A | 1 | 77 | 0002 | P | 2 | 5 | 4 | 0 | 00 | A2 |  | Audit Improvement Plan c/o | Own Funds c/o | 0 |  |  |  | 6400281 | 6400281 |  |  |  | 0 |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 6400281 | 6400281 | 0% | 0%
Municipal Manager's Office | Office of the Municipal Manager |  | 205005 |  |  | 0002 | KPA5 | N/A | 1 | 77 | 0025 | P | 2 | 5 | 0 | 0 | 02 | D4 | All Wards | Audit Improvement Plan | TRUST FUNDS | 1979270 |  |  |  |  | 1979270 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 1979270 | 1979270 | 0% | 0% | Ongoing multi-year project- invoices being processed
Municipal Manager's Office | Office of the Municipal Manager | EPMO | 205005 |  |  | 0355 | KPA5 | N/A | 1 | 77 | 0098 | P | 2 | 5 | 0 | 0 | 03 | N3 | All Wards | Project Management Funding (USDG Projects) | USDG | 29914500 |  |  |  |  | 29914500 | 1900290.37 | 5780.6 | 1906070.97 | 1814948.97 |  | 1814948.97 | 2373811.44 | 76524.28 | 2450335.72 | [21 empty] | 102169.2 | 6089050.78 | 6171355.66 |  | 23825449.22 | 23743144.34 | 20.35% | 20.63% | USDG funding for project management office-. Procurement is ongoing.
Municipal Manager's Office | Office of the Municipal Manager | EPMO | 205005 |  |  | 0355 | KPA5 | N/A | 1 | 77 | 0098 | P | 2 | 5 | 0 | 0 | 06 | N3 | All Wards | Filling and repair , cleaning of Roads and stormwater drainage | EPWP | 945000 |  |  |  |  | 945000 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 945000 | 945000 | 0% | 0% | Project ongoing, funds committed, invoices being processed.
Municipal Manager's Office |  |  | 205005 | [5 empty] | 1 | 77 | 0098 | P | 2 | 5 | 0 | 0 | 08 | N3 | All Wards | Maintenance of ECO Parks | EPWP | 378000 |  |  |  |  | 378000 | 0 | 0 | 0 | 0 |  | 0 | 254450 |  | 254450 | [21 empty] | 0 | 254450 | 254450 |  | 123550 | 123550 | 67.31% | 67.31% | Project ongoing, funds committed, invoices being processed.
Municipal Manager's Office |  |  | 205005 | [5 empty] | 1 | 77 | 0098 | P | 2 | 5 | 0 | 0 | 09 | N3 | All Wards | Operating and Maintenance of Public Ablutions | EPWP | 567000 |  |  |  |  | 567000 | 0 | 0 | 0 | 0 |  | 0 | 535200 |  | 535200 | [21 empty] | 0 | 535200 | 535200 |  | 31800 | 31800 | 94.39% | 94.39% | Project ongoing, funds committed, invoices being processed.
Municipal Manager's Office |  |  | 205005 | [5 empty] | 1 | 77 | 0098 | P | 2 | 5 | 0 | 0 | 04 | V1 | All Wards | Vuna Awards | Vuna Awards | 1048758 |  |  |  |  | 1048758 | 0 | 0 | 0 | 0 |  | 0 | 26691.47 |  | 26691.47 | [21 empty] | 0 | 26691.47 | 26691.47 |  | 1022066.53 | 1022066.53 | 2.545% | 2.545%
Municipal Manager's Office | Internal Audit |  | 215005 | 1 | 77 | 0002 | KPA5 | N/A | 1 | 77 | 0002 | P | 2 | 5 | 0 | 0 | 05 | A2 | All Wards | Combined Assurance Model | Own Funds | 3000000 |  |  |  |  | 3000000 | 0 | 0 | 0 | 219349 |  | 219349 | 73237.5 |  | 73237.5 | [21 empty] | 0 | 292586.5 | 292586.5 |  | 2707413.5 | 2707413.5 | 9.753% | 9.753% | The Internal Audit plan for the 2014/15 financial year is being developed. Projects will start as soon as it is approved and expenditure will be incurred.
Municipal Manager's Office | Legal and Admin |  | 220005 | 1 | 77 | 0002 | KPA5 | N/A | 1 | 77 | 0002 | P | 2 | 5 | 0 | 0 | 07 | A2 | All Wards | Development and Review of By-Laws | Own Funds | 99996 |  |  |  |  | 99996 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 99996 | 99996 | 0% | 0% | Project to commence upon appointment of Project Advisor
Municipal Manager's Office |  |  | 220005 | [5 empty] | 1 | 77 | 0002 | P | 2 | 5 | 0 | 0 | 10 | A2 | All Wards | Professional Project Advisor | Own Funds | 284175 |  |  |  |  | 284175 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 284175 | 284175 | 0% | 0% | Project advisor to be appointed before end September 2014
Municipal Manager's Office |  |  | 220005 | [5 empty] | 1 | 77 | 0002 | P | 2 | 5 | 0 | 0 | 11 | A2 | All Wards | Admin Assistant to Project Advisor | Own Funds | 115829 |  |  |  |  | 115829 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 115829 | 115829 | 0% | 0% | Appoitment to be done by end September 2014
Municipal Manager's Office |  |  | 220005 | [5 empty] | 1 | 77 | 0150 | P | 2 | 5 | 2 | 0 | 00 | A2 |  | Development and Review of By-Laws | Own Funds c/o | 0 |  |  |  | 500000 | 500000 |  |  |  | 0 |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 500000 | 500000 | 0% | 0%
[20 empty] | TOTAL : MUNICIPAL MANAGER'S OFFICE |  | 42082528 |  |  |  | 6900281 | 48982809 | 1900290.37 | 5780.6 | 1906070.97 | 2034297.97 | 0 | 2034297.97 | 3263390.41 | 76524.28 | 3339914.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102169.2 | 7197978.75 | 7280283.63 | 0 | 41784830.25 | 41702525.37 | 14.69% | 14.86%
DIRECTORATE OF FINANCIAL SERVICES | [19 empty] | DIRECTORATE OF FINANCIAL SERVICES
Financial Services |  |  | 305005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 0 | 0 | 04 | A2 | All Wards | Directorates Financial Management Capacity Project | Own Funds | 2100000 |  |  |  |  | 2100000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 2100000 | 2100000 | 0% | 0% | Two positions have closed (electricity and community services) and shortlisting to be undertaken.
Financial Services |  |  | 305005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 1 | 0 | 00 | A2 |  | Immovable Asset Management Project | Own Funds c/o | 0 |  |  |  | 32639 | 32639 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 32639 | 32639 | 0% | 0%
Financial Services |  |  | 305005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 2 | 0 | 00 | A2 |  | Directorates Financial Management Capacity Project c/o | Own Funds c/o | 0 |  |  |  | 344250 | 344250 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 344250 | 344250 | 0% | 0%
Financial Services |  |  | 305005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 3 | 0 | 00 | A2 |  | Financial Support | Own Funds c/o | 0 |  |  |  | 750000 | 750000 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 750000 | 750000 | 0% | 0% | Refer to below - The 2 Technical positions to provide support for Financial Statements and Asset Reporting have been advertised.
Financial Services |  |  | 315005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 4 | 0 | 00 | A2 |  | Accounting Reforms Project | Own Funds c/o | 0 |  |  |  | 373767 | 373767 | [5 empty] | 0 | 289144.5 |  | 289144.5 | [22 empty] | 289144.5 | 289144.5 |  | 84622.5 | 84622.5 | 77.36% | 77.36% | Project is ongoing.
Financial Services | Budget Office |  | 315005 | 1 | 77 | 0060 | KPA4 | N/A | 1 | 77 | 0060 | P | 3 | 5 | 0 | 0 | 05 | F1 | All Wards | Training interns | FMG | 85210 |  |  |  |  | 85210 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 85210 | 85210 | 0% | 0% | IMFO training will be rolled on in September 2014 for interns and is ongoing.
Financial Services |  |  | 315005 | [5 empty] | 1 | 77 | 0060 | P | 3 | 5 | 0 | 0 | 06 | F1 | All Wards | SCM Projects | FMG | 84790 |  |  |  |  | 84790 | 0 | 0 | 0 | 84503.91 |  | 84503.91 |  |  | 0 | [21 empty] | 0 | 84503.91 | 84503.91 |  | 286.09 | 286.09 | 99.66% | 99.66% | The programme is in progress. Expenditure will be reflective throughout the months.
Financial Services |  |  | 315005 | [5 empty] | 1 | 77 | 0060 | P | 3 | 5 | 0 | 0 | 07 | F1 | All Wards | Remunerations Interns | FMG | 1165210 |  |  |  |  | 1165210 | 114326 | 0 | 114326 | 102830.57 |  | 102830.57 | 89087.6 |  | 89087.6 | [21 empty] | 0 | 306244.17 | 306244.17 |  | 858965.83 | 858965.83 | 26.28% | 26.28% | The payment of Intern's salaries is an ongoing project, done monthly. Expenditure is reflected on a monthly basis.
Financial Services |  |  | 315005 | [5 empty] | 1 | 77 | 0061 | P | 3 | 5 | 0 | 0 | 10 | F1 | All Wards | Standard Chart Of Accounts(SCOA) | FMG | 164790 |  |  |  |  | 164790 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 164790 | 164790 | 0% | 0% | Expenditure should reflect in October 2014, as the advert on work to be done was advertised in September 2014.
Financial Services |  |  | 320005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 0 | 0 | 01 | A2 | All Wards | Standard Chart Of Accounts(SCOA) | Own Funds | 5250000 |  |  |  | 11500000 | 16750000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 16750000 | 16750000 | 0% | 0% | The process has commenced and the funds will be used for SCOA
Financial Services |  |  | 320005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 0 | 0 | 02 | A2 | All Wards | Financial Technical Support | Own Funds | 1500000 |  |  |  |  | 1500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 1500000 | 1500000 | 0% | 0% | This funding is to be used to appoint 2 Programme Managers for Financial Statements and Asset Reporting.
Financial Services |  |  | 320005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 0 | 0 | 03 | A2 | All Wards | Immovable Assets Project | Own Funds | 15000000 |  |  |  | -7000000 | 8000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 8000000 | 8000000 | 0% | 0% | A service provider has been appointed and is assisting with the preparation of PPE disclosure in the AFS.
Financial Services |  |  | 320005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 0 | 0 | 11 | A2 |  | Asset Componetisation | Own Funds c/o | 0 |  |  |  | 7000000 | 7000000 |  |  |  | 150144 |  | 150144 | -150144 |  | -150144 | [22 empty] | 0 | 0 |  | 7000000 | 7000000 | 0% | 0%
Financial Services |  |  | 320005 | [5 empty] | 1 | 77 | 0015 | P | 3 | 5 | 0 | 0 | 09 | D2 | All Wards | Immovable Assets Project - Counterfunding | LGTH | 1336512 |  |  |  |  | 1336512 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 1336512 | 1336512 | 0% | 0%
Financial Services |  |  | 320010 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 6 | 0 | 00 | A2 |  | SCM Turn Around Projects | Own Funds c/o | 0 |  |  |  | 980229 | 980229 | [5 empty] | 0 | 113461.57 |  | 113461.57 | [22 empty] | 113461.57 | 113461.57 |  | 866767.43 | 866767.43 | 11.58% | 11.58% | Journal entries for Human Resources appointed in the project are being processed, funding is being utilised throughout the year.
Financial Services |  |  | 320010 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 7 | 0 | 00 | A2 |  | SCM Capacity Project | Own Funds c/o | 0 |  |  |  | 375123 | 375123 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 375123 | 375123 | 0% | 0% | Journal entries for Human Resources appointed in the project are being processed, and all funding will be exhausted by end of September 2014.
Financial Services |  |  | 330010 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 8 | 0 | 00 | A2 |  | Supplementary Valuations | Own Funds c/o | 0 |  |  |  | 106235 | 106235 |  |  |  | 2598.76 |  | 2598.76 |  |  | 0 | [22 empty] | 2598.76 | 2598.76 |  | 103636.24 | 103636.24 | 2.446% | 2.446% | Sopplementary valuations 2 to b eimplemented in December 2014, spending to commence then.
Financial Services | Debtors Management Office |  | 330015 | 1 | 77 | 0002 | KPA4 | N/A | 1 | 77 | 0002 | P | 3 | 5 | 0 | 0 | 08 | A2 | All Wards | Customer Service Level Agreements | Own Funds | 500000 |  |  |  |  | 500000 | 29225.5 | 0 | 29225.5 | -29225.5 |  | -29225.5 | -21013.24 |  | -21013.24 | [21 empty] | 0 | -21013.24 | -21013.24 |  | 521013.24 | 521013.24 | -4.203% | -4.203% | SLA Project is in progres and the expenditure will incur as the year progresses.
Financial Services | Debtors Management Office |  | 330015 | 1 | 77 | 0002 | KPA4 | N/A | 1 | 77 | 0002 | P | 3 | 5 | 9 | 0 | 00 | A2 |  | Billing Data Cleanup | Own Funds c/o | 0 |  |  |  | 1312847 | 1312847 |  |  |  | 23001.49 |  | 23001.49 | -4587.01 |  | -4587.01 | [22 empty] | 18414.48 | 18414.48 |  | 1294432.52 | 1294432.52 | 1.403% | 1.403% | SLA Project is in progres and the expenditure will incur as the year progresses.
[20 empty] | TOTAL : FINANCIAL SERVICES |  | 27186512 |  |  |  | 15775090 | 42961602 | 143551.5 | 0 | 143551.5 | 333853.23 | 0 | 333853.23 | 315949.42 | 0 | 315949.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 793354.15 | 793354.15 | 0 | 42168247.85 | 42168247.85 | 1.847% | 1.847%
DIRECTORATE OF CORPORATE SERVICES | [19 empty] | DIRECTORATE OF CORPORATE SERVICES
Corporate Services |  |  | 415025 | [5 empty] | 1 | 77 | 0002 | P | 4 | 5 | 7 | 0 | 00 | A2 | All Wards | IT Fibre Installations for SCM, IDZ and Community Services in 2014/2015 (KWT and Bhisho in 2015/2016 and Mdantsane, Reeston, East London Traffic and Mechanical Workshop in 2016/2017) | Own Funds | 4000000 |  |  |  | -500000 | 3500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 3500000 | 3500000 | 0% | 0% | CE 184 is underway, expected expenditure is Jan / Feb 2015.
Corporate Services |  |  | 415025 | [5 empty] | 1 | 77 | 0002 | P | 4 | 5 | 6 | 0 | 00 | A2 | All Wards | ICT Policies, Framework, Processes and Procedures - Implementation | Own Funds | 2000000 |  |  |  |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | CE 181 is underway, expected expenditure in Feb 2015.
Corporate Services |  |  | 415025 | [5 empty] | 1 | 77 | 0002 | [7 empty] | All Wards | Share Point (Intranet) | Own Funds | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Corporate Services |  |  | 415025 | [5 empty] | 1 | 77 | 0002 | P | 4 | 5 | 5 | 0 | 00 | A2 | All Wards | Website Phase 2 | Own Funds | 400000 |  |  |  |  | 400000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 400000 | 400000 | 0% | 0% | CE 182 is underway, expected expenditure in March / April 2015.
Corporate Services |  |  | 415025 | [5 empty] | 1 | 77 | 0002 | P | 4 | 5 | 4 | 0 | 00 | A2 | All Wards | Computer Equipment - BCMM Leases | Own Funds | 2000000 |  |  |  |  | 2000000 | 0 | 0 | 0 |  |  | 0 | 2871.57 |  | 2871.57 | [21 empty] | 0 | 2871.57 | 2871.57 |  | 1997128.43 | 1997128.43 | 0.1436% | 0.1436% | CE 186 is underway, expected expenditure in Feb / March 2015.
Corporate Services | H.R. Administration |  | 420005 | 1 | 77 | 0002 | KPA1 | N/A | 1 | 77 | 0002 | P | 4 | 5 | 3 | 0 | 00 | A2 | All Wards | Roll out of employee Performance Management System | Own Funds | 200000 |  |  |  |  | 200000 | 0 | 0 | 0 |  |  | 0 | 58696.6 |  | 58696.6 | [21 empty] | 0 | 58696.6 | 58696.6 |  | 141303.4 | 141303.4 | 29.35% | 29.35% | Expenditure will take place in the second quarter when running EPMDS refresher workshops for Task Grades 15 upwards in preparation of Performance Assessments.
Corporate Services | H.R. Administration |  | 420005 | [5 empty] | 1 | 77 | 0015 | P | 4 | 5 | 1 | 0 | 00 | D2 | All Wards | Roll out of employee Performance Management System - Counterfunding | LGTH | 113769 |  |  |  |  | 113769 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 113769 | 113769 | 0% | 0% | EPMDS marketing & communication is ongoing to result in the first expenditure in September 2014.
Corporate Services | H.R. Administration |  | 420005 | 1 | 77 | 0098 | KPA1 | N/A | 1 | 77 | 0098 | P | 4 | 5 | 2 | 0 | 00 | 11 | All Wards | Infrastructure Skills Development | ISDG | 5400000 |  |  |  |  | 5400000 | 386216.39 | 3244.07 | 389460.46 | 370435.8 |  | 370435.8 | 545475.18 | 11984.65 | 557459.83 | [21 empty] | 0 | 1302127.37 | 1317356.09 |  | 4097872.63 | 4082643.91 | 24.11% | 24.4% | The funding is used to pay salaries of engineering interns.
Corporate Services |  |  | 420005 | [5 empty] | 1 | 77 | 0002 | P | 4 | 5 | 0 | 0 | 11 | A2 |  | Local Labour Forum Project - Grievances | Own Funds | 0 |  |  |  | 500000 | 500000 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Funds will only be utilized from November 2014
Corporate Services |  |  | 420005 | [5 empty] | 1 | 77 | 0002 | P | 4 | 5 | 0 | 0 | 10 | A2 |  | Employee Relations Improvement Programme | Own Funds c/o | 0 |  |  |  | 251169 | 251169 | [5 empty] | 0 | 102167.94 |  | 102167.94 | [22 empty] | 102167.94 | 102167.94 |  | 149001.06 | 149001.06 | 40.68% | 40.68% | Roll over from previous financial year will be used until depleted, and thereafter the additional amount of R500 000 will be utilized.
[20 empty] | TOTAL : CORPORATE SERVICES |  | 14113769 |  |  |  | 251169 | 14364938 | 386216.39 | 3244.07 | 389460.46 | 370435.8 | 0 | 370435.8 | 709211.29 | 11984.65 | 721195.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1465863.48 | 1481092.2 | 0 | 12899074.52 | 12883845.8 | 10.2% | 10.31%
DIRECTORATE OF ENGINEERING SERVICES | [19 empty] | DIRECTORATE OF ENGINEERING SERVICES
Engineering Services |  |  | 530020 | [5 empty] | 1 | 77 | 0002 | [7 empty] | All Wards | BCMM Fleet Management System | Own Funds | 2000000 |  |  |  |  | 2000000 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | [21 empty] | 0 | 0 | 0 |  | 2000000 | 2000000 | 0% | 0%
[20 empty] | TOTAL : ENGINEERING SERVICES |  | 2000000 |  |  |  | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0% | 0%
DIRECTORATE OF DEVELOPMENT PLANNING | [19 empty] | DIRECTORATE OF DEVELOPMENT PLANNING
Development Planning |  |  | 615070 | [5 empty] | 1 | 76 | 0185 | P | 6 | 5 | 2 | 0 | 00 | H2 |  | Cambridge 1 & 2 (Kei Road Dawn) | HSDG c/o | 0 |  |  |  | 31000 | 31000 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 31000 | 31000 | 0% | 0% | Report for the approval of the Township Establishment was submitted to the Development and Planning Standing Committee Meeting of 22nd of July 2014, which did not take place. Reports were then considered by the Development and Planning Standing Committe of 12 August 2014 and have been recommended further by the Mayoral Committee Meeting of 2 September 2014 to Council for approval..
Development Planning |  |  | 615070 | [5 empty] | 1 | 76 | 0185 | P | 6 | 5 | 3 | 0 | 00 | H2 |  | N2 Road Reserve P2 | HSDG c/o | 0 |  |  |  | 147300 | 147300 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 147300 | 147300 | 0% | 0% | Report for the approval of the Township Establishment was submitted to the Development and Planning Standing Committee Meeting of 22nd of July 2014, which did not take place. Reports were then considered by the Development and Planning Standing Committe of 12 August 2014 and have been recommended further by the Mayoral Committee Meeting of the 2 September 2014 to Council for approval.
Development Planning |  |  | 615070 | [5 empty] | 1 | 76 | 0185 | P | 6 | 5 | 4 | 0 | 00 | H2 |  | Ford Msimango 1 (LU Housing Nomp School) - P2 | HSDG c/o | 0 |  |  |  | 36053 | 36053 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 36053 | 36053 | 0% | 0% | Report for the approval of the Township Establishment was submitted to the Development and Planning Standing Committee Meeting of 22nd of July 2014, which did not take place. Reports were then considered by the Development and Planning Standing Committe of 12 August 2014 and have been recommended further by the Mayoral Committee Meeting of the 2 September 2014 to Council for approval..
Development Planning |  |  | 615070 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 30 | A2 |  | Changes to BCM Zoning Scheme | Own Funds c/o | 0 |  |  |  | 35382 | 35382 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 35382 | 35382 | 0% | 0% | A draft Land Use Enforcemnt By-Law has been finalised and have been submitted to BCMM for scrutiny and comments
Development Planning |  |  | 615070 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 31 | A2 |  | Township Establishment for Mzamomhle Informal Settlement Study Phase 3 | Own Funds c/o | 0 |  |  |  | 240235 | 240235 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 240235 | 240235 | 0% | 0% | Feasibility study has been completed and draft layout has been submitted for comments. Consultation has taken place with Enviromental Affairs in regard to environmental issues and final response is still awaited.
Development Planning |  |  | 615070 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 32 | A2 |  | Land Identification for Partial or Full Relocation of Informal Settlement in BCMM | Own Funds c/o | 0 |  |  |  | 115707 | 115707 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 115707 | 115707 | 0% | 0% | Feasibility study has started, which includes the desk top study and then then the on-site verification which is currently underway.
Development Planning |  |  | 615070 | [5 empty] | 1 | 77 | 0020 | P | 6 | 5 | 0 | 0 | 01 | D3 |  | Planning and Map Preparation | DLA | 80654 |  |  |  |  | 80654 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 80654 | 80654 | 0% | 0% | Waiting for final approval by MEC for the Establishment of Township for Needs Camp and Potsdam Unit V which has been completed by BCMM before final payment can be done.
Development Planning |  |  | 615070 | [5 empty] | 1 | 77 | 0098 | P | 6 | 5 | 1 | 0 | 00 | I1 |  | East Bank Restitution Township Establishment | RLCC c/o | 0 |  |  |  | 71782 | 71782 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 71782 | 71782 | 0% | 0% | Final layout and Motivation report was completed and submitted. Application is currently being circulation for comments,
Development Planning | Land Admin |  | 615080 | 1 | 76 | 0185 | KPA2 | 13 | 1 | 76 | 0185 | P | S | C | 1 | 0 | 11 | H2 |  | Reeston Phase 3: Stage 2 - P4 (Transfers) | HSDG | 480000 |  |  |  |  | 480000 | 0 | 0 | 0 | 117102.81 |  | 117102.81 | 76187.37 |  | 76187.37 | [22 empty] | 193290.18 | 193290.18 | 0 | 286709.82 | 286709.82 | 40.27% | 40.27% | 61 transfers registered for the month of September 2014.
Development Planning | Land Admin |  | 615080 | 1 | 76 | 0185 | KPA2 | 45 | 1 | 76 | 0185 | P | S | C | 1 | 9 | 01 | H2 |  | Ilitha South - 439 Units P4 (Transfers) | HSDG | 40400 |  |  |  |  | 40400 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 | 0 | 40400 | 40400 | 0% | 0% | No Deeds of Sale received for Ilitha Project for onward transmission to Conveyancer.
Development Planning |  |  | 615080 | 1 | 77 | 0003 | KPA3 | N/A | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 06 | A2 |  | Land transactions upgrading of former R293 & CPA Areas | Own Funds | 500000 |  |  |  |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 | 0 | 500000 | 500000 | 0% | 0% | Awaiting Consents from Owners
Development Planning |  |  | 620005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 33 | A2 |  | Integrated Transport Plan Review | Own Funds c/o | 0 |  |  |  | 505923 | 505923 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 505923 | 505923 | 0% | 0% | Arterial Road Network Development Plan advertised and presented to BEC August 2014. Awaiting award.
[20 empty] | TOTAL : DEVELOPMENT PLANNING |  | 1101054 |  |  |  | 1183382 | 2284436 | 0 | 0 | 0 | 117102.81 | 0 | 117102.81 | 76187.37 | 0 | 76187.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193290.18 | 193290.18 | 0 | 2091145.82 | 2091145.82 | 8.461% | 8.461%
DIRECTORATE OF ECONOMIC DEVELOPMENT | [19 empty] | DIRECTORATE OF ECONOMIC DEVELOPMENT
Economic Development | [19 empty] | Local Economic Development - LED | Own Funds | [6 empty] | 0 | 0 | 0 |  |  | 0
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 22 | A2 |  | NTCE | Own Funds | 500000 |  |  |  |  | 500000 | 0 | 0 | 0 |  |  | 0 | 500000 |  | 500000 | [22 empty] | 500000 | 500000 |  | 0 | 0 | 100% | 100% | Budget has been completed for contribution towards the NTCE programme which is running from 02 October to 04 October 2014.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 23 | A2 |  | SMME Support | Own Funds | 100000 |  |  |  | 200000 | 300000 | 0 | 0 | 0 | 45103.2 |  | 45103.2 | 62525.52 |  | 62525.52 | [22 empty] | 107628.72 | 107628.72 |  | 192371.28 | 192371.28 | 35.88% | 35.88% | Funds are allocated for SMME support programmes.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 24 | A2 |  | Tourism SMME Support | Own Funds | 100000 |  |  |  | 200000 | 300000 | 0 | 0 | 0 |  |  | 0 | 69060 |  | 69060 | [21 empty] | 25400 | 69060 | 69060 |  | 230940 | 230940 | 23.02% | 23.02% | The project is progressing well. More invoices will be submitted for payment.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 25 | A2 |  | Geo. Assessment impact study | Own Funds | 60000 |  |  |  |  | 60000 | 0 | 0 | 0 |  |  | 0 | 402 |  | 402 | [22 empty] | 402 | 402 |  | 59598 | 59598 | 0.67% | 0.67% | The informal tender to appoint the service provider to do the study has been advertised and closed on 30 September 2014. The assessment will be conducted and award will be made if suitable service provider is found.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 26 | A2 |  | Trade & Investment Strategy and Policy | Own Funds | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 | 188800 |  | 188800 | 297041.22 |  | 297041.22 | [21 empty] | 94025.86 | 485841.22 | 485841.22 |  | 514158.78 | 514158.78 | 48.58% | 48.58% | Funding is for trade and investment missions and for development of marketing and colatteral.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 27 | A2 |  | Trade & Investment Marketing and Promotions | Own Funds | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 | 243859.65 |  | 243859.65 | 194210.52 |  | 194210.52 | [22 empty] | 438070.17 | 438070.17 |  | 561929.83 | 561929.83 | 43.81% | 43.81% | The allocation is for the development of Trade and Investment Strategy and Policy. Tender has been advertised and closing on 10 October 2014.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 28 | A2 |  | Trade & Investment Export Support Programme | Own Funds | 240000 |  |  |  |  | 240000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 240000 | 240000 | 0% | 0% | Funding is allocated for the development and empowerment of existing and emerging exporters.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 34 | A2 |  | Buyelekhaya Pan African Festival | Own Funds |  |  |  |  | 3200000 | 3200000 | [8 empty] | 0 | [22 empty] | 0 |  |  | 3200000 | 3200000 | 0% | 0% | Payment for securing of artists is in process. Funds will be utilised end of this month.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 35 | A2 |  | Summer Season 2014 | Own Funds |  |  |  |  | 2400000 | 2400000 | [8 empty] | 0 | [22 empty] | 0 |  |  | 2400000 | 2400000 | 0% | 0% | The project is progressing well. The department will use services of the annual contractors.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 36 | A2 |  | Rental | Own Funds |  |  |  |  | 1000000 | 1000000 | [8 empty] | 0 | [22 empty] | 0 |  |  | 1000000 | 1000000 | 0% | 0% | To be utilised once tender for office space has been finalised.
Economic Development | [19 empty] | Local Economic Development - LED | DEDEAT
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0013 | P | 6 | 5 | 0 | 0 | 16 | D9 |  | Packshed | DEDEAT | 239408 |  |  |  |  | 239408 | 0 | 0 | 0 |  |  | 0 | 8800.7 |  | 8800.7 | [21 empty] | 10290.21 | 8800.7 | 8800.7 |  | 230607.3 | 230607.3 | 3.676% | 3.676% | Funding allocated for operations of the centre
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0013 | P | 6 | 5 | 0 | 0 | 17 | D9 |  | Agricultural Show | DEDEAT | 200000 |  |  |  |  | 200000 | 0 | 0 | 0 |  |  | 0 | 56499 |  | 56499 | [21 empty] | 88142 | 56499 | 56499 |  | 143501 | 143501 | 28.25% | 28.25% | Project rescheduled from Sept. to October 2014, Service Provider appointed for supply of inputs.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0013 | P | 6 | 5 | 0 | 0 | 18 | D9 |  | Emerging Farmers & Co-operatives | DEDEAT | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 |  |  | 0 | 13850.68 |  | 13850.68 | [21 empty] | 0 | 13850.68 | 13850.68 |  | 986149.32 | 986149.32 | 1.385% | 1.385% | Projgramme allocated for Supply and delivery of inputs in 6 villages. It is on BEC stage.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0013 | P | 6 | 5 | 0 | 0 | 19 | D9 |  | Centre operations | DEDEAT | 300000 |  |  |  |  | 300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 300000 | 300000 | 0% | 0% | Invoice submitted for SMME workshop that was held in Mdantsane. Invoices also submitted for SMME's that participated in the Home Expo 2014, as well as for the Cooperatives Amendments Workshop.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0013 | P | 6 | 5 | 0 | 0 | 20 | D9 |  | Trainings: Plumbing, Governance, Contractor development | DEDEAT | 1400000 |  |  |  |  | 1400000 | 0 | 0 | 0 | 4481 |  | 4481 | 27500 |  | 27500 | [21 empty] | 336055.9 | 31981 | 31981 |  | 1368019 | 1368019 | 2.284% | 2.284% | Invoice submitted for Contractor Development Programme amount. Service Provider has been appointed for the Plumbing Training which will commence on the 2nd October 2014. Specification to source service provider for the Co- operative Governance have been completed
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0013 | P | 6 | 5 | 0 | 0 | 21 | D9 |  | Franchise Expo | DEDEAT | 300000 |  |  |  |  | 300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 300000 | 300000 | 0% | 0% | The Bid to appoint an events manager has closed on the 30th September 2014, quotations for the venue have been sourced. Funds will be completed by the end of the second quarter
[20 empty] | TOTAL : ECONOMIC DEVELOPMENT |  | 6439408 | 0 | 0 | 0 | 7000000 | 13439408 | 0 | 0 | 0 | 482243.85 | 0 | 482243.85 | 1229889.64 | 0 | 1229889.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553913.97 | 1712133.49 | 1712133.49 | 0 | 11727274.51 | 11727274.51 | 12.74% | 12.74%
HUMAN SETTLEMENTS | [19 empty] | DIRECTORATE OF HUMAN SETTLEMENTS
Human Settlements | DVRI |  | 250005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 27 | H1 |  |  | DVRI Planning Budget (FROM 8.7MIL) | Dept of LGTH | 900000 |  |  |  |  | 900000 | 0 | 0 | 0 | 402905.5 |  | 402905.5 | 198657.4 |  | 198657.4 | [21 empty] | 86682.07 | 601562.9 | 601562.9 |  | 298437.1 | 298437.1 | 66.84% | 66.84% | Still waiting for the business plan to be completed and these funds will be allocated once the business plan has been completed.
Human Settlements | DVRI |  | 250005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 38 | H1 |  |  | DVRI Planning Budget c/o | Dept of LGTH c/o | 0 |  |  |  | 1694293 | 1694293 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 1694293 | 1694293 | 0% | 0%
Human Settlements | DVRI |  | 250005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 39 | H1 |  |  | DVRI Business Plan | Dept of LGTH c/o | 0 |  |  |  | 96379 | 96379 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 96379 | 96379 | 0% | 0% | the tender was advertised and there was discrepancy in the information provided by the bidder. Still seeking advice on how to proceed with the matter
Human Settlements | DVRI |  | 250005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 35 | H1 |  |  | DVRI News | Dept of LGTH | 500000 |  |  |  |  | 500000 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Advertorials and radio interviews were done with the following departments: Sanitation, LED, Housing and DVRI projects. The project is going very well but the R500 000 budget allocated is not sufficient as we would like to flight other project implemented in Duncan Village from various department.
Human Settlements | DVRI |  | 250005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 36 | H1 |  |  | Funding Mobilisation Strategy | Dept of LGTH | 200000 |  |  |  |  | 200000 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 200000 | 200000 | 0% | 0% | the tender will be advertised before the end of September.
Human Settlements | DVRI |  | 250005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 37 | H1 |  |  | Quality of Life | Dept of LGTH | 1400000 |  |  |  |  | 1400000 |  |  | 0 |  |  | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 1400000 | 1400000 | 0% | 0% | the project is progressing well and the implementation phase stage one has been completed which is data collection phase and the report submitted.
Human Settlements | Housing Projects |  | 250005 | [5 empty] | 1 | 77 | 0020 | P | P | P | 50 | 30 | D3 |  |  | Reeston Phase 2 | DLA | 696589 |  |  |  |  | 696589 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 696589 | 696589 | 0% | 0%
Human Settlements | MURP |  | 250005 |  |  | 0355 | KPA2 | All | 1 | 77 | 0058 | P | P | P | 50 | 29 | E4 |  |  | MURP Sustainability Plan | European Commission | 500000 |  |  |  |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | The report will be tabled to BEC
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 13 | 1 | 76 | 0185 | P | T | S | 50 | 01 | H3 |  |  | Reeston Phase 3: Stage 2 - P5 | HSDG | 10000000 |  |  |  |  | 10000000 | 0 | 0 | 0 | 121000 |  | 121000 |  |  | 0 | [21 empty] | 0 | 121000 | 121000 |  | 9879000 | 9879000 | 1.21% | 1.21% | The Implementing Agent has been recently appointed to construct 550 top structures, anticipated to commence beginning of November 2014.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 13 | 1 | 76 | 0185 | P | T | S | 50 | 40 | H3 |  |  | Reeston Phase 3: Stage 2 - P5 c/o | HSDG c/o | 0 |  |  |  | 2000000 | 2000000 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | The Implementing Agent has been recently appointed to construct 550 top structures, anticipated to commence beginning of November 2014.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 13 | 1 | 76 | 0185 | P | E | D | 50 | 02 | H3 |  |  | Beneficiary Registration DVRI Projects (Reeston, Cambridge, DVRI Pilot, Braelyn ext 10, C Section and Triangular Site, D Hostel) | HSDG | 500000 |  |  |  |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | All displaced beneficiaries are being considered in this project from all DV Wards affected however these beneficiaries are still struggling to come forward and effect changes
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 13 | 1 | 76 | 0185 | P | E | D | 50 | 41 | H3 |  |  | Beneficiary Registration DVRI Projects (Reeston, Cambridge, DVRI Pilot, Braelyn ext 10, C Section and Triangular Site, D Hostel) c/o | HSDG c/o | 0 |  |  |  | 400000 | 400000 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 400000 | 400000 | 0% | 0% | All displaced beneficiaries are being considered in this project from all DV Wards affected however these beneficiaries are still struggling to come forward and effect changes
Human Settlements | Housing Projects | Housing | 255005 | [5 empty] | 1 | 76 | 0645 | P | E | D | 50 | 22 | H2 |  |  | Beneficiary Registration (Potsdam Unit V, Cluster 3, Orange Groove, Mdantsane Zone CC, Cluster 1, Cluster 2, Peelton Cluster, Hanover, Skobeni, Sunny South, Ilitha North, Dimbaza 110, Dimbaza Phase 3,Potsdam Village; North Kanana, Ikhwezi Block 1 & 2, Amalinda Co-op, Eradication of Wooden Houses to Formal Houses | USDG | 1350000 |  |  |  |  | 1350000 | 0 | 0 | 0 | 126815.49 |  | 126815.49 | 253447 |  | 253447 | [21 empty] | 0 | 380262.49 | 380262.49 |  | 969737.51 | 969737.51 | 28.17% | 28.17% | Registration is ongoing and awaiting for more approvals from Province. Most of these beneficiaries have a challenge with Title Deeds which they sold the houses to each other and it is very expensive for them to de-register the title deeds. A Beneficiary Admin is busy compiling a list of all those who have a title deed challenges. In Peelton Cluster the Registration Team is busy with compiling of the beneficiary lists.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 45 | 1 | 76 | 0185 | P | E | D | 50 | 03 | H3 |  |  | Ilitha Eradication of Wooden Houses to Formal Houses | HSDG | 18180294 |  |  |  |  | 18180294 | 0 | 0 | 0 | 421886.81 |  | 421886.81 | 276153.95 |  | 276153.95 | [21 empty] | 0 | 698040.76 | 698040.76 |  | 17482253.24 | 17482253.24 | 3.84% | 3.84% | This project is going ahead, 68 slabs have been completed, the contractor is delayed due to non availability of steel doors and window frames, a scheduled meeting on 03/10/14 with beneficiaries will discuss an alternative material to use in this contract on agreement the contractor will start with block work.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 45 | 1 | 76 | 0185 | P | E | D | 50 | 42 | H3 |  |  | Ilitha Eradication of Wooden Houses to Formal Houses | HSDG c/o | 0 |  |  |  | 4817139 | 4817139 | [5 empty] | 0 | 1483256.62 |  | 1483256.62 | [22 empty] | 1483256.62 | 1483256.62 |  | 3333882.38 | 3333882.38 | 30.79% | 30.79% | This project is going ahead, 68 slabs have been completed, the contractor is delayed due to non availability of steel doors and window frames, a scheduled meeting on 03/10/14 with beneficiaries will discuss an alternative material to use in this contract on agreement the contractor will start with block work.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 43 | 1 | 76 | 0185 | P | T | S | 50 | 04 | H3 |  |  | Tyutyu Phase 2 - P 5 (Top Structure) | HSDG | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | This project is going ahead with the assistance of an assisting contractor, the completion is anticipated to be at the end of November 2014
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 43 | 1 | 76 | 0185 | P | T | S | 50 | 43 | H3 |  |  | Tyutyu Phase 2 - P 5 (Top Structure) c/o | HSDG c/o | 0 |  |  |  | 6205903 | 6205903 | [5 empty] | 0 | 773029.18 |  | 773029.18 | [22 empty] | 773029.18 | 773029.18 |  | 5432873.82 | 5432873.82 | 12.46% | 12.46% | This project is going ahead with the assistance of an assisting contractor, the completion is anticipated to be at the end of November 2014
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | [8 empty] | Ilitha North - 177 Units P5 | HSDG | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 17,24,25,26,31,33,35,36,37,38,39,40,43,44,45 | 1 | 76 | 0185 | P | E | D | 50 | 05 | H3 |  |  | Reconstruction of Storm Damaged Houses | HSDG | 10000000 |  |  |  |  | 10000000 | 0 | 0 | 0 | 188610 |  | 188610 |  |  | 0 | [21 empty] | 0 | 188610 | 188610 |  | 9811390 | 9811390 | 1.886% | 1.886% | Contractor has been appointed for the construction of 260 Units in Cluster 2 and has commenced with the construction.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 17,24,25,26,31,33,35,36,37,38,39,40,43,44,45 | 1 | 76 | 0185 | P | E | D | 50 | 45 | H3 |  |  | Reconstruction of Storm Damaged Houses | HSDG c/o | 0 |  |  |  | 3906828 | 3906828 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 3906828 | 3906828 | 0% | 0% | Contractor has been appointed for the construction of 260 Units in Cluster 2 and has commenced with the construction.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 31 | 1 | 76 | 0185 | P | T | S | 50 | 06 | H3 |  |  | Sunny South -P5 | HSDG | 11000000 |  |  |  |  | 11000000 | 0 | 0 | 0 | 6362965.12 |  | 6362965.12 | 1795552.03 |  | 1795552.03 | [21 empty] | 0 | 8158517.15 | 8158517.15 |  | 2841482.85 | 2841482.85 | 74.17% | 74.17% | Contractor is on site progressing with the construction of 526 Units, the project is to completed in December 2014
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 31 | 1 | 76 | 0185 | P | T | S | 50 | 46 | H3 |  |  | Sunny South -P5 c/o | HSDG c/o | 0 |  |  |  | 10681830 | 10681830 | [5 empty] | 0 | 359973.96 |  | 359973.96 | [22 empty] | 359973.96 | 359973.96 |  | 10321856.04 | 10321856.04 | 3.37% | 3.37% | Contractor is on site progressing with the construction of 526 Units, the project is to completed in December 2014
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 23 | 1 | 76 | 0185 | P | T | S | 50 | 07 | H3 |  |  | Potsdam Village Phase 1 & 2 - P5 | HSDG | 2300000 |  |  |  |  | 2300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 2300000 | 2300000 | 0% | 0% | Project on design stage.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 48,12,21,11,17,11, 20 | 1 | 76 | 0185 | P | T | S | 50 | 08 | H3 |  |  | Cluster 1 (Masibambane; Masibulele; Velwano; Ilinge and Dacawa) P5 | HSDG | 10000000 |  |  |  | -8750000 | 1250000 | 0 | 0 | 0 | 6240458.82 |  | 6240458.82 |  |  | 0 | [21 empty] | 0 | 6240458.82 | 6240458.82 |  | -4990458.82 | -4990458.82 | 499.2% | 499.2% | The contractor is on site progressing with internal services and top structures. | #VALUE!
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 48,12,21,11,17,11, 20 | 1 | 76 | 0185 | P | T | S | 50 | 47 | H3 |  |  | Cluster 1 (Masibambane; Masibulele; Velwano; Ilinge and Dacawa) P5 c/o | HSDG c/o | 0 |  |  |  | 471932 | 471932 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 471932 | 471932 | 0% | 0% | The contractor is on site progressing with internal services and top structures.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 17,14 | 1 | 76 | 0185 | P | T | S | 50 | 09 | H3 |  |  | Cluster 2 (Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe) P5 (Name Change) | HSDG | 3000000 |  |  |  |  | 3000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 3000000 | 3000000 | 0% | 0% | Contrator on site busy with site establishment to commence with the construction of services and top structures
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 10,5 | 1 | 76 | 0185 | P | T | S | 50 | 10 | H3 |  |  | Cluster 3 (Fynbos 1; Fynbos 2; Ndancama, ) P5 | HSDG | 3000000 |  |  |  | -2700000 | 300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 300000 | 300000 | 0% | 0% | Contractor has been appointed for the construction of both internal services and top structure. | #VALUE!
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 6,8 | 1 | 76 | 0185 | P | T | S | 50 | 11 | H3 |  |  | DVRI Pilot Project (Mekeni, Haven Hills, Competition Site) P5 | HSDG | 5000000 |  |  |  |  | 5000000 | 0 | 0 | 0 | 1800007.11 |  | 1800007.11 |  |  | 0 | [21 empty] | 0 | 1800007.11 | 1800007.11 |  | 3199992.89 | 3199992.89 | 36% | 36% | The contractor is on site anticipated to hand over 30 houses by the 15th of October 2014.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 6,8 | 1 | 76 | 0185 | P | T | S | 50 | 48 | H3 |  |  | DVRI Pilot Project (Mekeni, Haven Hills, Competition Site) P5 c/o | HSDG c/o | 0 |  |  |  | 5122540 | 5122540 | [5 empty] | 0 | 1478920.65 |  | 1478920.65 | [22 empty] | 1478920.65 | 1478920.65 |  | 3643619.35 | 3643619.35 | 28.87% | 28.87% | The contractor is on site anticipated to hand over 30 houses by end of September 2014.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 19 | 1 | 76 | 0185 | P | T | S | 50 | 12 | H3 |  |  | Second Creek - P5 | HSDG | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 | 1000000 |  | 1000000 |  |  | 0 | [21 empty] | 0 | 1000000 | 1000000 |  | 0 | 0 | 100% | 100% | Project is at completion stage.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 19 | 1 | 76 | 0185 | P | T | S | 50 | 49 | H3 |  |  | Second Creek - P5 c/o | HSDG c/o | 0 |  |  |  | 2374275 | 2374275 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 2374275 | 2374275 | 0% | 0% | Project is at completion stage.
Human Settlements |  |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | E | D | 50 | 13 | H3 |  |  | Housing Needs Database and Accreditation | HSDG | 10327914 |  |  |  |  | 10327914 | 525879.76 | 0 | 525879.76 | 493177.39 |  | 493177.39 | 481576.12 |  | 481576.12 | [21 empty] | 0 | 1500633.27 | 1500633.27 |  | 8827280.73 | 8827280.73 | 14.53% | 14.53% | Funding is used for compensation of employees for the Accreditation funded posts.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 1-50 | 1 | 76 | 0185 | [8 empty] | Housing Needs Database and Accreditation | HSDG | [5 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 14 | H3 |  |  | Reeston Phase 3 Stage 3 P5 | HSDG | 5500000 |  |  |  | 9465387 | 14965387 | 0 | 0 | 0 |  |  | 0 | 2182830.86 |  | 2182830.86 | [21 empty] | 0 | 2182830.86 | 2182830.86 |  | 12782556.14 | 12782556.14 | 14.59% | 14.59% | The contractor is on site busy with internal services and top structures. Anticipated to hand over 100 top structures units on the 14th of December 2014. | #VALUE!
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 44 | H3 |  |  | Reeston Phase 3 Stage 3 P5 c/o | HSDG c/o | 0 |  |  |  | 2375000 | 2375000 | [5 empty] | 0 | 2375000 |  | 2375000 | [22 empty] | 2375000 | 2375000 |  | 0 | 0 | 100% | 100% | The contractor is on site busy with internal services and top structures. Anticipated to hand over 100 top structures units on the 14th of December 2014.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 15 | H3 |  |  | Amalinda Co - Op P5 | HSDG | 500000 |  |  |  |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Project on design stage.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | [8 empty] | Amalinda Fairlands P5 | HSDG | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | [8 empty] | Braelyn Ext 10 North - P5 | HSDG | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | [8 empty] | C Section and Triangular Site - P5 | HSDG | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | [8 empty] | D Hostel - P5 | HSDG | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 16 | H3 |  |  | Mdantsane Zone 18CC - P5 | HSDG | 3109500 |  |  |  |  | 3109500 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 3109500 | 3109500 | 0% | 0% | Contractor appointed for services, the department still to appoint consultant to design for the top structure
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 17 | H3 |  |  | Potsdam Ikhwezi Block 1 - P5 | HSDG | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Project is at design stage.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | [8 empty] | Potsdam Ikhwezi Block 2- P5 | HSDG | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | [8 empty] | Potsdam North Kanana - P5 | HSDG | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 18 | H3 |  |  | Dimbaza 110 -P 5 (Top Structure) | HSDG | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | This project is going ahead with the assistance of an assisting contractor, the completion is anticipated to be at the end of November 2014
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 50 | H3 |  |  | Dimbaza 110 -P 5 (Top Structure) c/o | HSDG c/o | 0 |  |  |  | 6000000 | 6000000 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 6000000 | 6000000 | 0% | 0% | This project is going ahead with the assistance of an assisting contractor, the completion is anticipated to be at the end of November 2014
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | [8 empty] | Dimbaza Destitute 27 Units - P5 | HSDG | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | E | D | 50 | 19 | H3 |  |  | Peelton Cluster (Majali, Mdange, Kwatrain, Nkqonqweni, Drayini & Esixekweni) - P5 | HSDG | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 | 81840 |  | 81840 | 479050 |  | 479050 | [21 empty] | 0 | 560890 | 560890 |  | 439110 | 439110 | 56.09% | 56.09% | Consultant is finalising beneficiary registration, awaiting approvals to go out on tender for the appointment of contractor. Geotechnical investigation is and house plans are complete.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 21 | H3 |  |  | Hanover - P5 | HSDG | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | The service provider has submitted the geotechnical report and it was accepted by the Department. The designs are complete will be submitted to NHBRC.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 20 | H3 |  |  | Skobeni - P5 | HSDG | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | The service provider has submitted the geotechnical report and it was accepted by the Department. The designs are complete will be submitted to NHBRC.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0645 | P | P | P | 50 | 23 | H2 |  |  | Potsdam Village | USDG | 200000 |  |  |  |  | 200000 | 37000 | 5180 | 42180 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 37000 | 42180 |  | 163000 | 157820 | 18.5% | 21.09% | Project is at design stage.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0645 | P | P | P | 50 | 24 | H2 |  |  | Disaster Project - Tsholomnqa | USDG | 2000000 |  |  |  |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | The project is waiting for the appointment of annual contractors to commence with the construction
Human Settlements | Housing Projects |  | 255005 | 1 | 77 | 0002 | KPA2 | 1-50 | 1 | 77 | 0002 | P | P | P | 50 | 28 | A2 |  |  | Relocation of beneficiaries to formal houses for all housing programmes - All Projects | Own Funds | 2140000 |  |  |  |  | 2140000 | 11900 | 0 | 11900 | 17464 |  | 17464 | -29364 |  | -29364 | [21 empty] | 48000 | 0 | 0 |  | 2140000 | 2140000 | 0% | 0% | The project is dependant on completed housing units and demand (need) of emergency movement of beneficiaries, expenditure will increase as the year progresses
Human Settlements | Housing Projects |  | 255005 | 1 | 77 | 0002 | KPA2 | 1-50 | 1 | 77 | 0002 | P | P | P | 50 | 51 | A2 |  |  | Relocation of beneficiaries to formal houses for all housing programmes - All Projects c/o | Own Funds c/o | 0 |  |  |  | 379096 | 379096 | [5 empty] | 0 | 7800 |  | 7800 | [22 empty] | 7800 | 7800 |  | 371296 | 371296 | 2.058% | 2.058% | The project is dependant on completed housing units and demand (need) of emergency movement of beneficiaries, expenditure will increase as the year progresses
Human Settlements | Housing Projects |  | 255005 | 1 | 77 | 0002 | KPA2 | 1-50 | 1 | 77 | 0002 | P | P | P | 50 | 52 | A2 |  |  | Rectification title deeds | Own Funds c/o | 0 |  |  |  | 500000 | 500000 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 500000 | 500000 | 0% | 0% | This project is in process, Land Administration together with Housing Department appointed conveyancers to fast track the rectification of Title Deeds. Awaiting registration of the title deeds in the Deeds office in order to pay the conveyancers
Human Settlements | Housing Projects |  | 255005 | 1 | 77 | 0002 | KPA2 | 1-50 | 1 | 77 | 0002 | P | P | P | 50 | 53 | A2 |  |  | Maintenance of Rental Stock | Own Funds c/o | 0 |  |  |  | 400000 | 400000 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0 | 0 |  | 400000 | 400000 | 0% | 0% | The project is progressing, service provider as been appointed with the help of Building Maintenance.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 26 | H1 |  |  | Housing Pilot Projects | LGTH | 515387 |  |  |  |  | 515387 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 515387 | 515387 | 0% | 0% | Project is still on pre-planning stage.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 25 | H1 |  |  | Informal Settlement Upgrading | LGTH | 2007857 |  |  |  |  | 2007857 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [21 empty] | 0 | 0 | 0 |  | 2007857 | 2007857 | 0% | 0% | Project is still on pre-planning stage.
[20 empty] | TOTAL: HUMAN SETTLEMENTS |  | 111827541 |  |  |  | 45440602 | 157268143 | 574779.76 | 5180 | 579959.76 | 17257130.24 | 0 | 17257130.24 | 12115883.77 | 0 | 12115883.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134682.07 | 29947793.77 | 29952973.77 | 0 | 127320349.23 | 127315169.23 | 19.04% | 19.05%
DIRECTORATE OF HEALTH AND PUBLIC SAFETY | [19 empty] | DIRECTORATE OF HEALTH AND PUBLIC SAFETY
Health and Public Safety |  |  | 710040 | [5 empty] | 1 | 77 | 0013 | P | 7 | 5 | 0 | 0 | 01 | D9 | 1 to 50 | Climate Protection | DEDEAT | 106835 |  |  |  | -106835 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | [21 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Health and Public Safety |  |  | 725015 | [5 empty] | 1 | 77 | 0002 | P | 7 | 5 | 0 | 0 | 02 | A2 |  | CCTV Masterplan | Own Funds c/o | 0 |  |  |  | 101522 | 101522 |  |  |  | 0 |  | 0 | 0 |  | 0 | [22 empty] | 0 | 0 |  | 101522 | 101522 | 0% | 0% | Project currently in progress and almost nearing completion.
Health and Public Safety |  |  | 725055 | [5 empty] | 1 | 77 | 0025 | P | 7 | 5 | 0 | 0 | 04 | D4 | 1 to 50 | Disaster Management | TRUST FUNDS | 176266 |  |  |  |  | 176266 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | [21 empty] | 0 | 0 | 0 |  | 176266 | 176266 | 0% | 0% | This is Trust funding of which approximately R20 000.00 was derived from public donations made during the 2002 flooding. Disaster Management requires confirmation on the source of the remaining R150 000.00 so that appropriate business plans can be prepared.
[20 empty] | TOTAL: HEALTH AND PUBLIC SAFETY |  | 283101 |  |  |  | -5313 | 277788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277788 | 277788 | 0% | 0%
DIRECTORATE OF COMMUNITY SERVICES | [19 empty] | DIRECTORATE OF COMMUNITY SERVICES
Community Services |  |  | 755005 | [5 empty] | 1 | 77 | 0013 | P | 8 | 5 | 0 | 0 | 08 | D9 |  | Climate Protection | DEDEAT | 0 |  |  |  | 106835 | 106835 |  |  |  | 0 |  | 0 | 0 |  | 0 | [22 empty] | 0 | 0 |  | 106835 | 106835 | 0% | 0% | To obtain more information from Finance on the purpose of funding
Community Services |  |  | 755035 | [5 empty] | 1 | 77 | 0002 | P | 8 | 5 | 0 | 0 | 09 | A2 |  | BCMM Climate Change Strategy | Own Funds c/o | 0 |  |  |  | 37189 | 37189 |  |  |  | 0 |  | 0 | 0 |  | 0 | [22 empty] | 0 | 0 |  | 37189 | 37189 | 0% | 0% | report submitted for council approval
Community Services |  |  | 755035 | [5 empty] | 1 | 77 | 0002 | P | 8 | 5 | 0 | 0 | 10 | A2 |  | Environmental Education Strategy | Own Funds c/o | 0 |  |  |  | 65655 | 65655 |  |  |  | 0 |  | 0 | 0 |  | 0 | [22 empty] | 0 | 0 |  | 65655 | 65655 | 0% | 0% | invoice submitted to finance for payment
Community Services |  |  | 755035 | [5 empty] | 1 | 77 | 0002 | P | 8 | 5 | 0 | 0 | 11 | A2 |  | Reviewable of the Integrated Environmental Plan & Coastal Zone Management Plan | Own Funds c/o | 0 |  |  |  | 234971 | 234971 |  |  |  | 0 |  | 0 | 0 |  | 0 | [22 empty] | 0 | 0 |  | 234971 | 234971 | 0% | 0% | draft report has been submitted by service provider ,repor to be presented to Top Management Committe. invoice submitted to finance for payment
Community Services |  |  | 760020 | [5 empty] | 1 | 77 | 0013 | P | 8 | 5 | 0 | 0 | 01 | D9 |  | John Dube Village | DEDEAT | 199168 |  |  |  |  | 199168 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | [21 empty] | 0 | 0 | 0 |  | 199168 | 199168 | 0% | 0% | Department to meet Cllr Tokwe to determine utilization of funds
Community Services |  |  | 760020 | [5 empty] | 1 | 77 | 0098 | P | 8 | 5 | 0 | 0 | 03 | N3 |  | Art Centres | DSRAC | 37438 |  |  |  |  | 37438 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | [21 empty] | 0 | 0 | 0 |  | 37438 | 37438 | 0% | 0% | Department to identify an Art Centre to utilize the funds
Community Services |  |  | 760025 | [5 empty] | 1 | 77 | 0015 | P | 8 | 5 | 0 | 0 | 04 | D2 |  | Community Development Projects | LGTH | 2127846 |  |  |  |  | 2127846 | 1125060 | 0 | 1125060 | 1252201.6 |  | 1252201.6 | 257920.5 |  | 257920.5 | [21 empty] | 20222.1 | 2635182.1 | 2635182.1 |  | -507336.1 | -507336.1 | 123.8% | 123.8% | Memo for utilization of funding for the Cleaning Intervention Project has been approved by the City Manager.
Community Services |  |  | 760025 | [5 empty] | 1 | 77 | 0025 | P | 8 | 5 | 0 | 0 | 05 | D4 |  | Refurbishment and Maintenace of Halls - Rural Areas | TRUST FUNDS | 427011 |  |  |  |  | 427011 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | [21 empty] | 0 | 0 | 0 |  | 427011 | 427011 | 0% | 0% | Department to identify a rural hall in order to utilize funding
Community Services | Amenities |  | 765005 |  |  | 0002 | KPA2 |  | 1 | 77 | 0002 | P | 8 | 5 | 0 | 0 | 02 | A2 |  | Amenities Masterplan | Own Funds | 1200000 |  |  |  |  | 1200000 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | [21 empty] | 0 | 0 | 0 |  | 1200000 | 1200000 | 0% | 0% | Bid specifications being developed
Community Services |  |  | 765010 | [5 empty] | 1 | 77 | 0098 | P | 8 | 5 | 0 | 0 | 06 | N3 |  | Premier's Fund | Premiers Fund | 67421 |  |  |  |  | 67421 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | [21 empty] | 0 | 0 | 0 |  | 67421 | 67421 | 0% | 0% | To obtain more information from Finance on the purpose of funding
Community Services |  |  | 770030 | [5 empty] | 1 | 77 | 0002 | P | 8 | 5 | 0 | 0 | 07 | A2 |  | Biodiveristy Conservation Plan | Own Funds | 600000 |  |  |  |  | 600000 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | [21 empty] | 0 | 0 | 0 |  | 600000 | 600000 | 0% | 0% | The department is in the process of developing terms of reference.
[20 empty] | TOTAL : COMMUNITY SERVICES |  | 4658884 |  |  |  | 444650 | 5103534 | 1125060 | 0 | 1125060 | 1252201.6 | 0 | 1252201.6 | 257920.5 | 0 | 257920.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20222.1 | 2635182.1 | 2635182.1 | 0 | 2468351.9 | 2468351.9 | 51.63% | 51.63%
[20 empty] | TOTAL OPERATING PROJECTS |  | 210971670 | 0 | 0 | 0 | 77466153 | 288437823 | 4163028.02 | 14204.67 | 4177232.69 | 21850241.81 | 0 | 21850241.81 | 18065136.62 | 88508.93 | 18153645.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810987.34 | 44078406.45 | 44181120.05 | 0 | 244359416.55 | 244256702.95 | 15.28% | 15.32%
[20 empty] | LED - PROJECTS TAKEN OFF | [6 empty] | 288437823 | 4163028.02 | 14204.67 |  | 21850241.81 | 0 |  | 18065136.62 | 88508.93 | 18153645.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 44078406.45 | -44181120.05
Housing Projects TRF to OPEX - USDG
[20 empty] | Budget Reforms - Adjusted FMG |  |  | -200000
[20 empty] | Housing Projects TRF to OPEX - USDG |  |  | 1903000
[20 empty] | Housing Projects Adjusted - HSDG |  |  | -25277477
[20 empty] | ACEGrant |  |  | 7991312.28
[20 empty] | Housing Projects - Own Funds |  |  | 1700000
[20 empty] | DVRI Projects - LGHT |  |  | 5000000
[20 empty] | Beneficiary Education - Funded by Own Funds |  |  | 200000
Development Planning |  |  | 635005 | [16 empty] | Destination Marketing Programme | Own Funds
Development Planning |  |  | 635005 | [16 empty] | Bussiness Support Programme | Own Funds
Development Planning |  |  | 635005 | [16 empty] | Economic Empowerment Programme | Own Funds
Development Planning |  |  | 635005 | [16 empty] | Trade and Investment Programme | Own Funds
Development Planning |  |  | 635005 | [16 empty] | Economic Events Programme | Own Funds
Development Planning |  |  | 635005 | [16 empty] | Rural Economic Development Programme | Own Funds
Development Planning |  |  | 635005 | [16 empty] | Economic Planning | Own Funds
Executive Support Services | Public Participation & Ward Committees |  | 120005 | 1 | 77 | 0002 | KPA5 | N/A | 1 | 77 | 0002 | P | 1 | 4 | 0 | 0 | 15 | A2 |  | Intergovernmental Relations | Own Funds |  | 80000 |  | 80000 |  | 80000 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [13 empty] | 0 | 0 |  | 80000 | 80000 | 0% | 0%
Executive Support Services | Special Programmes |  | 105030 | 1 | 77 | 0002 | KPA5 | All | 1 | 77 | 0002 | P | 1 | 4 | 0 | 0 | 11 | A2 |  | Municipal Bursaries | Own Funds |  | 1200000 |  | 1200000 |  | 1200000 | 331189.13 |  |  | 12515.56 |  |  | 33145.98 |  | 33145.98 | 71221.85 |  | 71221.85 | 78738 |  | 78738 | 3816 |  | 3816 | [12 empty] | Nil | 530626.52 | 530626.52 |  | 669373.48 | 669373.48 | 44.22% | 44.22%
Executive Support Services | Special Programmes |  | 105030 | 1 | 77 | 0002 | KPA5 | All | 1 | 77 | 0002 | P | 1 | 4 | 0 | 0 | 12 | A2 |  | Youth Advisory Centres | Own Funds |  | 1200000 |  | 1200000 |  | 1200000 | 0 |  |  | 4070 |  |  | 191315.75 |  | 191315.75 | 106274.84 |  | 106274.84 | 246403.17 |  | 246403.17 | 238137.33 |  | 238137.33 | [12 empty] | Nil | 786201.09 | 786201.09 |  | 413798.91 | 413798.91 | 65.52% | 65.52%
Executive Support Services | Special Programmes |  | 105030 | 1 | 77 | 0002 | KPA5 | All | 1 | 77 | 0002 | P | 1 | 4 | 0 | 0 | 13 | A2 |  | Days of Importance | Own Funds |  | 500000 |  | 500000 |  | 500000 | 6819.5 |  |  | 18526 |  |  | 106724.51 |  | 106724.51 | 57908.63 |  | 57908.63 | 8696.71 |  | 8696.71 | 45704.79 |  | 45704.79 | [12 empty] | Nil | 244380.14 | 244380.14 |  | 255619.86 | 255619.86 | 48.88% | 48.88%
Executive Support Services | Special Programmes |  | 105030 | 1 | 77 | 0002 | KPA5 | All | 1 | 77 | 0002 | P | 1 | 4 | 0 | 0 | 14 | A2 |  | Women's Caucus | Own Funds |  | 300000 |  | 300000 |  | 300000 | 3155 |  |  | 8400 |  |  | 21550 |  | 21550 | 80117.24 |  | 80117.24 | 18976.55 |  | 18976.55 | 87113.16 |  | 87113.16 | [12 empty] | Nil | 219311.95 | 219311.95 |  | 80688.05 | 80688.05 | 73.1% | 73.1%
Municipal Manager's Office | Office of the Municipal Manager |  | 205005 | 1 | 77 | 0002 | KPA5 | N/A | 1 | 77 | 0002 | P | 2 | 4 | 2 | 0 | 00 | A2 |  | Risk Management | Own Funds |  | 500000 |  | 500000 |  | 500000 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 22073 |  | 22073 | 0 |  | 0 | [13 empty] | 22073 | 22073 |  | 477927 | 477927 | 4.415% | 4.415%
Municipal Manager's Office |  |  | 205005 |  |  | 0354 | KPA4 | N/A | 1 | 77 | 0002 | P | 2 | 4 | 7 | 0 | 00 | A2 |  | MPAC | Own Funds |  | 0 | 200000 | 200000 |  | 200000 |  |  |  | 0 |  |  | 8059.5 | 0 | 8059.5 | 55997.04 |  | 55997.04 | 57811.67 |  | 57811.67 | 17548.26 |  | 17548.26 | [13 empty] | 139416.47 | 139416.47 |  | 60583.53 | 60583.53 | 69.71% | 69.71%
Development Planning | Transportation |  | 620005 | 1 | 77 | 0002 | KPA2 | All Wards | 1 | 77 | 0002 | P | 6 | 4 | 0 | 0 | 01 | A2 |  | Integrated Transport Plan Review | Own Funds |  | 800000 |  | 800000 |  | 800000 |  |  |  | 54455.95 |  |  | 132989.8 |  | 132989.8 | -66494.9 |  | -66494.9 | 0 |  | 0 |  |  | 0 | [13 empty] | 120950.85 | 120950.85 | 0 | 679049.15 | 679049.15 | 15.12% | 15.12%
Development Planning | Local Economic Development |  | 635005 |  |  | 0002 | KPA3 | 31,34,39 | 1 | 77 | 0002 | P | 6 | 4 | 0 | 0 | 04 | A2 |  | Rural Economic Development Programme | Own Funds |  | 3000000 |  | 3000000 |  | 3000000 | 24196.63 |  |  | 232262.76 |  |  |  |  | 0 | 285513.31 |  | 285513.31 | 64303.38 |  | 64303.38 | 56985.07 |  | 56985.07 | [13 empty] | 663261.15 | 663261.15 | 0 | 2336738.85 | 2336738.85 | 22.11% | 22.11%
Development Planning | Local Economic Development |  | 635005 |  |  | 0002 | KPA3 | All Wards | 1 | 77 | 0002 | P | 6 | 4 | 0 | 0 | 05 | A2 |  | Economic Planning | Own Funds |  | 200000 |  | 200000 |  | 200000 | [8 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [13 empty] | 0 | 0 | 0 | 200000 | 200000 | 0% | 0%
Development Planning | Land Survey |  | 615085 | 1 | 77 | 0002 | KPA2 | N/A | 1 | 77 | 0002 | P | 6 | 4 | 0 | 0 | 07 | A2 |  | Subdivision of Municipal Leased Properties | Own Funds |  | 400000 | 0 | 400000 |  | 400000 | [8 empty] | 0 | 3295.68 |  | 3295.68 | 0 |  | 0 | 0 |  | 0 | [13 empty] | 3295.68 | 3295.68 | 0 | 396704.32 | 396704.32 | 0.8239% | 0.8239%
Development Planning | City Planning |  | 615070 | 1 | 77 | 0002 | KPA2 | 11,12,14,17,20-24,30,42,48,50 | 1 | 77 | 0002 | [8 empty] | Mdantsane Industrial Township Feasibility Study | Own Funds |  | 0 |  | 0 |  | 0 | [11 empty] | 0 | 0 |  | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 0 | 0 | 0% | 0%
Development Planning | City Planning |  | 615070 | 1 | 77 | 0002 | KPA2 | 17, 26 | 1 | 77 | 0002 | P | 6 | 4 | 0 | 0 | 09 | A2 |  | Newlands Local Spatial Development Framework | Own Funds |  | 400000 |  | 400000 |  | 400000 | [8 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 27120 |  | 27120 | [13 empty] | 27120 | 27120 | 0 | 372880 | 372880 | 6.78% | 6.78%
Development Planning | City Planning |  | 615070 | 1 | 77 | 0002 | KPA2 | All Wards | 1 | 77 | 0002 | [6 empty] | A2 |  | BCMM Township Establishment | Own Funds |  | 0 |  | 0 |  | 0 | [11 empty] | 0 | 0 |  | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 0 | 0 | 0% | 0%
Development Planning | Local Economic Development |  | 635005 | 1 | 77 | 0002 | KPA3 | All Wards | 1 | 77 | 0002 | [8 empty] | Destination Marketing Programme | Own Funds |  | 0 |  |  |  | 0 | [14 empty] | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 0 | 0 | 0% | 0%
Development Planning | Local Economic Development |  | 635005 | 1 | 77 | 0002 | KPA3 | All Wards | 1 | 77 | 0002 | [6 empty] | A2 |  | Business Support Programme | Own Funds |  | 0 |  |  |  | 0 | [14 empty] | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 0 | 0 | 0% | 0%
Development Planning | Local Economic Development |  | 635005 | 1 | 77 | 0355 | KPA3 | All Wards | 1 | 77 | 0002 | [8 empty] | Economic Empowerment Programme | Own Funds |  | 0 |  |  |  | 0 | [11 empty] | 0 |  |  | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 0 | 0 | 0% | 0%
Development Planning |  |  | 635005 | 1 | 77 | 0356 | KPA4 | All Wards | 1 | 77 | 0002 | P | 6 | 4 | 0 | 0 | 26 | A2 |  | Trade and Investment Programme | Own Funds |  | 0 | 1166032 | 1166032 |  | 1166032 | [8 empty] | 0 | 0 |  | 0 | 4500 |  | 4500 | 0 |  | 0 | [13 empty] | 4500 | 4500 | 0 | 1161532 | 1161532 | 0.3859% | 0.3859%
Development Planning | Local Economic Development |  | 635005 |  |  | 0002 | KPA3 | All Wards | 1 | 77 | 0002 | P | 6 | 4 | 0 | 0 | 03 | A2 |  | Economic Events Programme | Own Funds |  | 4000000 |  | 4000000 |  | 4000000 | [6 empty] | 483935.98 |  | 483935.98 | 1079225.89 |  | 1079225.89 | 895486.05 |  | 895486.05 | 1474774.41 |  | 1474774.41 | [13 empty] | 3933422.33 | 3933422.33 | 0 | 66577.67 | 66577.67 | 98.34% | 98.34%
Chief Operations Officer | Housing Projects |  | 255005 | [5 empty] | 1 | 77 | 0002 | P | E | D | 20 | 35 | A2 |  |  | Maintenance of all rental stock | Own Funds |  | 1000000 |  | 1000000 |  | 1000000 |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 1000000 | 1000000 | 0% | 0%
Chief Operations Officer | Housing Projects |  | 255005 | [5 empty] | 1 | 77 | 0002 | P | E | D | 20 | 34 | A2 |  |  | Rectification of all title deeds | Own Funds |  | 700000 |  | 700000 |  | 700000 |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 700000 | 700000 | 0% | 0%
Engineering Services | Water Administration |  | 520005 | 1 | 77 | 0002 | KPA2 | 1,2,5,6,7,8,10 | 1 | 77 | 0002 | [8 empty] | Caretakers - Duncan Village and Information Settlements | Own Funds |  | 2000000 | 1200000 | 3200000 |  | 3200000 | 334200 |  |  | 22332.29 |  |  | 371090 |  | 371090 | 379951.76 |  | 379951.76 | 534917.14 |  | 534917.14 | 44809.75 |  | 44809.75 | [13 empty] | 1687300.94 | 1687300.94 |  | 1512699.06 | 1512699.06 | 52.73% | 52.73%
Engineering Services | Electricity |  | 535025 | 1 | 77 | 0002 | KPA2 | N/A | 1 | 77 | 0002 | [8 empty] | Electricity and Water Meter Tampering | Own Funds |  | 1000000 |  | 1000000 |  | 1000000 | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 1000000 | 1000000 | 0% | 0%
Health and Public Safety | Health Services |  | 710030 |  |  | 0002 | KPA2 | 1 to 50 | 1 | 77 | 0002 | P | 7 | 4 | 0 | 0 | 0 | 5 |  | Municipal Health Services - I.T & Database Development | Own Funds |  | 450000 | -450000 | 0 |  | 0 | 0 |  |  | 0 | [8 empty] | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 0 | 0 | 0% | 0%
Health and Public Safety | Health Services |  | 710030 |  |  | 0002 | KPA2 | 1 to 50 | 1 | 77 | 0002 | P | 7 | 4 | 0 | 0 | 0 | 6 |  | Automation of Air Quality Monitoring Stations | Own Funds |  | 250000 | -250000 | 0 |  | 0 | 0 |  |  | 5561.46 |  |  | -5561.46 |  | -5561.46 |  |  |  | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 0 | 0 | 0% | 0%
Community Services | IEMP |  | 755035 |  |  | 0002 | KPA2 | All | 1 | 77 | 0002 | P | 8 | 4 | 0 | 0 | 03 | A2 |  | BCMM Climate Change Strategy | Own Funds |  | 0 | 250000 | 250000 |  | 250000 |  |  |  | 0 |  |  | 3501.66 |  | 3501.66 | 0 |  | 0 | 0 |  | 0 | 145057.39 |  | 145057.39 | [12 empty] | 0 | 148559.05 | 148559.05 |  | 101440.95 | 101440.95 | 59.42% | 59.42%
Community Services | IEMP |  | 755035 |  |  | 0002 | KPA2 | All | 1 | 77 | 0002 | P | 8 | 4 | 0 | 0 | 04 | A2 |  | Environmental Education Strategy | Own Funds |  | 0 | 67715 | 67715 |  | 67715 |  |  |  | 0 |  |  | 2059.8 |  | 2059.8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 2059.8 | 2059.8 |  | 65655.2 | 65655.2 | 3.042% | 3.042%
Financial Services |  |  | 330010 | [16 empty] | Office Accomodation for Call Centre | Own Funds |  |  |  | 0 |  | 0
Financial Services |  |  | 330010 | [16 empty] | CRM & IVR Systems | Own Funds |  |  |  | 0 |  | 0
Financial Services |  |  | 330010 | [16 empty] | Microsoft CRM Licenses | Own Funds |  |  |  | 0 |  | 0
Chief Operations Officer | Housing Projects |  | 255005 |  |  | 0355 | KPA2 | All | 1 | 77 | 0002 | P | P | 2 | 04 | 02 | A2 | 2 |  | Beneficiary Education ( All Projects) | Own Funds |  | 200000 |  | 200000 |  | 200000 | 0 |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 307 |  | 307 | [13 empty] | 307 | 307 |  | 199693 | 199693 | 0.1535% | 0.1535%
Health and Public Safety | Disaster Management |  | 725055 |  |  | 0002 | KPA2 | 1 to 50 | 1 | 77 | 0002 | p | 7 | 4 | 0 | 0 | 0 | 4 |  | Disaster Management Structures | Own Funds |  | 40000 |  | 40000 |  | 40000 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 40000 | 40000 | 0% | 0%
Community Services |  |  | 770030 |  |  | 0354 | KPA1 | 40 | 1 | 77 | 0002 | P | 8 | 4 | 0 | 0 | 07 | A2 |  | Waste Management Programme (Take it Off to General Expenses 1/65) | Own Funds |  | 0 | 1352043 | 1352043 |  | 1352043 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 294409.79 |  | 294409.79 | 97746 |  | 97746 | [12 empty] | 0 | 392155.79 | 392155.79 |  | 959887.21 | 959887.21 | 29% | 29%
Note on D11: Ndzondi Kati: Ccentre s/be 105030 and is sitting under 120005

## Sheet1
667025500 |  | 679010100
31264500 |  | 32147900
698290000 |  | 711158000
698290000 |  | 722958000
0 |  | 11800000
| 2555 | 4088
| 7670 | 6132