## Per Funding
ANNEXURE A
2011/2012 1ST ROLL-OVER ADJUSTMENT BUDGET - CAPITAL PROJECTS
DIRECTORATE | COST CENTRE DESCRIPTION |  | PROJECT DESCRIPTION | 2011/2012 | 2011/2012 | 2011/2012 | COMMENTS | PROJECT STATUS phase as at 30 June 2010 (e.g. Contract not awarded, contract awarded, project on site, design phase, tender etc.) | REASONS why spending was not 100%: Name key challenges | TIME PERIOD to complete the rolled-over money
|  | COST |  | APPROVED | BUDGET | 1st ROLL-OVER
|  | CENTRE |  | BUDGET | ADJUSTMENTS | ADJ. BUDGET
1. Buffalo City Metropolitan Transport c/o
Directorate of Development Planning | Transport Planning & Operations Admin | 620005 | Potsdam/Needs Camp Bridge Feasibility Study | 710630 |  | 710630
|  |  |  | 710630 |  | 710630 | 0
2. Disaster Management Fund c/o
Directorate of Health & Public Safety | Disaster Management | 725055 | Disaster Management Capacity | 43940 | -7150 | 36790 |  | Tender Phase | Tender withdrawn, re-advertise. | March 2012
Directorate of Health & Public Safety | Disaster Management | 725055 | Disaster Management Centres | 84779 |  | 84779
Directorate of Health & Public Safety | Disaster Management | 725055 | Flood Relocation (DM Structures) | 0 | 41025 | 41025 |  | Funding transferred to City Planning for the calculation of Duncan Village floodlines
|  |  |  | 128719 | 33875 | 162594
3. DBSA Phase 4 and 5 c/o
Directorate of Engineering Services | Roads and Stormwater Drainage | 525025 | West Bank Restitution | 0 | 5577424 | 5577424 |  | DBSA Funding has been redirected to fund this project in this 2011/2012 Adjustment Budget Coastal Wards – (32, 9, 7, 6, 8, 13, 16 and 33/ Midland Wards 11, 20, 21, 22, 30, 48 and 50 / Inland Wards – 37, 39, 36, 35, 43, 36) | DBSA Funding has been redirected to fund this project in this 2011/2012 Adjustment Budget Coastal Wards – (32, 9, 7, 6, 8, 13, 16 and 33/ Midland Wards 11, 20, 21, 22, 30, 48 and 50 / Inland Wards – 37, 39, 36, 35, 43, 36) | December 2011
Directorate of Engineering Services | Roads and Stormwater Drainage | 525025 | Rural and Urban Roads | 0 | 10000000 | 10000000 |  | DBSA Funding has been redirected to fund this project in this 2011/2012 Adjustment Budget Coastal Wards – (32, 9, 7, 6, 8, 13, 16 and 33/ Midland Wards 11, 20, 21, 22, 30, 48 and 50 / Inland Wards – 37, 39, 36, 35, 43, 36) | DBSA Funding has been redirected to fund this project in this 2011/2012 Adjustment Budget Coastal Wards – (32, 9, 7, 6, 8, 13, 16 and 33/ Midland Wards 11, 20, 21, 22, 30, 48 and 50 / Inland Wards – 37, 39, 36, 35, 43, 36) | December 2011
Directorate of Health & Public Safety | Fire and Rescure Services | 725010 | KWT Fire Station | 0 | 2000000 | 2000000 |  | DBSA Funding has been redirected to TOP-UP this project in this 2011/2012 Adjustment Budget | No expenditure due to insuffient budget and that has been resolved by this additional R2 million from DBSA | December 2011
|  |  |  | 0 | 17577424 | 17577424
4. DEDEAT c/o
Directorate of Development Planning | Local Economic Development | 635005 | Hydro-ponics - MDT (funded by DEDEAT) | 0 | 5239.19 | 5239.19 | Roll Overs from 2009/10 | Procuring of seeds for Mdantsane Hydroponics | Late issuing of order number | 1 month after budget Approval by Council
|  |  |  | 0 | 5239.19 | 5239.19
5. Dept of Sports Arts and Culture c/o
Executive Support Services | Executive Support Sevices Office | 105005 | Upgrading of Sisa Dukashe, New Lands, Ndevana Stadium & Gompo Stadium. | 0 | 2272302.94 | 2272302.94 |  | Other sub-projects within the cluster are complete with exception of Ndevana. | Delays with electric connection from Eskom | Nov-2011
Executive Support Services | Executive Support Sevices Office | 105005 | Upgrading of Bisho, Dimbaza, Peelton, Madramini & Victoria Grounds Stadium | 0 | 6598469.31 | 6598469.31 |  | Project was in progress(Bhisho Stadium will utilize the internal contractor and portion with annual contractor to complete the outstanding works once the funds are available) | Contracts for Bisho, Peelton & Victoria Grounds were terminated due to contractor's perfomance & had to be re-advertised. Victoria Grounds has since been completed. | Jan-2012
Executive Support Services | Executive Support Sevices Office | 105005 | Upgrading of Tsholomnqa, Parkside, Needs Camp & North End. | 0 | 2208934.68 | 2208934.68 |  | Other sub-projects within the cluster are complete with exception of Tsholomnqa which is awaiting eskom connection. | Delays with electric connection from Eskom | Nov-2011
|  |  |  | 0 | 11079706.93 | 11079706.93
6. Dept of Science and Technology c/o
Directorate of Community Services | Integrated Enviromental Management | 755035 | Dry Sanitation & Greywater Recycling | 0 | 173830.13 | 173830.13 |  | Project incomplete. | There's a pending investigation on project implementation and current expenditure
Directorate of Community Services | Integrated Enviromental Management | 755035 | Waste Minimisation | 0 | 160317 | 160317 |  | Ongoing process | Waste Minimisation is an ongoing process as the institution is faced with a huge challenge around waste management | Ongoing process
|  |  |  | 0 | 334147.13 | 334147.13
7. Dept of Land Affairs c/o
Directorate of Development Planning | Land Administration | 615080 | West Bank Restitution Project | 0 | 4141302.75 | 4141302.75 |  | 80% of Titles have been registered. | Process of registration is protracted. | 01 June 2012
Directorate of Development Planning | Land Administration | 615080 | West Bank Land Restitution | 0 | 243551.48 | 243551.48 |  | 80% of Titles have been registered. | Process of registration is protracted. | 01 June 2012
|  |  |  | 0 | 4384854.23 | 4384854.23
8. DLGTA c/o
Directorate of Financial Services | Supply Chain Management | 320010 | Implementation of Intenda Electronic Software System | 0 | 10642.88 | 10642.88 | Roll Overs from 2009/10 | Project on site | Ongoing project | FYE
|  |  |  | 0 | 10642.88 | 10642.88
9. Eastern Cape Development Co-Operation c/o
Directorate of Engineering Services | Sewerage Interceptors | 515035 | Bulk Sanitation | 0 | 67358.44 | 67358.44 | Roll Overs from 2009/10 | Roll Over from 2010/2011 Fin Year. Project to be completed this financial year 2011/2012 | Roll Over from 2010/2011 Fin Year. Project to be completed this financial year 2011/2012 | Roll Over from 2010/2011 Fin Year. Project to be completed this financial year 2011/2012
|  |  |  | 0 | 67358.44 | 67358.44
10. European Commission c/o
Directorate of Health & Public Safety | Fire and Rescure Services | 725010 | Upgrade Mdantsane Fire Stations | 0 | 171183.39 | 171183.39 |  | Design Phase | Delays with appointment of service providers. | June 2012
|  |  |  | 0 | 171183.39 | 171183.39
11. Electricity Demand Side Management
Directorate of Engineering Services | Electricity Planning & Design | 535025 | Replacement of Street Lights | 4000000 |  | 4000000 | Roll Overs from 2009/10
|  |  |  | 4000000 | 0 | 4000000
12. Human Settlements Development Grant (HSDG)
Chief Operations Officer | Housing Department | 255005 | Reeston Phase 3 Stage 2-P3 | 22418000 |  | 22418000 | Roll Overs from 2009/10
Chief Operations Officer | Housing Department | 255005 | DVRI Pilot project 323 units (Mekeni ,Competition site,Haven Hills) | 7241014 |  | 7241014 | Roll Overs from 2009/10
Chief Operations Officer | Housing Department | 255005 | Mdantsane Access/Buffalo | 1412820 |  | 1412820 | Roll Overs from 2009/10
Chief Operations Officer | Housing Department | 255005 | Reeston Phase 3 Stage 3 | 5604500 |  | 5604500 | Roll Overs from 2009/10
Chief Operations Officer | Housing Department | 255005 | Block yard TRA-P3 | 2668500 |  | 2668500 | Roll Overs from 2009/10
|  |  |  | 39344834 | 0 | 39344834
13. Intergrated National Electricity Programme (INEP)
Directorate of Engineering Services | Electricity Planning & Design | 535025 | Electrification | 21000000 |  | 21000000 | Roll Overs from 2009/10
|  |  |  | 21000000 | 0 | 21000000
14. Leiden Platform c/o
Executive Support Services | Development Co-Operation | 120005 | Leiden Twinning - Floodplain | 0 | 488000 | 488000 |  | Work continuation of past financial year | Work continuation of past financial year | Dec. 2012
Executive Support Services | Development Co-Operation | 120005 | Leiden Twinning - Solid Waste Drop-off Points | 0 | 974717.59 | 974717.59 |  | SCM processes are in place to draft a memo to the Bid Adjudication for the appointment of the Secon Lowest Bidder | Service provider submitted a withdrawal letter | June 2012
Executive Support Services | Development Co-Operation | 120005 | Leiden Twinning - Sanitation | 0 | 746896.53 | 746896.53 |  | Construction of ablution blocks in Nompumelelo -Project lifecycle different to BCMM financial year | Work continuation of past financial year | Dec. 2012
Executive Support Services | Development Co-Operation | 120005 | Leiden Twinning Project - Solid Waste | 0 | 512605.52 | 512605.52 |  | Work continuation of past financial year | Capacity issues with Solid waste department | Dec. 2012
|  |  |  | 0 | 2722219.64 | 2722219.64
15. Local Government and Housing c/o
Chief Operations Officer | Housing | 255005 | Potsdam Unit P : Stage 2 : 1000 units : P3 : Infrastructure | 0 | 336462.15 | 336462.15 |  | Contractor on site | Work practically completed on site payments will held till end retention period. | Budget will be spent in this current financial year
Chief Operations Officer | Housing | 255005 | Accreditation | 0 | 33903 | 33903 |  | Ongoing | The funding is for office requirements for the demand database programme. | Budget will be spent in this current financial year
Chief Operations Officer | Housing | 255005 | Z. Soga: P3: Infrastructure | 0 | 274096.84 | 274096.84 |  | Almost complete. (Practical complete) | Awaiting the approval of additional funding by the PDoHS to pay the final payment of the service provider.The project should be closed off in 2011/2012 financial year. | On approval of additional funding by PDoHS and roll over budget by the Council.
|  |  |  | 0 | 644461.99 | 644461.99
16. Office of the Premier
Directorate of Community Services | Arts & Cultural Services Admin | 760005 | Egerton Railway Station Massacre Memorial Site | 0 | 500000 | 500000 | Roll Overs from 2009/10 | Project is at tender Stage | The project has been delayed, due to not having received the necessary approvals timeously from the Donor, however it is currently at Bid Adjudication stage. | June 2012
|  |  |  | 0 | 500000 | 500000
17. Own Funds
Municipal Manager | Office of the Municipal Manager & Support Services | 205005 | Councillor's IT requirements (Laptops) | 1000000 |  | 1000000
Directorate of Financial Services | Asset and Risk | 320005 | Asset Replacements | 0 | 10000000 | 10000000 |  | R10 million is for the Asset Replacements in respect of Insurance Claims for the entire BCM for 2011/2012 financial year | R10 million is for the Asset Replacements in respect of Insurance Claims for the entire BCM for 2011/2012 financial year | June 2012
Directorate of Corporate services | General Admin & Telecomm Services | 415015 | BCM IT Requirements (All Directorates) | 5000000 |  | 5000000
Directorate of Corporate services | Management Information Services | 415025 | Integrated Enterprise Resource planning System | 2000000 |  | 2000000
Directorate of Engineering Services | Sewerage Pump Station - Coastal | 515021 | Ablution Blocks Duncan Village | 2095378 |  | 2095378
Directorate of Engineering Services | Fleet management - Braelyn | 530020 | BCM Fleet | 7500000 |  | 7500000
Directorate of Development Planning | Market | 635010 | Extension of Sales Hall | 2000000 |  | 2000000
Directorate of Community Services | Refuse Removal | 770010 | Purchase of 7 Refuse Compactor Trucks - Mdantsane | 10500000 |  | 10500000
Directorate of Community Services | Refuse Removal | 770010 | Purchase of 3 Refuse Compactor Trucks (Mdantsane) | 4500000 |  | 4500000
Directorate of Community Services | Refuse Removal | 770010 | Purchase of 2 x LDV Bakkie's | 460000 |  | 460000
Directorate of Community Services | Refuse Removal | 770010 | Purchase of 1 X Load lugger | 800000 |  | 800000
Directorate of Community Services | Office of the Director of Community Services | 750005 | Refuse 5 Compactor Trucks - Coastal Region | 10000000 |  | 10000000
Directorate of Community Services | Office of the Director of Community Services | 750005 | Vehicles for Solid Waste Supervisors, Safety Officers, District Cleansing Officers and Superintendents -(9 X Sedans, 8 LDV's, 3 X Double Cabs, 2X3 Ton Trucks (Inland,Midlands and Coastal Areas) | 4000000 |  | 4000000
Directorate of Community Services | Interments | 755025 | Mitsubishi Fuso Canter - M07/212 | 385000 |  | 385000
Directorate of Community Services | Halls | 760025 | Continuation of refurbishment of KWT Hall | 2792507 |  | 2792507
Directorate of Community Services | Halls | 760025 | Upgrading of Beacon Bay Library | 363795 |  | 363795
Directorate of Community Services | Swimming Pools | 765015 | Ruth Belonsky Swimming Pool | 137822 |  | 137822
Directorate of Community Services | Resorts | 765035 | Intergrated Beach Front hub | 500000 |  | 500000
Directorate of Community Services | Cleansing Administration Support | 770005 | Grass Cutting Equipment | 1300000 |  | 1300000
Directorate of Community Services | Waste Disposal Sites | 770015 | Refuse removal Skips | 1000000 |  | 1000000
Directorate of Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 770030 | Regional Waste Disposal Site | 1000000 |  | 1000000
Directorate of Health & Public Safety | Traffic Administration | 725020 | Traffic Vehicles | 450000 |  | 450000
Directorate of Health & Public Safety | Vehicle Test Station / Examination | 725035 | Learners Licence Centre - Mdantsane | 800000 |  | 800000
|  |  |  | 58584502 | 10000000 | 68584502
18. Own Funds c/o
Directorate of Financial Services | Customer Care | 330020 | KWT civic Centre Payments Hall upgrade | 1998597 |  | 1998597 | Roll Overs from 2009/10
Directorate of Financial Services | Customer Care | 330020 | Upgrading of all Zone Offices -Mdantsane | 3498597 |  | 3498597
Directorate of Corporate services | Management Information Services | 415025 | Telecommunication network system | 107884.68 | 94390 | 202274.68 |  | Informal tender was awarded but the service provider could not deliver. | The service provider appointed could not deliver the service. | 2011-11-30
Directorate of Corporate services | Management Information Services | 415025 | Conferencing system | 598941.28 | -338911 | 260030.28 |  | Contract not awarded. | We were awaiting the award of network support tender. | 2011-03-31
Directorate of Corporate services | Management Information Services | 415025 | Radio Data Network - Mdantsane | 166469.24 | 8762 | 175231.24 |  | Informal tender was awarded but the service provider could not deliver. | The service provider appointed could not deliver the service. | 2011-11-30
Directorate of Engineering Services | Office of the Director of Engineering Services | 505005 | Building Security | 300000 | -174341 | 125659
Directorate of Engineering Services | Electricity Administration | 535005 | Electrification - Counterfunding Reeston & Other Areas | 2800000 | -2800000 | 0
Directorate of Engineering Services | Electricity Planning & Design | 535025 | Electricity Building Upgrade- Ablution Blocks | 145000 | 20923 | 165923 |  | Design Phase | Delays in compiling tender documents | 30 June 2012
Directorate of Engineering Services | Electricity Planning & Design | 535025 | Upgrade Electricity Reticulation (KWT and Coastal) | 3500000 | -3448826 | 51174 |  | Ongoing Project | Insufficient Funding | Insufficient Funding
Directorate of Engineering Services | Roads and Stormwater Drainage | 525025 | Rehabilitation of BCM bridges and culverts( Breidbach, Dimbaza, Quigney) | 1992904 | -19908 | 1972996 |  | Project at bid specification stage | Funding was not available | April 2012
Directorate of Engineering Services | Sewerage Pump Station - Coastal | 515021 | Upgrade Augmentation | 110220 | 415030 | 525250 |  | Will be completed this financial year | Will be completed this financial year | Will be completed this financial year
Directorate of Engineering Services | Scientific Services | 510005 | Upgrading of the Laboratory infrastructure and equipment | 757856 | 150732 | 908588 |  | Funding for 2 tenders awarded in 2010/11 financial year. 1st tender awarded and awaiting equipment delivery. 2nd tender awarded and configuration in progress. | 1st tender - equipment shipped from overseas. 2nd tender - configuration requires input of large volume of laboratory data. | 1st tender - October 2011. 2nd tender - February 2012.
Directorate of Development Planning | Local Economic Development | 635005 | Tourism infrastructure development | 1000000 | 797478 | 1797478
Directorate of Development Planning | Local Economic Development | 635005 | Roll – Out Hydroponics | 3500000 | 130503 | 3630503 |  | Was in the process of Bid Committess because the contract had to be readvertised due to non response to previous advert | Contract awarded in September 2011 | 4 months from the date of Budget Approval by Council
Directorate of Development Planning | Local Economic Development | 635005 | Buffalo City Agric & Rural Development Infrastructure | 2992741 | -199740 | 2793001 |  | In the bid committees, validity period expired. Still awaiting approval for cancellation of bids and readvertising | Still awaiting approval for cancellation of bids and readvertising of bids | 6 months from the date of Budget Approval by Council
Directorate of Development Planning | Local Economic Development | 635005 | Cooperative Support Programme | 1449188 | -1202733 | 246455
Directorate of Development Planning | Market | 635010 | Upgrade of Market | 1320000 | -360105 | 959895 |  | Phase one of the project was complete. Planning for phase 2 was underway. | Project implementation relied on completion of Phase One (Extension of sales hall). Phase one was only completed at the end of April 2011. | Project to be completed by June 2012
Directorate of Development Planning | Transport Planning & Operations Admin | 620005 | Rural non Motorised Transport facilities | 494490.5 |  | 494490.5
Directorate of Development Planning | Transport Planning & Operations Admin | 620005 | Traffic Management Measures | 1100000 | 714607 | 1814607 |  | Designs completed, moving to construction phase. | Project postponed as all contract 26 civil contractors had already been fully utilised by roads maintenance department. | Project to be completed by June 2012
Directorate of Development Planning | Transport Planning & Operations Admin | 620005 | Pedestrian facilities | 600000 | -256092 | 343908 |  | Annual milestones achieved, project ongoing | Sole supplier purchase issues with SCM. Informal tender process had to be used. | Project to be completed by June 2012
Directorate of Development Planning | Transport Planning & Operations Admin | 620005 | Guidance Signage | 600000 | -13554 | 586446 |  | Annual milestones achieved, project ongoing | Funding only released in third quarter and delays with procurement processes due to tender not being minuted at Bid Specification meeting | Project to be completed by June 2012
Directorate of Development Planning | Transport Planning & Operations Admin | 620005 | Yellowwoods River Bridge | 1900000 | 202612 | 2102612 |  | Contractor is on site and project is in the final stages of completion | This is a multi-year project and some delays were incurred due to rain | Project is complete
Directorate of Community Services | Office of the Director of Community Services | 750005 | Miscallaneous Bins | 58000 | -58000 | 0 |  | Project Complete | Project Complete | Project Complete
Directorate of Community Services | Interments | 755025 | Fencing of Rural Cemeteries Upgrade | 160000 | 154956 | 314956 |  | Order to Palisade fencing with SCM | Project initiated in 2010/11 financial year and thus a roll over | Dec 2011
Directorate of Community Services | Sportsfields | 765010 | Upgrading of Needs Camp Sportfield | 2350877 | 149123 | 2500000 |  | The terms of reference for the appointment of a professional service provider was forwarded to SCM on 30 June 2011. No feedback from SCM to date. | Lack of feedback from SCM | June 2012
Directorate of Community Services | Sportsfields | 765010 | Upgrading of Rural Sportsfields | 275821 | -203783 | 72038 |  | Service Provider on site levelling the playing area at Nkqonkqweni as part of scope of work for phase 1. Stock fencing of sportsfields to follow | Project was initiated late in the 2010/11 financial year and thus was rolled over. Lack of feedback from SCM | June 2012
Directorate of Community Services | Zoo | 765025 | Upgrading Of Zoo Offices & Ablution Blocks | 920501 | -197247 | 723254 |  | The letter of appointment of service provider has been received. According to Architects Division, they are awaiting a construction guarantee from the service provider before proceeding with implementation of the project | Project was initiated late in the 2010/11 financial year and thus was rolled over. Competitive bidding process was followed for this project and thus took up a significant amount of time | June 2012
Directorate of Community Services | Zoo | 765025 | Fencing Of Zoo c/o | 606481 |  | 606481 |  | Chacma baboon, hamadrayas enclosure and tiger swimming pool completed. Jaguaur swimming pool not yet completed. | Jaguar pool was not yet completed, therefore payment was not done to the service provider. According to the Architects Division a portion of the funding from this project will be combined with the project of Upgrading of the zoo offices and ablution blocks. | June 2012
Directorate of Community Services | Beaches | 765030 | Isuzu NQR 500 Cage Tipper - M09/153 | 348765 | -348765 | 0 |  | Tenders advertised by Mechanical Services | Awaiting feedback from Mechanical Services on progress with the tender | June 2012
Directorate of Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 770030 | Drop Off Points - Solid Waste | 210479 | -210479 | 0 |  | Project Complete | Project Complete | Project Complete
Directorate of Health & Public Safety | Pollution Control | 710040 | Air quality monitoring station equipment | 412163.49 | -311895 | 100268.49 |  | Informal requesition to be forwarded to SCM 18/10/11
Directorate of Health & Public Safety | Clinics | 710020 | Mobile Clinics Equipment | 235495 |  | 235495
Directorate of Health & Public Safety | Clinics | 710020 | Upgrading of Clinics - Ginsberg | 598124 | 100000 | 698124 |  | An Amount of R73 659.79 has been paid to Life Connections Manufacturing & Supply. The progress of the construction is a bit slow. | The progress of the construction is a bit slow.
Directorate of Health & Public Safety | Security Services | 725015 | Law Enforcement Equipment | 180000 | -161399 | 18601 |  | Contract awarded for licence plate recognition system - R161 399. | Tender prices were less than anticipated. | March 2012
Directorate of Health & Public Safety | Fire and Rescue Services | 725010 | Fire Engines Roll 0ver | 11502141 | 4456705 | 15958846 |  | Contract awarded. | Awaiting delivery & final invoice. | Nov. 2012
Directorate of Health & Public Safety | Fire and Rescue Services | 725010 | Fire Engine Equipment | 2874803 | -503399 | 2371404 |  | Tender phase | Awaiting delivery & final invoice. | Rescue sets January 2012 B.A Sets x 100 January 2012 Urban Rescue Veh. Jun. 2012
Executive Support Services | Executive Support Sevices Office | 105005 | Councillors Office | 0 | 2060844.76 | 2060844.76
Directorate of Engineering Services | Fleet Management - Braelyn | 530020 | Replacement of Bus Fleet | 0 | 5998398.75 | 5998398.75 |  | 5 solid waste trucks | The manufacture is still building the trucks | In 2months for the entire delivery
Directorate of Engineering Services | Fleet Management - Braelyn | 530020 | Traffic & Law Enforcement Fleet | 0 | 3000000 | 3000000 |  | 10 Traffic & Law enforcement sedans (2924) | The vehicles were delivered after the end of the financial year | Vehicles delivered & paid
|  |  |  | 51666539.19 | 7645887.51 | 59312426.7
19. Provincial Treasury Office - LED Support Programme
Directorate of Development Planning | LED | 635005 | Inner City regeneration - Pedestrian Priority Zone | 0 | 375269.23 | 375269.23 | Roll Overs from 2009/10 | Contract Awarded | Roll over is requested to do the final payment of R309,215-50 | Final payment as soon as the Report has been approved by Council
|  |  |  | 0 | 375269.23 | 375269.23
20. Public Transport Infrastructure and Systems Grant (PTISG)
Directorate of Development Planning | Transport Planning & Operations Admin | 620005 | Construction of BRT lanes | 180000000 |  | 180000000 | Roll Overs from 2009/10
|  |  |  | 180000000 | 0 | 180000000
21. Urban Settlement Development Grant (USDG)
Chief Operations Officer | Housing Department | 255005 | Mdantsane Zone 18 CC Phase 2-P3 | 11209000 |  | 11209000 | Roll Overs from 2009/10
Chief Operations Officer | Housing Department | 255005 | Manyano & Thembelihle Phase 2-P3 | 19055300 |  | 19055300
Chief Operations Officer | Housing Department | 255005 | Second Creek (Turn Key)-P3 | 5940770 |  | 5940770
Chief Operations Officer | Housing Department | 255005 | Masibambane-P3 | 1748604 |  | 1748604
Chief Operations Officer | Housing Department | 255005 | Masibulele-P3 | 1793440 |  | 1793440
Chief Operations Officer | Housing Department | 255005 | Velwano | 2241800 |  | 2241800
Chief Operations Officer | Housing Department | 255005 | Chris Hani Park Phase 3-P3 | 2353890 |  | 2353890
Chief Operations Officer | Housing Department | 255005 | Ilinge -P 3 | 2241800 |  | 2241800
Chief Operations Officer | Housing Department | 255005 | Gwentshe Village- P3 | 560450 |  | 560450
Chief Operations Officer | Housing Department | 255005 | Fynbos Informal 1-P3 | 2398726 |  | 2398726
Chief Operations Officer | Housing Department | 255005 | Fynbos Informal 2-P3 | 2241800 |  | 2241800
Chief Operations Officer | Housing Department | 255005 | Ndacama-P3 | 2241800 |  | 2241800
Chief Operations Officer | Housing Department | 255005 | Mathemba Vuso-P3 | 1681350 |  | 1681350
Chief Operations Officer | Housing Department | 255005 | Deluxolo Village-P3 | 1972784 |  | 1972784
Chief Operations Officer | Housing Department | 255005 | Francis Mei-P3 | 762212 |  | 762212
Chief Operations Officer | Housing Department | 255005 | Mahlangu Village-P3 | 2040038 |  | 2040038
Chief Operations Officer | Housing Department | 255005 | Sisulu Village-P3 | 1726186 |  | 1726186
Chief Operations Officer | Housing Department | 255005 | Winnie Mandela-P3 | 1681350 |  | 1681350
Chief Operations Officer | Housing Department | 255005 | Dacawa-P3 | 1681350 |  | 1681350
Chief Operations Officer | Housing Department | 255005 | Sunny South-P3 | 2241800 |  | 2241800
Directorate of Engineering Services | Roads and Stormwater Drainage | 525025 | Mdantsane Roads | 42375700 |  | 42375700
Directorate of Engineering Services | Roads Design | 525020 | West Bank Restitution | 15000000 |  | 15000000
Directorate of Engineering Services | Roads Design | 525020 | Rural Roads Upgrade | 5000000 |  | 5000000
Directorate of Engineering Services | Roads and Stormwater Drainage | 525025 | Rehabilitation of Rural Roads Upgrade | 5000000 |  | 5000000
Directorate of Engineering Services | Sewerage Admin | 515010 | Nord Avenue Pump station | 8000000 |  | 8000000
Directorate of Engineering Services | Sewerage Admin | 515010 | Quinera Treatment Works | 50000000 |  | 50000000
Directorate of Engineering Services | Sewerage Treatment- Coastal | 515026 | Waste Water Treatment Capacity (Zwelitsha) | 15000000 |  | 15000000
Directorate of Engineering Services | Sewerage Treatment- Central | 515027 | Reeston Phase 3 Bulk Services Sewer | 25000000 |  | 25000000
Directorate of Engineering Services | Sewerage Treatment- Inland | 515028 | Bufferstrip Sanitation - Mdantsane | 15000000 |  | 15000000
Directorate of Engineering Services | Sewerage Reticulation -Coastal | 515031 | Mdantsane Sewers - Refurbishment | 5000000 |  | 5000000
Directorate of Engineering Services | Sewerage Admin | 515010 | Diversion of Amalinda and Wilsonia effluent to Reeston | 50000000 |  | 50000000
Directorate of Engineering Services | Bulk pumping stations | 520015 | Augmentation of Water Treatment Capacity - Umzonyana/Raising Upper weir | 5000000 |  | 5000000
Directorate of Engineering Services | Sewerage Admin | 515010 | Inland Rural Sanitation (Dimbaza Villages,Ngxwalane and Kwalini) | 36000000 |  | 36000000
Directorate of Engineering Services | Umzonyana Water Treatment Works | 520021 | Bulk Water Supply Newlands and other areas | 1000000 |  | 1000000
Directorate of Engineering Services | Water Ops and Maint.-Inland | 520025 | Ward 33 Bulk Water Supply Scheme | 7000000 |  | 7000000
Directorate of Engineering Services | Water Ops and Maint.-Inland | 520025 | Bulk Water Supply Coastal Areas | 8000000 |  | 8000000
Directorate of Development Planning | Local Economic Development | 635005 | BCM Urban Agriculture Infrastructure Development | 3000000 |  | 3000000
Directorate of Development Planning | Transport Planning & Operations Admin | 620005 | Taxi Ranks | 5000000 |  | 5000000
Directorate of Development Planning | Transport Planning & Operations Admin | 620005 | Gonubie Main Road | 10000000 |  | 10000000
Directorate of Development Planning | Local Economic Development | 635005 | Economic Infrastructure | 5000000 |  | 5000000
Directorate of Community Services | Cleansing Administration Support | 755010 | Development of Community Parks(Mdantsane, Potsdam, Reeston) | 1016303 |  | 1016303
Directorate of Community Services | Interments | 755025 | Development of 3 New Cemetries(Inland, Midland and Coastal) | 3000000 |  | 3000000
Directorate of Community Services | Halls | 760025 | Scenery Park Community Hall | 2000000 |  | 2000000
Directorate of Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 770030 | Solid waste management | 8800000 |  | 8800000
Directorate of Community Services | Sportsfields | 765010 | Sport Facilities | 2000000 |  | 2000000
Directorate of Health & Public Safety | Fire and Rescue Services | 725010 | Fire and Clinics | 6227453 |  | 6227453
Directorate of Health & Public Safety | Clinics | 710020 | Clinics | 3000000 |  | 3000000
|  |  |  | 409233906 | 0 | 409233906
|  |  |  | 764669130.19 | 55552269.56 | 820221399.75 | #REF!