## 2014-2017 Projects
BUFFALO CITY METROPOLITAN MUNICIPALITY | [65 empty] | Annexure D
2014-2015 OPERATING PROJECTS BUDGET
Directorate | Directorate | USDG Per Service | Vote Number | [8 empty] | Job Number | [6 empty] | Ward No. | Project Name | Funding Source | 2014/2015 Approved Budget | 2013/2014 Approved Opex Budget | Adjustment | Rollover Budget Adjustment | Adjustments | 2014/2015 Rollover Adjustment Budget | Jul14 | VAT | Jul 14 inc. VAT | Aug 14 | VAT | Aug 14 (incl. VAT | Sept 14 | VAT | Sept 2014 (Incl. Vat) | Oct 14 | Vat | October Incl. VAT | Nov 14 | Vat | Nov 14 including VAT | Dec 14 | VAT | Dec (Inc. Vat) | Jan 15 | VAT | Feb 15 | VAT | Mar 15 | VAT | Apr 15 | VAT | May 15 | VAT | June 15 | VAT | Commitments (Venus) | 2014/2015 TOTAL EXPENDITURE TO DATE (VENUS) | YTD Expenditure (VAT incl) | Commitments (Outstanding invoices for work done not yet paid | 2014/2015 AVAILABLE BUDGET | Available Budget ( Budget -Expenditure including VAT) | % EXPENDITURE VS BUDGET | % Expenditure (including VAT) | COMMENTS
EXECUTIVE SUPPORT SERVICES
DIRECTORATE OF EXECUTIVE SUPPORT SERVICES
Executive Support Services |  |  | 110005 | [5 empty] | 1 | 77 | 0002 | P | 1 | 5 | 0 | 0 | 15 | A2 |  | Millenium Development Goals Framework Rollout | Own Funds c/o | 0 |  |  |  | 100000 | 100000 |  |  |  | 0 |  | 0 | 50764.04 |  | 50764.04 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [13 empty] | 50764.04 | 50764.04 |  | 49235.96 | 49235.96 | 50.76% | 50.76% | Project on track and further payments will be effected in the 3rd quarter of financial year
Executive Support Services |  |  | 120005 | [5 empty] | 1 | 77 | 0025 | P | 1 | 5 | 2 | 0 | 00 | D4 | All Wards | Community Support Centre | Leiden | 136315 |  |  |  |  | 136315 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 136315 | 136315 | 0% | 0% | Preparatory work in progress.
Executive Support Services |  |  | 120005 | [5 empty] | 1 | 77 | 0025 | P | 1 | 5 | 0 | 0 | 16 | D4 |  | Intergovernmental Relations | Own Funds c/o | 0 |  |  |  | 80000 | 80000 |  |  |  | 0 |  | 0 | 27850 |  | 27850 |  |  | 0 | 3500 |  | 3500 | 0 |  | 0 | [12 empty] | 0 | 31350 | 31350 |  | 48650 | 48650 | 39.19% | 39.19% | Expenditure incurred is for Exco Outreach that was conducted by the Premier for 16 Days of Activist. Expenditure will improve as the year progresses and the funds will be fully spent by 30 June 2015.
Executive Support Services |  |  | 120010 | [5 empty] | 1 | 77 | 0025 | P | 1 | 5 | 3 | 0 | 00 | D4 | All Wards | Ward Committee Training | TRUST FUNDS | 132152 |  |  |  |  | 132152 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 132152 | 132152 | 0% | 0% | Procurement process underway
Executive Support Services |  |  | 120005 | [5 empty] | 1 | 77 | 0025 | P | 1 | 5 | 4 | 0 | 00 | D4 | All Wards | Umsobomvu Youth Fund | Umsobomvu Youth Fund | 710406 |  |  |  |  | 710406 | 33130 | 0 | 33130 | 2976.31 |  | 2976.31 | 18090.18 |  | 18090.18 | 103895.87 |  | 103895.87 | 85010.62 |  | 85010.62 | 6080.44 |  | 6080.44 | [12 empty] | 0 | 249183.42 | 249183.42 |  | 461222.58 | 461222.58 | 35.08% | 35.08% | Project is ongoing and is progressing well.
Executive Support Services | Knowledge Management |  | 130005 | 1 | 77 | 0002 | KPA5 | N/A | 1 | 77 | 0002 | P | 1 | 5 | 1 | 0 | 00 | A2 | All Wards | Documentation of case studies | Own Funds | 300000 |  |  |  |  | 300000 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 2540.24 |  | 2540.24 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 2540.24 | 2540.24 |  | 297459.76 | 297459.76 | 0.8467% | 0.8467% | Procurement process underway
Executive Support Services |  |  | 130005 | [5 empty] | 1 | 77 | 0002 | P | 1 | 5 | 0 | 0 | 29 | A2 |  | Documentation of case studies c/o | Own Funds c/o | 0 |  |  |  | 296292 | 296292 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 | 1546.23 |  | 1546.23 | 3976.02 |  | 3976.02 | [13 empty] | 5522.25 | 5522.25 |  | 290769.75 | 290769.75 | 1.864% | 1.864% | Procurement process underway
[20 empty] | TOTAL : EXECUTIVE SUPPORT SERVICES |  | 1278873 |  |  |  | 476292 | 1755165 | 33130 | 0 | 33130 | 2976.31 | 0 | 2976.31 | 96704.22 | 0 | 96704.22 | 106436.11 | 0 | 106436.11 | 90056.85 | 0 | 90056.85 | 10056.46 | 0 | 10056.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339359.95 | 339359.95 | 0 | 1415805.05 | 1415805.05 | 19.33% | 19.33%
MUNICIPAL MANAGER'S OFFICE | [19 empty] | MUNICIPAL MANAGER'S OFFICE
Municipal Manager's Office | Office of the Municipal Manager |  | 205005 |  |  | 0002 | KPA5 | N/A | 1 | 77 | 0002 | P | 2 | 5 | 0 | 0 | 01 | A2 | All Wards | Audit Improvement Plan | Own Funds | 3750000 |  |  |  |  | 3750000 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 3750000 | 3750000 | 0% | 0% | Ongoing multi-year project- invoices being processed
Municipal Manager's Office |  |  | 205005 |  |  | 0002 | KPA5 | N/A | 1 | 77 | 0002 | P | 2 | 5 | 4 | 0 | 00 | A2 |  | Audit Improvement Plan c/o | Own Funds c/o | 0 |  |  |  | 6400281 | 6400281 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 6400281 | 6400281 | 0% | 0% | Ongoing multi-year project- invoices being processed
Municipal Manager's Office | Office of the Municipal Manager |  | 205005 |  |  | 0002 | KPA5 | N/A | 1 | 77 | 0025 | P | 2 | 5 | 0 | 0 | 02 | D4 | All Wards | Audit Improvement Plan / SCM Irregular Expenditure | TRUST FUNDS | 1979270 |  |  |  |  | 1979270 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 1979270 | 1979270 | 0% | 0% | Ongoing multi-year project- invoices being processed
Municipal Manager's Office | Office of the Municipal Manager | EPMO | 205005 |  |  | 0355 | KPA5 | N/A | 1 | 77 | 0098 | P | 2 | 5 | 0 | 0 | 03 | N3 | All Wards | Project Management Funding (USDG Projects) | USDG | 29914500 |  |  |  |  | 29914500 | 1900290.37 | 5780.6 | 1906070.97 | 1814948.97 |  | 1814948.97 | 2373811.44 | 76524.28 | 2450335.72 | 1983297.55 | 24829.5 | 2008127.05 | 2370313.7 | 55458.89 | 2425772.59 | 2312190.16 | 20384 | 2332574.16 | [12 empty] | 102169.2 | 12754852.19 | 12937829.46 |  | 17159647.81 | 16976670.54 | 42.64% | 43.25% | USDG funding for project management office-. Procurement is ongoing. 3 Senior officials have been appointed.
Municipal Manager's Office | Office of the Municipal Manager | EPMO | 205005 |  |  | 0355 | KPA5 | N/A | 1 | 77 | 0098 | P | 2 | 5 | 0 | 0 | 06 | N3 | All Wards | Filling and repair , cleaning of Roads and stormwater drainage | EPWP | 945000 |  |  |  |  | 945000 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 378000 |  | 378000 | 283500 |  | 283500 | 0 |  | 0 | [12 empty] | 0 | 661500 | 661500 |  | 283500 | 283500 | 70% | 70% | Ongoing multi-year project
Municipal Manager's Office |  |  | 205005 | [5 empty] | 1 | 77 | 0098 | P | 2 | 5 | 0 | 0 | 08 | N3 | All Wards | Maintenance of ECO Parks | EPWP | 378000 |  |  |  |  | 378000 | 0 | 0 | 0 | 0 |  | 0 | 254450 |  | 254450 | 20580 |  | 20580 | 17890 |  | 17890 | 22270 | 0 | 22270 | [12 empty] | 0 | 315190 | 315190 |  | 62810 | 62810 | 83.38% | 83.38% | Ongoing multi-year project
Municipal Manager's Office |  |  | 205005 | [5 empty] | 1 | 77 | 0098 | P | 2 | 5 | 0 | 0 | 09 | N3 | All Wards | Operating and Maintenance of Public Ablutions | EPWP | 567000 |  |  |  |  | 567000 | 0 | 0 | 0 | 0 |  | 0 | 535200 |  | 535200 | 31200 |  | 31200 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 566400 | 566400 |  | 600 | 600 | 99.89% | 99.89% | Ongoing multi-year project
Municipal Manager's Office |  |  | 205005 | [5 empty] | 1 | 77 | 0098 | P | 2 | 5 | 0 | 0 | 04 | V1 | All Wards | Vuna Awards | Vuna Awards | 1048758 |  |  |  |  | 1048758 | 0 | 0 | 0 | 0 |  | 0 | 26691.47 |  | 26691.47 | -26691.48 |  | -26691.48 | 532.03 |  | 532.03 | 0 |  | 0 | [12 empty] | 0 | 532.02 | 532.02 |  | 1048225.98 | 1048225.98 | 0.05073% | 0.05073% | Preparatory work underway, project to be completed on time before financial year end.
Municipal Manager's Office | Internal Audit |  | 215005 | 1 | 77 | 0002 | KPA5 | N/A | 1 | 77 | 0002 | P | 2 | 5 | 0 | 0 | 05 | A2 | All Wards | Combined Assurance Model | Own Funds | 3000000 |  |  |  |  | 3000000 | 0 | 0 | 0 | 219349 |  | 219349 | 73237.5 |  | 73237.5 | 403216.77 |  | 403216.77 | 31970.27 |  | 31970.27 | 0 |  | 0 | [12 empty] | 0 | 727773.54 | 727773.54 |  | 2272226.46 | 2272226.46 | 24.26% | 24.26% | The Internal Audit plan for the 2014/15 financial year has been approved. Projects are being implemented as per the approved Internal Audit Plan. Invoices will be received from the service provider and expenditure will be incurred.
Municipal Manager's Office | Legal and Admin |  | 220005 | 1 | 77 | 0002 | KPA5 | N/A | 1 | 77 | 0002 | P | 2 | 5 | 0 | 0 | 07 | A2 | All Wards | Development and Review of By-Laws | Own Funds | 99996 |  |  |  |  | 99996 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 99996 | 99996 | 0% | 0% | Project to commence upon appointment of Project Advisor
Municipal Manager's Office |  |  | 220005 | [5 empty] | 1 | 77 | 0002 | P | 2 | 5 | 0 | 0 | 10 | A2 | All Wards | Professional Project Advisor | Own Funds | 284175 |  |  |  |  | 284175 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 284175 | 284175 | 0% | 0% | Project advisor declined appointment, Legal liasing with HR for post to be re advertised
Municipal Manager's Office |  |  | 220005 | [5 empty] | 1 | 77 | 0002 | P | 2 | 5 | 0 | 0 | 11 | A2 | All Wards | Admin Assistant to Project Advisor | Own Funds | 115829 |  |  |  |  | 115829 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 115829 | 115829 | 0% | 0% | Admin Assist has been appointed and expenditure will start reflecting from next month.
Municipal Manager's Office |  |  | 220005 | [5 empty] | 1 | 77 | 0150 | P | 2 | 5 | 2 | 0 | 00 | A2 |  | Development and Review of By-Laws | Own Funds c/o | 0 |  |  |  | 500000 | 500000 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [13 empty] | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Project to commence upon appointment of Project Advisor
[20 empty] | TOTAL : MUNICIPAL MANAGER'S OFFICE |  | 42082528 |  |  |  | 6900281 | 48982809 | 1900290.37 | 5780.6 | 1906070.97 | 2034297.97 | 0 | 2034297.97 | 3263390.41 | 76524.28 | 3339914.69 | 2789602.84 | 24829.5 | 2814432.34 | 2704206 | 55458.89 | 2759664.89 | 2334460.16 | 20384 | 2354844.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102169.2 | 15026247.75 | 15209225.02 | 0 | 33956561.25 | 33773583.98 | 30.68% | 31.05%
DIRECTORATE OF FINANCIAL SERVICES | [19 empty] | DIRECTORATE OF FINANCIAL SERVICES
Financial Services |  |  | 305005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 0 | 0 | 04 | A2 | All Wards | Directorates Financial Management Capacity Project | Own Funds | 2100000 |  |  |  |  | 2100000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 2100000 | 2100000 | 0% | 0% | A decision has been taken to appoint two Finance Managers. Currently the job descriptions are being prepared.
Financial Services |  |  | 305005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 1 | 0 | 00 | A2 |  | Immovable Asset Management Project | Own Funds c/o | 0 |  |  |  | 32639 | 32639 | [5 empty] | 0 |  |  | 0 | 32639 |  | 32639 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 32639 | 32639 |  | 0 | 0 | 100% | 100% | The project is complete.
Financial Services |  |  | 305005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 2 | 0 | 00 | A2 |  | Directorates Financial Management Capacity Project c/o | Own Funds c/o | 0 |  |  |  | 344250 | 344250 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 344250 | 344250 | 0% | 0% | A decision has been taken to appoint two Finance Managers. Currently the job descriptions are being prepared.
Financial Services |  |  | 305005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 3 | 0 | 00 | A2 |  | Financial Support | Own Funds c/o | 0 |  |  |  | 750000 | 750000 | [5 empty] | 0 |  |  | 0 | 595177.08 |  | 595177.08 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 595177.08 | 595177.08 |  | 154822.92 | 154822.92 | 79.36% | 79.36% | The project is progressing well to update the Asset Register in respect of Work In Progress (WIP).
Financial Services |  |  | 315005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 4 | 0 | 00 | A2 |  | Accounting Reforms Project | Own Funds c/o | 0 |  |  |  | 373767 | 373767 | [5 empty] | 0 | 289144.5 |  | 289144.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 289144.5 | 289144.5 |  | 84622.5 | 84622.5 | 77.36% | 77.36% | The project is progressing well and payments are made monthly.
Financial Services | Budget Office |  | 315005 | 1 | 77 | 0060 | KPA4 | N/A | 1 | 77 | 0060 | P | 3 | 5 | 0 | 0 | 05 | F1 | All Wards | Training interns | FMG | 85210 |  |  |  |  | 85210 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 23684.21 |  | 23684.21 | 0 |  | 0 | [12 empty] | 0 | 23684.21 | 23684.21 |  | 61525.79 | 61525.79 | 27.8% | 27.8% | Further training has been identified through Institute of Municpal Finance Officers (IMFO) for finance management interns. The funds will be fully spent before the end of the financial year.
Financial Services |  |  | 315005 | [5 empty] | 1 | 77 | 0060 | P | 3 | 5 | 0 | 0 | 06 | F1 | All Wards | SCM Projects | FMG | 84790 |  |  |  |  | 84790 | 0 | 0 | 0 | 84503.91 |  | 84503.91 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 84503.91 | 84503.91 |  | 286.09 | 286.09 | 99.66% | 99.66% | Project is complete
Financial Services |  |  | 315005 | [5 empty] | 1 | 77 | 0060 | P | 3 | 5 | 0 | 0 | 07 | F1 | All Wards | Remunerations Interns | FMG | 1165210 |  |  |  |  | 1165210 | 114326 | 0 | 114326 | 102830.57 |  | 102830.57 | 89087.6 |  | 89087.6 | 87187.5 |  | 87187.5 | 92010.34 | 3315.79 | 95326.13 | 97291.98 |  | 97291.98 | [12 empty] | 0 | 582733.99 | 586049.78 |  | 582476.01 | 579160.22 | 50.01% | 50.3% | The payment of Intern's salaries is ongoing and done monthly. The project is progressing well.
Financial Services |  |  | 315005 | [5 empty] | 1 | 77 | 0060 | P | 3 | 5 | 0 | 0 | 40 | F1 | All Wards | Standard Chart Of Accounts(SCOA) | FMG | 164790 |  |  |  |  | 164790 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 164790 | 164790 | 0% | 0% | The process has commenced payments for SCOA activities to be processed.
Financial Services |  |  | 320005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 0 | 0 | 01 | A2 | All Wards | Standard Chart Of Accounts(SCOA) | Own Funds | 5250000 |  |  |  | 11500000 | 16750000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 79236.41 |  | 79236.41 | 0 |  | 0 | 66274.5 |  | 66274.5 | [12 empty] | 2208.9 | 145510.91 | 145510.91 |  | 16604489.09 | 16604489.09 | 0.8687% | 0.8687% | Procurement process at advanced stage.
Financial Services |  |  | 320005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 0 | 0 | 02 | A2 | All Wards | Financial Technical Support | Own Funds | 1500000 |  |  |  |  | 1500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 1500000 | 1500000 | 0% | 0% | The 2 Programme Managers for Asset & Risk are still to be appointed, awaiting benchmarking and reports have already been submitted to H.R.
Financial Services |  |  | 320005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 0 | 0 | 03 | A2 | All Wards | Immovable Assets Project | Own Funds | 15000000 |  |  |  | -7000000 | 8000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 4553461.92 |  | 4553461.92 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 4553461.92 | 4553461.92 |  | 3446538.08 | 3446538.08 | 56.92% | 56.92% | The project is progressing well.
Financial Services |  |  | 320005 | [5 empty] | 1 | 77 | 0015 | P | 3 | 5 | 0 | 0 | 09 | D2 | All Wards | Immovable Assets Project - Counterfunding | LGTH | 1336512 |  |  |  |  | 1336512 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 1336512 | 1336512 | 0% | 0% | A service provider was appointed to assist with the preparation of PPE disclosure in the AFS. Awaiting invoice.
Financial Services |  |  | 320005 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 0 | 0 | 11 | A2 |  | Asset Componetisation | Own Funds c/o | 0 |  |  |  | 7000000 | 7000000 |  |  |  | 150144 |  | 150144 | -150144 |  | -150144 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 7000000 | 7000000 | 0% | 0% | A service provider was appointed to assist with the preparation of PPE disclosure in the AFS. Awaiting invoice.
Financial Services |  |  | 320010 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 6 | 0 | 00 | A2 |  | SCM Turn Around Projects | Own Funds c/o | 0 |  |  |  | 980229 | 980229 | [5 empty] | 0 | 113461.57 |  | 113461.57 | 94236.55 |  | 94236.55 | 0 |  | 0 | 58245.42 |  | 58245.42 | [12 empty] | 0 | 265943.54 | 265943.54 |  | 714285.46 | 714285.46 | 27.13% | 27.13% | Project is progressing well, payments made continously on a monthly basis until the end of financial year
Financial Services |  |  | 320010 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 7 | 0 | 00 | A2 |  | SCM Capacity Project | Own Funds c/o | 0 |  |  |  | 375123 | 375123 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 108129.86 |  | 108129.86 | 36692 |  | 36692 | [12 empty] | 0 | 144821.86 | 144821.86 |  | 230301.14 | 230301.14 | 38.61% | 38.61% | Project is progressing well, payments made continously on a monthly basis until the end of financial year
Financial Services |  |  | 330010 | [5 empty] | 1 | 77 | 0002 | P | 3 | 5 | 8 | 0 | 00 | A2 |  | Supplementary Valuations | Own Funds c/o | 0 |  |  |  | 106235 | 106235 |  |  |  | 2598.76 |  | 2598.76 | -2598.76 |  | -2598.76 |  |  | 0 | 161022.74 |  | 161022.74 | -80511.37 |  | -80511.37 | [12 empty] | 0 | 80511.37 | 80511.37 |  | 25723.63 | 25723.63 | 75.79% | 75.79% | The project is progressing well, the implementation date of second supplementary valuation is 1 June 2015, payments are made continuously until the end of the financial year.
Financial Services | Debtors Management Office |  | 330015 | 1 | 77 | 0002 | KPA4 | N/A | 1 | 77 | 0002 | P | 3 | 5 | 0 | 0 | 08 | A2 | All Wards | Customer Service Level Agreements | Own Funds | 500000 |  |  |  |  | 500000 | 29225.5 | 0 | 29225.5 | -29225.5 |  | -29225.5 | 0 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Project is in progress and the expenditure will incur as the year progresses. However,progress is slow due to resignations and slow productivity by fieldworkers collecting information from BCMM households.
Financial Services | Debtors Management Office |  | 330015 | 1 | 77 | 0002 | KPA4 | N/A | 1 | 77 | 0002 | P | 3 | 5 | 9 | 0 | 00 | A2 |  | Billing Data Cleanup | Own Funds c/o | 0 |  |  |  | 1312847 | 1312847 |  |  |  | 23001.49 |  | 23001.49 | -23001.49 |  | -23001.49 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 1312847 | 1312847 | 0% | 0% | Project is in progress and the expenditure will incur as the year progresses. However,progress is slow due to resignations and slow productivity by fieldworkers collecting information from BCMM households.
[20 empty] | TOTAL : FINANCIAL SERVICES |  | 27186512 |  |  |  | 15775090 | 42961602 | 143551.5 | 0 | 143551.5 | 333853.23 | 0 | 333853.23 | 315949.42 | 0 | 315949.42 | 5441938.46 | 0 | 5441938.46 | 384847.15 | 3315.79 | 388162.94 | 177992.53 | 0 | 177992.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2208.9 | 6798132.29 | 6801448.08 | 0 | 36163469.71 | 36160153.92 | 15.82% | 15.83%
DIRECTORATE OF CORPORATE SERVICES | [19 empty] | DIRECTORATE OF CORPORATE SERVICES
Corporate Services |  |  | 415025 | [5 empty] | 1 | 77 | 0002 | P | 4 | 5 | 7 | 0 | 00 | A2 | All Wards | IT Fibre Installations for SCM, IDZ and Community Services in 2014/2015 (KWT and Bhisho in 2015/2016 and Mdantsane, Reeston, East London Traffic and Mechanical Workshop in 2016/2017) | Own Funds | 4000000 |  |  |  | -500000 | 3500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 3500000 | 3500000 | 0% | 0% | Contract 184 is underway, expenditure is expected to be incurrred between January and February 2015.
Corporate Services |  |  | 415025 | [5 empty] | 1 | 77 | 0002 | P | 4 | 5 | 6 | 0 | 00 | A2 | All Wards | ICT Policies, Framework, Processes and Procedures - Implementation | Own Funds | 2000000 |  |  |  |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Contract 181 is underway, expenditure is expected to be incurrred between January and February 2015.
Corporate Services |  |  | 415025 | [5 empty] | 1 | 77 | 0002 | [7 empty] | All Wards | Share Point (Intranet) | Own Funds | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Corporate Services |  |  | 415025 | [5 empty] | 1 | 77 | 0002 | P | 4 | 5 | 5 | 0 | 00 | A2 | All Wards | Website Phase 2 | Own Funds | 400000 |  |  |  |  | 400000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 400000 | 400000 | 0% | 0% | Contract 182 is underway, expenditure is expected to be incurrred between March and April 2015.
Corporate Services |  |  | 415025 | [5 empty] | 1 | 77 | 0002 | P | 4 | 5 | 4 | 0 | 00 | A2 | All Wards | Computer Equipment - BCMM Leases | Own Funds | 2000000 |  |  |  |  | 2000000 | 0 | 0 | 0 |  |  | 0 | 2871.57 |  | 2871.57 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 2871.57 | 2871.57 |  | 1997128.43 | 1997128.43 | 0.1436% | 0.1436% | Contract 186 is underway, expenditure is expected to be incurrred between February and March 2015.
Corporate Services | H.R. Administration |  | 420005 | 1 | 77 | 0002 | KPA1 | N/A | 1 | 77 | 0002 | P | 4 | 5 | 3 | 0 | 00 | A2 | All Wards | Roll out of employee Performance Management System | Own Funds | 200000 |  |  |  |  | 200000 | 0 | 0 | 0 |  |  | 0 | 58696.6 |  | 58696.6 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 58696.6 | 58696.6 |  | 141303.4 | 141303.4 | 29.35% | 29.35% | Expenditure could not take place in the second quarter on conducting the EPMDS refresher workshop for Task Grades 15 upwards in preparation of Performance Assessments due to the unresponsiveness of line management in terms of conducting 2014/15 Performance Planning. Focus was thus given to getting them to first do performance plans. The third quarter has now been earmarked for the Refresher workshop and expenditure will take place then.
Corporate Services | H.R. Administration |  | 420005 | [5 empty] | 1 | 77 | 0015 | P | 4 | 5 | 1 | 0 | 00 | D2 | All Wards | Roll out of employee Performance Management System - Counterfunding | LGTH | 113769 |  |  |  |  | 113769 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 113769 | 113769 | 0% | 0% | Procurement process underway
Corporate Services | H.R. Administration |  | 420005 | 1 | 77 | 0098 | KPA1 | N/A | 1 | 77 | 0098 | P | 4 | 5 | 2 | 0 | 00 | 11 | All Wards | Infrastructure Skills Development | ISDG | 5400000 |  |  |  |  | 5400000 | 386216.39 | 3244.07 | 389460.46 | 370435.8 |  | 370435.8 | 545475.18 | 11984.65 | 557459.83 | 933293.69 | 88697.66 | 1021991.35 | 528857.52 |  | 528857.52 | 1080492.47 | 108562.74 | 1189055.21 | [12 empty] | 0 | 3844771.05 | 4057260.17 |  | 1555228.95 | 1342739.83 | 71.2% | 75.13% | The funding is used to pay salaries of engineering interns, and will be utilised by year end.
Corporate Services |  |  | 420005 | [5 empty] | 1 | 77 | 0002 | P | 4 | 5 | 0 | 0 | 11 | A2 |  | Local Labour Forum Project - Grievances | Own Funds | 0 |  |  |  | 500000 | 500000 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | This project is an extention of the project below (Employee Relations Improvement Programme), the funds are going to be utilised once the budget for the project below is depleted.
Corporate Services |  |  | 420005 | [5 empty] | 1 | 77 | 0002 | P | 4 | 5 | 0 | 0 | 10 | A2 |  | Employee Relations Improvement Programme | Own Funds c/o | 0 |  |  |  | 251169 | 251169 | [5 empty] | 0 | 102167.94 |  | 102167.94 |  |  | 0 | 0 |  | 0 | 51083.97 |  | 51083.97 | [12 empty] | 0 | 153251.91 | 153251.91 |  | 97917.09 | 97917.09 | 61.02% | 61.02% | Project is progressing well
[20 empty] | TOTAL : CORPORATE SERVICES |  | 14113769 |  |  |  | 251169 | 14364938 | 386216.39 | 3244.07 | 389460.46 | 370435.8 | 0 | 370435.8 | 709211.29 | 11984.65 | 721195.94 | 933293.69 | 88697.66 | 1021991.35 | 528857.52 | 0 | 528857.52 | 1131576.44 | 108562.74 | 1240139.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4059591.13 | 4272080.25 | 0 | 10305346.87 | 10092857.75 | 28.26% | 29.74%
DIRECTORATE OF ENGINEERING SERVICES | [19 empty] | DIRECTORATE OF ENGINEERING SERVICES
Engineering Services |  |  | 530020 | [5 empty] | 1 | 77 | 0002 | [7 empty] | All Wards | BCMM Fleet Management System | Own Funds | 2000000 |  |  |  |  | 2000000 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | 793800 | 0 | 793800 | [12 empty] | 0 | 793800 | 793800 |  | 1206200 | 1206200 | 39.69% | 39.69% | The contract has been awarded, invoices are being processed
[20 empty] | TOTAL : ENGINEERING SERVICES |  | 2000000 |  |  |  | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 793800 | 0 | 793800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 793800 | 793800 | 0 | 1206200 | 1206200 | 39.69% | 39.69%
DIRECTORATE OF DEVELOPMENT PLANNING | [19 empty] | DIRECTORATE OF DEVELOPMENT PLANNING
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 22 | A2 |  | NTCE | Own Funds | 500000 |  |  |  |  | 500000 | 0 | 0 | 0 |  |  | 0 | 500000 |  | 500000 | 0 |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 500000 | 500000 | 0 | 0 | 0 | 100% | 100% | Budget has been completed.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 23 | A2 |  | SMME Support | Own Funds | 100000 |  |  |  | 200000 | 300000 | 0 | 0 | 0 | 45103.2 |  | 45103.2 | 62525.52 |  | 62525.52 | 28298.6 |  | 28298.6 | 5100 |  | 5100 | 2600 |  | 2600 | [12 empty] | 0 | 143627.32 | 143627.32 | 0 | 156372.68 | 156372.68 | 47.88% | 47.88% | Budget is almost exhausted as there are a number of workshops that have been held for SMME and invoices still to be processed
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 24 | A2 |  | Tourism SMME Support | Own Funds | 100000 |  |  |  | 200000 | 300000 | 0 | 0 | 0 |  |  | 0 | 69060 |  | 69060 | 25400 |  | 25400 | 2770 |  | 2770 | 0 |  | 0 | [12 empty] | 0 | 97230 | 97230 | 0 | 202770 | 202770 | 32.41% | 32.41% | The project is progressing well. More invoices will be submitted for payment.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 25 | A2 |  | Geo. Assessment impact study | Own Funds | 60000 |  |  |  |  | 60000 | 0 | 0 | 0 |  |  | 0 | 402 |  | 402 | 700 |  | 700 | 9450 |  | 9450 | 0 |  | 0 | [12 empty] | 46220 | 10552 | 10552 | 0 | 49448 | 49448 | 17.59% | 17.59% | The service provider to conduct the study was appointed in December. Implementation will commence in January 2015.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 26 | A2 |  | Trade & Investment Strategy and Policy | Own Funds | 1000000 |  |  |  |  | 850000 | 0 | 0 | 0 | 188800 |  | 188800 | 297041.22 |  | 297041.22 | 205635.29 |  | 205635.29 | 64176.5 |  | 64176.5 | 633.3 |  | 633.3 | [12 empty] | 35147.79 | 756286.31 | 756286.31 | 0 | 93713.69 | 93713.69 | 88.97% | 88.97% | The project is progressing well.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 27 | A2 |  | Trade & Investment Marketing and Promotions | Own Funds | 1000000 |  |  |  |  | 1450000 | 0 | 0 | 0 | 243859.65 |  | 243859.65 | 194210.52 |  | 194210.52 | 34357.5 |  | 34357.5 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 472427.67 | 472427.67 | 0 | 977572.33 | 977572.33 | 32.58% | 32.58% | Two outstanding trade missions to be undertaken in the third and fourth quarters, respectively.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 28 | A2 |  | Trade & Investment Export Support Programme | Own Funds | 240000 |  |  |  |  | 240000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 207888.71 |  | 207888.71 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 207888.71 | 207888.71 | 0 | 32111.29 | 32111.29 | 86.62% | 86.62% | The project has been completed.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 34 | A2 |  | Buyelekhaya Pan African Festival | Own Funds |  |  |  |  | 3200000 | 2900000 | [8 empty] | 0 | 2631578.95 |  | 2631578.95 | 197411.14 |  | 197411.14 | 59779.6 |  | 59779.6 | [12 empty] | 0 | 2888769.69 | 2888769.69 | 0 | 11230.31 | 11230.31 | 99.61% | 99.61% | The project has been completed and funds have been exhausted.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 35 | A2 |  | Summer Season 2014 | Own Funds |  |  |  |  | 2400000 | 2400000 | [8 empty] | 0 | 0 |  | 0 | 335784.29 |  | 335784.29 | 1745697.97 |  | 1745697.97 | [12 empty] | 177773.84 | 2081482.26 | 2081482.26 | 0 | 318517.74 | 318517.74 | 86.73% | 86.73% | The project is progressing well. The department will use services of the annual contractors.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 36 | A2 |  | Rental | Own Funds |  |  |  |  | 1000000 | 1000000 | [8 empty] | 0 | 0 |  | 0 | 111405.54 |  | 111405.54 | 0 |  | 0 | [12 empty] | 0 | 111405.54 | 111405.54 | 0 | 888594.46 | 888594.46 | 11.14% | 11.14% | To be utilised once tender for office space has been finalised.
Economic Development | [19 empty] | Local Economic Development - LED | DEDEAT | [17 empty] | 0 |  |  | 0 |  |  | 0 | [14 empty] | 0
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0013 | P | 6 | 5 | 0 | 0 | 16 | D9 |  | Packshed | DEDEAT | 239408 |  |  |  |  | 239408 | 0 | 0 | 0 |  |  | 0 | 8800.7 |  | 8800.7 | 103535.82 |  | 103535.82 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 112336.52 | 112336.52 | 0 | 127071.48 | 127071.48 | 46.92% | 46.92% | The expenditure pattern is flowing normally as it is almost 50% by end of mid-term
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0013 | P | 6 | 5 | 0 | 0 | 17 | D9 |  | Agricultural Show | DEDEAT | 200000 |  |  |  |  | 200000 | 0 | 0 | 0 |  |  | 0 | 56499 |  | 56499 | 88142 |  | 88142 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 144641 | 144641 | 0 | 55359 | 55359 | 72.32% | 72.32% | The project has been completed, the only delays were due to the processing of the last invoice which has kept the expenditure below 100%. The outstanding payment still to be processed.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0013 | P | 6 | 5 | 0 | 0 | 18 | D9 |  | Emerging Farmers & Co-operatives | DEDEAT | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 |  |  | 0 | 13850.68 |  | 13850.68 | 53700 |  | 53700 | 6200 |  | 6200 | 187347 |  | 187347 | [12 empty] | 102708 | 261097.68 | 261097.68 | 0 | 738902.32 | 738902.32 | 26.11% | 26.11% | The ploughing project for BCMM farmers is at BAC stage, awaiting for award of tender.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0013 | P | 6 | 5 | 0 | 0 | 19 | D9 |  | Centre operations | DEDEAT | 300000 |  |  |  |  | 300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 5670 |  | 5670 | [12 empty] | 0 | 5670 | 5670 | 0 | 294330 | 294330 | 1.89% | 1.89% | Invoice submitted for SMME workshop that was held in Mdantsane. Invoices also submitted for SMME's that participated in the Home Expo 2014, as well as for the Cooperatives Amendments Workshop.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0013 | P | 6 | 5 | 0 | 0 | 20 | D9 |  | Trainings: Plumbing, Governance, Contractor development | DEDEAT | 1400000 |  |  |  |  | 1400000 | 0 | 0 | 0 | 4481 |  | 4481 | 27500 |  | 27500 | 599436.49 |  | 599436.49 | 116074.09 |  | 116074.09 | 159927.89 |  | 159927.89 | [12 empty] | 122192.98 | 907419.47 | 907419.47 | 0 | 492580.53 | 492580.53 | 64.82% | 64.82% | An outstanding invoice for the co-operative governance which was held on the first week of December is still to be processed.
Economic Development |  |  | 635005 | [5 empty] | 1 | 77 | 0013 | P | 6 | 5 | 0 | 0 | 21 | D9 |  | Franchise Expo | DEDEAT | 300000 |  |  |  |  | 300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 52572.24 |  | 52572.24 |  |  | 0 | 167605.26 |  | 167605.26 | [12 empty] | 0 | 220177.5 | 220177.5 | 0 | 79822.5 | 79822.5 | 73.39% | 73.39% | Project progresssing well
Development Planning |  |  | 615070 | [5 empty] | 1 | 76 | 0185 | P | 6 | 5 | 2 | 0 | 00 | H2 |  | Cambridge 1 & 2 (Kei Road Dawn) | HSDG c/o | 0 |  |  |  | 31000 | 31000 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 26956.14 |  | 26956.14 | [12 empty] | 0 | 26956.14 | 26956.14 | 0 | 4043.86 | 4043.86 | 86.96% | 86.96% | The Township Establishment was approved by Council on 29 October 2014 and now the project has been completed. Final invoice has been submitted for payment.
Development Planning |  |  | 615070 | [5 empty] | 1 | 76 | 0185 | P | 6 | 5 | 3 | 0 | 00 | H2 |  | N2 Road Reserve P2 | HSDG c/o | 0 |  |  |  | 147300 | 147300 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 | 129148.81 |  | 129148.81 | 0 |  | 0 | [12 empty] | 0 | 129148.81 | 129148.81 | 0 | 18151.19 | 18151.19 | 87.68% | 87.68% | The Township Establishment was approved by Council on 29 October 2014 and now the project has been completed. Final invoice has been submitted for payment.
Development Planning |  |  | 615070 | [5 empty] | 1 | 76 | 0185 | P | 6 | 5 | 4 | 0 | 00 | H2 |  | Ford Msimango 1 (LU Housing Nomp School) - P2 | HSDG c/o | 0 |  |  |  | 36053 | 36053 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 | 31625.44 |  | 31625.44 | 0 |  | 0 | [12 empty] | 0 | 31625.44 | 31625.44 | 0 | 4427.56 | 4427.56 | 87.72% | 87.72% | The Township Establishment was approved by Council on 29 October 2014 and now the project has been completed. Final invoice has been submitted for payment.
Development Planning |  |  | 615070 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 30 | A2 |  | Changes to BCM Zoning Scheme | Own Funds c/o | 0 |  |  |  | 35382 | 35382 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 | 0 | 35382 | 35382 | 0% | 0% | A draft Land Use Enforcement By-Law has been finalised and has been submitted to the Legal Department for comments
Development Planning |  |  | 615070 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 31 | A2 |  | Township Establishment for Mzamomhle Informal Settlement Study Phase 3 | Own Funds c/o | 0 |  |  |  | 240235 | 240235 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 | 0 | 240235 | 240235 | 0% | 0% | Feasibility study has been completed and draft layout has been submitted for comments. Consultation has taken place with Enviromental Affairs in regard to environmental issues and final response is still awaited. Site meetings were held with Wetland specilaist and awaiting the report.
Development Planning |  |  | 615070 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 32 | A2 |  | Land Identification for Partial or Full Relocation of Informal Settlement in BCMM | Own Funds c/o | 0 |  |  |  | 115707 | 115707 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 70000 |  | 70000 | [12 empty] | 0 | 70000 | 70000 | 0 | 45707 | 45707 | 60.5% | 60.5% | Feasibility study has started, which includes the desktop study and then the on-site verification which is currently underway. The draft report is being processed.
Development Planning |  |  | 615070 | [5 empty] | 1 | 77 | 0020 | P | 6 | 5 | 0 | 0 | 01 | D3 |  | Planning and Map Preparation | DLA | 80654 |  |  |  |  | 80654 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 18540.22 |  | 18540.22 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 18540.22 | 18540.22 | 0 | 62113.78 | 62113.78 | 22.99% | 22.99% | Waiting for final approval by the MEC of Local Government and Traditional Affairs for the Establishment of Township for Needs Camp and Potsdam Unit V before final payment can be done.
Development Planning |  |  | 615070 | [5 empty] | 1 | 77 | 0098 | P | 6 | 5 | 1 | 0 | 00 | I1 |  | East Bank Restitution Township Establishment | RLCC c/o | 0 |  |  |  | 71782 | 71782 | [5 empty] | 0 |  |  | 0 | 62966.03 |  | 62966.03 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 62966.03 | 62966.03 | 0 | 8815.97 | 8815.97 | 87.72% | 87.72% | Final layout and Motivation report was completed and submitted. Application is currently being circulated for comments.
Development Planning | Land Admin |  | 615080 | 1 | 76 | 0185 | KPA2 | 13 | 1 | 76 | 0185 | P | S | C | 1 | 0 | 11 | H2 |  | Reeston Phase 3: Stage 2 - P4 (Transfers) | HSDG | 480000 |  |  |  |  | 480000 | 0 | 0 | 0 | 117102.81 |  | 117102.81 | 76187.37 |  | 76187.37 | 0 |  | 0 | 5643.51 |  | 5643.51 | 0 |  | 0 | [12 empty] | 0 | 198933.69 | 198933.69 | 0 | 281066.31 | 281066.31 | 41.44% | 41.44% | No transfers registered for the month of December 2014. The anticipated registration date is early January 2015 as the Deeds Office closes in December 2014.
Development Planning | Land Admin |  | 615080 | 1 | 76 | 0185 | KPA2 | 45 | 1 | 76 | 0185 | P | S | C | 1 | 9 | 01 | H2 |  | Ilitha South - 439 Units P4 (Transfers) | HSDG | 40400 |  |  |  |  | 40400 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 | 0 | 40400 | 40400 | 0% | 0% | No Deeds of Sale received for Ilitha Project for onward transmission to Conveyancer.
Development Planning |  |  | 615080 | 1 | 77 | 0003 | KPA3 | N/A | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 06 | A2 |  | Land transactions upgrading of former R293 & CPA Areas | Own Funds | 500000 |  |  |  |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 2910 |  | 2910 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 2910 | 2910 | 0 | 497090 | 497090 | 0.582% | 0.582% | The Department met the Conveyancer to discuss process to be followed to expediate Mdantsane Unit 2 upgrading . The forms to be completed by property owners affected by double registration to consent to the cancellation of Deed of Grant, and returned to the Converyancer for onwards transfmission to the MEC for cooperative governance for approval.
Development Planning |  |  | 620005 | [5 empty] | 1 | 77 | 0002 | P | 6 | 5 | 0 | 0 | 33 | A2 |  | Integrated Transport Plan Review | Own Funds c/o | 0 |  |  |  | 505923 | 505923 | [5 empty] | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 | 0 | 505923 | 505923 | 0% | 0% | Procurement process underway
[20 empty] | TOTAL : DEVELOPMENT PLANNING |  | 1101054 |  |  |  | 1183382 | 15723844 | 0 | 0 | 0 | 599346.66 | 0 | 599346.66 | 1306077.01 | 0 | 1306077.01 | 4115661.85 | 0 | 4115661.85 | 1014789.32 | 0 | 1014789.32 | 2426217.16 | 0 | 2426217.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484042.61 | 9462092 | 9462092 | 0 | 6261752 | 6261752 | 60.18% | 60.18%
HUMAN SETTLEMENTS | [19 empty] | DIRECTORATE OF HUMAN SETTLEMENTS
Human Settlements | DVRI |  | 250005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 27 | H1 |  |  | DVRI Planning Budget (FROM 8.7MIL) | Dept of LGTH | 900000 |  |  |  |  | 900000 | 0 | 0 | 0 | 402905.5 |  | 402905.5 | 198657.4 |  | 198657.4 | -567673 |  | -567673 |  |  | 0 | -2691.2 |  | -2691.2 | [12 empty] | 18414.53 | 31198.7 | 31198.7 |  | 868801.3 | 868801.3 | 3.467% | 3.467% | Awaiting for the completion of business plan,after which these funds will be allocated to projects.
Human Settlements | DVRI |  | 250005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 38 | H1 |  |  | DVRI Planning Budget c/o | Dept of LGTH c/o | 0 |  |  |  | 1584293 | 1584293 | [5 empty] | 0 |  |  | 0 | 2710 |  | 2710 |  |  | 0 | 183056.21 |  | 183056.21 | [12 empty] | 0 | 185766.21 | 185766.21 |  | 1398526.79 | 1398526.79 | 11.73% | 11.73% | Awaiting for the completion of business plan,after which these funds will be allocated to projects.
Human Settlements | DVRI |  | 250005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 39 | H1 |  |  | DVRI Business Plan | Dept of LGTH c/o | 0 |  |  |  | 96379 | 96379 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 96379 | 96379 | 0% | 0% | A registered professinal planner has been appointed to complete the Business Plan. They are currently busy with the draft Implemantation Plan and the final will be completed by the 30th of January 2015.
Human Settlements | DVRI |  | 250005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 35 | H1 |  |  | DVRI News | Dept of LGTH | 500000 |  |  |  |  | 500000 |  |  | 0 |  |  | 0 |  |  | 0 | 251414.45 |  | 251414.45 | 0 |  | 0 | 73096.59 |  | 73096.59 | [12 empty] | 20800 | 324511.04 | 324511.04 |  | 175488.96 | 175488.96 | 64.9% | 64.9% | Project is going well
Human Settlements | DVRI |  | 250005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 36 | H1 |  |  | Funding Mobilisation Strategy | Dept of LGTH | 200000 |  |  |  |  | 200000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 200000 | 200000 | 0% | 0% | Procurement process underway
Human Settlements | DVRI |  | 250005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 37 | H1 |  |  | Quality of Life | Dept of LGTH | 1400000 |  |  |  |  | 1400000 |  |  | 0 |  |  | 0 |  |  | 0 | 613052.3 |  | 613052.3 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 613052.3 | 613052.3 |  | 786947.7 | 786947.7 | 43.79% | 43.79% | The Consultants are currently busy completing the first draft report, this report will be ready by the 30 January 2015.
Human Settlements | DVRI |  | 250005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 50 | H1 |  |  | DVRI ICT Centre | Dept of LGTH | 0 |  |  |  | 110000 | 110000 | [9 empty] | 17422.43 |  | 17422.43 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 17422.43 | 17422.43 |  | 92577.57 | 92577.57 | 15.84% |  | Procurement process underway
Human Settlements | Housing Projects |  | 250005 | [5 empty] | 1 | 77 | 0020 | P | P | P | 50 | 30 | D3 |  |  | Reeston Phase 2 | DLA | 696589 |  |  |  |  | 696589 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 696589 | 696589 | 0% | 0% | The project is at planning stage and the planning is done by the department
Human Settlements | MURP |  | 250005 |  |  | 0355 | KPA2 | All | 1 | 77 | 0058 | P | P | P | 50 | 29 | E4 |  |  | MURP Sustainability Plan | European Commission | 500000 |  |  |  |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | The study has not yet commenced awaiting the completion of the MURP Impact Assessment Study.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 13 | 1 | 76 | 0185 | P | T | S | 50 | 01 | H3 |  |  | Reeston Phase 3: Stage 2 - P5 | HSDG | 10000000 |  |  |  |  | 10000000 | 0 | 0 | 0 | 121000 |  | 121000 |  |  | 0 |  |  | 0 |  |  | 0 | 5791255.91 |  | 5791255.91 | [12 empty] | 0 | 5912255.91 | 5912255.91 |  | 4087744.09 | 4087744.09 | 59.12% | 59.12% | The Implementing Agent has been recently appointed to construct 550 top structures, anticipated to commence Mid January 2015 as per their programme.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 13 | 1 | 76 | 0185 | P | T | S | 50 | 40 | H3 |  |  | Reeston Phase 3: Stage 2 - P5 c/o | HSDG c/o | 0 |  |  |  | 2000000 | 2000000 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | The Implementing Agent has been recently appointed to construct 550 top structures, anticipated to commence Mid January 2015 as per their programme.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 13 | 1 | 76 | 0185 | P | E | D | 50 | 02 | H3 |  |  | Beneficiary Registration DVRI Projects (Reeston, Cambridge, DVRI Pilot, Braelyn ext 10, C Section and Triangular Site, D Hostel) | HSDG | 500000 |  |  |  |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | All displaced beneficiaries are being considered for registration and registrations are guided by the Implementing Agent. The challenge is to get people to register.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 13 | 1 | 76 | 0185 | P | E | D | 50 | 41 | H3 |  |  | Beneficiary Registration DVRI Projects (Reeston, Cambridge, DVRI Pilot, Braelyn ext 10, C Section and Triangular Site, D Hostel) c/o | HSDG c/o | 0 |  |  |  | 400000 | 400000 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 400000 | 400000 | 0% | 0% | All displaced beneficiaries are being considered for registration and registrations are guided by the Implementing Agent. The challenge is to get people to register.
Human Settlements | Housing Projects | Housing | 255005 | [5 empty] | 1 | 76 | 0645 | P | E | D | 50 | 22 | H2 |  |  | Beneficiary Registration (Potsdam Unit V, Cluster 3, Orange Groove, Mdantsane Zone CC, Cluster 1, Cluster 2, Peelton Cluster, Hanover, Skobeni, Sunny South, Ilitha North, Dimbaza 110, Dimbaza Phase 3,Potsdam Village; North Kanana, Ikhwezi Block 1 & 2, Amalinda Co-op, Eradication of Wooden Houses to Formal Houses | USDG | 1350000 |  |  |  |  | 1350000 | 0 | 0 | 0 | 126815.49 |  | 126815.49 | 253447 |  | 253447 | 0 | 18270 | 18270 | 90000 | 12600 | 102600 | 496068.94 | 20393.53 | 516462.47 | [12 empty] | 0 | 966331.43 | 1017594.96 |  | 383668.57 | 332405.04 | 71.58% | 75.38% | In most of these projects registration is ongoing and awaiting for more approvals from Province. Some projects such as Dimbaza Wooden, Dimbaza 110 and Ilitha Wooden houses are consolidation projects where some of the title holders cannot be located. Registration in Potsdam Unit V, Hanover, Skobeni, Ilitha North Kanana has not started yet.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 45 | 1 | 76 | 0185 | P | E | D | 50 | 03 | H3 |  |  | Ilitha Eradication of Wooden Houses to Formal Houses | HSDG | 18180294 |  |  |  | -14700000 | 3480294 | 0 | 0 | 0 | 421886.81 |  | 421886.81 | 276153.95 |  | 276153.95 | 825487.94 |  | 825487.94 | 411768.89 |  | 411768.89 | 1062061.82 |  | 1062061.82 | [12 empty] | 0 | 2997359.41 | 2997359.41 |  | 482934.59 | 482934.59 | 86.12% | 86.12% | Contractor is on site but behind the schedule, construction period is extended to May 2015
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 45 | 1 | 76 | 0185 | P | E | D | 50 | 42 | H3 |  |  | Ilitha Eradication of Wooden Houses to Formal Houses | HSDG c/o | 0 |  |  |  | 4817139 | 4817139 | [5 empty] | 0 | 1483256.62 |  | 1483256.62 | -1483256.62 |  | -1483256.62 |  |  | 0 | 401968 |  | 401968 | [12 empty] | 0 | 401968 | 401968 |  | 4415171 | 4415171 | 8.345% | 8.345% | Contractor is on site but behind the schedule, construction period is extended to May 2015
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 43 | 1 | 76 | 0185 | P | T | S | 50 | 04 | H3 |  |  | Tyutyu Phase 2 - P 5 (Top Structure) | HSDG | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Contractor is on site but behind the schedule, construction period will be extended due to delays in a project
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 43 | 1 | 76 | 0185 | P | T | S | 50 | 43 | H3 |  |  | Tyutyu Phase 2 - P 5 (Top Structure) c/o | HSDG c/o | 0 |  |  |  | 6205903 | 6205903 | [5 empty] | 0 | 773029.18 |  | 773029.18 |  |  | 0 |  |  | 0 | -773029 |  | -773029 | [12 empty] | 0 | 0.18 | 0.18 |  | 6205902.82 | 6205902.82 | 2.9e-06% | 2.9e-06% | Contractor is on site but behind the schedule, construction period will be extended due to delays in a project
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 17,24,25,26,31,33,35,36,37,38,39,40,43,44,45 | 1 | 76 | 0185 | P | E | D | 50 | 05 | H3 |  |  | Reconstruction of Storm Damaged Houses | HSDG | 10000000 |  |  |  |  | 10000000 | 0 | 0 | 0 | 188610 |  | 188610 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 188610 | 188610 |  | 9811390 | 9811390 | 1.886% | 1.886% | Contractor for the balance of 260 units is on site, to date 35 slabs casted and the project is expected to be completed in March 2015.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 17,24,25,26,31,33,35,36,37,38,39,40,43,44,45 | 1 | 76 | 0185 | P | E | D | 50 | 45 | H3 |  |  | Reconstruction of Storm Damaged Houses | HSDG c/o | 0 |  |  |  | 3906828 | 3906828 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 520498.98 |  | 520498.98 | 995429.45 |  | 995429.45 | [12 empty] | 0 | 1515928.43 | 1515928.43 |  | 2390899.57 | 2390899.57 | 38.8% | 38.8% | Contractor for the balance of 260 units is on site, to date 35 slabs casted and the project is expected to be completed in March 2015.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 31 | 1 | 76 | 0185 | P | T | S | 50 | 06 | H3 |  |  | Sunny South -P5 | HSDG | 11000000 |  |  |  |  | 11000000 | 0 | 0 | 0 | 6362965.12 |  | 6362965.12 | 1795552.03 |  | 1795552.03 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 8158517.15 | 8158517.15 |  | 2841482.85 | 2841482.85 | 74.17% | 74.17% | Contractor is on site progressing with implementation, to date 112 units completed. Anticipated completion date is March 2015
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 31 | 1 | 76 | 0185 | P | T | S | 50 | 46 | H3 |  |  | Sunny South -P5 c/o | HSDG c/o | 0 |  |  |  | 10681830 | 10681830 | [5 empty] | 0 | 359973.96 |  | 359973.96 | 2640014.08 |  | 2640014.08 | 691305.18 |  | 691305.18 | 4547037.87 |  | 4547037.87 | [12 empty] | 0 | 8238331.09 | 8238331.09 |  | 2443498.91 | 2443498.91 | 77.12% | 77.12% | Contractor is on site progressing with implementation, to date 112 units completed. Anticipated completion date is March 2015
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 23 | 1 | 76 | 0185 | P | T | S | 50 | 07 | H3 |  |  | Potsdam Village Phase 1 & 2 - P5 | HSDG | 2300000 |  |  |  |  | 2300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 2300000 | 2300000 | 0% | 0% | Consultant has submitted the tender document for construction of top structures. Procurement will commence mid January 2015.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 48,12,21,11,17,11, 20 | 1 | 76 | 0185 | P | T | S | 50 | 08 | H3 |  |  | Cluster 1 (Masibambane; Masibulele; Velwano; Ilinge and Dacawa) P5 | HSDG | 10000000 |  |  |  | 5950000 | 15950000 | 0 | 0 | 0 | 6240458.82 |  | 6240458.82 |  |  | 0 | 5891763.9 |  | 5891763.9 | 3817777 |  | 3817777 | 0 |  | 0 | [12 empty] | 0 | 15949999.72 | 15949999.72 |  | 0.28 | 0.28 | 100% | 100% | Contractor is on site, progressing with installation of internal services and construction of top structures. | #VALUE!
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 48,12,21,11,17,11, 20 | 1 | 76 | 0185 | P | T | S | 50 | 47 | H3 |  |  | Cluster 1 (Masibambane; Masibulele; Velwano; Ilinge and Dacawa) P5 c/o | HSDG c/o | 0 |  |  |  | 471932 | 471932 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 452234.15 |  | 452234.15 | 0 |  | 0 | [12 empty] | 0 | 452234.15 | 452234.15 |  | 19697.85 | 19697.85 | 95.83% | 95.83% | Contractor is on site, progressing with installation of internal services and construction of top structures.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 17,14 | 1 | 76 | 0185 | P | T | S | 50 | 09 | H3 |  |  | Cluster 2 (Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe) P5 (Name Change) | HSDG | 3000000 |  |  |  |  | 3000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 3000000 | 3000000 | 0% | 0% | Contractor is on site, site establishment complete, to commence with construction of internal services and top structures.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 10,5 | 1 | 76 | 0185 | P | T | S | 50 | 10 | H3 |  |  | Cluster 3 (Fynbos 1; Fynbos 2; Ndancama, ) P5 | HSDG | 3000000 |  |  |  | -2700000 | 300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 300000 | 300000 | 0% | 0% | The contractor has commenced with the works of construction for both internal services and top structure. | #VALUE!
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 6,8 | 1 | 76 | 0185 | P | T | S | 50 | 11 | H3 |  |  | DVRI Pilot Project (Mekeni, Haven Hills, Competition Site) P5 | HSDG | 5000000 |  |  |  |  | 5000000 | 0 | 0 | 0 | 1800007.11 |  | 1800007.11 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 1800007.11 | 1800007.11 |  | 3199992.89 | 3199992.89 | 36% | 36% | The contractor is on site, progressing with the works.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 6,8 | 1 | 76 | 0185 | P | T | S | 50 | 48 | H3 |  |  | DVRI Pilot Project (Mekeni, Haven Hills, Competition Site) P5 c/o | HSDG c/o | 0 |  |  |  | 5122540 | 5122540 | [5 empty] | 0 | 1478920.65 |  | 1478920.65 |  |  | 0 | 1544404.59 |  | 1544404.59 | 1469141.87 |  | 1469141.87 | [13 empty] | 4492467.11 | 4492467.11 |  | 630072.89 | 630072.89 | 87.7% | 87.7% | The contractor is on site, progressing with the works.
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 19 | 1 | 76 | 0185 | P | T | S | 50 | 12 | H3 |  |  | Second Creek - P5 | HSDG | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 | 1000000 |  | 1000000 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 1000000 | 1000000 |  | 0 | 0 | 100% | 100% | The project is complete
Human Settlements | Housing Projects |  | 255005 | 1 | 76 | 0185 | KPA2 | 19 | 1 | 76 | 0185 | P | T | S | 50 | 49 | H3 |  |  | Second Creek - P5 c/o | HSDG c/o | 0 |  |  |  | 2374275 | 2374275 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 260054.96 |  | 260054.96 | [12 empty] | 0 | 260054.96 | 260054.96 |  | 2114220.04 | 2114220.04 | 10.95% | 10.95% | The project is complete
Human Settlements |  |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | E | D | 50 | 13 | H3 |  |  | Housing Needs Database and Accreditation | HSDG | 10327914 |  |  |  |  | 10327914 | 525879.76 | 0 | 525879.76 | 493177.39 |  | 493177.39 | 481576.12 |  | 481576.12 | 470926.29 |  | 470926.29 | 439546.25 |  | 439546.25 | 511753.39 |  | 511753.39 | [12 empty] | 0 | 2922859.2 | 2922859.2 |  | 7405054.8 | 7405054.8 | 28.3% | 28.3% | Funding is used for compensation of employees for the Accreditation funded posts, expenditure to increase as the year progresses.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 14 | H3 |  |  | Reeston Phase 3 Stage 3 P5 | HSDG | 5500000 |  |  |  | 9465387 | 14965387 | 0 | 0 | 0 |  |  | 0 | 2182830.86 |  | 2182830.86 | 2191486.61 |  | 2191486.61 | 6421441.53 |  | 6421441.53 | 0 |  | 0 | [12 empty] | 0 | 10795759 | 10795759 |  | 4169628 | 4169628 | 72.14% | 72.14% | The contractor is on site progressing very well with the works. | #VALUE!
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 44 | H3 |  |  | Reeston Phase 3 Stage 3 P5 c/o | HSDG c/o | 0 |  |  |  | 2375000 | 2375000 | [5 empty] | 0 | 2375000 |  | 2375000 |  |  | 0 |  |  | 0 | 0 |  | 0 | [13 empty] | 2375000 | 2375000 |  | 0 | 0 | 100% | 100% | The contractor is on site progressing very well with the works.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 15 | H3 |  |  | Amalinda Co - Op P5 | HSDG | 500000 |  |  |  |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | The project is at final stage of design stage waiting for comments from service departments.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 16 | H3 |  |  | Mdantsane Zone 18CC - P5 | HSDG | 3109500 |  |  |  |  | 3109500 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2605995.48 |  | 2605995.48 | [12 empty] | 0 | 2605995.48 | 2605995.48 |  | 503504.52 | 503504.52 | 83.81% | 83.81% | The appointed consultant is finalizing tender document for the appointment of the contractor.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 17 | H3 |  |  | Potsdam Ikhwezi Block 1 - P5 | HSDG | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Preliminary designs submitted to service branches, awaiting comments
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 18 | H3 |  |  | Dimbaza 110 -P 5 (Top Structure) | HSDG | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Contractor is on site but behind the schedule.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 50 | H3 |  |  | Dimbaza 110 -P 5 (Top Structure) c/o | HSDG c/o | 0 |  |  |  | 6000000 | 6000000 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 505798.87 |  | 505798.87 | 487835.79 |  | 487835.79 | [12 empty] | 0 | 993634.66 | 993634.66 |  | 5006365.34 | 5006365.34 | 16.56% | 16.56% | Contractor is on site but behind the schedule.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | E | D | 50 | 19 | H3 |  |  | Peelton Cluster (Majali, Mdange, Kwatrain, Nkqonqweni, Drayini & Esixekweni) - P5 | HSDG | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 | 81840 |  | 81840 | 479050 |  | 479050 | 173100 |  | 173100 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 733990 | 733990 |  | 266010 | 266010 | 73.4% | 73.4% | The appointed consultant has finalised tender document. Procurement process being finalised for the appointment of the contractor. (Evaluation report to be tabled to the next BAC meeting). Additional budget for the project will be requested during the mid year budget adjustment.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 21 | H3 |  |  | Hanover - P5 | HSDG | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Consultant completed geotechnical report, house designs and presently consultant is working on a tender document which should be finalised by March 2015
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0185 | P | T | S | 50 | 20 | H3 |  |  | Skobeni - P5 | HSDG | 1000000 |  |  |  |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Consultant completed geotechnical report, house designs and presently consultant is working on a tender document which should be finalised by March 2015
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0645 | P | P | P | 50 | 23 | H2 |  |  | Potsdam Village | USDG | 200000 |  |  |  |  | 200000 | 37000 | 5180 | 42180 |  |  | 0 |  |  | 0 | 130500 |  | 130500 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 167500 | 172680 |  | 32500 | 27320 | 83.75% | 86.34% | The appointed consultant has finalised tender document. The document is being evaluated by the department in order to begin with the procurement process for the appointment of the contractor. (The tender document should be tabled to the BSC meeting before the end of January 2015)
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 76 | 0645 | P | P | P | 50 | 24 | H2 |  |  | Disaster Project - Tsholomnqa | USDG | 2000000 |  |  |  |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Procurement process underway
Human Settlements | Housing Projects |  | 255005 | 1 | 77 | 0002 | KPA2 | 1-50 | 1 | 77 | 0002 | P | P | P | 50 | 28 | A2 |  |  | Relocation of beneficiaries to formal houses for all housing programmes - All Projects | Own Funds | 2140000 |  |  |  |  | 2140000 | 11900 | 0 | 11900 | 17464 |  | 17464 | -29364 |  | -29364 | 0 |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 2140000 | 2140000 | 0% | 0% | The project is dependant on completed housing units and the demand (need) of emergency movement of beneficiaries. Expenditure will increase as the year progresses
Human Settlements | Housing Projects |  | 255005 | 1 | 77 | 0002 | KPA2 | 1-50 | 1 | 77 | 0002 | P | P | P | 50 | 51 | A2 |  |  | Relocation of beneficiaries to formal houses for all housing programmes - All Projects c/o | Own Funds c/o | 0 |  |  |  | 379096 | 379096 | [5 empty] | 0 | 7800 |  | 7800 | 242420 |  | 242420 | 9500 |  | 9500 | 81452.6 |  | 81452.6 | [12 empty] | 33120 | 341172.6 | 341172.6 |  | 37923.4 | 37923.4 | 90% | 90% | The project is dependant on completed housing units and the demand (need) of emergency movement of beneficiaries. Expenditure will increase as the year progresses
Human Settlements | Housing Projects |  | 255005 | 1 | 77 | 0002 | KPA2 | 1-50 | 1 | 77 | 0002 | P | P | P | 50 | 52 | A2 |  |  | Rectification title deeds | Own Funds c/o | 0 |  |  |  | 500000 | 500000 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Experiencing challenges with beneficiaries debts on rates payments in order to proceed with rectification of deeds. Department trying to assist in resolving the challenge with Debt Management.
Human Settlements | Housing Projects |  | 255005 | 1 | 77 | 0002 | KPA2 | 1-50 | 1 | 77 | 0002 | P | P | P | 50 | 53 | A2 |  |  | Maintenance of Rental Stock | Own Funds c/o | 0 |  |  |  | 400000 | 400000 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 400000 | 400000 | 0% | 0% | The project is progressing well , the service provider as been appointed with assistance from Building Maintenance.
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 26 | H1 |  |  | Housing Pilot Projects | LGTH | 515387 |  |  |  |  | 515387 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 515387 | 515387 | 0% | 0% | The project is at planning stage and the planning is done by the department
Human Settlements | Housing Projects |  | 255005 | [5 empty] | 1 | 77 | 0015 | P | P | P | 50 | 25 | H1 |  |  | Informal Settlement Upgrading | LGTH | 2007857 |  |  |  |  | 2007857 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 2007857 | 2007857 | 0% | 0% | The project is at planning stage and the planning is done by the department
[20 empty] | TOTAL: HUMAN SETTLEMENTS |  | 111827541 |  |  |  | 45440602 | 157268143 | 574779.76 | 5180 | 579959.76 | 17257130.24 | 0 | 17257130.24 | 12115883.77 | 0 | 12115883.77 | 11399368.38 | 18270 | 11417638.38 | 14904275.44 | 12600 | 14916875.44 | 18190488.68 | 20393.53 | 18210882.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72334.53 | 74441926.27 | 74498369.8 | 0 | 82826216.73 | 82769773.2 | 47.33% | 47.37%
DIRECTORATE OF HEALTH AND PUBLIC SAFETY | [19 empty] | DIRECTORATE OF HEALTH AND PUBLIC SAFETY
Health and Public Safety |  |  | 725015 | [5 empty] | 1 | 77 | 0002 | P | 7 | 5 | 0 | 0 | 02 | A2 |  | CCTV Masterplan | Own Funds c/o | 0 |  |  |  | 101522 | 101522 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 29930.28 |  | 29930.28 | 0 |  | 0 | [13 empty] | 29930.28 | 29930.28 |  | 71591.72 | 71591.72 | 29.48% | 29.48% | Project currently in progress and nearing completion.
Health and Public Safety |  |  | 725055 | [5 empty] | 1 | 77 | 0025 | P | 7 | 5 | 0 | 0 | 04 | D4 | 1 to 50 | Disaster Management | TRUST FUNDS | 176266 |  |  |  |  | 176266 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 176266 | 176266 | 0% | 0% | This funding will be used for the Community Based Risk Reduction intervention project which is currently underway.
[20 empty] | TOTAL: HEALTH AND PUBLIC SAFETY |  | 176266 |  |  |  | 101522 | 277788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29930.28 | 0 | 29930.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29930.28 | 29930.28 | 0 | 247857.72 | 247857.72 | 10.77% | 10.77%
DIRECTORATE OF COMMUNITY SERVICES | [19 empty] | DIRECTORATE OF COMMUNITY SERVICES
Community Services |  |  | 755005 | [5 empty] | 1 | 77 | 0013 | P | 8 | 5 | 0 | 0 | 08 | D9 |  | Climate Protection | DEDEAT | 0 |  |  |  | 106835 | 106835 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [13 empty] | 0 | 0 |  | 106835 | 106835 | 0% | 0% | Planning in progress
Community Services |  |  | 755035 | [5 empty] | 1 | 77 | 0002 | P | 8 | 5 | 0 | 0 | 09 | A2 |  | BCMM Climate Change Strategy | Own Funds c/o | 0 |  |  |  | 37189 | 37189 |  |  |  | 0 |  | 0 | 0 |  | 0 | 5437.53 |  | 5437.53 | 0 |  | 0 | 0 |  | 0 | [13 empty] | 5437.53 | 5437.53 |  | 31751.47 | 31751.47 | 14.62% | 14.62% | A report has been submitted for council approval, and will be tabled in the next community Services portfolio Committee (23 January 2015)
Community Services |  |  | 755035 | [5 empty] | 1 | 77 | 0002 | P | 8 | 5 | 0 | 0 | 10 | A2 |  | Environmental Education Strategy | Own Funds c/o | 0 |  |  |  | 65655 | 65655 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 52380 |  | 52380 | [12 empty] | 6545.11 | 52380 | 52380 |  | 13275 | 13275 | 79.78% | 79.78% | in progress and near complection
Community Services |  |  | 755035 | [5 empty] | 1 | 77 | 0002 | P | 8 | 5 | 0 | 0 | 11 | A2 |  | Reviewable of the Integrated Environmental Plan & Coastal Zone Management Plan | Own Funds c/o | 0 |  |  |  | 234971 | 234971 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [13 empty] | 0 | 0 |  | 234971 | 234971 | 0% | 0% | The final draft report for IEM and CZMP's has been submited by the service prvider to be presented to Top Management Committee in January 2015. Once approved the report will be sent to Council for approval.
Community Services |  |  | 760020 | [5 empty] | 1 | 77 | 0013 | P | 8 | 5 | 0 | 0 | 01 | D9 |  | John Dube Village | DEDEAT | 199168 |  |  |  |  | 199168 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 199168 | 199168 | 0% | 0% | Funding to be transfered to the overspent Community Development Project.
Community Services |  |  | 760020 | [5 empty] | 1 | 77 | 0098 | P | 8 | 5 | 0 | 0 | 03 | N3 |  | Art Centres | DSRAC | 37438 |  |  |  |  | 37438 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 37438 | 37438 | 0% | 0% | Funding to be transfered to the overspent Community Development Project.
Community Services |  |  | 760025 | [5 empty] | 1 | 77 | 0015 | P | 8 | 5 | 0 | 0 | 04 | D2 |  | Community Development Projects | LGTH | 2127846 |  |  |  |  | 2127846 | 1125060 | 0 | 1125060 | 1252201.6 |  | 1252201.6 | 257920.5 |  | 257920.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 2635182.1 | 2635182.1 |  | -507336.1 | -507336.1 | 123.8% | 123.8% | Project complete
Community Services |  |  | 760025 | [5 empty] | 1 | 77 | 0025 | P | 8 | 5 | 0 | 0 | 05 | D4 |  | Refurbishment and Maintenace of Halls - Rural Areas | TRUST FUNDS | 427011 |  |  |  |  | 427011 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 427011 | 427011 | 0% | 0% | Funding to be transfered to the overspent Community Development Project.
Community Services | Amenities |  | 765005 |  |  | 0002 | KPA2 |  | 1 | 77 | 0002 | P | 8 | 5 | 0 | 0 | 02 | A2 |  | Amenities Masterplan | Own Funds | 1200000 |  |  |  |  | 1200000 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 1200000 | 1200000 | 0% | 0% | Procurement process underway
Community Services |  |  | 765010 | [5 empty] | 1 | 77 | 0098 | P | 8 | 5 | 0 | 0 | 06 | N3 |  | Premier's Fund | Premiers Fund | 67421 |  |  |  |  | 67421 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 67421 | 67421 | 0% | 0% | Funding to be transfered to the overspent Community Development Project.
Community Services |  |  | 755035 | [5 empty] | 1 | 77 | 0002 | P | 8 | 5 | 0 | 0 | 07 | A2 |  | Biodiveristy Conservation Plan | Own Funds | 600000 |  |  |  |  | 600000 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 600000 | 600000 | 0% | 0% | The department is in the process of developing terms of reference with the affected stakeholders.
[20 empty] | TOTAL : COMMUNITY SERVICES |  | 4658884 |  |  |  | 444650 | 5103534 | 1125060 | 0 | 1125060 | 1252201.6 | 0 | 1252201.6 | 257920.5 | 0 | 257920.5 | 5437.53 | 0 | 5437.53 | 0 | 0 | 0 | 52380 | 0 | 52380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6545.11 | 2692999.63 | 2692999.63 | 0 | 2410534.37 | 2410534.37 | 52.77% | 52.77%
[20 empty] | TOTAL OPERATING PROJECTS |  | #VALUE! | #REF! | #REF! | #REF! | #VALUE! | 288437823 | 4163028.02 | 14204.67 | 4177232.69 | 21850241.81 | 0 | 21850241.81 | 18065136.62 | 88508.93 | 18153645.55 | 24791738.86 | 131797.16 | 24923536.02 | 19656962.56 | 71374.68 | 19728337.24 | 25116971.43 | 149340.27 | 25266311.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 667300.35 | 113644079.3 | 114099305.01 | 0 | 174793743.7 | 174338517.99 | 3.0484 | 39.56%
[20 empty] | LED - PROJECTS TAKEN OFF | [6 empty] | 288437823 | 4163028.02 | 14204.67 |  | 21850241.81 | 0 |  | 18065136.62 | 88508.93 | 18153645.55 | 24791738.86 | 131797.16 | 24923536.02 | 19656962.56 | 71374.68 | 19728337.24 | 25116971.43 | [15 empty] | 113644079.3 | -114099305.01
Housing Projects TRF to OPEX - USDG
[20 empty] | Budget Reforms - Adjusted FMG |  |  | -200000
[20 empty] | Housing Projects TRF to OPEX - USDG |  |  | 1903000
[20 empty] | Housing Projects Adjusted - HSDG |  |  | -25277477
[20 empty] | ACEGrant |  |  | 7991312.28
[20 empty] | Housing Projects - Own Funds |  |  | 1700000
[20 empty] | DVRI Projects - LGHT |  |  | 5000000
[20 empty] | Beneficiary Education - Funded by Own Funds |  |  | 200000
Development Planning |  |  | 635005 | [16 empty] | Destination Marketing Programme | Own Funds
Development Planning |  |  | 635005 | [16 empty] | Bussiness Support Programme | Own Funds
Development Planning |  |  | 635005 | [16 empty] | Economic Empowerment Programme | Own Funds
Development Planning |  |  | 635005 | [16 empty] | Trade and Investment Programme | Own Funds
Development Planning |  |  | 635005 | [16 empty] | Economic Events Programme | Own Funds
Development Planning |  |  | 635005 | [16 empty] | Rural Economic Development Programme | Own Funds
Development Planning |  |  | 635005 | [16 empty] | Economic Planning | Own Funds
Executive Support Services | Public Participation & Ward Committees |  | 120005 | 1 | 77 | 0002 | KPA5 | N/A | 1 | 77 | 0002 | P | 1 | 4 | 0 | 0 | 15 | A2 |  | Intergovernmental Relations | Own Funds |  | 80000 |  | 80000 |  | 80000 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [13 empty] | 0 | 0 |  | 80000 | 80000 | 0% | 0%
Executive Support Services | Special Programmes |  | 105030 | 1 | 77 | 0002 | KPA5 | All | 1 | 77 | 0002 | P | 1 | 4 | 0 | 0 | 11 | A2 |  | Municipal Bursaries | Own Funds |  | 1200000 |  | 1200000 |  | 1200000 | 331189.13 |  |  | 12515.56 |  |  | 33145.98 |  | 33145.98 | 71221.85 |  | 71221.85 | 78738 |  | 78738 | 3816 |  | 3816 | [12 empty] | Nil | 530626.52 | 530626.52 |  | 669373.48 | 669373.48 | 44.22% | 44.22%
Executive Support Services | Special Programmes |  | 105030 | 1 | 77 | 0002 | KPA5 | All | 1 | 77 | 0002 | P | 1 | 4 | 0 | 0 | 12 | A2 |  | Youth Advisory Centres | Own Funds |  | 1200000 |  | 1200000 |  | 1200000 | 0 |  |  | 4070 |  |  | 191315.75 |  | 191315.75 | 106274.84 |  | 106274.84 | 246403.17 |  | 246403.17 | 238137.33 |  | 238137.33 | [12 empty] | Nil | 786201.09 | 786201.09 |  | 413798.91 | 413798.91 | 65.52% | 65.52%
Executive Support Services | Special Programmes |  | 105030 | 1 | 77 | 0002 | KPA5 | All | 1 | 77 | 0002 | P | 1 | 4 | 0 | 0 | 13 | A2 |  | Days of Importance | Own Funds |  | 500000 |  | 500000 |  | 500000 | 6819.5 |  |  | 18526 |  |  | 106724.51 |  | 106724.51 | 57908.63 |  | 57908.63 | 8696.71 |  | 8696.71 | 45704.79 |  | 45704.79 | [12 empty] | Nil | 244380.14 | 244380.14 |  | 255619.86 | 255619.86 | 48.88% | 48.88%
Executive Support Services | Special Programmes |  | 105030 | 1 | 77 | 0002 | KPA5 | All | 1 | 77 | 0002 | P | 1 | 4 | 0 | 0 | 14 | A2 |  | Women's Caucus | Own Funds |  | 300000 |  | 300000 |  | 300000 | 3155 |  |  | 8400 |  |  | 21550 |  | 21550 | 80117.24 |  | 80117.24 | 18976.55 |  | 18976.55 | 87113.16 |  | 87113.16 | [12 empty] | Nil | 219311.95 | 219311.95 |  | 80688.05 | 80688.05 | 73.1% | 73.1%
Municipal Manager's Office | Office of the Municipal Manager |  | 205005 | 1 | 77 | 0002 | KPA5 | N/A | 1 | 77 | 0002 | P | 2 | 4 | 2 | 0 | 00 | A2 |  | Risk Management | Own Funds |  | 500000 |  | 500000 |  | 500000 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 22073 |  | 22073 | 0 |  | 0 | [13 empty] | 22073 | 22073 |  | 477927 | 477927 | 4.415% | 4.415%
Municipal Manager's Office |  |  | 205005 |  |  | 0354 | KPA4 | N/A | 1 | 77 | 0002 | P | 2 | 4 | 7 | 0 | 00 | A2 |  | MPAC | Own Funds |  | 0 | 200000 | 200000 |  | 200000 |  |  |  | 0 |  |  | 8059.5 | 0 | 8059.5 | 55997.04 |  | 55997.04 | 57811.67 |  | 57811.67 | 17548.26 |  | 17548.26 | [13 empty] | 139416.47 | 139416.47 |  | 60583.53 | 60583.53 | 69.71% | 69.71%
Development Planning | Transportation |  | 620005 | 1 | 77 | 0002 | KPA2 | All Wards | 1 | 77 | 0002 | P | 6 | 4 | 0 | 0 | 01 | A2 |  | Integrated Transport Plan Review | Own Funds |  | 800000 |  | 800000 |  | 800000 |  |  |  | 54455.95 |  |  | 132989.8 |  | 132989.8 | -66494.9 |  | -66494.9 | 0 |  | 0 |  |  | 0 | [13 empty] | 120950.85 | 120950.85 | 0 | 679049.15 | 679049.15 | 15.12% | 15.12%
Development Planning | Local Economic Development |  | 635005 |  |  | 0002 | KPA3 | 31,34,39 | 1 | 77 | 0002 | P | 6 | 4 | 0 | 0 | 04 | A2 |  | Rural Economic Development Programme | Own Funds |  | 3000000 |  | 3000000 |  | 3000000 | 24196.63 |  |  | 232262.76 |  |  |  |  | 0 | 285513.31 |  | 285513.31 | 64303.38 |  | 64303.38 | 56985.07 |  | 56985.07 | [13 empty] | 663261.15 | 663261.15 | 0 | 2336738.85 | 2336738.85 | 22.11% | 22.11%
Development Planning | Local Economic Development |  | 635005 |  |  | 0002 | KPA3 | All Wards | 1 | 77 | 0002 | P | 6 | 4 | 0 | 0 | 05 | A2 |  | Economic Planning | Own Funds |  | 200000 |  | 200000 |  | 200000 | [8 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [13 empty] | 0 | 0 | 0 | 200000 | 200000 | 0% | 0%
Development Planning | Land Survey |  | 615085 | 1 | 77 | 0002 | KPA2 | N/A | 1 | 77 | 0002 | P | 6 | 4 | 0 | 0 | 07 | A2 |  | Subdivision of Municipal Leased Properties | Own Funds |  | 400000 | 0 | 400000 |  | 400000 | [8 empty] | 0 | 3295.68 |  | 3295.68 | 0 |  | 0 | 0 |  | 0 | [13 empty] | 3295.68 | 3295.68 | 0 | 396704.32 | 396704.32 | 0.8239% | 0.8239%
Development Planning | City Planning |  | 615070 | 1 | 77 | 0002 | KPA2 | 11,12,14,17,20-24,30,42,48,50 | 1 | 77 | 0002 | [8 empty] | Mdantsane Industrial Township Feasibility Study | Own Funds |  | 0 |  | 0 |  | 0 | [11 empty] | 0 | 0 |  | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 0 | 0 | 0% | 0%
Development Planning | City Planning |  | 615070 | 1 | 77 | 0002 | KPA2 | 17, 26 | 1 | 77 | 0002 | P | 6 | 4 | 0 | 0 | 09 | A2 |  | Newlands Local Spatial Development Framework | Own Funds |  | 400000 |  | 400000 |  | 400000 | [8 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 27120 |  | 27120 | [13 empty] | 27120 | 27120 | 0 | 372880 | 372880 | 6.78% | 6.78%
Development Planning | City Planning |  | 615070 | 1 | 77 | 0002 | KPA2 | All Wards | 1 | 77 | 0002 | [6 empty] | A2 |  | BCMM Township Establishment | Own Funds |  | 0 |  | 0 |  | 0 | [11 empty] | 0 | 0 |  | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 0 | 0 | 0% | 0%
Development Planning | Local Economic Development |  | 635005 | 1 | 77 | 0002 | KPA3 | All Wards | 1 | 77 | 0002 | [8 empty] | Destination Marketing Programme | Own Funds |  | 0 |  |  |  | 0 | [14 empty] | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 0 | 0 | 0% | 0%
Development Planning | Local Economic Development |  | 635005 | 1 | 77 | 0002 | KPA3 | All Wards | 1 | 77 | 0002 | [6 empty] | A2 |  | Business Support Programme | Own Funds |  | 0 |  |  |  | 0 | [14 empty] | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 0 | 0 | 0% | 0%
Development Planning | Local Economic Development |  | 635005 | 1 | 77 | 0355 | KPA3 | All Wards | 1 | 77 | 0002 | [8 empty] | Economic Empowerment Programme | Own Funds |  | 0 |  |  |  | 0 | [11 empty] | 0 |  |  | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 0 | 0 | 0% | 0%
Development Planning |  |  | 635005 | 1 | 77 | 0356 | KPA4 | All Wards | 1 | 77 | 0002 | P | 6 | 4 | 0 | 0 | 26 | A2 |  | Trade and Investment Programme | Own Funds |  | 0 | 1166032 | 1166032 |  | 1166032 | [8 empty] | 0 | 0 |  | 0 | 4500 |  | 4500 | 0 |  | 0 | [13 empty] | 4500 | 4500 | 0 | 1161532 | 1161532 | 0.3859% | 0.3859%
Development Planning | Local Economic Development |  | 635005 |  |  | 0002 | KPA3 | All Wards | 1 | 77 | 0002 | P | 6 | 4 | 0 | 0 | 03 | A2 |  | Economic Events Programme | Own Funds |  | 4000000 |  | 4000000 |  | 4000000 | [6 empty] | 483935.98 |  | 483935.98 | 1079225.89 |  | 1079225.89 | 895486.05 |  | 895486.05 | 1474774.41 |  | 1474774.41 | [13 empty] | 3933422.33 | 3933422.33 | 0 | 66577.67 | 66577.67 | 98.34% | 98.34%
Chief Operations Officer | Housing Projects |  | 255005 | [5 empty] | 1 | 77 | 0002 | P | E | D | 20 | 35 | A2 |  |  | Maintenance of all rental stock | Own Funds |  | 1000000 |  | 1000000 |  | 1000000 |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 1000000 | 1000000 | 0% | 0%
Chief Operations Officer | Housing Projects |  | 255005 | [5 empty] | 1 | 77 | 0002 | P | E | D | 20 | 34 | A2 |  |  | Rectification of all title deeds | Own Funds |  | 700000 |  | 700000 |  | 700000 |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 700000 | 700000 | 0% | 0%
Engineering Services | Water Administration |  | 520005 | 1 | 77 | 0002 | KPA2 | 1,2,5,6,7,8,10 | 1 | 77 | 0002 | [8 empty] | Caretakers - Duncan Village and Information Settlements | Own Funds |  | 2000000 | 1200000 | 3200000 |  | 3200000 | 334200 |  |  | 22332.29 |  |  | 371090 |  | 371090 | 379951.76 |  | 379951.76 | 534917.14 |  | 534917.14 | 44809.75 |  | 44809.75 | [13 empty] | 1687300.94 | 1687300.94 |  | 1512699.06 | 1512699.06 | 52.73% | 52.73%
Engineering Services | Electricity |  | 535025 | 1 | 77 | 0002 | KPA2 | N/A | 1 | 77 | 0002 | [8 empty] | Electricity and Water Meter Tampering | Own Funds |  | 1000000 |  | 1000000 |  | 1000000 | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | [13 empty] | 0 | 0 |  | 1000000 | 1000000 | 0% | 0%
Health and Public Safety | Health Services |  | 710030 |  |  | 0002 | KPA2 | 1 to 50 | 1 | 77 | 0002 | P | 7 | 4 | 0 | 0 | 0 | 5 |  | Municipal Health Services - I.T & Database Development | Own Funds |  | 450000 | -450000 | 0 |  | 0 | 0 |  |  | 0 | [8 empty] | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 0 | 0 | 0% | 0%
Health and Public Safety | Health Services |  | 710030 |  |  | 0002 | KPA2 | 1 to 50 | 1 | 77 | 0002 | P | 7 | 4 | 0 | 0 | 0 | 6 |  | Automation of Air Quality Monitoring Stations | Own Funds |  | 250000 | -250000 | 0 |  | 0 | 0 |  |  | 5561.46 |  |  | -5561.46 |  | -5561.46 |  |  |  | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 0 | 0 | 0% | 0%
Community Services | IEMP |  | 755035 |  |  | 0002 | KPA2 | All | 1 | 77 | 0002 | P | 8 | 4 | 0 | 0 | 03 | A2 |  | BCMM Climate Change Strategy | Own Funds |  | 0 | 250000 | 250000 |  | 250000 |  |  |  | 0 |  |  | 3501.66 |  | 3501.66 | 0 |  | 0 | 0 |  | 0 | 145057.39 |  | 145057.39 | [12 empty] | 0 | 148559.05 | 148559.05 |  | 101440.95 | 101440.95 | 59.42% | 59.42%
Community Services | IEMP |  | 755035 |  |  | 0002 | KPA2 | All | 1 | 77 | 0002 | P | 8 | 4 | 0 | 0 | 04 | A2 |  | Environmental Education Strategy | Own Funds |  | 0 | 67715 | 67715 |  | 67715 |  |  |  | 0 |  |  | 2059.8 |  | 2059.8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 2059.8 | 2059.8 |  | 65655.2 | 65655.2 | 3.042% | 3.042%
Financial Services |  |  | 330010 | [16 empty] | Office Accomodation for Call Centre | Own Funds |  |  |  | 0 |  | 0
Financial Services |  |  | 330010 | [16 empty] | CRM & IVR Systems | Own Funds |  |  |  | 0 |  | 0
Financial Services |  |  | 330010 | [16 empty] | Microsoft CRM Licenses | Own Funds |  |  |  | 0 |  | 0
Chief Operations Officer | Housing Projects |  | 255005 |  |  | 0355 | KPA2 | All | 1 | 77 | 0002 | P | P | 2 | 04 | 02 | A2 | 2 |  | Beneficiary Education ( All Projects) | Own Funds |  | 200000 |  | 200000 |  | 200000 | 0 |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 307 |  | 307 | [13 empty] | 307 | 307 |  | 199693 | 199693 | 0.1535% | 0.1535%
Health and Public Safety | Disaster Management |  | 725055 |  |  | 0002 | KPA2 | 1 to 50 | 1 | 77 | 0002 | p | 7 | 4 | 0 | 0 | 0 | 4 |  | Disaster Management Structures | Own Funds |  | 40000 |  | 40000 |  | 40000 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | [12 empty] | 0 | 0 | 0 |  | 40000 | 40000 | 0% | 0%
Community Services |  |  | 770030 |  |  | 0354 | KPA1 | 40 | 1 | 77 | 0002 | P | 8 | 4 | 0 | 0 | 07 | A2 |  | Waste Management Programme (Take it Off to General Expenses 1/65) | Own Funds |  | 0 | 1352043 | 1352043 |  | 1352043 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 294409.79 |  | 294409.79 | 97746 |  | 97746 | [12 empty] | 0 | 392155.79 | 392155.79 |  | 959887.21 | 959887.21 | 29% | 29%
Note on D11: Ndzondi Kati: Ccentre s/be 105030 and is sitting under 120005

## Summaries
2014-2015 DRAFT OPERATING PROJECTS BUDGET
[31 empty] | BG |  |  | BH |  |  | BI
OPERATING PROJECTS PER FUNDING SOURCE | 2014/2015 Opex Budget | Adjustment | 2014/2015 Opex Adjusted Budget | Jul 14 | VAT | Aug 14 | VAT | Sept 14 | VAT | Oct 14 | VAT | Nov 14 | VAT | Dec 14 | VAT | Jan 15 | VAT | Feb 15 | VAT | Mar 15 | VAT | Apr 15 | VAT | May 15 | VAT | Jun 15 | VAT | COMMITMENTS | Mid-Year Adjustments | 2014/2015 Mid - Year Adjusted Budget | 2014/2015 Draft Capital Budget | Approved by Council | Diff | 2015/2016 Draft Capital Budget | Approved by Council | Diff | 2016/2017 Draft Capital Budget | 2014/2015 EXPENDITURE TO DATE (VENUS) | 2014/2015 EXPENDITURE TO DATE VAT | 2014/2015 AVAILABLE BUDGET | 2014/2015 AVAILABLE BUDGET VAT | % EXPENDITURE VS BUDGET VAT | % EXPENDITURE VS BUDGET
Own Funds | 49940000 | 0 | 61440000 | 41125.5 | 41125.5 | 685350.35 | 685350.35 | 1228680.93 | 0 | 8175224.39 | 0 | 758067.74 | 0 | 2668785.37 | 2668785.37 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 261350.53 | #REF! | #REF! | #REF! | 81300000 | #REF! | #REF! | 34620000 | #REF! | #REF! | 13557234.28 | 13557234.28 | 47882765.72 | 47882765.72 | 22.07% | 22.07% | 49940000 | 52650000 | 32790000
Own Funds c/o | 0 | 0 | 21518512 | 0 | 0 | 175744.25 | 175744.25 | 415443.8 | 0 | 969910.16 | 0 | 313629.11 | 0 | 273318.64 | 273318.64 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 39665.11 | #REF! | #REF! | #REF! | 0 | #REF! | #REF! |  | #REF! | #REF! | 2148045.96 | 2148045.96 | 19370466.04 | 19370466.04 | 9.982% | 9.982%
Total Own Funding | 49940000 | 0 | 82958512 | 41125.5 | 41125.5 | 861094.6 | 861094.6 | 1644124.73 | 0 | 9145134.55 | 0 | 1071696.85 | 0 | 2942104.01 | 2942104.01 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 301015.64 | #REF! | #REF! | #REF! | 81300000 | #REF! | #REF! | 34620000 | #REF! | #REF! | 15705280.24 | 15705280.24 | 67253231.76 | 67253231.76 | 18.93% | 18.93% | #REF! | #REF! | #REF!
Department of Land Affairs | 777243 | 0 | 777243 | 0 | 0 | 0 | 0 | 0 | 0 | 18540.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 18540.22 | 18540.22 | 758702.78 | 758702.78 | 2.385% | 2.385%
Department of Land Affairs c/o | 0 |  | 71782 | 0 | 0 | 0 | 0 | 0 | 0 | 62966.03 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [9 empty] | 62966.03 | 62966.03 | 8815.97 | 8815.97 | 87.72% | 87.72%
Department of Local Government & Traditional Affairs | 3000000 | 0 | 3110000 | 0 | 0 | 402905.5 | 402905.5 | 198657.4 | 0 | 314216.18 | 0 | 0 | 0 | 70405.39 | 70405.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39214.53 | #REF! | #REF! | #REF! | 2000000 | #REF! | #REF! | 0 | #REF! | #REF! | 986184.47 | 986184.47 | 2123815.53 | 2123815.53 | 31.71% | 31.71%
Department of Local Government & Traditional Affairs c/o | 0 |  | 1680672 | 0 | 0 | 0 | 0 | 0 | 0 | 2710 | 0 | 0 | 0 | 183056.21 | [13 empty] | 0 | [9 empty] | 185766.21 | 185766.21 | 1494905.79 | 1494905.79 | 11.05% | 11.05%
Department of Sport, Recreation and Arts and Culture | 37438 | 0 | 37438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37438 | 37438 | 0% | 0%
Department of Economic Development, Environmental Affairs and Tourism(DEDEAT) | 3638576 | 0 | 3745411 | 0 | 0 | 4481 | 4481 | 106650.38 | 0 | 897386.55 | 0 | 122274.09 | 0 | 520550.15 | 897386.55 | 0 | 897386.55 | 0 | 897386.55 | 0 | 897386.55 | 0 | 897386.55 | 0 | 897386.55 | 0 | 897386.55 | 224900.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1651342.17 | 1651342.17 | 2094068.83 | 2094068.83 | 44.09% | 44.09%
European Commission | 500000 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000 | 0 | 500000 | 0 | 500000 | 0 | 500000 | 0 | 500000 | 0 | 500000 | 0 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0 | 0 | 500000 | 500000 | 0% | 0%
Expanded Public Works Programme Incentives Grant | 1890000 | 0 | 1890000 | 0 | 0 | 0 | 0 | 789650 | 0 | 429780 | 0 | 301390 | 0 | 22270 | 22270 | 0 | 301390 | 0 | 301390 | 0 | 301390 | 0 | 301390 | 0 | 301390 | 0 | 301390 | 0 | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 1543090 | 1543090 | 346910 | 346910 | 81.64% | 81.64%
Finance Management Grant | 1500000 | 0 | 1500000 | 114326 | 114326 | 187334.48 | 187334.48 | 89087.6 | 0 | 87187.5 | 0 | 115694.55 | 3315.79 | 97291.98 | 97291.98 | 0 | 119010.34 | 0 | 119010.34 | 0 | 119010.34 | 0 | 119010.34 | 0 | 119010.34 | 0 | 119010.34 | 0 | #REF! | #REF! | #REF! | 1500000 | #REF! | #REF! | 1500000 | #REF! | #REF! | 690922.11 | 694237.9 | 809077.89 | 805762.1 | 46.28% | 46.28%
Human Settlement Development Grant | 99938108 | 0 | 97953495 | 525879.76 | 525879.76 | 16827048.06 | 16827048.06 | 5291350.33 | 0 | 9552764.74 | 0 | 11096177.18 | 0 | 9971066.6 | 9971066.6 | 0 | 11096177.18 | 0 | 11096177.18 | 0 | 11096177.18 | 0 | 11096177.18 | 0 | 11096177.18 | 0 | 11096177.18 | 0 | #REF! | #REF! | #REF! | 99138314 | #REF! | #REF! | 87969705 | #REF! | #REF! | 53264286.67 | 53264286.67 | 44689208.33 | 44689208.33 | 54.38% | 54.38% | 366372335
Human Settlement Development Grant c/o | 0 |  | 44569800 | 0 | 0 | 0 | 0 | 6470180.41 | 0 | 1156757.46 | 0 | 3875016.02 | 0 | 7415395.08 | [13 empty] | 0 | [9 empty] | 18917348.97 | 18917348.97 | 25652451.03 | 25652451.03 | 42.44% | 42.44%
Infrastructure Skills Development Grant | 5400000 | 0 | 5400000 | 386216.39 | 389460.46 | 370435.8 | 370435.8 | 545475.18 | 11984.65 | 933293.69 | 88697.66 | 528857.52 | 0 | 1080492.47 | 1189055.21 | 0 | 528857.52 | 0 | 528857.52 | 0 | 528857.52 | 0 | 528857.52 | 0 | 528857.52 | 0 | 528857.52 | 0 | #REF! | #REF! | #REF! | 8380000 | #REF! | #REF! | 8889000 | #REF! | #REF! | 3844771.05 | 4057260.17 | 1555228.95 | 1342739.83 | 75.13% | 75.13%
Leiden | 136315 | 0 | 136315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136315 | 0 | 136315 | 0 | 136315 | 0 | 136315 | 0 | 136315 | 0 | 136315 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136315 | 136315 | 0% | 0%
Leiden c/o | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
Local Government and Traditional Affairs | 6101371 | 0 | 6101371 | 1125060 | 1125060 | 1252201.6 | 1252201.6 | 257920.5 | 0 | 0 | 0 | 0 | 0 | 0 | 6101371 | 0 | 6101371 | 0 | 6101371 | 0 | 6101371 | 0 | 6101371 | 0 | 6101371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2635182.1 | 2635182.1 | 3466188.9 | 3466188.9 | 43.19% | 43.19%
Premiers Fund | 67421 | 0 | 67421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67421 | 0 | 67421 | 0 | 67421 | 0 | 67421 | 0 | 67421 | 0 | 67421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67421 | 67421 | 0% | 0%
Trust Funds | 2714699 | 0 | 2714699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2714699 | 2714699 | 0% | 0%
Umsobomvu Youth Fund | 710406 | 0 | 710406 | 33130 | 33130 | 2976.31 | 2976.31 | 18090.18 | 0 | 103895.87 | 0 | 85010.62 | 0 | 6080.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249183.42 | 249183.42 | 461222.58 | 461222.58 | 35.08% | 35.08%
Urban Settlement Development Grant | 33464500 | 0 | 33464500 | 1937290.37 | 1948250.97 | 1941764.46 | 1941764.46 | 2627258.44 | 76524.28 | 2113797.55 | 43099.5 | 2460313.7 | 68058.89 | 2808259.1 | 2849036.63 | 0 | 2528372.59 | 0 | 2528372.59 | 0 | 2528372.59 | 0 | 2528372.59 | 0 | 2528372.59 | 0 | 0 | 102169.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13888683.62 | 14128104.42 | 19575816.38 | 19336395.58 | 42.22% | 42.22%
Vuna Awards | 1048758 | 0 | 1048758 | 0 | 0 | 0 | 0 | 26691.47 | 0 | -26691.48 | 0 | 532.03 | 0 | 0 | -26691.48 | 0 | -26691.48 | 0 | -26691.48 | 0 | -26691.48 | 0 | -26691.48 | 0 | -26691.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 532.02 | 532.02 | 1048225.98 | 1048225.98 | 0.05073% | 0.05073%
Total Grants | 160924835 | 0 | 205479311 | 4121902.52 | 4136107.19 | 20989147.21 | 20989147.21 | 16421011.89 | 88508.93 | 15646604.31 | 131797.16 | 18585265.71 | 71374.68 | 22174867.42 | 21901619.36 | 0 | 22276301.18 | 0 | 22276301.18 | 0 | 22276301.18 | 0 | 22276301.18 | 0 | 22276301.18 | 0 | 13442821.59 | 366284.71 | #REF! | #REF! | #REF! | 111518314 | #REF! | #REF! | 98858705 | #REF! | #REF! | 97938799.06 | 98394024.77 | 107540511.94 | 107085286.23 | 47.89% | 47.66%
TOTAL PER FUNDING | 210864835 | 0 | 288437823 | 4163028.02 | 4177232.69 | 21850241.81 | 21850241.81 | 18065136.62 | 88508.93 | 24791738.86 | 131797.16 | 19656962.56 | 71374.68 | 25116971.43 | 24843723.37 | 0 | 22276301.18 | 0 | 22276301.18 | 0 | 22276301.18 | 0 | 22276301.18 | 0 | 22276301.18 | 0 | 13442821.59 | 667300.35 | #REF! | #REF! | #REF! | 192818314 | #REF! | #REF! | 133478705 | #REF! | #REF! | 113644079.3 | 114099305.01 | 174793743.7 | 174338517.99 | 39.56% | 39.4%
| #VALUE! |  | 0
0
OPERATING PROJECTS PER DIRECTORATE | 2014/2015 Opex Budget | 2013/2014 Roll- Over Adj Opex Budget | 2014/2015 Opex Adjusted Budget | Jul 14 | VAT | Aug 14 | VAT | Sept 14 | VAT | Oct 14 | VAT | Nov 14 | VAT | Dec 14 | VAT | Jan 15 | VAT | Feb 15 | VAT | Mar 15 | VAT | Apr 15 | VAT | May 15 | VAT | Jun 15 | VAT | COMMITMENTS | Mid-Year Adjustments | 2014/2015 Draft Capital Budget |  | Approved by Council | Diff | 2015/2016 Draft Capital Budget | Approved by Council | Diff | 2019/2017 Draft Capital Budget | 2014/2015 EXPENDITURE TO DATE (VENUS) | 2014/2015 EXPENDITURE TO DATE (VENUS) VAT | 2014/2015 AVAILABLE BUDGET | 2014/2015 AVAILABLE BUDGET VAT | % EXPENDITURE VS BUDGET VAT | % EXPENDITURE VS BUDGET
1. Executive Support Services | 1278873 | 0 | 1755165 | 33130 | 33130 | 2976.31 | 2976.31 | 96704.22 | 0 | 106436.11 | 0 | 90056.85 | 90056.85 | 10056.46 | 10056.46 | 0 | 90056.85 | 0 | 90056.85 | 0 | 90056.85 | 0 | 90056.85 | 0 | 90056.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339359.95 | 339359.95 | 1415805.05 | 1415805.05 | 19.33% | 19.33%
2. Municipal Manager's Office | 42082528 | 0 | 48982809 | 1900290.37 | 1906070.97 | 2034297.97 | 2034297.97 | 3263390.41 | 76524.28 | 2789602.84 | 24829.5 | 2704206 | 2759664.89 | 2334460.16 | 2354844.16 | 0 | 2759664.89 | 0 | 2759664.89 | 0 | 2759664.89 | 0 | 2759664.89 | 0 | 2759664.89 | 0 | 0 | 102169.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15026247.75 | 15209225.02 | 33956561.25 | 33773583.98 | 31.05% | 30.68%
3. Chief Operations Officer | 111827541 | 0 | 157268143 | 574779.76 | 579959.76 | 17257130.24 | 17257130.24 | 12115883.77 | 0 | 11399368.38 | 0 | 14904275.44 | 0 | 18190488.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72334.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74441926.27 | 74498369.8 | 82826216.73 | 82769773.2 | 47.37% | 47.33%
4. Directorate of Financial Services | 27186512 | 0 | 42961602 | 143551.5 | 143551.5 | 333853.23 | 333853.23 | 315949.42 | 0 | 5441938.46 | 0 | 384847.15 | 388162.94 | 177992.53 | 177992.53 | 0 | 388162.94 | 0 | 388162.94 | 0 | 388162.94 | 0 | 388162.94 | 0 | 388162.94 | 0 | 0 | 2208.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6798132.29 | 6801448.08 | 36163469.71 | 36160153.92 | 15.83% | 15.82%
5. Directorate of Corporate Services | 14113769 | 0 | 14364938 | 386216.39 | 389460.46 | 370435.8 | 370435.8 | 709211.29 | 11984.65 | 933293.69 | 88697.66 | 528857.52 | 528857.52 | 1131576.44 | 1240139.18 | 0 | 528857.52 | 0 | 528857.52 | 0 | 528857.52 | 0 | 528857.52 | 0 | 528857.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4059591.13 | 4272080.25 | 10305346.87 | 10092857.75 | 29.74% | 28.26%
6. Directorate of Engineering Services | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 793800 | 793800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 793800 | 793800 | 1206200 | 1206200 | 39.69% | 39.69%
7. Directorate of Development Planning | 1101054 | 0 | 2284436 | 0 | 0 | 117102.81 | 117102.81 | 76187.37 | 0 | 84416.25 | 0 | 166417.76 | 166417.76 | 96956.14 | 96956.14 | 0 | 166417.76 | 0 | 166417.76 | 0 | 166417.76 | 0 | 166417.76 | 0 | 166417.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541080.33 | 541080.33 | 1743355.67 | 1743355.67 | 23.69% | 23.69%
8. Directorate of Economic Development | 6439408 | 0 | 13439408 | 0 | 0 | 482243.85 | 482243.85 | 1229889.64 | 0 | 4031245.6 | 0 | 848371.56 | 166417.76 | 2329261.02 | 96956.14 | 0 | 166417.76 | 0 | 166417.76 | 0 | 166417.76 | 0 | 166417.76 | 0 | 166417.76 | 0 | 0 | 484042.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8921011.67 | 8921011.67 | 4518396.33 | 4518396.33 | 66.38% | 66.38%
9. Directorate of Health & Public Safety | 176266 | 0 | 277788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29930.28 | 29930.28 | 0 | 0 | 0 | 29930.28 | 0 | 29930.28 | 0 | 29930.28 | 0 | 29930.28 | 0 | 29930.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29930.28 | 29930.28 | 247857.72 | 247857.72 | 10.77% | 10.77%
10. Directorate of Community Services | 4658884 | 0 | 5103534 | 1125060 | 1125060 | 1252201.6 | 1252201.6 | 257920.5 | 0 | 5437.53 | 0 | 0 | 0 | 52380 | 52380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6545.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2692999.63 | 2692999.63 | 2410534.37 | 2410534.37 | 52.77% | 52.77%
| 210864835 | 0 | 288437823 | 4163028.02 | 4177232.69 | 21850241.81 | 21850241.81 | 18065136.62 | 88508.93 | 24791738.86 | 113527.16 | 19656962.56 | 4129508 | 25116971.43 | 4823124.61 | 0 | 4129508 | 0 | 4129508 | 0 | 4129508 | 0 | 4129508 | 0 | 4129508 | 0 | 0 | 667300.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113644079.3 | 114099305.01 | 174793743.7 | 174338517.99 | 39.56% | 39.4%
| 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [29 empty] | 0 |  | 0 |  | #DIV/0!
| #VALUE! |  | 0
KEY OBJECTIVES | #VALUE!
#VALUE!
1.Municipal Transformation and Organisational Development | #VALUE!
2.Service Delivery and Basic Infrastructure | #VALUE!
3.Local Economic Development | #VALUE!
4.Municipal Financial Viability and Management | #VALUE!
5.Good Governance and public Participation | #VALUE!
TOTAL | #VALUE!
TOTAL | #VALUE!
#VALUE!
1.Municipal Transformation and Organisational Development | #VALUE!
2.Service Delivery and Basic Infrastructure | #VALUE!
3.Local Economic Development | #VALUE!
4.Municipal Financial Viability and Management | #VALUE!
5.Good Governance and public Participation | #VALUE!
#VALUE!
PER SERVICE USDG
SERVICE | 2013/2014 Opex Budget | 2013/2014 Roll- Over Adj Opex Budget | 201314 Conditional Grants rollover Adjustment budget | Jul 13 | VAT | Aug 13 | VAT | Sept 13 | VAT | Oct 13 | VAT | Nov 13 | VAT | Dec 13 | VAT | Jan 14 | VAT | Feb 14 | VAT | Mar 14 | VAT | Apr 14 | VAT | May 14 | VAT | Jun 14 | VAT | COMMITMENTS | [9 empty] | 2013/2014 EXPENDITURE TO DATE (VENUS) | 2013/2014 EXPENDITURE TO DATE (VENUS) VAT | 2013/2014 AVAILABLE BUDGET | 2013/2014 AVAILABLE BUDGET VAT | % EXPENDITURE VS BUDGET VAT | % EXPENDITURE VS BUDGET
Cleansing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [17 empty] | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0% | 0%
Environmental Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [17 empty] | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0% | 0%
Housing | 0 | 0 | 1350000 | 0 | 0 | 126815.49 | 126815.49 | 253447 |  | 0 | [17 empty] | 0 | [9 empty] | 966331.43 | 1017594.96 | 383668.57 | 332405.04 | #DIV/0! | #DIV/0!
Land Administration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [17 empty] | 0 | [9 empty] | 0 |  | 0 | 0 | 0% | 0%
LED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [17 empty] | 0 | [9 empty] | 0 |  | 0 | 0 | 0% | 0%
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [17 empty] | 0 | [9 empty] | 0 |  | 0 | 0 | 0% | 0%
Planning & Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [17 empty] | 0 | [9 empty] | 0 |  | 0 | 0 | 0% | 0%
Public Safety | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [17 empty] | 0 | [9 empty] | 0 |  | 0 | 0 | 0% | 0%
Roads | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [17 empty] | 0 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
EPMO | 0 | 0 | 30859500 | 1900290.37 | 1900290.37 | 1814948.97 | 1814948.97 | 2373811.44 |  | 2361297.55 | [17 empty] | 102169.2 | [9 empty] | 13416352.19 | 13599329.46 | 17443147.81 | 17260170.54 | #DIV/0! | #DIV/0!
Transport Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [17 empty] | 0 | [9 empty] | 0 |  | 0 | 0 | 0% | 0%
Water | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [17 empty] | 0 | [9 empty] | 0 |  | 0 | 0 | 0% | 0%
0
TOTAL PER SERVICE USDG | 0 | 0 | 32209500 | 1900290.37 | 1900290.37 | 1941764.46 | 1941764.46 | 2627258.44 | 0 | 2361297.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102169.2 | [9 empty] | 14382683.62 | 14616924.42 | 17826816.38 | 17592575.58 | 45.38% | 44.65%
|  | 0 |  | -37000 |  | 0 |  | 0 |  | 247500 |  | -2460313.7 |  | -2808259.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [9 empty] | 494000 |  | #VALUE!

## Sheet1
667025500 |  | 679010100
31264500 |  | 32147900
698290000 |  | 711158000
698290000 |  | 722958000
0 |  | 11800000
| 2555 | 4088
| 7670 | 6132