## 2014-2017 Projects
ANNEXURE "E"
BUFFALO CITY METROPOLITAN MUNICIPALITY
CAPITAL EXPENDITURE REPORT AS AT 30 SEPTEMBER 2014
Directorate | Cost centre name | C5C | USDG Service | Cost Centre No. |  |  |  | A5 | Service | V1 | V1 | V1 | VT | VT | VT | VT | VT | VT | 34a & 34b | New Asset | Renewal | A9 | Asset Sub Class- SA36 | KPA'S | Ward No. | Project Name | Funding Source | 2013/2014 Approved Budget | Adjustment | 2013/2014 Rollover Adjustment Budget | Adjustments | 2013/14 Conditional Grants Rollover Adjustment Budget | Mid-Year Adjustments | 2013/2014 Mid-Year Adjusted Budget | Savings | 2014/2015 Approved Capital Budget | Adjustment | 2014/2015 Rollover Adjustment Budget | July 2014 | Vat | July 2014 (VAT incl) | August 2014 | Vat | August 2014 (VAT incl) | September 2014 | Vat | September 2014 (VAT incl) | October 2014 | Vat | October 2014 (VAT incl) | November 2014 | Vat | November 2014 (VAT incl) | December 2014 | Vat | December 2014 (VAT incl) | January 2015 | Vat | January 2015 (VAT incl) | February 2015 | Vat | February 2015 (VAT incl) | March 2015 | Vat | March 2015 (VAT incl) | April 2015 | Vat | April 2015 (VAT incl) | May 2015 | Vat | May 2015 (VAT incl) | June 2015 | Vat | June 2015 (VAT incl) | Commitments as per Venus | YTD Expenditure | YTD Expenditure (VAT incl) | Commitments (Outstanding invoices for work done not yet paid) | Available Budget | Available Budget ( Budget -Expenditure including VAT) | % Expenditue | % Expenditue including VAT) | Comments | 2015/2016 Draft Capital Budget | 2016/2017 Draft Capital Budget | 2017/2018 Draft Capital Budget | 2018/2019 Draft Capital Budget | July Expenditure | July Expenditure(VAT inc.) | August Expenditure | August Expenditure ( VAT inc.) | September Expenditure | Vat | September Expenditure (VAT inc.) | 1st Quarter Expenditure (Exc. VAT) | 1st Quarter Expenditure (incl. VAT) | October Expenditure | Vat | October Expenditure (VAT inc.) | November Expenditure | Vat | November Expenditure (VAT inc.) | December Expenditure | Vat | December Expenditure (VAT inc.) | January Expenditure | January Expenditure (VAT inc.) | February Expenditure | February Expenditure (VAT inc.) | March Expenditure | March Expenditure (VAT inc.) | April Expenditure | April Expenditure (VAT inc.) | May Expenditure | May Expenditure ( VAT inc.) | June Expenditure | June Expenditure ( VAT inc.) | Commitments as per Venus | YTD Expenditure | YTD Expenditure ( VAT inc.) | Commitments (Outstanding invoices for work done not yet paid) | Available Budget | Available Budget ( Budget -Expenditure including VAT) | % Expenditue | % Expenditue including VAT) | 2017/2018 Draft Capital Budget | 2018/2019 Draft Capital Budget | 2017/2018 Draft Capital Budget | Comments
EXECUTIVE SUPPORT SERVICES | [25 empty] | DIRECTORATE OF EXECUTIVE SUPPORT SERVICES
Executive Support Services | Office of the Director of Executive Support Services | 1.1 - Office of The Director of Executive Support |  | 105005 | 4 | 01 | 1501 | Executive and council | Support Services | 4 | 01 |  | 05 | 01 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA5 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Loudhailers have been procured and awaiting for an invoice from service provider. Expenditure will reflect mid October 2014 | 500000 | 500000
Executive Support Services | Office of the Director of Executive Support Services | 4.4 - Asset Risk & Financial Services |  | 105005 | 5 | 05 | 1518 | Budget and treasury | Support Services |  |  |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of Laptop - LT Sikhinzi - A13/116 | Own Funds | [10 empty] | 13000 | [8 empty] | 0 | [28 empty] | 0 | 0 |  | 13000 | 13000 | 0% | 0%
Executive Support Services | Office of the Director of Executive Support Services | 1.1 - Office of The Director of Executive Support |  | 105005 | 6 | 01 | 1501 | Executive and council | Support Services |  |  |  | 05 | 01 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other assets |  |  | All Wards | Office Furniture and Equipment (Councillors) | Own Funds c/o | [9 empty] | 1284326 | 1284326 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1284326 | 1284326 | 0% | 0% | Tender process will commence after office accommodation is finalised.
Executive Support Services | Office of the Director of Executive Support Services | 1.1 - Office of The Director of Executive Support |  | 105005 | 6 | 01 | 1502 | Executive and council | Support Services |  |  |  | 05 | 01 | 01 | 01 | 271 | 002 | New-270 | Yes |  | Other assets |  |  | All Wards | Back up Generator | Own Funds c/o | [9 empty] | 1489573 | 1489573 | [5 empty] | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 1489573 | 1489573 | 0% | 0% | Service Level Agreement forwarded for signature. Meeting planned with the contractor to start implementation of the project before end of October 2014.
Executive Support Services | Office of the Director of Executive Support Services | 1.1 - Office of The Director of Executive Support |  | 105005 | 6 | 01 | 1503 | Executive and council | Support Services |  |  |  | 05 | 01 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other assets |  |  | All Wards | Councillors Office Accomodation | Own Funds c/o | [9 empty] | 2996498 | 2996498 | [5 empty] | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 2996498 | 2996498 | 0% | 0% | The specifications is being finalised for submission to initiate tender processes.
Executive Support Services | Counsillors | 4.4 - Asset Risk & Financial Services |  | 105012 | 5 | 05 | 1504 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Asset Replacements - Insurance | Own Funds |  |  |  |  | 0 |  | 0 |  |  | 14000 | 14000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 7619 | 0 | 0 |  | 14000 | 14000 | 0% | 0% | New Laptop replaced and received by Cllr Green
Executive Support Services | Development Co-Oeration | 1.11 - Development Co-Operation |  | 120005 | 6 | 83 | 1501 | Executive and council | Housing |  |  |  | 05 | 01 | 01 | 01 | 312 | 002 | New-312 | Yes |  | Other assets |  |  |  | Garcia Flats | Leiden c/o | [9 empty] | 458860 | 458860 | [5 empty] | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 458860 | 458860 | 0% | 0% | Project management unit is awaiting for service provider to submit a quote.
Executive Support Services | Research Policy & Knowledge Management Unit | 4.4 - Asset Risk & Financial Services |  | 130005 | 5 | 05 | 1514 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 55000 | 55000 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 55000 | 55000 | 0% | 0% | Informal Tender Re: Replacement of Video Equipment re-advertised on 9 September 2014, and closed on 16 September 2014.Re-advertised tender again non-resposive, requiring further re-advertisment of the Informal Tender. Awaiting feedback from SCM with respect to the report submitted in this regard before confirming re-advertisement of the Informal tender. Digital Projector in process of being procured by IT.
[26 empty] | TOTAL: EXECUTIVE SUPPORT SERVICES |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 500000 | 6298257 | 6811257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7619 | 0 | 0 | 0 | 6811257 | 6811257 | 0% | 0% |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0
[32 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
MUNICIPAL MANAGER'S OFFICE | [25 empty] | MUNICIPAL MANAGERS 'OFFICE | [5 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Municipal Manager's Office | Municipal Manager's Office | 2.1 - Office of The Municipal Manager & Support Services |  | 205005 | 4 | 67 | 1501 | Executive and council | Support Services | 4 | 67 |  | 05 | 02 | 01 | 01 | 320 | 001 | New-320 | Yes |  | Other | Other | KPA2 | All Wards | Neighbourhood Development Partnership | NDPG | 10000000 |  | 10000000 |  | 10000000 | -10000000 | 0 |  | 5000000 |  | 5000000 | 0 | 0 | 0 |  |  | 0 | 107792 | 0 | 107792 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3002726.36 | 107792 | 107792 |  | 4892208 | 4892208 | 2.156% | 2.156% | Obtaining quotations for road refurbishment from Annual Contractors lengthy. NDPG department at NT will review quotations and provide BCMM confirmation and permission to proceedto implement grant funding. | 16878000 | 17744000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 10000000 | 10000000 | 0% | 0%
Municipal Manager's Office | Municipal Manager's Office | 2.1 - Office of The Municipal Manager & Support Services |  | 205005 | 4 | 01 | 1502 | Executive and council | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Furniture | KPA5 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds | 250000 |  | 250000 |  | 250000 |  | 250000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Procurement process underway | 500000 | 500000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 171173.4 | 0 | 0 |  | 250000 | 250000 | 0% | 0%
Municipal Manager's Office | Municipal Manager's Office | 2.1 - Office of The Municipal Manager & Support Services | Support Services | 205005 | 4 | 36 | 1501 | Executive and council | Support Services | 4 | 36 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other |  | KPA2 | All Wards | Furniture and Equipment - Project Management Office | USDG |  |  | 0 | 2500000 | 2500000 |  | 2500000 |  | 1500000 |  | 1500000 | 0 | 0 | 0 | 170805 | 23912.7 | 194717.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 170805 | 194717.7 |  | 1329195 | 1305282.3 | 11.39% | 12.98% | Vehicles and office furniture are being procured. Awating delivery of Laptops for new EPMO staff. | 1500000 | 1500000 | [19 empty] | 0 | [14 empty] | 0 |  | 2500000 | 2500000 | 0% | 0%
Municipal Manager's Office | Internal Audit | 4.4 - Asset Risk & Financial Services |  | 215005 | 5 | 05 | 1515 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 8500 | 8500 | [5 empty] | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 8500 | 8500 | 0% | 0%
[26 empty] | TOTAL: MUNICIPAL MANAGERS 'OFFICE |  | 10250000 | 0 | 10250000 | 2500000 | 12750000 | -10000000 | 2750000 | 0 | 7000000 | 8500 | 7008500 | 0 | 0 | 0 | 170805 | 23912.7 | 194717.7 | 107792 | 0 | 107792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3002726.36 | 278597 | 302509.7 | 0 | 6729903 | 6705990.3 | 3.975% | 4.316% |  | 18878000 | 19744000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171173.4 | 0 | 0 | 0 | 12750000 | 12750000 | 0% | 0% |  |  | 0
[32 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
HUMAN SETTLEMENTS | [25 empty] | DIRECTORATE OF HUMAN SETTLEMENTS | [5 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Human Settlements |  | 3.2 - Office of The Chief Operations Officer |  | 250005 | 4 | 01 | 1503 | Housing | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other | Housing | KPA2 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 | 0 | 0 | 0 | 14706.1 |  | 14706.1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 33098.3 | 14706.1 | 14706.1 |  | 485293.9 | 485293.9 | 2.941% | 2.941% | Procurement stage | 500000 | 500000
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 01 | 1504 | Housing | Housing | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other | Housing | KPA2 |  | Beneficiary Administration (Procure GPS Devices) | Own Funds | 200000 |  | 200000 |  | 200000 | 200000 | 400000 |  | 100000 |  | 100000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 100000 | 100000 | 0% | 0% | Informal tender for the procurement of the devices has been advertised, closing on 10 October 2014 | 150000 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 01 | 1504 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other | Housing | KPA3 |  | Beneficiary Administration (Procure GPS Devices) | Own Funds c/o | [9 empty] | 102199 | 102199 | 0 |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 102199 | 102199 | 0% | 0% | Informal tender for the procurement of the devices has been advertised, closing on 10 October 2014
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 01 | 1505 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other | Housing | KPA4 |  | Refurbishment of all Rental Stock | Own Funds c/o | [9 empty] | 200000 | 200000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 200000 | 200000 | 0% | 0% | The project is in process. Service provider as been appointed with the help of Building Maintenance.
Human Settlements | DVRI | 3.1 - Mdantsane Urban Renewal Unit |  | 250005 | 4 | 35 | 1501 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | Reeston MPCC - DVRI | HSDG-(MPCC) | 2100000 |  | 2100000 |  | 2100000 |  | 2100000 |  | 10068500 | -10068500 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 13068500 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 33675 |  | 33675 | 53800 |  | 53800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 87475 | 87475 |  | 2012525 | 2012525 | 4.165% | 4.165%
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1502 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3: Stage 2 | HSDG | 11684600 |  | 11684600 |  | 11684600 |  | 11684600 |  | 7000000 |  | 7000000 | 0 | 0 | 0 |  |  | 0 | 1519732.96 |  | 1519732.96 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3175774.64 | 1519732.96 | 1519732.96 |  | 5480267.04 | 5480267.04 | 21.71% | 21.71% | The 951 serviced sites that were implemented by the Annual Contractors will be completed end October 2014. Phase 2 of the project (1579) is on procurement stage. | 15000000 | 20000000 | 10000000 | 10000000 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8771929.82 | 0 | 0 |  | 11684600 | 11684600 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1502 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA3 | 13 | Reeston Phase 3: Stage 2 - P1 & P3 | HSDG c/o | [9 empty] | 5104919 | 5104919 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 5104919 | 5104919 | 0% | 0% | The 951 serviced sites that were implemented by the Annual Contractors will be completed end October 2014. Phase 2 of the project (1579) is on procurement stage.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1503 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 3 | HSDG | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 7000000 |  | 7000000 | 2245000.06 | 0 | 2245000.06 | 3355847.36 |  | 3355847.36 | 492390.71 |  | 492390.71 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 6093238.13 | 6093238.13 |  | 906761.87 | 906761.87 | 87.05% | 87.05% | The contractor is on site, progressing very well and is anticipated to hand over 131 serviced sites in October 2014. | 15000000 | 12000000 | 10000000 | 7590000 |  | 0 | 48240 | 48240 |  |  | 0 | 48240 | 48240 |  |  | 0 |  |  | 0 | 18152.9 |  | 18152.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 66392.9 | 66392.9 |  | 9933607.1 | 9933607.1 | 0.6639% | 0.6639% |  |  |  |  | 44000000
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1503 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 3 - P1 & P3 | HSDG c/o | [9 empty] | 6922271 | 6922271 |  |  | 0 |  |  | 0 | 21421.49 |  | 21421.49 | [28 empty] | 21421.49 | 21421.49 |  | 6900849.51 | 6900849.51 | 0.3095% | 0.3095% | The contractor is on site, progressing very well and is anticipated to hand over 131 serviced sites in October 2014.
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1502 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 2 | USDG | 6815400 |  | 6815400 |  | 6815400 | 5000000 | 11815400 |  | 2970400 | 1306712 | 4277112 | 0 | 0 | 0 |  |  | 0 | 183604.45 | 25704.63 | 209309.08 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 183604.45 | 209309.08 |  | 4093507.55 | 4067802.92 | 4.293% | 4.894% | The 951 serviced sites that were implemented by the Annual Contractors will be completed end October 2014. Phase 2 of the project (1579) is on procurement stage. | 5000000 | 10000000 |  |  |  | 0 | 4119.6 | 4119.6 | -4119.6 | 0 | -4119.6 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3614075.5 | 0 | 0 |  | 6815400 | 6815400 | 0% | 0% | 55265000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1551 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 3 | USDG |  |  |  |  | 0 |  | 0 |  | 2000000 |  | 2000000 | 2000000 | 280000 | 2280000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 2000000 | 2280000 |  | 0 | -280000 | 100% | 114% | The contractor is on site, progressing very well and is anticipated to hand over 131 serviced sites in October 2014. | 5000000 | 10000000 | [44 empty] | 17000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1503 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam Ikhwezi Block 1 | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Project on design stage. | 5900000 | 13000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 175438.6 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1504 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam Ikhwezi Block 2 | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Project on design stage. | 200000 | 200000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1505 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam North Kanana | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Project on design stage. | 200000 | 200000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1506 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 36 | Dimbaza Destitute 27 Units | USDG | 2500000 |  | 2500000 | -2300000 | 200000 |  | 200000 |  | 200000 |  | 200000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0% | Work has been suspended due to land claim by the community of Amahleke Tribal Authority | 0 |  |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 169290 | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1507 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 45 | Ilitha North 177 Units | USDG | 700000 |  | 700000 |  | 700000 |  | 700000 |  | 1500000 |  | 1500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1500000 | 1500000 | 0% | 0% | This project is in process, designs have been submitted to service departments for approval | 4000000 | 6800000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 700000 | 700000 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1508 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | DVRI Pilot Project (Mekeni, Haven Hills, Competition Site) | USDG | 2500000 |  | 2500000 | 1000000 | 3500000 |  | 3500000 |  | 775000 |  | 775000 | 0 | 0 | 0 | 23366.2 | 3271.27 | 26637.47 | 45833.96 | 6416.75 | 52250.71 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 69200.16 | 78888.18 |  | 705799.84 | 696111.82 | 8.929% | 10.18% | The contractor is on site, progressing very slow with the implementation of both internal services and top structures. | 0 |  |  |  |  | 0 |  | 0 | 81590 | 11422.6 | 93012.6 | 81590 | 93012.6 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 81590 | 93012.6 |  | 3418410 | 3406987.4 | 2.331% | 2.658%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1506 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | DVRI Pilot Project (Mekeni, Haven Hills, Competition Site) P1 & P3 | HSDG c/o | [9 empty] | 5687069 | 5687069 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 5687069 | 5687069 | 0% | 0% | The contractor is on site, progressing very slow with the implementation of both internal services and top structures.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1505 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 15 | Duncan Village Proper | HSDG | 350000 |  | 350000 |  | 350000 |  | 350000 |  | 700000 |  | 700000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 700000 | 700000 | 0% | 0% | The project is at design stage. | 1300000 | 3300000 | 10000000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 350000 | 350000 | 0% | 0%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1501 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 15 | Duncan Village Proper | HSDG c/o | [9 empty] | 350000 | 350000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 350000 | 350000 | 0% | 0% | The project is at design stage.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1506 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | C Section and Triangular Site | HSDG | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 700000 |  | 700000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 700000 | 700000 | 0% | 0% | The project is at design stage. | 1300000 | 2000000 | 10000000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 3707.64 |  | 3707.64 | -3707.64 |  | -3707.64 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1504 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | C Section and Triangular Site P1-P3 | HSDG c/o | [9 empty] | 770420 | 770420 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 770420 | 770420 | 0% | 0% | The project is at design stage.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1507 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | D Hostel | HSDG | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 700000 |  | 700000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 700000 | 700000 | 0% | 0% | The project is at design stage. | 1300000 | 2000000 | 10000000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1505 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | D Hostel P1 & P3 | HSDG c/o | [9 empty] | 600000 | 600000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 600000 | 600000 | 0% | 0% | The project is at design stage.
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1509 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 23 | Mdantsane Zone 18 CC Phase 2 | USDG | 3000000 |  | 3000000 |  | 3000000 | -1000000 | 2000000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | Contractor appointed for 500 internal services. The 1000 Units part of the project is at design stage. | 8500000 | 18500000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 382.04 | 382.04 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 382.04 |  | 3000000 | 2999617.96 | 0% | 0.01273% | 16500000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1510 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1 | Block Yard TRA | USDG | 500000 |  | 500000 | 1831500 | 2331500 |  | 2331500 |  | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Annual Contractors are on site busy with the construction of roads. | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 295.58 | 295.58 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 175180.32 | 0 | 295.58 |  | 2331500 | 2331204.42 | 0% | 0.01268%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1508 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 1 | Block Yard TRA | HSDG c/o | [9 empty] | 608785 | 608785 |  |  | 0 |  |  | 0 |  |  | 0 | [27 empty] | 534021.93 | 0 | 0 |  | 608785 | 608785 | 0% | 0% | Annual Contractors are on site busy with the construction of roads.
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1511 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 19 | Second Creek (Turn Key) | USDG | 8000000 |  | 8000000 | 1800000 | 9800000 |  | 9800000 |  | 100000 |  | 100000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 100000 | 100000 | 0% | 0% | Project is at completion stage, awaiting final claims from the service provider. | 0 | 0 |  |  |  | 0 | 149203.55 | 170092.05 | 761056.68 | 106547.93 | 867604.61 | 910260.23 | 1037696.66 |  |  | 0 | 340800.89 | 47712.12 | 388513.01 | 751461.26 |  | 751461.26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2002522.38 | 2177670.93 |  | 7797477.62 | 7622329.07 | 20.43% | 22.22%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1512 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 9 | Amalinda Co- Op | USDG | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 2200000 | -180000 | 2020000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2020000 | 2020000 | 0% | 0% | Project on design stage. | 4800000 | 100000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0% | 6000000
Human Settlements |  | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1513 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 |  | Amalinda Fairlands | USDG | 0 |  | 0 |  | 0 |  | 0 |  | 300000 |  | 300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 300000 | 300000 | 0% | 0% | Project at planning stage. | 300000 | 500000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1514 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 48,12,21,11,17,11,20 | Cluster 1 (Masibambane; Masibulele; Velwano; Ilinge and Dacawa) | USDG | 3500000 |  | 3500000 |  | 3500000 |  | 3500000 |  | 15000000 | -1306712 | 13693288 | 92322.33 | 12925.13 | 105247.46 | 2636185.49 | 335267.91 | 2971453.4 | 4404470.01 | 555616.39 | 4960086.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 7132977.83 | 8036787.26 |  | 6560310.17 | 5656500.74 | 52.09% | 58.69% | The contractor is on site progressing with internal services and top structures. | 19000000 | 76000000 |  |  |  | 0 | 4737.54 | 4737.54 | -4737.54 | 0 | -4737.54 | 0 | 0 |  |  | 0 |  |  | 0 | 9997.5 | 1399.65 | 11397.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 9997.5 | 11397.15 |  | 3490002.5 | 3488602.85 | 0.2856% | 0.3256% | 73047792 |  |  |  | 113500000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1515 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 17,14, | Cluster 2 (Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe) | USDG | 3500000 |  | 3500000 |  | 3500000 | -2500000 | 1000000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | Contrator on site busy with site establishment to commence with the construction of services and top structures | 10000000 | 36464685 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | -3707.64 |  | -3707.64 | 3707.64 |  | 3707.64 | 2574.75 | 360.46 | 2935.21 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2574.75 | 2935.21 |  | 3497425.25 | 3497064.79 | 0.07356% | 0.08386% | 46000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1516 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 10 | Cluster 3 (Fynbos Informal 1, Fynbos Informal 2, Ndancama) P1 & P3 | USDG | 5524440 |  | 5524440 | -1300000 | 4224440 | -2000000 | 2224440 |  | 7775000 |  | 7775000 | 0 | 0 | 0 |  |  | 0 | 825710.32 | 115599.44 | 941309.76 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 825710.32 | 941309.76 |  | 6949289.68 | 6833690.24 | 10.62% | 12.11% | Project has just been awarded to commence with the works. | 25350000 | 20100000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 417514 | 58451.96 | 475965.96 | 168266.6 | 23557.32 | 191823.92 | 13864.37 | 1941.01 | 15805.38 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 599644.97 | 683595.26 |  | 3624795.03 | 3540844.74 | 14.19% | 16.18% | 68000000
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1508 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 9 | Braelyn ext 10 | HSDG | 500000 |  | 500000 |  | 500000 | -500000 | 0 |  | 2000000 | 0 | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Project on pre-planning stage for the approval of general plans. | 10000000 | 20000000 | 8000000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1509 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 9 | Braelyn ext 10 - P1 & P3 | HSDG c/o | [9 empty] | 118812 | 118812 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 118812 | 118812 | 0% | 0% | Project on pre-planning stage for the approval of general plans.
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1517 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 31 | Sunny South | USDG | 10000000 |  | 10000000 | 4000000 | 14000000 |  | 14000000 |  | 2000000 | 180000 | 2180000 | 82100.88 | 11494.12 | 93595 | 126676.4 | 17734.7 | 144411.1 | 1347611.08 | 11494.12 | 1359105.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1556388.36 | 1597111.3 |  | 623611.64 | 582888.7 | 71.39% | 73.26% | Contractor is on site constructing road and water services. The project is anticipated to be completed by end of December. | 100000 | 0 |  |  |  | 0 |  | 0 | 312750 |  | 312750 | 312750 | 312750 | 34750 | 43785 | 78535 | 793348.34 | 107369.96 | 900718.3 | 439562.11 | 61538.7 | 501100.81 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1580410.45 | 1793104.11 |  | 12419589.55 | 12206895.89 | 11.29% | 12.81%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1518 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 43 | Tyutyu Phase 3 | USDG | 200000 |  | 200000 | 0 | 200000 |  | 200000 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 100000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1519 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 46 | Westbank Restitution | USDG | 2000000 |  | 2000000 | 0 | 2000000 |  | 2000000 |  | 3547208 |  | 3547208 | 0 | 0 | 0 | 1372549.25 | 192156.89 | 1564706.14 | 409895.51 | 57385.38 | 467280.89 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1782444.76 | 2031987.03 |  | 1764763.24 | 1515220.97 | 50.25% | 57.28% | Project on bulk implementation stage. | 16000000 | 15000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | 140000000 |  | R70mill from 15/16
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1507 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | Housing Needs Database and Accreditation (Capacity Enhancement) | HSDG c/o | [9 empty] | 273172 | 273172 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 273172 | 273172 | 0% | 0% | Budget reserved for procurement of office requirements for additional person to be acquired through the Capacity Enhancement Grant, much dependant on availability of additional office space.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1509 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | Housing Needs Database and Accreditation (Capacity Enhancement) | HSDG | 390000 |  | 390000 |  | 390000 |  | 390000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Budget reserved for procurement of office requirements for additional person to be acquired through the Capacity Enhancement Grant, much dependant on availability of additional office space. | 1000000 |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 60641.08 |  | 60641.08 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 60641.08 | 60641.08 |  | 329358.92 | 329358.92 | 15.55% | 15.55%
[26 empty] | TOTAL : HUMAN SETTLEMENTS |  | 75564440 | 0 | 75564440 | 5931500 | 81495940 | -800000 | 80695940 | 0 | 90136108 | 10669147 | 100805255 | 4419423.27 | 304419.25 | 4723842.52 | 7529330.8 | 548430.77 | 8077761.57 | 9250670.49 | 772216.71 | 10022887.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3742894.87 | 21199424.56 | 22824491.29 | 0 | 79605830.44 | 77980763.71 | 21.03% | 22.64% |  | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 206300.69 | 227189.19 | 1146539.54 | 117970.53 | 1264510.07 | 1352840.23 | 1491699.26 | 452264 | 102236.96 | 554500.96 | 1396731.91 | 179317.02 | 1576048.93 | 1289412.89 | 65239.82 | 1354652.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12905914.24 | 4491249.03 | 4976901.86 | 0 | 77004690.97 | 76519038.14 | 5.511% | 6.107% |  |  | 0
[32 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF FINANCIAL SERVICES | [25 empty] | DIRECTORATE OF FINANCIAL SERVICES | [5 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Financial Services |  | 4.1 - Office of The Director of Finance |  | 305005 | 4 | 01 | 1505 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 | 19074.32 | 0 | 19074.32 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 19074.32 | 19074.32 |  | 480925.68 | 480925.68 | 3.815% | 3.815% | The department will be procuring furniture as per requests during the year. | 500000 | 500000
Financial Services |  | 4.1 - Office of The Director of Finance |  | 305005 | 6 | 01 | 1506 | Budget and treasury | Support Services |  |  |  | 05 | 03 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Office Furniture and Equipment | Own Funds c/o | [9 empty] | 431902 | 431902 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 431902 | 431902 | 0% | 0%
Financial Services |  | 4.9 - Consolidated Billing & Miscellaneous Revenue Office |  | 330010 | 4 | 01 | 1507 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Partitioning of Offices for SCM | Own Funds |  |  |  |  | 0 |  | 0 |  | 350000 |  | 350000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 350000 | 350000 | 0% | 0% | Informal tenders for the project will be out in September 2014 and spending will start reflecting in October/November 2014 | 0 | 0
Financial Services | Consolidated Billing and Miscellaneous Revenue Office | 4.4 - Asset Risk & Financial Services |  | 330010 | 5 | 05 | 1519 | Budget and treasury | Support Services |  |  |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Laptop S. Peter - A14/15 | Own Funds | [10 empty] | 18500 | [8 empty] | 0 | [28 empty] | 0 | 0 |  | 18500 | 18500 | 0% | 0%
Financial Services | Debtors Management Office | 4.4 - Asset Risk & Financial Services |  | 330015 | 5 | 05 | 1517 | Budget and treasury | Support Services | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Laptop - Z. Mjali - A14/12 | Own Funds | [10 empty] | 13000 | 0 |  | 0 |  |  | 0 |  |  | 0 | [27 empty] | 10251 | 0 | 0 |  | 13000 | 13000 | 0% | 0%
Financial Services |  | 4.11 - Customer Care Office |  | 330020 | 4 | 01 | 1508 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 260 | 001 | New-260 | Yes |  |  |  | KPA4 | All Wards | CCTV Cameras for BCMM Cash Offices | Own Funds |  |  |  |  | 0 |  | 0 |  | 1500000 |  | 1500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1500000 | 1500000 | 0% | 0% | Please note that this project is not handled by Counter Services but under Law Enforcement. | 1500000
[26 empty] | TOTAL : FINANCIAL SERVICES |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 2350000 | 431902 | 2813402 | 19074.32 | 0 | 19074.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10251 | 19074.32 | 19074.32 | 0 | 2794327.68 | 2794327.68 | 0.678% | 0.678% |  | 2000000 | 500000 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0
[32 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF CORPORATE SERVICES | [25 empty] | DIRECTORATE OF CORPORATE SERVICES | [5 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Corporate services |  | 5.1 - Office of The Director of Corporate Services |  | 405005 | 4 | 01 | 1509 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA1 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Tender for office furniture and equipment will be considered at BEC scheduled for 15 September 2014. | 500000 | 500000
Corporate services |  | 4.4 - Asset Risk & Financial Services |  | 415010 | 5 | 05 | 1516 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 150000 | 150000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 150000 | 150000 | 0% | 0% | The process of procuring a new vehicle is at BEC
Corporate services |  | 5.4 - Auxilliary & Telecommunication Support |  | 415010 | 6 | 01 | 1510 | Corporate Services | Support Services |  |  |  | 05 | 04 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Vehicle | Own Funds c/o | [9 empty] | 150000 | 150000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 150000 | 150000 | 0% | 0% | The process of procuring a new vehicle is at BEC
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1510 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Procurement of Pre-Payment Vending Machines | Own Funds | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 | 168270 |  | 168270 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 168270 | 168270 |  | 331730 | 331730 | 33.65% | 33.65% | The delivery have delayed and expected by end of september 2014. | 0 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 23472.6 |  | 23472.6 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23472.6 | 23472.6 |  | 476527.4 | 476527.4 | 4.695% | 4.695%
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1511 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Systems Intergration - (Process Implementation) | Own Funds | 5250000 | -250000 | 5000000 |  | 5000000 |  | 5000000 |  | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | The procurement process shall commence for the period of 3 years for the total amount of R25 million in November 2014. | 12000000 | 12000000 |  |  |  | 0 |  | 0 | 581900 |  | 581900 | 581900 | 581900 | 1191020 |  | 1191020 | 574780.65 |  | 574780.65 | 553836.65 |  | 553836.65 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1548136.26 | 2901537.3 | 2901537.3 |  | 2098462.7 | 2098462.7 | 58.03% | 58.03%
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1512 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Security Software | Own Funds |  |  |  |  | 0 |  | 0 |  | 2400000 |  | 2400000 | 0 | 0 | 0 |  |  | 0 | 2135.27 |  | 2135.27 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 2135.27 | 2135.27 |  | 2397864.73 | 2397864.73 | 0.08897% | 0.08897% | In the tender process, expenditure is expected in November / December 2014. CE 183 | 0 | 0
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1513 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Infrastructure Network Upgrade | Own Funds | 0 |  | 0 |  | 0 |  | 0 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | In the tender process, expenditure is expected in November / December 2014. CE 188 | 4000000 | 4000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 6 | 01 | 1507 | Corporate Services | Support Services |  |  |  | 05 | 04 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Infrastructure Upgrade | Own Funds c/o | [9 empty] | 7154862 | 7154862 |  |  | 0 |  |  | 0 | 362979.88 |  | 362979.88 | [27 empty] | 1598506.04 | 362979.88 | 362979.88 |  | 6791882.12 | 6791882.12 | 5.073% | 5.073% | In the tender process, expenditure is expected in November / December 2014. CE 187
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 6 | 01 | 1508 | Corporate Services | Support Services |  |  |  | 05 | 04 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Duncan Village ICT Centre - DVRI | Own Funds c/o | [9 empty] | 137926 | 137926 |  |  | 0 |  |  | 0 |  |  | 0 | [27 empty] | 114824.56 | 0 | 0 |  | 137926 | 137926 | 0% | 0% | In the tender process, expenditure is expected in December 2014 / January 2015. CE 186
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 6 | 01 | 1509 | Corporate Services | Support Services |  |  |  | 05 | 04 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Systerms - ( Anti Virus) | Own Funds c/o | [9 empty] | 723345 | 723345 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 723345 | 723345 | 0% | 0% | In the tender process, expenditure is expected in December 2014 / January 2015. CE 109
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1514 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Computer Equipment - BCMM | Own Funds | 1000000 |  | 1000000 |  | 1000000 |  | 1000000 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 | 53630.52 |  | 53630.52 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 315324.23 | 53630.52 | 53630.52 |  | 1946369.48 | 1946369.48 | 2.682% | 2.682% | In the tender process, expenditure is expected in November / December 2014. CE 185 | 0 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 491628.54 |  | 491628.54 | 295850.02 |  | 295850.02 | 110520 |  | 110520 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 82826.35 | 897998.56 | 897998.56 |  | 102001.44 | 102001.44 | 89.8% | 89.8%
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1515 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Infrastructure Servers | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | In the tender process, expenditure is expected in November / December 2014. CE 189 | 2000000 | 2000000
Corporate services | Management Information Services | 5.7 - H.R. Administration |  | 420005 | 4 | 28 | 1501 | Corporate Services | Support Services | 4 | 28 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Office Furniture and Equipment and Computers | ISDG | 100000 |  | 100000 |  | 100000 |  | 100000 |  | 100000 |  | 100000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 100000 | 100000 | 0% | 0% | Procure of computers I and other equipment s underway, the expenditure is expected to show by end of October 2014.. IT is assisting with procurement | 100000 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 19673.6 | 2754.3 | 22427.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 65646.91 | 19673.6 | 22427.9 |  | 80326.4 | 77572.1 | 19.67% | 22.43%
Corporate services | H.R. Administration | 5.7 - H.R. Administration |  | 420005 | 4 | 01 | 1518 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Electronic Attandance Control System | Own Funds | 0 |  | 0 |  | 0 |  | 0 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | In the tender process, expenditure is expected in November / December 2014. CE 185 | 1500000 | 1000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Corporate services | H.R. Administration | 4.4 - Asset Risk & Financial Services |  | 420005 | 5 | 05 | 1507 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 8500 | 8500 | [5 empty] | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 8500 | 8500 | 0% | 0%
Corporate services | H.R. Administration | 4.4 - Asset Risk & Financial Services |  | 420005 | 5 | 05 | 1520 | Budget and treasury | Support Services |  |  |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Laptop V. Forosi - A13/78 | Own Funds | [10 empty] | 13000 | [8 empty] | 0 | [28 empty] | 0 | 0 |  | 13000 | 13000 | 0% | 0%
Corporate services | Occupational Risk Mnagement | 5.8 - Occupational Risk Management |  | 420010 | 4 | 01 | 1519 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other assets | Land & Buildings | KPA1 | All Wards | Extensions to Employee Wellness Centre | Own Funds | 0 |  | 0 |  | 0 |  | 0 |  | 2500000 |  | 2500000 | 0 | 0 | 0 |  |  | 0 | 2761.12 |  | 2761.12 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 2761.12 | 2761.12 |  | 2497238.88 | 2497238.88 | 0.1104% | 0.1104% | Tender Evaluation was done at SCM on the 27th of August 2014 . Preliminary Report was signed and delivered to SCM on the 29th August 2014. Report will tabled at BEC schedule for 15 September 2014. | 0 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1516 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Land & Buildings | KPA1 | All Wards | ICT Networks and Communications for Call Centre | Own Funds |  |  |  |  | 0 |  | 0 |  | 800000 |  | 800000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 800000 | 800000 | 0% | 0% | In the tender process, expenditure is expected in November / December 2014. CE 188 | 500000 | 200000
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1517 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Land & Buildings | KPA1 | All Wards | IT Hardware for Call Centre | Own Funds |  |  |  |  | 0 |  | 0 |  | 800000 |  | 800000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 800000 | 800000 | 0% | 0% | In the tender process, expenditure is expected in November / December 2014. CE 188 | 1500000 | 500000
[26 empty] | TOTAL : CORPORATE SERVICES |  | 6850000 | -250000 | 6600000 | 0 | 6600000 | 0 | 6600000 | 0 | 15100000 | 8324633 | 23437633 | 0 | 0 | 0 | 0 | 0 | 0 | 589776.79 | 0 | 589776.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2028654.83 | 589776.79 | 589776.79 | 0 | 22847856.21 | 22847856.21 | 2.516% | 2.516% |  | 22100000 | 20200000 | 0 | 0 | 0 | 0 | 0 | 0 | 581900 | 0 | 581900 | 581900 | 581900 | 1682648.54 | 0 | 1682648.54 | 894103.27 | 0 | 894103.27 | 684030.25 | 2754.3 | 686784.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1696609.52 | 3842682.06 | 3845436.36 | 0 | 2757317.94 | 2754563.64 | 58.22% | 58.26% |  |  | 0
[32 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF ENGINEERING SERVICES | [25 empty] | DIRECTORATE OF ENGINEERING SERVICES | [5 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Engineering Services | Office of the Director of Engineering Services | 6.1 - Office of The Director of Engineering Services |  | 505005 | 4 | 01 | 1520 | Other | Support Services | 4 | 01 |  | 05 | 05 |  |  | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA2 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 133843.34 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | SCM is assisting in preparing specifications | 500000 | 500000
Engineering Services | Scientific Services | 6.9 - Sewerage Admin |  | 510005 | 4 | 01 | 1559 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Water |  | KPA2 | All Wards | Upgrading of Laboratory Infrastructure | Own Funds | [9 empty] | 2000000 | 2000000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Formal tender in process of re-advertisement (85%), informal tender awaiting advertisement 3 Oct 2014 (10%)
Engineering Services | Scientific Services | 6.9 - Sewerage Admin |  | 510005 | 6 | 01 | 1511 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 002 | Renewal-70 |  | Yes | Water |  | KPA2 | All Wards | Upgrading of Laboratory Infrastructure | Own Funds c/o | [9 empty] | 1574513 | 1574513 |  |  | 0 |  |  | 0 |  |  | 0 | [27 empty] | 295591.66 | 0 | 0 |  | 1574513 | 1574513 | 0% | 0% | Submitted invoices not captured (9%), informal tender being evaluated (10%), informal tender awarded (8%), 2 formal tenders in process of re-advertisement (66%), awaiting invoices for payment (16%)
Engineering Services | Sewerage Admin | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1520 | Waste Water Management | Waste Water | 4 | 36 |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Bulk Sanitation Provision - Programme | USDG | 37854000 |  | 37854000 | 20000000 | 57854000 |  | 57854000 |  | 176507892 | -175507892 | 1000000 | 76820 | 0 | 76820 | 555847.54 | 74348.55 | 630196.09 | -138617.26 | 0 | -138617.26 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 494050.28 | 568398.83 |  | 505949.72 | 431601.17 | 49.41% | 56.84% | Projects on going. Annual contractor has been appointed and is implementing project-Multi year ongoing project. | 190000000 | 97000000 |  |  |  | 0 | 3961956.8 | 4516630.75 | 7810659.85 | 1250665.11 | 9061324.96 | 11772616.65 | 13577955.71 | 8848276.78 | 1132017.03 | 9980293.81 | 9756441.29 | 1265741.02 | 11022182.31 | 16134838.1 | 1207170.73 | 17342008.83 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 46512172.82 | 51922440.66 | 625034.64 | 11341827.18 | 5931559.34 | 80.4% | 89.75% | 120000000
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1552 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Waste Water Infrastructure Capacity ( KWT Reg Scheme | USDG | [9 empty] | 54507892 | 22857892 |  |  | 0 |  |  | 0 | 543944.88 | 76152.28 | 620097.16 | [28 empty] | 543944.88 | 620097.16 |  | 22313947.12 | 22237794.84 | 2.38% | 2.713% | Civil Works contract awarded. Mechanical & Electrical Works contract awarded but another bidder appealed the award to preferred bidder.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1553 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Reeston Phase 3 Bulk Services Sewer | USDG | [9 empty] | 50000000 | 50000000 |  |  | 0 | 2978423.71 | 372528.8 | 3350952.51 | 3869608.52 | 481925.25 | 4351533.77 | [28 empty] | 6848032.23 | 7702486.28 |  | 43151967.77 | 42297513.72 | 13.7% | 15.4% | Civil works on going, 45% complete. Mechanical & Electrical Works contract awarded but another bidder appealed the award to preferred bidder.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1554 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Mdantsane Infrastructure- Refurbishment/ Augmentatio n | USDG | [9 empty] | 20000000 | 20000000 |  |  | 0 | 5202755.74 | 663036.59 | 5865792.33 | -2086248.95 | 414183.12 | -1672065.83 | [28 empty] | 3116506.79 | 4193726.5 |  | 16883493.21 | 15806273.5 | 15.58% | 20.97% | Project progressing well, 65% complete.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1555 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Diversion of Amalinda & Wilsonia Effluent | USDG | [9 empty] | 1000000 | 1017458 |  |  | 0 |  |  | 0 | 439435.42 | 61520.96 | 500956.38 | [28 empty] | 439435.42 | 500956.38 |  | 578022.58 | 516501.62 | 43.19% | 49.24% | Phase 1A complete. Design for phase 2 completed-Tunnel option, awaiting for funds to go out to tender.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1556 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Sanitation Backlog Eradication - ( Coastal | USDG | [9 empty] | 40000000 | 40000000 |  |  | 0 | 940264.83 | 153505.26 | 1093770.09 | 3422872.13 | 445761.59 | 3868633.72 | [28 empty] | 4363136.96 | 4962403.81 |  | 35636863.04 | 35037596.19 | 10.91% | 12.41% | 23 consortiums have been appointed, work on going on 5 projects.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1557 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Eastern Beach Sewers | USDG | [9 empty] | 1000000 | 1056888 |  |  | 0 |  |  | 0 | 927094.74 | 129793.26 | 1056888 | [28 empty] | 927094.74 | 1056888 |  | 129793.26 | 0 | 87.72% | 100% | Tenders closed 9 September 2014.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1558 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Sludge Handling & Chlorination Facilities | USDG | [9 empty] | 1000000 | 1729909 |  |  | 0 | 180844.29 | 25318.2 | 206162.49 |  |  | 0 | [28 empty] | 180844.29 | 206162.49 |  | 1549064.71 | 1523746.51 | 10.45% | 11.92% | PSP appointed 95 % complete.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1559 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Ablution Blocks | USDG | [9 empty] | 3000000 | 3949029 | -276650.91 |  | -276650.91 | 101276.44 | 10634.59 | 111911.03 |  |  | 0 | [27 empty] | 312094.43 | -175374.47 | -164739.88 |  | 4124403.47 | 4113768.88 | -4.441% | -4.172% | The Ablution Blocks project on going. Annual contractors have been appointed for provision of Ablution Facilities and fencing
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1560 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Berlin Sewers | USDG | [9 empty] | 5000000 | 5029611 |  |  | 0 | 116918.57 | 16368.59 | 133287.16 | 593257.87 | 83056.1 | 676313.97 | [28 empty] | 710176.44 | 809601.13 |  | 4319434.56 | 4220009.87 | 14.12% | 16.1% | Tender evaluation currently being undertaken.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1568 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes |  |  |  |  | West Bank Restitution Sewer Infrastructure | USDG | [10 empty] | 10000000 | [8 empty] | 0 | [28 empty] | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | Annual contractor to implement.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1569 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes |  |  |  |  | Quinera WWTW | USDG | [10 empty] | 11200000 | [8 empty] | 0 | [28 empty] | 0 | 0 |  | 11200000 | 11200000 | 0% | 0% | Commissioning of works.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1570 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes |  |  |  |  | Gqozo Village Phase 2 | USDG | [10 empty] | 10000000 | [8 empty] | 0 | [28 empty] | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | Within the SCM process. Tenders closed.
Engineering Services | Sewerage Admin | 6.9 - Sewerage Admin |  | 515010 | 4 | 01 | 1521 | Waste Water Management | Waste Water | 4 | 01 |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Bulk Sanitation Provision - Replacing Existing Infrastructure | Own Funds |  |  |  |  | 0 |  | 0 |  | 40000000 | -2000000 | 38000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 38000000 | 38000000 | 0% | 0% | Eastern Beach Sewers contract currently within the procurement process | 40000000 | 40000000
Engineering Services | Water Treatment Works | 6.20 - Water Administration | Water | 520005 | 4 | 36 | 1521 | Water | Water | 4 | 36 |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes | Road Transport | Roads | KPA2 | 34,37,38,39,40,41,43,44,49,35,11,12,13,14,42,48,50,17,20,23,1-25 & 28,29,30,31, & 33,27,31,33,36,1,2,7,14,17,20,21,22,23,30,2,8,25,34,44,41 | Bulk Water Provision - Programme | USDG | 0 |  |  |  | 0 |  | 0 |  | 52500000 |  | 51167105 | 0 | 0 | 0 | 1511048.24 | 195288.57 | 1706336.81 | 929320.16 | 125133.92 | 1054454.08 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 220513 | 2440368.4 | 2760790.89 |  | 48726736.6 | 48406314.11 | 4.769% | 5.396% | The programme is progressing well. | 51000000 | 51000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [13 empty] | 0 |  |  | 0 |  | 0% |  | 73000000
Engineering Services | Water Treatment Works | 6.20 - Water Administration |  | 520005 | 4 | 01 | 1522 | Water | Water | 4 | 01 |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes | Road Transport | Roads | KPA2 | 34,37,38,39,40,41,43,44,49,35,11,12,13,14,42,48,50,17,20,23,1-25 & 28,29,30,31, & 33,27,31,33,36,1,2,7,14,17,20,21,22,23,30,2,8,25,34,44,41 | Bulk Water Provision Replacing of Existing Infrastructure | Own Funds |  |  |  |  | 0 |  | 0 |  | 40000000 |  | 40000000 | 0 | 0 | 0 | 268846.57 |  | 268846.57 | 1115607.01 |  | 1115607.01 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 409912.71 | 1384453.58 | 1384453.58 |  | 38615546.42 | 38615546.42 | 3.461% | 3.461% | Annual contractors for Contract 3 and 21 have been appointed and expendoture is expected to increase in the second quarter | 40000000 | 40000000
Engineering Services | Water Admin | 6.20 - Water Administration | Water | 520005 | 4 | 36 | 1522 | Water | Water | 4 | 36 |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes | Road Transport | Roads | KPA2 | 34,37,38,39,40,41,43,44,49,35,11,12,13,14,42,48,50,17,20,23,1-25 & 28,29,30,31, & 33,27,31,33,36,1,2,7,14,17,20,21,22,23,30,2,8,25,34,44,41 | West Bank Restitution - Water | USDG | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 5000000 |  | 5000000 | 0 | 0 | 0 | 67797.4 | 9491.64 | 77289.04 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 67797.4 | 77289.04 |  | 4932202.6 | 4922710.96 | 1.356% | 1.546% | Processes are being followed so that project can be re-advertised. | 0 | 0 |  |  |  | 0 | -1849660.37 | -1849660.37 |  |  | 0 | -1849660.37 | -1849660.37 |  |  | 0 |  |  | 0 | 3541740.65 |  | 3541740.65 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1692080.28 | 1692080.28 |  | 8307919.72 | 8307919.72 | 16.92% | 16.92%
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1523 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Urban Roads - Programme | USDG | 30000000 |  |  |  | 0 |  | 0 |  | 110000000 | -110000000 | 1581556 | -47814.16 | 0 | -47814.16 | 75959.59 |  | 75959.59 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 28145.43 | 28145.43 |  | 1553410.57 | 1553410.57 | 1.78% | 1.78% | Budget re allocated to adress short fall | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1562 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Upgrade Mdantsane Roads | USDG | 30000000 |  |  |  | 0 |  | 0 |  |  | 30000000 | 29000000 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 29000000 | 29000000 | 0% | 0% | Work progressing well, expenditure to reflect by October 2014 | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1563 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Quinera Arterial Road | USDG | 30000000 |  |  |  | 0 |  | 0 |  |  | 30000000 | 31325132 |  | 0 | 0 | 1370589 | 175671.96 | 1546260.96 | 279125.87 | 39077.62 | 318203.49 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1649714.87 | 1864464.45 |  | 29675417.13 | 29460667.55 | 5.266% | 5.952% | Work progressing well, expenditure to reflect by October 2014 | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1564 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Fleet Street | USDG | 30000000 |  |  |  | 0 |  | 0 |  |  | 20000000 | 20463013 |  | 0 | 0 | 1170655.39 | 163891.76 | 1334547.15 | 318205.64 | 44548.79 | 362754.43 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1488861.03 | 1697301.58 |  | 18974151.97 | 18765711.42 | 7.276% | 8.294% | Contractor on site, there are delays on the project | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1565 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Gonubie Main Road | USDG | 30000000 |  |  |  | 0 |  | 0 |  |  | 30000000 | 19689137 |  | 0 | 0 | 153007.76 | 21421.09 | 174428.85 | 209352.69 | 29309.38 | 238662.07 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 362360.45 | 413090.92 |  | 19326776.55 | 19276046.08 | 1.84% | 2.098% | Work progressing well, expenditure to reflect by October 2014 | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services |  | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1567 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 |  | RDP Houses- Roads Refurbishment | USDG | [10 empty] | 4431601 | [37 empty] | 0 | 0 |  | 4431601 | 4431601 | 0% | 0%
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1524 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 11, 12, 14, 17, 20, 20, 21, 22, 23, 30, 42,48 50 | Upgading of Mdantsane Roads | USDG | 0 |  |  |  | 0 |  | 0 |  | 53000000 |  | 56063757 | 0 | 0 | 0 | 5803174.76 | 783490.07 | 6586664.83 | 16914156.71 | 1582124.54 | 18496281.25 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3779308.93 | 22717331.47 | 25082946.08 |  | 33346425.53 | 30980810.92 | 40.52% | 44.74% | Work progressing well, expenditure to reflect by October 2014 | 60000000 | 60000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [13 empty] | 0 |  |  | 0 |  | 0%
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1525 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 46 | Rehabilitation of BCMM Bridges | USDG | 0 |  |  |  | 0 |  | 0 |  | 8000000 |  | 8000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2435524.98 | 0 | 0 |  | 8000000 | 8000000 | 0% | 0% | Project on going, Settlers Pedestrian Bridge repaired, expenditure to reflect in October 2014 | 5000000 | 10000000 | [16 empty] | 0 |  |  | 0 | [16 empty] | 0 |  |  |  | 80000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1526 | Road transport | Other - BCM Fleet | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 24,26,31, 33, 35,36, 37, 38, 39, 40, 41, 49, 44, 43, 45, | Procurement of Graders for Rural Roads | USDG | 25000000 |  | 25000000 | 8000000 | 33000000 | 3500000 | 36500000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | Mechanical and Fleet Division procuring Plant | 30000000 | 30000000 |  |  |  | 0 | 2916096.53 | 3323571.44 | 5902572.57 | 533811.63 | 6436384.2 | 8818669.1 | 9759955.64 | 4676639.56 | 948056.69 | 5624696.25 | 4623433.85 | 647280.74 | 5270714.59 | 4357834.3 | 610096.82 | 4967931.12 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2038718.1 | 22476576.81 | 25623297.6 |  | 10523423.19 | 7376702.4 | 68.11% | 77.65% | 110000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1527 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 24,26,31, 33, 35,36, 37, 38, 39, 40, 41, 49, 44, 43, 45, | Rehabilitation of Rural Roads | USDG |  |  |  |  | 0 |  | 0 |  | 15000000 |  | 15445804 | 0 | 0 | 0 | 1400662.06 | 196092.69 | 1596754.75 | 1662796.5 | 232791.49 | 1895587.99 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 5242659.62 | 3063458.56 | 3492342.74 |  | 12382345.44 | 11953461.26 | 19.83% | 22.61% | Work progressing well, expenditure to reflect by October 2014 | 0 | 0
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1528 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Quinera Arterial Road | USDG | 15000000 |  | 15000000 | -6000000 | 9000000 |  | 9000000 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Work progressing well, expenditure to reflect by October 2014 | 0 | 0 |  |  |  | 0 |  | 0 | 90883.71 |  | 90883.71 | 90883.71 | 90883.71 |  |  | 0 |  |  | 0 | 7999784.83 |  | 7999784.83 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 8090668.54 | 8090668.54 |  | 909331.46 | 909331.46 | 89.9% | 89.9%
Engineering Services | Fleet management - Braelyn | 6.43 - Fleet Management - Braelyn |  | 530020 | 4 | 01 | 1523 | Electricity | Other - BCM Fleet | 4 | 01 |  | 05 | 05 | 01 | 01 | 250 | 001 | New-250 | Yes |  | Other assets | Vehicles | KPA2 | All Wards | BCMM Fleet, Plant and Specialised Equipment and Specialised Solid Waste Vehicles | Own Funds | 0 |  | 0 |  | 0 |  | 0 |  | 18300000 |  | 18300000 | 0 | 0 | 0 | 1888532.64 |  | 1888532.64 | 10484165.53 |  | 10484165.53 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 4205395.79 | 12372698.17 | 12372698.17 |  | 5927301.83 | 5927301.83 | 67.61% | 67.61% |  | 18000000 | 18000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Engineering Services |  | 6.43 - Fleet Management - Braelyn |  | 530020 | 6 | 01 | 1512 | Electricity | Other - BCM Fleet |  |  |  | 05 | 05 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Other assets | Vehicles | KPA2 | All Wards | BCMM Fleet | Own Funds c/o | [9 empty] | 3997668 | 3997668 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 3997668 | 3997668 | 0% | 0%
Engineering Services |  | 6.43 - Fleet Management - Braelyn |  | 530020 | 6 | 01 | 1513 | Electricity | Electricity |  |  |  | 05 | 05 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Other assets | Vehicles | KPA2 | All Wards | Electricity Dept. - Specialised Plant and Equipment | Own Funds c/o | [9 empty] | 3000000 | 3000000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 3000000 | 3000000 | 0% | 0%
Engineering Services | Electricity Administration | 4.4 - Asset Risk & Financial Services |  | 535005 | 5 | 05 | 1509 | Budget and treasury | Electricity | 4 | 01 |  | 05 | 05 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 8500 | 8500 |  |  | 0 |  |  | 0 |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 8500 | 8500 | 0% | 0% | Waiting for information from Operations on Claims
Engineering Services |  | 4.4 - Asset Risk & Financial Services |  | 535010 | 5 | 05 | 1513 | Budget and treasury | Electricity | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 39900 | 39900 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 39900 | 39900 | 0% | 0% | Waiting for information from Operations on Claims
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design |  | 535025 | 4 | 01 | 1524 | Electricity | Electricity | 4 | 01 |  | 05 | 05 | 01 | 01 | 060 | 001 | Renewal-60 |  | Yes | Electricity | Electricity reticulation | KPA2 | 16, 18,29,35 | Bulk Electricity Infrastructure Upgrade(Ring-Fenced 4% of the Total Electricity Revenue) | Own Funds | 5285700 |  | 438631.88 |  | 438631.88 | 29084305 | 29522936.88 |  | 40000000 |  | 40000000 | 0 | 0 | 0 | 153718.89 |  | 153718.89 | 531767.37 |  | 531767.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 5529980.27 | 685486.26 | 685486.26 |  | 39314513.74 | 39314513.74 | 1.714% | 1.714% | Electrical projects identified / design / planning stage - long delivery items; orders submitted to SCM expected delivery first batch 3 Nov 14 - switchboard panels ordered delivery 2015 | 50000000 | 60000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 438631.88 | 438631.88 | 0% | 0%
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design |  | 535025 | 4 | 01 | 1525 | Electricity | Electricity | 4 | 01 |  | 05 | 05 | 01 | 01 | 060 | 001 | Renewal-60 |  | Yes | Electricity | Electricity reticulation | KPA2 | 16, 18,29,35 | Bulk Electricity Infrastructure Upgrade - Replacing Existing Infrastructure | Own Funds |  |  |  |  | 0 |  | 0 |  | 40000000 |  | 40000000 | 0 | 0 | 0 | 551972.49 |  | 551972.49 | 4746762.37 |  | 4746762.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 8393652.52 | 5298734.86 | 5298734.86 |  | 34701265.14 | 34701265.14 | 13.25% | 13.25% | Electrical projects identified / design / planning stage - long delivery items; orders submitted to SCM expected delivery first batch 3 Nov 14 - RMU request submitted to contact delivery week of the 8th Sept 14 | 40000000 | 40000000
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design |  | 535025 | 4 | 56 | 1533 | Electricity | Electricity | 4 | 56 |  | 05 | 05 | 01 | 01 | 060 | 001 | New-60 | Yes |  | Electricity | Electricity reticulation | KPA2 | 1,3,19, | INEP Electrification Programme | DoE(Intergrated National Electrification Programme) | 1329000 |  | 1329000 | -1329000 | 0 |  | 0 |  | 27000000 |  | 27000000 | 34346 | 0 | 34346 | 128806.07 |  | 128806.07 | 2895383.81 | 423386.58 | 3318770.39 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 3058535.88 | 3481922.46 |  | 23941464.12 | 23518077.54 | 11.33% | 12.9% | Completion of ED329 & ED373 Queenspark Projects / Installation of Queenspark Cable / Electrification Duncan Village, Second Creek, Infills BCMM area | 27000000 | 12000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design | Electricity | 535025 | 4 | 36 | 1529 | Electricity | Electricity | 4 | 36 |  | 05 | 05 | 01 | 01 | 060 | 001 | New-60 | Yes |  | Electricity | Electricity reticulation | KPA2 | 1,2, 7, 8, 9,10 | INEP Electrification Programme - Counterfunding | USDG | 1600000 |  | 1600000 |  | 1600000 |  | 1600000 |  | 5000000 |  | 5000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 5000000 | 5000000 | 0% | 0% | ED383 MV LV Reticulation Potsdam Unit P - BSC | 5000000 | 5000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 1600000 | 1600000 | 0% | 0% | 5000000
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design | Electricity | 535025 | 4 | 36 | 1530 | Electricity | Electricity | 4 | 36 |  | 05 | 05 | 01 | 01 | 060 | 001 | New-60 | Yes |  | Electricity | Electricity reticulation | KPA2 | 2,7,8,9,11,12 | Electrification of Informal Dwelling Areas within BCMM | USDG | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 | 131675.29 | 18434.54 | 150109.83 | 374455.86 | 52423.82 | 426879.68 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 506131.15 | 576989.51 |  | 9493868.85 | 9423010.49 | 5.061% | 5.77% | Electrification projects Duncan Village / Mdantsane Zone 1 & 3 / Phakamisa identified in progress | 15000000 | 20000000 |  |  |  | 0 | 799580.21 | 911521.46 |  |  | 0 | 799580.21 | 911521.46 | 4082.92 | 571.61 | 4654.53 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 803663.13 | 916175.99 |  | 9196336.87 | 9083824.01 | 8.037% | 9.162% | 25000000
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design | Electricity | 535025 | 4 | 36 | 1531 | Electricity | Electricity | 4 | 36 |  | 05 | 05 | 01 | 01 | 060 | 001 | New-60 | Yes |  | Electricity | Electricity reticulation | KPA2 | 10,15,29,28,36,46 | Street Lighting and Highmasts within BCMM Areas of Supply - Informal Settlements | USDG | 853700 |  | 853700 |  | 853700 |  | 853700 |  | 3500000 |  | 3500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 3500000 | 3500000 | 0% | 0% | Major projects identified Breidbach / Gonubie Main Rd / ED384 Suppy & Del Highmast Lighting BCMM - Tenders to be invited | 3500000 | 3500000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 853700 | 853700 | 0% | 0% | 3500000
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design | Electricity | 535025 | 4 | 36 | 1532 | Electricity | Electricity | 4 | 36 |  | 05 | 05 | 01 | 01 | 060 | 001 | Renewal-60 |  | Yes | Electricity | Electricity reticulation | KPA2 | 10,15,29,28,36,46 | Replacement and Refurbishment of Bulk ELECT Infrastructure | USDG |  |  |  |  | 0 |  | 0 |  | 9199000 |  | 9199000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 9199000 | 9199000 | 0% | 0% | As per DES - funds to be transferred to Roads Dept - next Adjustment Budget | 2000000 | 8000000
Engineering Services | Water Admin | 6.20 - Water Administration |  | 520005 | 4 | 75 | 1501 | Water | Water | 4 |  |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes | Road Transport | Roads | KPA2 | 34,37,38,39,40,41,43,44,49,35,11,12,13,14,42,48,50,17,20,23,1-25 & 28,29,30,31, & 33,27,31,33,36,1,2,7,14,17,20,21,22,23,30,2,8,25,34,44,41 | Upgrade Water Supply in Rural Areas | LGTH |  |  |  |  | 0 |  | 0 |  | 188726 |  | 188726 | 0 | 0 | 0 |  |  | 0 | 178585.49 |  | 178585.49 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 178585.49 | 178585.49 |  | 10140.51 | 10140.51 | 94.63% | 94.63%
[26 empty] | TOTAL : ENGINEERING SERVICES |  | 256922400 | 0 | 102075331.88 | 20671000 | 122746331.88 | 32584305 | 155330636.88 | 0 | 665695618 | 8620581 | 674316199 | -213299.07 | 0 | -213299.07 | 24752777.27 | 2879522.9 | 27632300.17 | 48211032.36 | 4221188.7 | 52432221.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30958477.25 | 72750510.56 | 79851222.16 | 0 | 601565688.44 | 594464976.84 | 10.79% | 11.84% |  | 1027000000 | 895000000 | 0 | 0 | 0 | 0 | 5827973.17 | 6902063.28 | 13804116.13 | 1784476.74 | 15588592.87 | 19632089.3 | 22490656.15 | 13528999.26 | 2080645.33 | 15609644.59 | 14379875.14 | 1913021.76 | 16292896.9 | 32034197.88 | 1817267.55 | 33851465.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038718.1 | 79575161.58 | 88244663.07 | 625034.64 | 43171170.3 | 34501668.81 | 64.83% | 71.89% |  |  | 0
[32 empty] | 0 |  | 0 | [18 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [32 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF DEVELOPMENT PLANNING | [25 empty] | DIRECTORATE OF DEVELOPMENT PLANNING | [5 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Directorate of Development Planning | Director's Office | 7.1 - Office of The Director of Planning & Economic Dev. |  | 605005 | 4 | 01 | 1526 | Planning and Development | Planning and development | 4 | 01 |  | 05 | 06 | 01 | 01 | 270 | 001 | New-270 | Yes |  |  |  | KPA2 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 28699.69 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Requirements from the different departments have been consolidated and prioritized. Orders have subsequently been placed at Supply Chain Management Unit, but there are delays in the processing thereof. | 500000 | 500000
Directorate of Development Planning |  | 7.11 - City Planning |  | 615070 | 6 | 01 | 1514 | Planning and Development | Planning and development |  |  |  | 05 | 06 | 01 | 01 | 312 | 002 | Renewal-312 |  | Yes | Other assets | Other Assets | KPA2 | All Wards | Upgrading of the City Hall | Own Funds c/o | [9 empty] | 5395309 | 5395309 |  |  | 0 |  |  | 0 | 1609065.89 |  | 1609065.89 | [27 empty] | 3725154.75 | 1609065.89 | 1609065.89 |  | 3786243.11 | 3786243.11 | 29.82% | 29.82% | Replacement of the City Hall roof project underway.
Directorate of Development Planning | Architecture | 7.12 - Architecture | Development & Transport Planning | 615075 | 4 | 36 | 1534 | Planning and Development | Planning and development | 4 | 36 |  | 05 | 06 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other assets | Other Assets | KPA2 | All Wards | Upgrade KWT Payments Hall | USDG | 2800000 |  | 2800000 | -2800000 | 0 |  | 0 |  | 5000000 |  | 5000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 797099.25 | 0 | 0 |  | 5000000 | 5000000 | 0% | 0% | Professional service provider signed acceptance of appointment letter on 4 August 2014. Designs and specifications are now underway. | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0%
Directorate of Development Planning |  | 7.12 - Architecture |  | 615075 | 6 | 01 | 1515 | Planning and Development | Planning and development |  |  |  | 05 | 06 | 01 | 01 | 312 | 002 | Renewal-312 |  | Yes | Other assets | Other Assets | KPA2 | All Wards | Upgrade KWT Payments Hall | Own Funds c/o | [9 empty] | 477792 | 477792 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 477792 | 477792 | 0% | 0% | Professional service provider signed acceptance of appointment letter on 4 August 2014. Designs and specifications are now underway.
Directorate of Development Planning | Land Administration | 7.13 - Land Administration | Development & Transport Planning | 615080 | 4 | 36 | 1535 | Planning and Development | Planning and development | 4 | 36 |  | 05 | 06 | 01 | 01 | 311 | 001 | New-311 | Yes |  | Other assets | Land & Buildings | KPA2 | All Wards | Land Acquisition | USDG | 20000000 |  | 20000000 | -11000000 | 9000000 |  | 9000000 |  | 5500000 |  | 5500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 5500000 | 5500000 | 0% | 0% | Matter referred to the Office of the MEC COGTA. Independent valuer to be appointed by agreement by parties concerned. Terms of Reference for the appointment of Independent Valuer has been finalised by DOF (Rates & Valutations) in consultation with the office of the MEC - Mr Tau and BID Specification approved on the 1st October 2014 and sent to SCM on the 2nd October 2014 to advertise. | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 295925.4 | 23537.64 | 319463.04 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 295925.4 | 319463.04 | 0 | 8704074.6 | 8680536.96 | 3.288% | 3.55%
Directorate of Development Planning | Transport Planning & Operations Admin | 7.30 - Transport Planning & Operations Admin | Development & Transport Planning | 620005 | 4 | 36 | 1536 | Planning and development | Planning and development | 4 | 36 |  | 05 | 06 | 01 | 01 | 050 | 001 | New-50 | Yes |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 | All Wards | Integrated Transport Plan Implementation Programme | USDG | 3000000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 24000000 |  | 24000000 | 52995 | 1576.4 | 54571.4 | 1754959.43 | 276099.8 | 2031059.23 | 1633771.02 | 228727.97 | 1862498.99 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 5356950.42 | 3441725.45 | 3948129.62 |  | 20558274.55 | 20051870.38 | 14.34% | 16.45% | Traffic calming programme has commenced in Sweetawters, Beacon Bay, Braelyn, Cambridge, and Duncan Village and the payments of R2.5 m have been made . Sidewalks programme has commenced in Potsdam Village area and in Scenery Park still awiting for orders. Traffic Signage programme has commenced and it is at design stage.Traffic Signals are at the design stage, however, the implementation is on hold due to the non availability of cables. Needs Camp / Potsdam Bridge progressing through detailed designs stage. KwaTshatshu Bridge awarded 1 August 2014, inception stage complete,feasability study report submitted as well as first invoice. Guardrails are being implemented and a payment of R850,000.00 has been made. | 30000000 | 59500000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 162616.91 | 22766.37 | 185383.28 | 234124.03 | 32777.36 | 266901.39 | 866586.58 | 121322.12 | 987908.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 853992.67 | 1263327.52 | 1440193.37 | 0 | 1736672.48 | 1559806.63 | 42.11% | 48.01% |  |  |  |  | 109500000
Directorate of Development Planning |  | 7.30 - Transport Planning & Operations Admin |  | 620005 | 6 | 81 | 1501 | Planning and development | Planning and development |  |  |  | 05 | 06 | 01 | 01 | 050 | 002 | New-50 | Yes |  | Other |  | KPA2 | All Wards | BCMET Roads | BCMET c/o | [9 empty] | 256818 | 256818 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 256818 | 256818 | 0% | 0% | Work to be continued on Amalinda Main Road sidewalk project. Works instruction requested.
Directorate of Development Planning |  | 7.16 - Building Maintenance - Coastal / Central |  | 615095 | 4 | 01 | 1527 | Planning and Development | Planning and development | 4 | 01 |  | 05 | 06 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Rehabilitation of Midland Existing Municipal Buildings and Old Mutual Building (Finance) | Own Funds |  |  |  |  | 0 |  | 0 |  | 2471000 |  | 2471000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2471000 | 2471000 | 0% | 0% | This cost centre must be changed to 615075 Architectural Division, this project is with the PM Architecture and he is currently having meetings with the CFO on the budgets and the old Mutual refurbishment and moving of the payments hall and traffic. BMS has not been privey to the meetings at all. | 10000000 | 5000000
Directorate of Development Planning |  | 7.16 - Building Maintenance - Coastal / Central |  | 615095 | 4 | 01 | 1528 | Planning and Development | Planning and development | 4 | 01 |  | 05 | 06 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Building Refurbishments and Upgrading of Lifts for BCMM Buildings | Own Funds |  |  |  |  | 0 | 400000 | 400000 |  | 1424288 |  | 1424288 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1424288 | 1424288 | 0% | 0% | This cost centre must be changed to 615075 Architectural Division, this project is with the PM Architecture. The Building Maintenance Manager has been asked to assist the PM Arch. BMS will only draw up the informal tender documents for appointment of consultants. This project will then be run by the Facilities Assessment Section under the Architectural Division. | 820661 | 7755051 | [40 empty] | 8000000
Directorate of Development Planning |  | 7.16 - Building Maintenance - Coastal / Central |  | 615095 | 4 | 01 | 1529 | Planning and Development | Planning and development | 4 | 01 |  | 05 | 06 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 | All Wards | SCM Inventory Warehousing and Fencing | Own Funds |  |  |  |  | 0 | 400000 | 400000 |  | 6000000 | -4500000 | 1500000 | 0 | 0 | 0 | 1146359.07 |  | 1146359.07 | -1146359.07 |  | -1146359.07 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1500000 | 1500000 | 0% | 0% | This cost centre must be changed to the SCM cost centre and taken off the 615095 Building Maintenance Cost Centre. The project has also been reduced to R2million only and is currently under the Archtecture Service Branch for consultants. BMS is not privy to the meetings in this regard. | 900000 | 900000 | [40 empty] | 8000000
[26 empty] | TOTAL : DEVELOPMENT PLANNING |  | 25800000 | 0 | 25800000 | -13800000 | 12000000 | 800000 | 12800000 | 0 | 44895288 | 1629919 | 46525207 | 52995 | 1576.4 | 54571.4 | 2901318.5 | 276099.8 | 3177418.3 | 2096477.84 | 228727.97 | 2325205.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9907904.11 | 5050791.34 | 5557195.51 | 0 | 41474415.66 | 40968011.49 | 10.86% | 11.94% |  | 42220661 | 73655051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162616.91 | 22766.37 | 185383.28 | 234124.03 | 32777.36 | 266901.39 | 1162511.98 | 144859.76 | 1307371.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 853992.67 | 1559252.92 | 1759656.41 | 0 | 10440747.08 | 10240343.59 | 12.99% | 14.66%
[32 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF ECONOMIC DEVELOPMENT | [25 empty] | DIRECTORATE OF ECONOMIC DEVELOPMENT | [5 empty] | 0 |  | 0
Directorate of Economic Development |  | 7.35 - Local Economic Development | Development & Transport Planning | 635005 | 4 | 36 | 1537 | Planning and Development | Planning and development | 4 | 36 |  | 05 | 07 | 01 | 01 | 120 | 001 | New-120 | Yes |  |  |  | KPA3 |  | Enabling Infrastructure Programme - LED | USDG | 10000000 | 10000000 | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | Mechanical Workshops is assisting in prepairing specifications for the two Forklifts and a Scrubber for the Market | 10000000 | 10000000
[26 empty] | TOTAL : ECONOMIC DEVELOPMENT | [5 empty] | 0 |  | 0 |  | 10000000 | 0 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000 | 0% | 0% |  | 10000000 | 10000000
[32 empty] | 0 |  | 0
DIRECTORATE OF HEALTH AND PUBLIC SAFETY | [25 empty] | DIRECTORATE OF HEALTH AND PUBLIC SAFETY | [5 empty] | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Health and Public Safety | Office of the Director of Health & Public Safety | 8.1 - Office of The Director of Health & Public Safety |  | 705005 | 4 | 01 | 1530 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 30000 |  | 30000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 30000 | 30000 | 0% | 0% | Procurement process underway. | 500000 | 500000
Health and Public Safety | Health Administration | 8.1 - Office of The Director of Health & Public Safety |  | 710005 | 4 | 01 | 1553 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Health) | Own Funds |  |  |  |  | 0 |  | 0 |  | 70000 |  | 70000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 70000 | 70000 | 0% | 0% | Procurement process underway.
Health and Public Safety |  | 8.4 - Health Support |  | 710010 | 6 | 01 | 1517 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 271 | 002 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Municipal Health Services - IT & Database Development | Own Funds c/o | [9 empty] | 216000 | 216000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 216000 | 216000 | 0% | 0% | Service Provider to complete identified shortfalls.
Health and Public Safety | Public Safety Administration | 8.1 - Office of The Director of Health & Public Safety |  | 725005 | 4 | 01 | 1554 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (GM Public Safety) | Own Funds |  |  |  |  | 0 |  | 0 |  | 21000 |  | 21000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 21000 | 21000 | 0% | 0% | Procurement process underway.
Health and Public Safety | Fire & Rescue Services | 8.13 - Fire and Rescue Services |  | 725010 | 4 | 01 | 1533 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 360 | 001 | New-360 | Yes |  | Community |  | KPA2 | 1 to 50 | Fire Engine | Own Funds |  |  |  |  | 0 |  | 0 |  | 4000000 |  | 4000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 4000000 | 4000000 | 0% | 0% | Tender closed on 22 July 2014 and prelimary report for BEC completed and submitted to SCM.Waiting for BEC to convene. | 4000000 | 4000000
Health and Public Safety | Fire & Rescue Services | 8.1 - Office of The Director of Health & Public Safety |  | 725010 | 4 | 01 | 1555 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Fire & Rescue Sercices) | Own Funds |  |  |  |  | 0 |  | 0 |  | 80000 |  | 80000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 80000 | 80000 | 0% | 0% | Specifications for informal tender submitted to SCM.
Health and Public Safety |  | 8.13 - Fire and Rescue Services |  | 725010 | 6 | 01 | 1518 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 312 | 002 | New-312 | Yes |  | Other assets | Land & Buildings | KPA2 | All Wards | KWT Fire Station | Own Funds c/o | [9 empty] | 353709 | 353709 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 353709 | 353709 | 0% | 0% | KWT Station completed. Final checks and remedial work being undertaken. Generator to be installed.
Health and Public Safety |  | 8.13 - Fire and Rescue Services |  | 725010 | 6 | 01 | 1521 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Community |  |  | All Wards | Replacement of 2X Bush Fire Vehicles written off | Own Funds c/o | [9 empty] | 532200 | 532200 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 532200 | 532200 | 0% | 0% | Specifications has been completed and submitted to Management for approval.
Health and Public Safety |  | 8.13 - Fire and Rescue Services |  | 725010 | 6 | 01 | 1522 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Community |  |  | All Wards | Replacement of 5X Air Conditioners | Own Funds c/o | [9 empty] | 80000 | 80000 |  |  | 0 |  |  | 0 | 79776.8 |  | 79776.8 | [28 empty] | 79776.8 | 79776.8 |  | 223.2 | 223.2 | 99.72% | 99.72% | Project completed.
Health and Public Safety |  | 8.14 - Security Services |  | 725015 | 4 | 01 | 1534 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  |  | All Wards | Closed Circuit Television Network - CCTV | Own Funds | [8 empty] | 2000000 |  | 2000000 |  |  | 0 | 761505.76 |  | 761505.76 | -761455.82 |  | -761455.82 | [27 empty] | 178041.42 | 49.94 | 49.94 |  | 1999950.06 | 1999950.06 | 0.002497% | 0.002497% | Specifications submitted to BSC.Awaiting approval from BSC in order to advertise for consultants.
Health and Public Safety |  | 8.14 - Security Services |  | 725015 | 6 | 01 | 1516 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 271 | 002 | New-260 | Yes |  | Community |  |  | All Wards | Closed Circuit Television Network - CCTV c/o | Own Funds c/o | [9 empty] | 1196101 | 1196101 |  |  | 0 |  |  | 0 | 316911.22 |  | 316911.22 | [28 empty] | 316911.22 | 316911.22 |  | 879189.78 | 879189.78 | 26.5% | 26.5% | Letter submitted by BCMM to Transnet 13 August 2014, regarding request to install Relay Station on grain elevators. Awaiting their response.
Health and Public Safety | Law Enforcement Services | 8.14 - Security Services |  | 725015 | 4 | 01 | 1535 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 250 | 001 | New-250 | Yes |  | Community | Other Assets | KPA2 | 1 to 50 | Fire Arms - Traffic and Law Enforcement | Own Funds | 50000 |  | 50000 |  | 50000 |  | 50000 |  | 100000 |  | 100000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 100000 | 100000 | 0% | 0% | Procurement process underway. | 0 | 200000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 43280 |  | 43280 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 43280 | 43280 |  | 6720 | 6720 | 86.56% | 86.56%
Health and Public Safety | Law Enforcement Services | 8.1 - Office of The Director of Health & Public Safety |  | 725015 | 4 | 01 | 1557 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Law Enforcement) | Own Funds |  |  |  |  | 0 |  | 0 |  | 14110 |  | 14110 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 14110 | 14110 | 0% | 0% | Procurement process underway.
Health and Public Safety |  | 8.14 - Security Services |  | 725015 | 6 | 01 | 1520 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 280 | 002 | New-270 | Yes |  | Community |  |  | All Wards | Security Equipment - DVRI | Own Funds c/o | [9 empty] | 40000 | 40000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 40000 | 40000 | 0% | 0% | Meetings with DVRI to be arranged in order obtain security equipment requirements.
Health and Public Safety | Traffic Administration | 8.1 - Office of The Director of Health & Public Safety |  | 725020 | 4 | 01 | 1556 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Traffic Services) | Own Funds |  |  |  |  | 0 |  | 0 |  | 211190 |  | 211190 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 211190 | 211190 | 0% | 0% | Procurement process underway.
Health and Public Safety | Traffic Administration | 4.4 - Asset Risk & Financial Services |  | 725020 | 5 | 05 | 1511 | Budget and treasury | Public safety | 4 | 01 |  | 05 | 03 | 03 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 145000 | 145000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 145000 | 145000 | 0% | 0% | Specifications submitted to Fleet & Mechanical for replacement of vehicle.
Health and Public Safety | Traffic Control | 8.16 - Traffic Control | Public Safety | 725025 | 4 | 36 | 1538 | Public safety | Public safety | 4 | 36 |  | 05 | 07 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Community | Land & Buildings/ Fire Stations | KPA2 | 35 | KWT Traffic Building | USDG | 1500000 |  | 1500000 | 500000 | 2000000 | -2000000 | 0 | 2000000 | 3000000 |  | 3000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 3000000 | 3000000 | 0% | 0% | Service provider being professional planning team has been appointed and letter signed. Meetings with service provider & client held and draft plans being prepared based on requirements of clients. | 6000000 | 6000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0%
Health and Public Safety | Traffic Control | 8.16 - Traffic Control |  | 725025 | 4 | 01 | 1536 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 250 | 001 | New-250 | Yes |  | Community | Other Assets | KPA2 | 20 | Mdantsane Testing Station - Equipment | Own Funds | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 200000 | 1102.63 | 0 | 1102.63 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1102.63 | 1102.63 |  | 198897.37 | 198897.37 | 0.5513% | 0.5513% | Computer requirements submitted to IT for procurement of computer equipment for MLLC. | 0 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Health and Public Safety | Environmental Health |  |  | 710030 | 4 | 01 | 1531 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Air Monitoring Station | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 1800000
Health and Public Safety | Disaster Management |  |  | 725055 | 4 | 01 | 1542 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Tactic Radio Network | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 800000
Health and Public Safety | Disaster Management |  |  | 725055 | 4 | 01 | 1543 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Early Warning Systems | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 500000
Health and Public Safety | Traffic Control |  |  | 725025 | 4 | 01 | 1537 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Road Closure and Events Equipment | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 200000
Health and Public Safety | Traffic Control |  |  | 725025 | 4 | 01 | 1538 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Traffic Enforcement Equipment | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 1000000
Health and Public Safety | Fire & Rescue Services |  |  | 725010 | 4 | 01 | 1532 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Fire Equipment | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 2000000
Health and Public Safety | Traffic Control |  |  | 725025 | 4 | 01 | 1539 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 250 | 001 | New-250 | Yes |  | Community |  | KPA2 | 27 | Vehicle Pound | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 200000
Health and Public Safety | Vehicle Test Station / Examination |  |  | 725035 | 4 | 01 | 1540 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 27,1,41 | Vehicle Test Station Equipment | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 2000000
Health and Public Safety | Vehicle Test Station / Examination |  |  | 725035 | 4 | 01 | 1541 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Community |  | KPA2 | 27,1,41 | Upgrade Vehicle Test Station | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 2000000
Health and Public Safety |  | 8.18 - Vehicle Test Station / Examination |  | 725035 | 6 | 01 | 1519 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 312 | 002 | New-312 | Yes |  |  |  |  | All Wards | Learners Licence Centre - Mdantsane | Own Funds c/o | [9 empty] | 798970 | 798970 |  |  | 0 |  |  | 0 | 366421.75 |  | 366421.75 | [28 empty] | 366421.75 | 366421.75 |  | 432548.25 | 432548.25 | 45.86% | 45.86% | Balance of R432 548 will be paid out soon as project is completed. This amount is the final payment for the project and for the fencing of the project.
Health and Public Safety | Disaster Management | 8.1 - Office of The Director of Health & Public Safety |  | 725055 | 4 | 01 | 1558 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Disaster Management) | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 73700 |  | 73700 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 73700 | 73700 | 0% | 0% | Procurement process underway.
Health and Public Safety | Disaster Management | 4.4 - Asset Risk & Financial Services |  | 725055 | 5 | 05 | 1506 | Budget and treasury | Public safety | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Asset Replacements - Insurance | Own Funds |  |  | 0 |  | 0 |  | 0 |  |  | 95000 | 95000 | [5 empty] | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 95000 | 95000 | 0% | 0% | Informal tender submitted to IT for computers and requisitions being prepared for the replacement of furniture.
[26 empty] | TOTAL : HEALTH AND PUBLIC SAFETY |  | 1750000 | 0 | 1750000 | 500000 | 2250000 | -2000000 | 250000 | 2000000 | 9800000 | 3456980 | 13256980 | 1102.63 | 0 | 1102.63 | 761505.76 | 0 | 761505.76 | 1653.95 | 0 | 1653.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178041.42 | 764262.34 | 764262.34 | 0 | 12492717.66 | 12492717.66 | 5.765% | 5.765% |  | 10500000 | 21200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43280 | 0 | 43280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43280 | 43280 | 0 | 2206720 | 2206720 | 1.924% | 1.924% |  |  | 0
[30 empty] | 0 |  | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF COMMUNITY SERVICES | [25 empty] | DIRECTORATE OF COMMUNITY SERVICES |  |  |  | 0 |  | 0 |  | 0 | [72 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Community Services | Environmental Administration Support | 9.1 - Office of The Director of Community Services |  | 755005 | 4 | 01 | 1544 | Community and social services | Support Services | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 200000 |  | 200000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0% | The department is in the process of procuring furniture | 500000 | 500000
Community Services | Environmental Services | 9.4 - Environmental Services | Environmental Services | 755010 | 4 | 36 | 1539 | Community and social services | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 150 | 001 | New-150 | Yes |  | Community | Recreational Facilities | KPA2 | 13, 21,23 | Development of Community Parks(Inland, Midlands and Coastal) | USDG | 3000000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 658026.64 | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Specifications for playground equipment have been approved by the BSC on the 29/08/2014. Requisitions & quotes for installation of Palisade Fencing (Contract 144) amounting to R 658 023 were submitted to SCM on the 04/08/2014 for processing. | 0 | 0 |  |  |  | 0 |  | 0 | 4531.56 | 634.41 | 5165.97 | 4531.56 | 5165.97 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4531.56 | 5165.97 |  | 2995468.44 | 2994834.03 | 0.1511% | 0.1722%
Community Services | Cleansing Administration Support | 4.4 - Asset Risk & Financial Services |  | 755010 | 5 | 05 | 1505 | Budget and treasury | Amenities | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Asset Replacements - Insurance | Own Funds |  |  | 0 |  | 0 |  | 0 |  |  | 14000 | 14000 |  |  | 0 |  |  | 0 | 13675.44 |  | 13675.44 | [28 empty] | 13675.44 | 13675.44 |  | 324.56 | 324.56 | 97.68% | 97.68%
Community Services | Interments | 9.7 - Interments | Environmental Services | 755025 | 4 | 36 | 1540 | Environmental Protection | Environmental Services | 4 | 36 |  | 05 | 07 | 01 | 01 | 220 | 001 | New-220 | Yes |  | Community | Cemeteries | KPA2 | All Wards | Development and Upgrading of Cemeteries(Inland, Midland and Coastal) | USDG | 12040943 |  | 8040943 | 3000000 | 11040943 | 7500000 | 18540943 |  | 10000000 |  | 10000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | The department of cemeteries and crematorium is awaiting the expenditure from arts & culture to exclude the funding that was taken from their budget in the 213/14 fin year. The balance of the funding for the development and upgading of cemetreries will utilised to complete the Fort Jackson NU 15 road infrastructure as well as the tarring of the Steve Biko access road. The fencing of the KWT extention will be included. | 8000000 | 8000000 |  |  |  | 0 | 91583.2 | 94326.92 | 581732.54 | 8018.19 | 589750.73 | 673315.74 | 684077.65 | 660644.36 | 88006.48 | 748650.84 | 1691335.57 | 212536.29 | 1903871.86 | 3734448.25 | 432675.81 | 4167124.06 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4981912.06 | 6759743.92 | 7503724.41 |  | 4281199.08 | 3537218.59 | 61.22% | 67.96% | 10000000
Community Services |  | 9.7 - Interments |  | 755025 | 6 | 01 | 1523 | Environmental Protection | Amenities |  |  |  | 05 | 07 | 01 | 01 | 250 | 002 | New-250 | Yes | [5 empty] | Cemetery Vehicles | Own Funds c/o | [9 empty] | 1700000 | 1700000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 1700000 | 1700000 | 0% | 0% | The department in conjuction with fleet management (machanical workshop) will be purchasing vehicles i.e. 2 X 4x4 bakkies, a sedan and 2 X 2 and half Ton.
Community Services | Interments | 4.4 - Asset Risk & Financial Services |  | 755025 | 5 | 05 | 1512 | Budget and treasury | Amenities | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  |  |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 57250 | 57250 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 57250 | 57250 | 0% | 0%
Community Services | Libraries | 4.4 - Asset Risk & Financial Services |  | 760010 | 5 | 05 | 1508 | Budget and treasury | Amenities | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  |  |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 1700 | 1700 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 1700 | 1700 | 0% | 0% | The monitor has been procured for Berlin Library and commissioned into use.
Community Services | Halls | 9.14 - Halls | Amenities | 760025 | 4 | 36 | 1541 | Community and social services | Amenities |  |  |  | 05 | 07 | 01 | 01 | 170 | 001 | New-170 | Yes |  | Community |  | KPA2 |  | Construction of Nompumelelo Halls | USDG |  |  | 4000000 |  | 4000000 | -3000000 | 1000000 |  | 7000000 |  | 7000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 7000000 | 7000000 | 0% | 0% | BEC approved cancellation of Contract 3021. A cancellation memorandum was drafted to the CM and delivered to SCM on 29 September 2014 for signature. Await return thereof in order to submit CM's office for final approval/signature. | 0 | 0 | [19 empty] | 0 | [14 empty] | 0 |  | 4000000 | 4000000 | 0% | 0%
Community Services | Halls | 9.14 - Halls | Amenities | 760025 | 4 | 36 | 1542 | Community and social services | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 170 | 001 | New-170 | Yes |  | Community | Halls | KPA2 | 42,39,13,33,5 | Development and Upgrading of Community Halls - War Memorial Hall Upgrade of Parking Area, O.R.Tambo Hall Upgrade of Parking Area, Egoli Community Hall( New Hall), Needs Camp Community Hall Upgrade, Orient Theatre Upgrade, Continuation of KWT Town Hall and NU 5 Hall Mdantsane | USDG | 10000000 |  | 10000000 | -4000000 | 6000000 | -5000000 | 1000000 |  | 3000000 |  | 3000000 | 0 | 0 | 0 | 47492.13 | 5262.9 | 52755.03 | 121503.65 | 17010.51 | 138514.16 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 168995.78 | 191269.19 |  | 2831004.22 | 2808730.81 | 5.633% | 6.376% | Informal Tenders are in process for the refurbishment of Needs Camp Community Hall. War Memorial Hall and OR Thambo new parking areas - a site meeting was held with contractors on 19/09/2014. Waiting for quotation as per Contract 26 Annual Tender. | 9000000 | 9000000 |  |  |  | 0 | 123401.18 | 126631 | 485376.34 | 65891.88 | 551268.22 | 608777.52 | 677899.22 | 295837.21 | 8054.91 | 303892.12 | 132480 |  | 132480 | 727758.62 | 16971.31 | 744729.93 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1574808.82 | 1764853.35 | 1859001.27 |  | 4235146.65 | 4140998.73 | 29.41% | 30.98% | 20000000
Community Services |  | 9.14 - Halls |  | 760025 | 6 | 01 | 1524 | Community and social services | Amenities |  |  |  | 05 | 07 | 01 | 01 | 170 | 002 | New-170 | Yes | [5 empty] | Reeston Community Hall Renovations | Own Funds c/o | [9 empty] | 100000 | 100000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 100000 | 100000 | 0% | 0% | Await authorisation to utilise funds on non-municipal property. This budget is not sufficient to renovate the community hall
Community Services |  | 9.14 - Halls |  | 760025 | 6 | 01 | 1525 | Community and social services | Amenities |  |  |  | 05 | 07 | 01 | 01 | 170 | 002 | New-170 | Yes | [5 empty] | Continuation of Refurbishment of KWT Hall / Cambridge | Own Funds c/o | [9 empty] | 1075698 | 1075698 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 1075698 | 1075698 | 0% | 0% | BEC approved the cancellation of Contract 3032. A cancellation memorandum was drafted to the CM and delivered to SCM on 29 September 2014 for signature. Await return thereof in order to submit the CM's office for final approval/signature.
Community Services |  | 9.14 - Halls |  | 760025 | 6 | 01 | 1534 | Community and social services | Support Services |  |  |  | 05 | 07 | 01 | 01 | 271 | 002 | New-260 | Yes | [5 empty] | Replacement of 2 X Hifgh back chairs, 1 X Piano and 2 X Bar Stools | Own Funds c/o | [9 empty] | 51000 | 51000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 51000 | 51000 | 0% | 0% | SCM have indicated that the replacement of the items must go out to informal tender.
Community Services |  | 9.14 - Halls |  | 760025 | 6 | 01 | 1535 | Community and social services | Support Services |  |  |  | 05 | 07 | 01 | 01 | 271 | 002 | New-260 | Yes | [5 empty] | Replacement of Stove and Fridge | Own Funds c/o | [9 empty] | 12000 | 12000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 12000 | 12000 | 0% | 0% | Requisition completed & sent to SCM.
Community Services |  | 9.14 - Halls |  | 760025 | 4 | 35 | 1510 | Community and social services | Amenities |  |  |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes | [5 empty] | Reeston MPCC - DVRI | HSDG-(MPCC) | [9 empty] | 10068500 | 10068500 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 10068500 | 10068500 | 0% | 0% | Await authorisation to utilise funds on non municipal property
Community Services | Sportsfields | 9.16 - Sportsfields |  | 765010 | 4 | 01 | 1545 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes |  |  | KPA2 |  | Sports equipment and structures | Own Funds | [8 empty] | 1500000 |  | 1500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 314950 | 0 | 0 |  | 1500000 | 1500000 | 0% | 0% | Service Provider was appointed for goal post. Informal Tender for Cricket covers was awarded. Trailer - price HDI was done awaiting order from Supply Chain. Site meeting for Pedestrian roller and resurfacing of Selborne Tennis was held on the 09/09/2014 , informal tender closed on 19/09/2014. | 0 | 0
Community Services | Sportsfields | 9.16 - Sportsfields |  | 765010 | 4 | 01 | 1546 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Community | Sportsfields | KPA2 | 42,33,47,36,41,43,37,43,19,3 | Equipment for Jan Smuts Stadium | Own Funds | [8 empty] | 41907 |  | 41907 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 41907 | 41907 | 0% | 0% | Two marking machines were received by SCM.
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1543 | Sport and recreation | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Community | Swimming Pool | KPA2 | 20, 46 | Redevelopment of Mdantsane NU 2 Swimming Pool and Upgrading of Waterworld | USDG | 5000000 |  | 5000000 | -5000000 | 0 |  | 0 |  | 15000000 | -5000000 | 10000000 | 0 | 0 | 0 |  |  | 0 | 2024.82 | 283.48 | 2308.3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 2024.82 | 2308.3 |  | 9997975.18 | 9997691.7 | 0.02025% | 0.02308% | Tender was closed on the 09/09/2014 for Nu2 Mdantsane Pool and four tender document were received. Awaiting date of assessment, to be suppled by Supply Chain. | 5000000 | 5000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  | 10000000
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1544 | Sport and recreation | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Community | Sportsfields | KPA2 | 42,33,47,36,41,43,37,43,19,3 | Upgrading of Dimbaza and Zwelitsha Stadium | USDG | 4000000 |  | 4000000 | 1800000 | 5800000 | -5384413 | 415587 |  | 2250000 |  | 2250000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2250000 | 2250000 | 0% | 0% | Tender from previous financial year is in the process of being cancelled. Bid specification document for this financial year will be submitted to BSC as soon as the tender from last financial year is cancelled. | 4750000 | 4750000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 2111.29 | 295.58 | 2406.87 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2111.29 | 2406.87 |  | 5797888.71 | 5797593.13 | 0.0364% | 0.0415%
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1545 | Sport and recreation | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Community | Sportsfields | KPA2 | 42,33,47,36,41,43,37,43,19,3 | Upgrading of Floodlights at Victoria Grounds, Bhisho Stadium, Ginsberg stadium, Sisa Dukashe Stadium, Alfred Schoeman Stadium, North End Stadium, Jan Smuts Stadium, Amalinda Stadium, and Gompo Stadium | USDG | 5000000 |  | 5000000 | -1000000 | 4000000 | -2500000 | 1500000 |  | 3000000 |  | 3000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 3000000 | 3000000 | 0% | 0% | Service Provider is done with the remedial work at Jan Smuts, North End, Selborne Tennis, Bunkers Hill, Buffalo City Stadiumand Sisa Dukashe. | 0 | 0 |  |  |  | 0 |  | 0 | 7827.24 | 1095.81 | 8923.05 | 7827.24 | 8923.05 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7827.24 | 8923.05 |  | 3992172.76 | 3991076.95 | 0.1957% | 0.2231%
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1546 | Sport and recreation | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes |  |  | KPA2 |  | Upgrading of Phakamisa and Mount Coke sports fields | USDG | [8 empty] | 1000000 |  | 1000000 | 0 | 0 | 0 | 190000 |  | 190000 | 746098.5 | 0 | 746098.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 936098.5 | 936098.5 |  | 63901.5 | 63901.5 | 93.61% | 93.61% | Meeting was held on the 30/09/2014 with Cllr's and Sport Committee. Palisade fencing needs repairs at Phakamisa sportsfield and Mount Coke. Sports committee to confirm leveling and fencing of sportsfields to be put on scope of work. | 1500000 | 0
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1566 | Sport and recreation | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Community | Swimming Pool | KPA2 | 20, 46 | Upgrading of Waterworld | USDG | [9 empty] | 5000000 | 5000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 5000000 | 5000000 | 0% | 0% | Tender was closed on the 05/9/2014 and four tender document were received. Awaiting date of assessment, to be supply by Supply Chain.
Community Services |  | 9.16 - Sportsfields |  | 765010 | 6 | 36 | 1501 | Sport and recreation | Amenities |  |  |  | 05 | 07 | 01 | 01 | 160 | 002 | Renewal-160 |  | Yes |  |  |  |  | Completion of Upgrading of 2010 Stadium | DSRAC c/o | [9 empty] | 2686285 | 2686285 |  |  | 0 |  |  | 0 | 180000 |  | 180000 | [28 empty] | 180000 | 180000 |  | 2506285 | 2506285 | 6.701% | 6.701%
Community Services |  | 9.16 - Sportsfields |  | 765010 | 6 | 01 | 1526 | Sport and recreation | Amenities |  |  |  | 05 | 07 | 01 | 01 | 160 | 002 | Renewal-160 |  | Yes |  |  |  |  | Upgrading of Resort and Purchase of Equipment | Own Funds c/o | [9 empty] | 384660 | 384660 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 384660 | 384660 | 0% | 0% | Service provider appointed to deliver equipment from the last financial year, but due to price escalation from the service provider SCM does not agree and are investigating if the contract from the service providers side has a price escalation in and if not the service provider will have to deliver the balance of the order/ goods as per the original order.
Community Services | Swimming Pools | 9.17 - Swimming Pools |  | 765015 | 4 | 01 | 1547 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes |  |  | KPA2 |  | Refurbishment of Swimming Pools | Own Funds | [8 empty] | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Draft formal tender documents for Heating system at Joan Harrison, King Williams Town and Zwelitsha Pool to be finalized. Draft formal tender for Re-tiling and paving of Joan Harrison Pool will be finalized on 30/09/2014. | 2500000 | 0
Community Services | Aquarium | 9.18 - Aquarium | Amenities | 765020 | 4 | 36 | 1547 | Sport and recreation | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 190 | 001 | Renewal-190 |  | Yes |  |  | KPA2 |  | Relocation of Aquarium | USDG | [8 empty] | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Draft specification document for relocation of Aquarium to be finalized. Deviation report for appointment of a professional Service Provider for the urgent remedial work was resubmitted to the GM's office on the 30/09/2014. | 5000000 | 10000000
Community Services | Zoo | 9.19 - Zoo |  | 765025 | 4 | 01 | 1548 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 190 | 001 | Renewal-190 |  | Yes |  |  | KPA2 |  | Upgrading of Zoo Facilities | Own Funds | [8 empty] | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Informal tender for installation and barriers was submitted on the 12/09/2014 and awaiting advertisement at Supply Chain. Informal Tender for paving was submitted on the 08/09/2014 at Supply Chain also awaiting SCM to advertise. Informal tender for boundary wall and cages - scope of work to be finalized. | 1500000 | 0
Community Services | Zoo | 9.16 - Sportsfields |  | 765025 | 4 | 01 | 1549 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 190 | 001 | Renewal-190 |  | Yes |  |  | KPA2 |  | FEL Zoo - Aquarium | Own Funds | [8 empty] | 238502 |  | 238502 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 238502 | 238502 | 0% | 0% | Informal tender for repairs of Penguin enclosure, balustrade and upgrade of seabird rehabilitation pool was submitted to SCM. The designs of Sungazer enclosure to be included with the designs for the boundary wall and enclosure at the Zoo.
Community Services | Beaches | 9.20 - Beaches |  | 765030 | 4 | 01 | 1550 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 190 | 001 | Renewal-190 |  | Yes |  |  | KPA2 |  | Upgrading of Beaches Facilities | Own Funds | [8 empty] | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Informal tender for Eastern Beach for Electricity, plumbing repairs and repairs of three ablution blocks was submitted to SCM. Submitted informal tender for quantity surveyor for all beaches to SCM. Finalizing specifications for appointment of a Structural Engineer for the Orient Beach Complex. | 1500000 | 0
Community Services | Cleansing Administration Support | 9.1 - Office of The Director of Community Services |  | 770005 | 4 | 01 | 1552 | Community and social services | Waste Management | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 |  | Office Furniture and Equipment (Solid Waste Management) | Own Funds | [8 empty] | 300000 |  | 300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 300000 | 300000 | 0% | 0% | Specification has been submitted to Supply Chain on Friday 5 Sept 2014
Community Services | Cleansing Administration Support | 4.4 - Asset Risk & Financial Services |  | 770005 | 5 | 05 | 1510 | Budget and treasury | Amenities | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 1700000 | 1700000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 1700000 | 1700000 | 0% | 0% | Replacement of vehicles done at mechanical workshops
Community Services |  | 9.17 - Swimming Pools |  | 770005 | 6 | 01 | 1527 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 271 | 002 | New-260 | Yes | [5 empty] | Grass Cutting Equipment | Own Funds c/o | [9 empty] | 668126 | 668126 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 668126 | 668126 | 0% | 0% | Specifications for purchasing grass cutting equipment have been finalised are ready to go to BSC possibly on the 19/09/2014
Community Services |  | 9.23 - Refuse Removal |  | 770010 | 6 | 01 | 1533 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes |  | Community | Refuse | KPA2 | All Wards | Acquisition of Solid Waste Plant | Own Funds c/o | [9 empty] | 8804587 | 8804587 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 8804587 | 8804587 | 0% | 0% | Tender has been awarded awaiting delivery
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1528 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Upgrade & Refurbishment Disposal Sites - Phase 2 - Design & Construction of 3rd and 4th Cell and Ancillary Works | Own Funds c/o | [9 empty] | 1774658 | 1774658 |  |  | 0 |  |  | 0 | 1488773.47 |  | 1488773.47 | [28 empty] | 1488773.47 | 1488773.47 |  | 285884.53 | 285884.53 | 83.89% | 83.89% | Project in progress
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1529 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Solid Waste Programme- Weigh Bridge KWT | Own Funds c/o | [9 empty] | 2000000 | 2000000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | EPMO assisting the department in connection with this project
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1530 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Waste Management Programme - Plant and Equipment | Own Funds c/o | [9 empty] | 1268845 | 1268845 |  |  | 0 |  |  | 0 |  |  | 0 | [27 empty] | 1258179 | 0 | 0 |  | 1268845 | 1268845 | 0% | 0% | Awaiting delivery
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1531 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Counterfunding - Leiden Twinning - Solid Waste Drop-Off Points | Own Funds c/o | [9 empty] | 967405 | 967405 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 967405 | 967405 | 0% | 0% | Service provider has been appointed.
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1532 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Specialised Solid Waste Vehicles | Own Funds c/o | [9 empty] | 4000000 | 4000000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 4000000 | 4000000 | 0% | 0% | Awaiting delivery
Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 9.27 - E.L Regional Waste Disposal Site & Transfer Station | Waste Management | 770030 | 4 | 36 | 1548 | Waste Management | Waste Management | 4 | 36 |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes |  | Community | Refuse | KPA2 | Will provide ward no, as soon as land is availed/identified | Construction of Transfer Stations - 3 x Sites | USDG | 0 |  | 0 |  | 0 |  | 0 |  | 5000000 |  | 5000000 | 0 | 0 | 0 | 3976.02 | 556.64 | 4532.66 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 3976.02 | 4532.66 |  | 4996023.98 | 4995467.34 | 0.07952% | 0.09065% | Tender will be submitted in the next BEC | 5000000 | 5000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0%
Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 9.27 - E.L Regional Waste Disposal Site & Transfer Station | Waste Management | 770030 | 4 | 36 | 1549 | Waste Management | Waste Management | 4 | 36 |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes |  |  |  | KPA2 |  | KWT Tanery Site | USDG | [8 empty] | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Tender will be re - advertised | 1000000 | 1000000
Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 9.27 - E.L Regional Waste Disposal Site & Transfer Station | Waste Management | 770030 | 4 | 36 | 1550 | Waste Management | Waste Management | 4 | 36 |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes |  | Community | Refuse | KPA2 | 25 | Construction and Rehabilitation of Waste Cells | USDG | 0 |  | 0 |  | 0 |  | 0 |  | 20000000 |  | 20000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 20000000 | 20000000 | 0% | 0% | Tender will be submitted in the next BEC | 20710100 | 14412415 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0%
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 4 | 01 | 1560 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes | [5 empty] | Solid Waste Mechanical Plant and Vehicles | Own Funds | [9 empty] | 40000000 | 40000000 |  |  | 0 |  |  | 0 |  |  | 0 | [28 empty] | 0 | 0 |  | 40000000 | 40000000 | 0% | 0% | Awaiting delivery
Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 4 | 01 | 1551 | Waste Management | Waste Management | 4 | 01 |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes |  | Community |  | KPA2 |  | 17800 X240 Litre Wheelie Bins | Own Funds |  |  | 0 | 51990000 | 14240000 |  | 14240000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 | 641246.4 |  | 641246.4 | 961869.6 |  | 961869.6 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3009600 | 1603116 | 1603116 |  | 8396884 | 8396884 | 16.03% | 16.03% | The funding will pay the C3041 and C3046 which were awarded in the last financial year. | 10000000 | 10000000 | [19 empty] | 0 | [13 empty] | 0 | 0 |  | 14240000 | 14240000 | 0% | 0%
[26 empty] | TOTAL : COMMUNITY SERVICES |  | 39040943 | 0 | 39040943 | 46790000 | 48080943 | -8384413 | 39696530 | 0 | 86530409 | 77334714 | 163865123 | 0 | 0 | 0 | 882714.55 | 5819.54 | 888534.09 | 3513945.48 | 17293.99 | 3531239.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5240755.64 | 4396660.03 | 4419773.56 | 0 | 159468462.97 | 159445349.44 | 2.683% | 2.697% |  | 75960100 | 67662415 | 0 | 0 | 0 | 0 | 214984.38 | 220957.92 | 1079467.68 | 75640.29 | 1155107.97 | 1294452.06 | 1376065.89 | 956481.57 | 96061.39 | 1052542.96 | 1825926.86 | 212831.87 | 2038758.73 | 4462206.87 | 449647.12 | 4911853.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6556720.88 | 8539067.36 | 9379221.57 | 0 | 39541875.64 | 38701721.43 | 17.76% | 19.51%
[26 empty] | TOTAL : CAPITAL PROJECTS - ALL DIRECTORATES | [9 empty] | 932007423 | 116774633 | 1048839556 | 4279296.15 | 305995.65 | 4585291.8 | 36998451.88 | 3733785.71 | 40732237.59 | 63771348.91 | 5239427.37 | 69010776.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55077324.48 | 105049096.94 | 114328305.67 | 0 | 943790459.06 | 934511250.33 | 10.02% | 10.9%
Asset Replacement |  | 4.4 - Asset Risk & Financial Services |  | 320005 | 5 | 05 | 1501 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds |  |  |  |  | 0 |  | 0 |  | 10000000 |  | 7645150 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 7645150 | 7645150 | 0% | 0% | This is to be used to replace assets iro insurance claims. | 10000000 | 10000000
[26 empty] | TOTAL : BCMM CAPITAL BUDGET |  | #REF! | #REF! | #REF! | #REF! | #REF! | 12199892 | #REF! | 2000000 | 942007423 | 116774633 | 1056484706 | 4279296.15 | 305995.65 | 4585291.8 | 36998451.88 | 3733785.71 | 40732237.59 | 63771348.91 | 5239427.37 | 69010776.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55077324.48 | 105049096.94 | 114328305.67 | 0 | 951435609.06 | 942156400.33 | 9.943% | 10.82% |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
91458961
106541039
[26 empty] | Projects Deleted from the list |  | #REF!
Directorate of Development Planning |  |  |  | 620005 | [14 empty] | Renewal-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks |  |  | Public Transport Facilities | PTISG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 50000000 | [42 empty] | 50000000
Directorate of Development Planning |  |  |  | 615095 | [14 empty] | Renewal-312 |  |  | Other | Car Parks,Bus termonals & Taxi ranks |  |  | Replacement of Lift Shoprite Building | Own Funds |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 3500000
[36 empty] | 0 | [47 empty] | 0 | 3500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Oxford Street Mall (Pedestrianisation/Public Transport Zone) | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 6000000 | [42 empty] | 6000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Northwest Expressway widening and extension to Amalinda Main Road | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 5000000 | [42 empty] | 5000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Fitzpatrick Road/Currie Street Link Road (Sleeper Site) | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 4000000 | [42 empty] | 4000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Non-Motorised Transport Facilities Implementation | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 5000000 | [42 empty] | 5000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Traffic congestion improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 2000000 | [42 empty] | 2000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Bonza Bay Road LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 1500000 | [42 empty] | 1500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Vincent and Berea LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 1500000 | [42 empty] | 1500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | KWT LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 1500000 | [42 empty] | 1500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Mdantsane LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 1500000 | [42 empty] | 1500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Bhisho LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [47 empty] | 0 | 1500000 | [42 empty] | 1500000
[36 empty] | 86530409 | [47 empty] | 75960100
[36 empty] | 86530409 | [47 empty] | 75960100
[36 empty] | 0 | [47 empty] | 0
[38 empty] | 507185871 | [6 empty] | 549298835
[38 empty] | 507135271 | [6 empty] | 549349435
[38 empty] | 50600 | [6 empty] | -50600
17000000