## 2014-2017 Projects
ANNEXURE "E"
BUFFALO CITY METROPOLITAN MUNICIPALITY
CAPITAL EXPENDITURE REPORT AS AT 31 MARCH 2015
Directorate | Cost centre name | C5C | USDG Service | Cost Centre No. |  |  |  | A5 | Service | V1 | V1 | V1 | VT | VT | VT | VT | VT | VT | 34a & 34b | New Asset | Renewal | A9 | Asset Sub Class- SA36 | KPA'S | Ward No. | Project Name | Funding Source | 2013/2014 Approved Budget | Adjustment | 2013/2014 Rollover Adjustment Budget | Adjustments | 2013/14 Conditional Grants Rollover Adjustment Budget | Mid-Year Adjustments | 2013/2014 Mid-Year Adjusted Budget | Savings | 2014/2015 Approved Capital Budget | Adjustment | 2014/2015 Rollover Adjustment Budget | Adjustment | 2014/2015 Mid-year Adjustment Budget | July 2014 | Vat | July 2014 (VAT incl) | August 2014 | Vat | August 2014 (VAT incl) | September 2014 | Vat | September 2014 (VAT incl) | October 2014 | Vat | October 2014 (VAT incl) | November 2014 | Vat | November 2014 (VAT incl) | December 2014 | Vat | December 2014 (VAT incl) | January 2015 | Vat | January 2015 (VAT incl) | February 2015 | Vat | February 2015 (VAT incl) | March 2015 | Vat | March 2015 (VAT incl) | April 2015 | Vat | April 2015 (VAT incl) | May 2015 | Vat | May 2015 (VAT incl) | June 2015 | Vat | June 2015 (VAT incl) | Commitments as per Venus | YTD Expenditure | YTD Expenditure (VAT incl) | Commitments (Outstanding invoices for work done not yet paid) | Available Budget | Available Budget ( Budget -Expenditure including VAT) | % Expenditue | % Expenditure (including VAT) | Comments | 2015/2016 Draft Capital Budget | 2016/2017 Draft Capital Budget | 2017/2018 Draft Capital Budget | 2018/2019 Draft Capital Budget | July Expenditure | July Expenditure(VAT inc.) | August Expenditure | August Expenditure ( VAT inc.) | September Expenditure | Vat | September Expenditure (VAT inc.) | 1st Quarter Expenditure (Exc. VAT) | 1st Quarter Expenditure (incl. VAT) | October Expenditure | Vat | October Expenditure (VAT inc.) | November Expenditure | Vat | November Expenditure (VAT inc.) | December Expenditure | Vat | December Expenditure (VAT inc.) | January Expenditure | January Expenditure (VAT inc.) | February Expenditure | February Expenditure (VAT inc.) | March Expenditure | March Expenditure (VAT inc.) | April Expenditure | April Expenditure (VAT inc.) | May Expenditure | May Expenditure ( VAT inc.) | June Expenditure | June Expenditure ( VAT inc.) | Commitments as per Venus | YTD Expenditure | YTD Expenditure ( VAT inc.) | Commitments (Outstanding invoices for work done not yet paid) | Available Budget | Available Budget ( Budget -Expenditure including VAT) | % Expenditue | % Expenditue including VAT) | 2017/2018 Draft Capital Budget | 2018/2019 Draft Capital Budget | 2017/2018 Draft Capital Budget | Comments
EXECUTIVE SUPPORT SERVICES | [25 empty] | DIRECTORATE OF EXECUTIVE SUPPORT SERVICES
Executive Support Services | Office of the Director of Executive Support Services | 1.1 - Office of The Director of Executive Support |  | 105005 | 4 | 01 | 1501 | Executive and council | Support Services | 4 | 01 |  | 05 | 01 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA5 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 278508.77 |  | 278508.77 |  |  | 0 |  |  | 0 | 3699 |  | 3699 |  |  | 0 | 1592 |  | 1592 |  |  | 0 |  |  | 0 |  |  | 0 | 20262.04 | 283799.77 | 283799.77 |  | 216200.23 | 216200.23 | 56.76% | 56.76% | Office equipment and furniture is being procured for new offices for youth Advisory Centre in Duncan Village. Replacement of old furniture for staff is underway. Funding will be spent by the end of the FY. | 500000 | 500000
Executive Support Services | Office of the Director of Executive Support Services | 4.4 - Asset Risk & Financial Services |  | 105005 | 5 | 05 | 1518 | Budget and treasury | Support Services |  |  |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of Laptop - LT Sikhinzi - A13/116 | Own Funds | [10 empty] | 13000 |  | 13000 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 10826 | 0 | 0 |  | 13000 | 13000 | 0% | 0% | Procurement process underway
Executive Support Services | Office of the Director of Executive Support | 4.4 - Asset Risk & Financial Services |  | 105005 | 5 | 05 | 1527 | Budget and treasury | Support Services | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of Laptop J.A. Benneck - A14/30 | Own Funds | [10 empty] | 13000 |  | 13000 | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 10954 |  | 10954 |  |  | 0 | [9 empty] | 0 | 10954 | 10954 |  | 2046 | 2046 | 84.26% | 84.26% | Laptop received, balance will declared as savings.
Executive Support Services | Office of the Director of Executive Support Services | 1.1 - Office of The Director of Executive Support |  | 105005 | 6 | 01 | 1501 | Executive and council | Support Services |  |  |  | 05 | 01 | 01 | 01 | 270 | 002 | New-270 | Yes |  | Other assets |  |  | All Wards | Office Furniture and Equipment (Councillors) | Own Funds c/o | [9 empty] | 1284326 | 1284326 |  | 1284326 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 7100 |  | 7100 |  |  | 0 |  |  | 0 |  |  | 0 | 766211.27 | 7100 | 7100 |  | 1277226 | 1277226 | 0.5528% | 0.5528% | An order of R852,356.65 has been issued for Councillor's office equipment. Office furniture for Portfolio Councillors is being procured.
Executive Support Services | Office of the Director of Executive Support Services | 1.1 - Office of The Director of Executive Support |  | 105005 | 6 | 01 | 1502 | Executive and council | Support Services |  |  |  | 05 | 01 | 01 | 01 | 271 | 002 | New-260 | Yes |  | Other assets |  |  | All Wards | Back up Generator | Own Funds c/o | [9 empty] | 1489573 | 1489573 |  | 1489573 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 610843.75 |  | 610843.75 | [9 empty] | 0 | 610843.75 | 610843.75 |  | 878729.25 | 878729.25 | 41.01% | 41.01% | A process of linking the generator to the City Hall substation is underway through assistance from Electrical department. Expenditure to date is R696 361.88. Balance will be paid by end of May 2015.
Executive Support Services | Office of the Director of Executive Support Services | 1.1 - Office of The Director of Executive Support |  | 105005 | 6 | 01 | 1503 | Executive and council | Support Services |  |  |  | 05 | 01 | 01 | 01 | 270 | 002 | New-270 | Yes |  | Other assets |  |  | All Wards | Councillors Office Accomodation | Own Funds c/o | [9 empty] | 2996498 | 2996498 |  | 2996498 | [5 empty] | 0 |  |  | 0 | 1325.34 |  | 1325.34 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 1325.34 | 1325.34 |  | 2995172.66 | 2995172.66 | 0.04423% | 0.04423% | Procurement underway, funding will not be spent by the end of the FY however a commitment would have been made for the delivery of Park Homes.
Executive Support Services | Counsillors | 4.4 - Asset Risk & Financial Services |  | 105012 | 5 | 05 | 1504 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Asset Replacements - Insurance | Own Funds |  |  |  |  | 0 |  | 0 |  |  | 7619 | 7619 |  | 7619 |  |  | 0 |  |  | 0 |  |  | 0 | 7619 |  | 7619 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 7619 | 7619 |  | 0 | 0 | 100% | 100% | Laptop replaced.
Executive Support Services | Counsillors | 4.4 - Asset Risk & Financial Services |  | 105012 | 5 | 05 | 1542 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of Laptop - Cllr. GT Norexe | Own Funds |  |  |  |  | 0 |  | 0 |  |  | 7619 |  | 11000 | 11000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 11000 | 11000 | 0% | 0% | Procurement process underway.
Executive Support Services | Development Co-Oeration | 1.11 - Development Co-Operation |  | 120005 | 6 | 83 | 1501 | Executive and council | Housing |  |  |  | 05 | 01 | 01 | 01 | 312 | 002 | New-312 | Yes |  | Other assets |  |  |  | Garcia Flats | Leiden c/o | [9 empty] | 458860 | 458860 |  | 458860 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 458860 | 458860 | 0% | 0% | Tender process for the fencing underway
Executive Support Services | Public Relations & International Events | 4.4 - Asset Risk & Financial Services |  | 120010 | 5 | 05 | 1528 | Budget and treasury | Support Services | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of 2 x Cameras - A14/29 | Own Funds | [10 empty] | 22500 |  | 22500 | [11 empty] | 0 |  |  | 0 |  |  | 0 | 19575.96 |  | 19575.96 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 19575.96 | 19575.96 |  | 2924.04 | 2924.04 | 87% | 87% | Cameras have been purchased. Balance to be declared as savings.
Executive Support Services | Research Policy & Knowledge Management Unit | 4.4 - Asset Risk & Financial Services |  | 130005 | 5 | 05 | 1514 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 55000 | 55000 |  | 55000 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 55000 | 55000 | 0% | 0% | Informal Tender awarded. 100% of expenditure to be incurred on supply of Asset
[26 empty] | TOTAL: EXECUTIVE SUPPORT SERVICES |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 500000 | 6299495 | 6840376 | 11000 | 6851376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287453.11 | 0 | 287453.11 | 0 | 0 | 0 | 0 | 0 | 0 | 23274.96 | 0 | 23274.96 | 10954 | 0 | 10954 | 619535.75 | 0 | 619535.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 797299.31 | 941217.82 | 941217.82 | 0 | 5910158.18 | 5910158.18 | 13.74% | 13.74% |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0
[32 empty] | 0 |  | 0 | [74 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
MUNICIPAL MANAGER'S OFFICE | [25 empty] | MUNICIPAL MANAGERS 'OFFICE | [5 empty] | 0 |  | 0 | [74 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Municipal Manager's Office | Municipal Manager's Office | 2.1 - Office of The Municipal Manager & Support Services |  | 205005 | 4 | 67 | 1501 | Executive and council | Support Services | 4 | 67 |  | 05 | 02 | 01 | 01 | 320 | 001 | New-320 | Yes |  | Other | Other | KPA2 | All Wards | Neighbourhood Development Partnership | NDPG | 10000000 |  | 10000000 |  | 10000000 | -10000000 | 0 |  | 5000000 |  | 5000000 |  | 5000000 | 0 | 0 | 0 |  |  | 0 | 107792 | 0 | 107792 | 2583366.68 | 376762.21 | 2960128.89 |  |  | 0 |  |  | 0 | 154576.68 | 21640.73 | 176217.41 | 1439984.69 | 122487.58 | 1562472.27 | 25842.68 | 82728.25 | 108570.93 |  |  | 0 |  |  | 0 |  |  | 0 | 572888.26 | 4311562.73 | 4915181.5 |  | 688437.27 | 84818.5 | 86.23% | 98.3% | Project is progressing well and is near completion | 16878000 | 17744000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 10000000 | 10000000 | 0% | 0%
Municipal Manager's Office | Municipal Manager's Office | 2.1 - Office of The Municipal Manager & Support Services |  | 205005 | 4 | 01 | 1502 | Executive and council | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Furniture | KPA5 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds | 250000 |  | 250000 |  | 250000 |  | 250000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 15594.59 |  | 15594.59 | 4678.7 |  | 4678.7 |  |  | 0 | 22700 |  | 22700 |  |  | 0 |  |  | 0 |  |  | 0 | 25102.35 | 42973.29 | 42973.29 |  | 457026.71 | 457026.71 | 8.595% | 8.595% | Furniture procurred for the Internal Audit Unit, the funding will be utilised by year end. | 500000 | 500000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 171173.4 | 0 | 0 |  | 250000 | 250000 | 0% | 0%
Municipal Manager's Office | Municipal Manager's Office | 2.1 - Office of The Municipal Manager & Support Services | Support Services | 205005 | 4 | 36 | 1501 | Executive and council | Support Services | 4 | 36 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other |  | KPA2 | All Wards | Furniture and Equipment - Project Management Office | USDG |  |  | 0 | 2500000 | 2500000 |  | 2500000 |  | 1500000 |  | 1500000 | -500000 | 1000000 | 0 | 0 | 0 | 170805 | 23912.7 | 194717.7 |  |  | 0 | 129259.3 |  | 129259.3 |  |  | 0 |  |  | 0 | 14483.7 | 2027.72 | 16511.42 | 8890 | 1244.6 | 10134.6 | 13566.1 | 1899.25 | 15465.35 |  |  | 0 |  |  | 0 |  |  | 0 |  | 337004.1 | 366088.37 |  | 662995.9 | 633911.63 | 33.7% | 36.61% | In the process of procuring Office Furniture for Bhisho Office | 1500000 | 1500000 | [19 empty] | 0 | [14 empty] | 0 |  | 2500000 | 2500000 | 0% | 0%
Municipal Manager's Office | Internal Audit | 4.4 - Asset Risk & Financial Services |  | 215005 | 5 | 05 | 1515 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 8500 | 8500 |  | 8500 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 5916.19 | 0 | 0 |  | 8500 | 8500 | 0% | 0% | Order was generated, process still work in progress via Supply Chain Management
[26 empty] | TOTAL: MUNICIPAL MANAGERS 'OFFICE |  | 10250000 | 0 | 10250000 | 2500000 | 12750000 | -10000000 | 2750000 | 0 | 7000000 | 8500 | 7008500 | -500000 | 6508500 | 0 | 0 | 0 | 170805 | 23912.7 | 194717.7 | 107792 | 0 | 107792 | 2712625.98 | 376762.21 | 3089388.19 | 0 | 0 | 0 | 15594.59 | 0 | 15594.59 | 173739.08 | 23668.45 | 197407.53 | 1448874.69 | 123732.18 | 1572606.87 | 62108.78 | 84627.5 | 146736.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603906.8 | 4691540.12 | 5324243.16 | 0 | 1816959.88 | 1184256.84 | 72.08% | 81.8% |  | 18878000 | 19744000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171173.4 | 0 | 0 | 0 | 12750000 | 12750000 | 0% | 0% |  |  | 0
[32 empty] | 0 |  | 0 | [74 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
HUMAN SETTLEMENTS | [25 empty] | DIRECTORATE OF HUMAN SETTLEMENTS | [5 empty] | 0 |  | 0 | [74 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Human Settlements |  | 3.2 - Office of The Chief Operations Officer |  | 250005 | 4 | 01 | 1503 | Housing | Support Services | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other | Housing | KPA2 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 | 14706.1 |  | 14706.1 |  |  | 0 | 45043.26 |  | 45043.26 |  |  | 0 | 14084.26 |  | 14084.26 |  |  | 0 |  |  | 0 | 34330.97 |  | 34330.97 |  |  | 0 |  |  | 0 |  |  | 0 | 39871.73 | 108164.59 | 108164.59 |  | 391835.41 | 391835.41 | 21.63% | 21.63% | The existing expenditure is for office furnitture that has been supplied. The service provider is expected to deliver more furniture and once the order has been received a payment will made. | 500000 | 500000
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 01 | 1504 | Housing | Housing | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other | Housing | KPA2 |  | Beneficiary Administration (Procure GPS Devices) | Own Funds | 200000 |  | 200000 |  | 200000 | 200000 | 400000 |  | 100000 |  | 100000 | -100000 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! | The department is experiencing software challenges with current available devices and therefore procurement processes are on hold until the matter is resolved. Budget to be adjusted during mid-year review. | 150000 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 01 | 1504 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 270 | 002 | New-270 | Yes |  | Other | Housing | KPA3 |  | Beneficiary Administration (Procure GPS Devices) | Own Funds c/o | [9 empty] | 102199 | 102199 | -102199 | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! | The department is experiencing software challenges with current available devices and therefore procurement processes are on hold until the matter is resolved. Budget to be adjusted during mid-year review.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 01 | 1505 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 270 | 002 | New-270 | Yes |  | Other | Housing | KPA4 |  | Refurbishment of all Rental Stock | Own Funds c/o | [9 empty] | 200000 | 200000 | -200000 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! | Budget have been transferred and centralized under Developmental Planning (Building Maintenance Section).
Human Settlements | DVRI | 3.1 - Mdantsane Urban Renewal Unit |  | 250005 | 4 | 35 | 1501 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | Reeston MPCC - DVRI | HSDG-(MPCC) | 2100000 |  | 2100000 |  | 2100000 |  | 2100000 |  | 10068500 | -10068500 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! | Phase 1 of the project completed through annual contractors. The implementing agent will commence with Phase 2 work on the 26 of February 2015 with engineering services and then top structures. | 13068500 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 33675 |  | 33675 | 53800 |  | 53800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 87475 | 87475 |  | 2012525 | 2012525 | 4.165% | 4.165%
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1502 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3: Stage 2 | HSDG | 11684600 |  | 11684600 |  | 11684600 |  | 11684600 |  | 7000000 |  | 7000000 |  | 7000000 | 0 | 0 | 0 |  |  | 0 | 1519732.96 |  | 1519732.96 | 3175774.64 |  | 3175774.64 | -4555.42 |  | -4555.42 |  |  | 0 | 1968625.75 |  | 1968625.75 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 6659577.93 | 6659577.93 |  | 340422.07 | 340422.07 | 95.14% | 95.14% | The newly appointed implementing agent is busy with site establishment in preparation for the commencement of the first phase of the project which is the upgrading of internal roads from gravel to surfaced roads, the next phase which is the construction of top structures shall follow subsequent to the completion of the first phase. Expenditure in eminent based on the above for the payment of the contractor and the professional team for construction monitoring, and the current expenditure is a result of payment of professional team fees for procurement process. | 15000000 | 20000000 | 10000000 | 10000000 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8771929.82 | 0 | 0 |  | 11684600 | 11684600 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1502 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA3 | 13 | Reeston Phase 3: Stage 2 - P1 & P3 | HSDG c/o | [9 empty] | 5104919 | 5104919 | -5104919 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 5035371.4 |  | 5035371.4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 5035371.4 | 5035371.4 |  | -5035371.4 | -5035371.4 | #DIV/0! | #DIV/0! | The newly appointed implementing agent is busy with site establishment in preparation for the commencement of the first phase of the project which is the upgrading of internal roads from gravel to surfaced roads, the next phase which is the construction of top structures shall follow subsequent to the completion of the first phase. Expenditure in eminent based on the above for the payment of the contractor and the professional team for construction monitoring, and the current expenditure is a result of payment of professional team fees for procurement process.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1503 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 3 | HSDG | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 7000000 |  | 7000000 | 14895081 | 21895081 | 2245000.06 | 0 | 2245000.06 | 3355847.36 |  | 3355847.36 | 492390.71 |  | 492390.71 | 173475.74 |  | 173475.74 |  |  | 0 | 377191.88 |  | 377191.88 |  |  | 0 |  |  | 0 | 11706833.15 |  | 11706833.15 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 18350738.9 | 18350738.9 |  | 3544342.1 | 3544342.1 | 83.81% | 83.81% | The appointed contractor for the construction of engineering internal services and top structures has commenced with the works last calendar year in April. The contractor is currently working on the first phase of 480 top structures as the relevant engineering services. The current expenditure is as a result of the abovementioned. | 15000000 | 12000000 | 10000000 | 7590000 |  | 0 | 48240 | 48240 |  |  | 0 | 48240 | 48240 |  |  | 0 |  |  | 0 | 18152.9 |  | 18152.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 66392.9 | 66392.9 |  | 9933607.1 | 9933607.1 | 0.6639% | 0.6639% |  |  |  |  | 44000000
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1503 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 3 - P1 & P3 | HSDG c/o | [9 empty] | 6922271 | 6922271 | 5104919 | 12027190 |  |  | 0 |  |  | 0 | 21421.49 |  | 21421.49 | 6168337.19 |  | 6168337.19 | 542889.77 |  | 542889.77 | 26965.7 |  | 26965.7 |  |  | 0 |  |  | 0 | 3927575.69 |  | 3927575.69 | [9 empty] | 0 | 10687189.84 | 10687189.84 |  | 1340000.16 | 1340000.16 | 88.86% | 88.86% | The appointed contractor for the construction of engineering internal services and top structures has commence with the works last calendar year in April. The contractor is currently working on the first phase of 480 top structures as the relevant engineering services. The current expenditure is as a result of the abovementioned, the allocated budget shall be spent by the end of this financial year.
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1502 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 2 | USDG | 6815400 |  | 6815400 |  | 6815400 | 5000000 | 11815400 |  | 2970400 | 1306712 | 4277112 | -1093508 | 3183604 | 0 | 0 | 0 |  |  | 0 | 183604.45 | 25704.63 | 209309.08 |  |  | 0 |  |  | 0 | 4093507.54 | 573091.06 | 4666598.6 |  |  | 0 |  |  | 0 | -4093507.54 | -573091.06 | -4666598.6 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 183604.45 | 209309.08 |  | 2999999.55 | 2974294.92 | 5.767% | 6.575% | The newly appointed implementing agent is busy with site establishment in preparation for the commencement of the first phase of the project which is the upgrading of internal roads from gravel to surfaced roads, the next phase which is the construction of top structures shall follow subsequent to the completion of the first phase. Expenditure in eminent based on the above for the payment of the contractor and the professional team for construction monitoring, and the current expenditure is a result of payment of professional team fees for procurement process. | 5000000 | 10000000 |  |  |  | 0 | 4119.6 | 4119.6 | -4119.6 | 0 | -4119.6 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3614075.5 | 0 | 0 |  | 6815400 | 6815400 | 0% | 0% | 55265000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1551 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 3 | USDG |  |  |  |  | 0 |  | 0 |  | 2000000 |  | 2000000 | 15500000 | 17500000 | 2000000 | 280000 | 2280000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 4260926.99 | 596529.78 | 4857456.77 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 6260926.99 | 7137456.77 |  | 11239073.01 | 10362543.23 | 35.78% | 40.79% | The appointed contractor for the construction of engineering internal services and top structures has commenced with the works last calendar year in April. The contractor is currently working on the first phase of 480 top structures as the relevant engineering services. The current expenditure is as a result of the abovementioned. | 5000000 | 10000000 | [44 empty] | 17000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1503 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam Ikhwezi Block 1 | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 56248 | 7874.72 | 64122.72 | 148135 | 20738.9 | 168873.9 | 77868.65 | 10901.61 | 88770.26 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 282251.65 | 321766.88 |  | 217748.35 | 178233.12 | 56.45% | 64.35% | Appointed consultants have finalised preliminary designs and submitted to service branches and were approved. Consultant is busy with the tender documentation. | 5900000 | 13000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 175438.6 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1504 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam Ikhwezi Block 2 | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 71570 | 10019.8 | 81589.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 71570 | 81589.8 |  | 428430 | 418410.2 | 14.31% | 16.32% | The appointed consultants are busy with preliminary designs. | 200000 | 200000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1505 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam North Kanana | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Consultant is busy with preliminary designs | 200000 | 200000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1506 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 36 | Dimbaza Destitute 27 Units | USDG | 2500000 |  | 2500000 | -2300000 | 200000 |  | 200000 |  | 200000 |  | 200000 | -200000 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! | Appointed consultants have finalised preliminary designs and submitted to service branches for input and approval. Awaiting finalisation of comments to proceed. | 0 |  |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 169290 | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1507 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 45 | Ilitha North 177 Units | USDG | 700000 |  | 700000 |  | 700000 |  | 700000 |  | 1500000 |  | 1500000 |  | 1500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 448182 | 62745.48 | 510927.48 |  |  | 0 |  |  | 0 | -448182 | 0 | -448182 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 62745.48 |  | 1500000 | 1437254.52 | 0% | 4.183% | This contract is about putting in services i.e. sewer, water & roads, presently we are waiting for final designs from the service provider. Annual contractors will be utilised to speedup work. | 4000000 | 6800000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 700000 | 700000 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1508 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | DVRI Pilot Project (Mekeni, Haven Hills, Competition Site) | USDG | 2500000 |  | 2500000 | 1000000 | 3500000 |  | 3500000 |  | 775000 |  | 775000 |  | 775000 | 0 | 0 | 0 | 23366.2 | 3271.27 | 26637.47 | 45833.96 | 6416.75 | 52250.71 | 425949.5 | 59632.93 | 485582.43 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 275125.68 | 38517.6 | 313643.28 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 770275.34 | 878113.89 |  | 4724.66 | -103113.89 | 99.39% | 113.3% | The contractor is on site completing Haven Hills site, and then the contractor will proceed to competition site for the construction of top structures and internal services. The current expenditure is as a result of the payment of the professional team. | 0 |  |  |  |  | 0 |  | 0 | 81590 | 11422.6 | 93012.6 | 81590 | 93012.6 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 81590 | 93012.6 |  | 3418410 | 3406987.4 | 2.331% | 2.658%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1506 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | DVRI Pilot Project (Mekeni, Haven Hills, Competition Site) P1 & P3 | HSDG c/o | [9 empty] | 5687069 | 5687069 |  | 5687069 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 4874483.92 |  | 4874483.92 |  |  | 0 |  |  | 0 |  |  | 0 | -4874483.92 |  | -4874483.92 | [9 empty] | 0 | 0 | 0 |  | 5687069 | 5687069 | 0% | 0% | The contractor is on site completing Haven Hills site, and then the contractor will proceed to competition site for the construction of top structures and internal services. The current expenditure is as a result of the payment of the professional team.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1505 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 15 | Duncan Village Proper | HSDG | 350000 |  | 350000 |  | 350000 |  | 350000 |  | 700000 |  | 700000 |  | 700000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 700000 | 700000 | 0% | 0% | The project is on design stage by the implementing agent. | 1300000 | 3300000 | 10000000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 350000 | 350000 | 0% | 0%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1501 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 15 | Duncan Village Proper | HSDG c/o | [9 empty] | 350000 | 350000 |  | 350000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 350000 | 350000 | 0% | 0% | The project is on design stage by the implementing agent.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1506 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | C Section and Triangular Site | HSDG | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 700000 |  | 700000 |  | 700000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 700000 | 700000 | 0% | 0% | The project is on design stage by the implementing agent. | 1300000 | 2000000 | 10000000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 3707.64 |  | 3707.64 | -3707.64 |  | -3707.64 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1504 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | C Section and Triangular Site P1-P3 | HSDG c/o | [9 empty] | 770420 | 770420 |  | 770420 |  |  | 0 |  |  | 0 |  |  | 0 | 21703 |  | 21703 | 93121.16 |  | 93121.16 | 107824.56 |  | 107824.56 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 222648.72 | 222648.72 |  | 547771.28 | 547771.28 | 28.9% | 28.9% | The project is on design stage by the implementing agent.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1507 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | D Hostel | HSDG | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 700000 |  | 700000 |  | 700000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 700000 | 700000 | 0% | 0% | The project is on design stage by the implementing agent. | 1300000 | 2000000 | 10000000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1505 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | D Hostel P1 & P3 | HSDG c/o | [9 empty] | 600000 | 600000 |  | 600000 |  |  | 0 |  |  | 0 |  |  | 0 | 45990.01 |  | 45990.01 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 45990.01 | 45990.01 |  | 554009.99 | 554009.99 | 7.665% | 7.665% | The project is on design stage by the implementing agent.
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1509 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 23 | Mdantsane Zone 18 CC Phase 2 | USDG | 3000000 |  | 3000000 |  | 3000000 | -1000000 | 2000000 |  | 10000000 |  | 10000000 | -5000000 | 5000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 7790351.3 | 1090649.19 | 8881000.49 | -7567511.3 | -358479.76 | -7925991.06 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 222840 | 955009.43 |  | 4777160 | 4044990.57 | 4.457% | 19.1% | The contractor is on site, progressing with the works | 8500000 | 18500000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 382.04 | 382.04 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 382.04 |  | 3000000 | 2999617.96 | 0% | 0.01273% | 16500000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1510 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1 | Block Yard TRA | USDG | 500000 |  | 500000 | 1831500 | 2331500 |  | 2331500 |  | 1000000 |  | 1000000 | 4540286 | 5540286 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 38028.32 | 5323.96 | 43352.28 |  |  | 0 |  |  | 0 | 35985.16 | 5037.92 | 41023.08 |  |  | 0 |  |  | 0 |  |  | 0 | 4977859.1 | 74013.48 | 84375.36 |  | 5466272.52 | 5455910.64 | 1.336% | 1.523% | The scope argumentation for the professional team is still to be tabled by BAC, then the contractor can go back to site to proceed with the works of internal engineering services. The current expenditure is a result of a professional team fees and contractor. | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 295.58 | 295.58 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 175180.32 | 0 | 295.58 |  | 2331500 | 2331204.42 | 0% | 0.01268%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1508 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 1 | Block Yard TRA | HSDG c/o | [9 empty] | 608785 | 608785 |  | 608785 |  |  | 0 |  |  | 0 |  |  | 0 | 307405.79 |  | 307405.79 |  |  | 0 |  |  | 0 | 226604 |  | 226604 |  |  | 0 |  |  | 0 | [10 empty] | 534009.79 | 534009.79 |  | 74775.21 | 74775.21 | 87.72% | 87.72% | The scope argumentation for the professional team is still to be tabled by BAC, then the contractor can go back to site to proceed with the works of internal engineering services. The current expenditure is a result of a professional team fees and contractor.
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1511 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 19 | Second Creek (Turn Key) | USDG | 8000000 |  | 8000000 | 1800000 | 9800000 |  | 9800000 |  | 100000 |  | 100000 | 3547208 | 3647208 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2451100.29 | 0 | 2451100.29 |  |  | 0 |  |  | 0 |  |  | 0 |  | 2451100.29 | 2451100.29 |  | 1196107.71 | 1196107.71 | 67.2% | 67.2% | The contractor has completed the project. The project is currently on liability period which is the allowance of defects of completed works, this period is for 12 months, meaning is up August 2015. | 0 | 0 |  |  |  | 0 | 149203.55 | 170092.05 | 761056.68 | 106547.93 | 867604.61 | 910260.23 | 1037696.66 |  |  | 0 | 340800.89 | 47712.12 | 388513.01 | 751461.26 |  | 751461.26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2002522.38 | 2177670.93 |  | 7797477.62 | 7622329.07 | 20.43% | 22.22%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1512 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 9 | Amalinda Co- Op | USDG | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 2200000 | -180000 | 2020000 | -1000000 | 1020000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 99250 | 99520 | 198770 |  |  | 0 | 23642.93 | 3310.01 | 26952.94 |  |  | 0 |  |  | 0 | 208499.75 | 29189.97 | 237689.72 |  |  | 0 |  |  | 0 |  |  | 0 | 24972.58 | 331392.68 | 463412.66 |  | 688607.32 | 556587.34 | 32.49% | 45.43% | The project is on design stage, it is anticipated to go on tender by the end of this financial year. The current expenditure is a result of the professional team fees and the annual contractor for the construction of a sewer and water line. | 4800000 | 100000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0% | 6000000
Human Settlements |  | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1513 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 |  | Amalinda Fairlands | USDG | 0 |  | 0 |  | 0 |  | 0 |  | 300000 |  | 300000 | -300000 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! | Contractor is on site, performing well, busy with installation of internal services. | 300000 | 500000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1514 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 48,12,21,11,17,11,20 | Cluster 1 (Masibambane; Masibulele; Velwano; Ilinge and Dacawa) | USDG | 3500000 |  | 3500000 |  | 3500000 |  | 3500000 |  | 15000000 | -1306712 | 13693288 | 12680265 | 26373553 | 92322.33 | 12925.13 | 105247.46 | 2636185.49 | 335267.91 | 2971453.4 | 4404470.01 | 555616.39 | 4960086.4 | 4033709.64 | 512671.78 | 4546381.42 | 547961.1 | 76714.55 | 624675.65 | 25813.8 | 3613.93 | 29427.73 |  |  | 0 |  |  | 0 | 12775052.9 | 1154604.64 | 13929657.54 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 24515515.27 | 27166929.6 |  | 1858037.73 | -793376.6 | 92.95% | 103% | Contractor is on site and site establishment is complete. The contractor is currently busy with installation of internal services. To date 508 site have water and sewer connections, the available budget is not sufficient. | 19000000 | 76000000 |  |  |  | 0 | 4737.54 | 4737.54 | -4737.54 | 0 | -4737.54 | 0 | 0 |  |  | 0 |  |  | 0 | 9997.5 | 1399.65 | 11397.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 9997.5 | 11397.15 |  | 3490002.5 | 3488602.85 | 0.2856% | 0.3256% | 73047792 |  |  |  | 113500000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1515 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 17,14, | Cluster 2 (Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe) | USDG | 3500000 |  | 3500000 |  | 3500000 | -2500000 | 1000000 |  | 10000000 |  | 10000000 | 1553222 | 11553222 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 5921098.82 | 820808.63 | 6741907.45 | 0.8 |  | 0.8 |  |  | 0 | -2272829.62 | 301114.55 | -1971715.07 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 3648270 | 4770193.18 |  | 7904952 | 6783028.82 | 31.58% | 41.29% | The contractor is on site, for construction of both engineering services and top structures. To date the contractor is busy with excavations of sewer lines. Available budget will be spend this financial year. | 10000000 | 36464685 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | -3707.64 |  | -3707.64 | 3707.64 |  | 3707.64 | 2574.75 | 360.46 | 2935.21 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2574.75 | 2935.21 |  | 3497425.25 | 3497064.79 | 0.07356% | 0.08386% | 46000000
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1516 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 10 | Cluster 3 (Fynbos Informal 1, Fynbos Informal 2, Ndancama) P1 & P3 | USDG | 5524440 |  | 5524440 | -1300000 | 4224440 | -2000000 | 2224440 |  | 7775000 |  | 7775000 | 15250000 | 23025000 | 0 | 0 | 0 |  |  | 0 | 825710.32 | 115599.44 | 941309.76 |  |  | 0 |  |  | 0 | 324552.14 | 45437.3 | 369989.44 | 1765489.9 | 222451.73 | 1987941.63 | 4859247.63 | 680294.67 | 5539542.3 | 10558116.66 | 621741.86 | 11179858.52 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 18333116.65 | 20018641.65 |  | 4691883.35 | 3006358.35 | 79.62% | 86.94% | The appointed contractor for the construction of engineering internal services and top structures has commence with the works last calendar year. The expenditure on the project is still expected to proceed, covering the costs in construction and as well the construction monitoring by the professional team. | 25350000 | 20100000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 417514 | 58451.96 | 475965.96 | 168266.6 | 23557.32 | 191823.92 | 13864.37 | 1941.01 | 15805.38 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 599644.97 | 683595.26 |  | 3624795.03 | 3540844.74 | 14.19% | 16.18% | 68000000
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1508 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 9 | Braelyn ext 10 | HSDG | 500000 |  | 500000 |  | 500000 | -500000 | 0 |  | 2000000 | 0 | 2000000 | -1500000 | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | The project is on design stage, it is anticipated to go on tender by the end of this financial year. The current expenditure is a result of the professional team fees. | 10000000 | 20000000 | 8000000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1509 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 9 | Braelyn ext 10 - P1 & P3 | HSDG c/o | [9 empty] | 118812 | 118812 |  | 118812 |  |  | 0 |  |  | 0 |  |  | 0 | 89302.5 |  | 89302.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 89302.5 | 89302.5 |  | 29509.5 | 29509.5 | 75.16% | 75.16% | The project is on design stage, it is anticipated to go on tender by the end of this financial year. The current expenditure is a result of the professional team fees.
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1517 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 31 | Sunny South | USDG | 10000000 |  | 10000000 | 4000000 | 14000000 |  | 14000000 |  | 2000000 | 180000 | 2180000 | 1200000 | 3380000 | 82100.88 | 11494.12 | 93595 | 126676.4 | 17734.7 | 144411.1 | 1347611.08 | 11494.12 | 1359105.2 | 135369.1 | 11494.12 | 146863.22 |  |  | 0 | 160165.5 | 15451.45 | 175616.95 |  |  | 0 |  |  | 0 | 1476643.71 | 130728.42 | 1607372.13 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 3328566.67 | 3526963.6 |  | 51433.33 | -146963.6 | 98.48% | 104.3% | Contractor on site, there are technical delays on the project but the project is due to be completed in April 2015. | 100000 | 0 |  |  |  | 0 |  | 0 | 312750 |  | 312750 | 312750 | 312750 | 34750 | 43785 | 78535 | 793348.34 | 107369.96 | 900718.3 | 439562.11 | 61538.7 | 501100.81 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1580410.45 | 1793104.11 |  | 12419589.55 | 12206895.89 | 11.29% | 12.81%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1518 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 43 | Tyutyu Phase 3 | USDG | 200000 |  | 200000 | 0 | 200000 |  | 200000 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! | Budget reserved for procurement of office requirements for additional person to be acquired through the Capacity Enhancement Grant, much dependant on availability of additional office space. | 0 | 100000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Human Settlements | Housing Department | 3.3 - Housing Department | Housing | 255005 | 4 | 36 | 1519 | Housing | Housing | 4 | 36 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 46 | Westbank Restitution | USDG | 2000000 |  | 2000000 | 0 | 2000000 |  | 2000000 |  | 3547208 |  | 3547208 | -3547208 | 0 | 0 | 0 | 0 | 1372549.25 | 192156.89 | 1564706.14 | 409895.51 | 57385.38 | 467280.89 |  |  | 0 |  |  | 0 | 668655.53 | 93611.77 | 762267.3 |  |  | 0 |  |  | 0 | -2451100.29 | 0 | -2451100.29 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 343154.04 |  | 0 | -343154.04 | #DIV/0! | #DIV/0! | The project is still on bulk implementation stage by engineering services directorate. Housing will be in position to implement the project after the bulk implementation. | 16000000 | 15000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | 140000000 |  | R70mill from 15/16
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 6 | 35 | 1507 | Housing | Housing |  |  |  | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | Housing Needs Database and Accreditation (Capacity Enhancement) | HSDG c/o | [9 empty] | 273172 | 273172 | -273172 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! | Project on procurement stage.
Human Settlements | Housing Department | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1509 | Housing | Housing | 4 | 35 |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | Housing Needs Database and Accreditation (Capacity Enhancement) | HSDG | 390000 |  | 390000 |  | 390000 |  | 390000 |  | 500000 |  | 500000 | -500000 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! | Project on procurement stage. | 1000000 |  |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 60641.08 |  | 60641.08 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 60641.08 | 60641.08 |  | 329358.92 | 329358.92 | 15.55% | 15.55%
Human Settlements | Housing Department | 4.4 - Asset Risk & Financial Services |  | 255005 | 5 | 05 | 1525 | Housing | Housing | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of CPU & Monitor - A14/32 | Own Funds | [10 empty] | 12000 |  | 12000 | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 | 0 |  | 12000 | 12000 | 0% | 0% | Project at procurement stage.
Human Settlements |  | 3.3 - Housing Department |  | 255005 | 4 | 35 | 1511 | Housing | Housing |  |  |  | 05 | 01 | 91 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing |  |  | 10 Gates at Z. Soga Beneficiaries of Mdantsane West | Own Funds | [11 empty] | 30000 | 30000 | [23 empty] | 0 |  |  | 0 | [10 empty] | 0 | 0 |  | 30000 | 30000 | 0% | 0% | The project is on design stage by the implementing agent.
Human Settlements | Mdantsane Urban Renuwal Unit | 4.4 - Asset Risk & Financial Services |  | 255010 | 5 | 05 | 1524 | Budget and treasury | Support Services | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Laptop F. Melane - A14/25 | Own Funds | [10 empty] | 10826 |  | 10826 | [11 empty] | 0 | 10826 |  | 10826 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 10826 | 10826 |  | 0 | 0 | 100% | 100% | Laptop has been replaced
[26 empty] | TOTAL : HUMAN SETTLEMENTS |  | 75564440 | 0 | 75564440 | 5931500 | 81495940 | -800000 | 80695940 | 0 | 90136108 | 10669147 | 100828081 | 55379975 | 156208056 | 4419423.27 | 304419.25 | 4723842.52 | 7529330.8 | 548430.77 | 8077761.57 | 9250670.49 | 772216.71 | 10022887.2 | 14777558.37 | 691193.55 | 15468751.92 | 11319802.93 | 107473.25 | 11427276.18 | 12307581.63 | 1634295.2 | 13941876.83 | 3960720.45 | 222451.73 | 4183172.18 | 12649598.93 | 1770943.86 | 14420542.79 | 26002576.28 | 1945893.92 | 27948470.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5042703.41 | 102217263.15 | 110214581.39 | 0 | 53990792.85 | 45993474.61 | 65.44% | 70.56% |  | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 206300.69 | 227189.19 | 1146539.54 | 117970.53 | 1264510.07 | 1352840.23 | 1491699.26 | 452264 | 102236.96 | 554500.96 | 1396731.91 | 179317.02 | 1576048.93 | 1289412.89 | 65239.82 | 1354652.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12905914.24 | 4491249.03 | 4976901.86 | 0 | 77004690.97 | 76519038.14 | 5.511% | 6.107% |  |  | 0
[32 empty] | 0 |  | 0 | [74 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF FINANCIAL SERVICES | [25 empty] | DIRECTORATE OF FINANCIAL SERVICES | [5 empty] | 0 |  | 0 | [74 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Financial Services |  | 4.1 - Office of The Director of Finance |  | 305005 | 4 | 01 | 1505 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 |  | 500000 | 19074.32 | 0 | 19074.32 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 117610.12 |  | 117610.12 | 48961.96 |  | 48961.96 |  |  | 0 |  |  | 0 |  |  | 0 | 81941.91 | 185646.4 | 185646.4 |  | 314353.6 | 314353.6 | 37.13% | 37.13% | Procurement processes currently underway to ensure that funding is spent before end of June 2015. Departments have submitted their furniture requirements for procurement processes. | 500000 | 500000
Financial Services |  | 4.1 - Office of The Director of Finance |  | 305005 | 6 | 01 | 1506 | Budget and treasury | Support Services |  |  |  | 05 | 03 | 01 | 01 | 270 | 002 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Office Furniture and Equipment | Own Funds c/o | [9 empty] | 431902 | 431902 |  | 431902 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 431902 | 431902 | 0% | 0% | Procurement processes currently underway to ensure that funding is spent before end of June 2015. Departments have submitted their furniture requirements for procurement processes.
Financial Services |  | 4.9 - Consolidated Billing & Miscellaneous Revenue Office |  | 330010 | 4 | 01 | 1507 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Partitioning of Offices for SCM | Own Funds |  |  |  |  | 0 |  | 0 |  | 350000 |  | 350000 |  | 350000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 218597.94 |  | 218597.94 | 2511.2 |  | 2511.2 |  |  | 0 |  |  | 0 |  |  | 0 | 932.88 | 221109.14 | 221109.14 |  | 128890.86 | 128890.86 | 63.17% | 63.17% | Service provider is on site , payments are to be made by third week of February 2015. Remainder of funding to be used to purchase furniture for the partitioned area by March 2015. | 0 | 0
Financial Services | Consolidated Billing and Miscellaneous Revenue Office | 4.4 - Asset Risk & Financial Services |  | 330010 | 5 | 05 | 1519 | Budget and treasury | Support Services |  |  |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Laptop S. Peter - A14/15 | Own Funds | [10 empty] | 14774 |  | 14774 | [8 empty] | 0 |  |  | 0 | 14773.5 |  | 14773.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 14773.5 | 14773.5 |  | 0.5 | 0.5 | 100% | 100% | The laptop has been replaced.
Financial Services | Consolidated Billing and Miscellaneous Revenue Office | 4.4 - Asset Risk & Financial Services |  | 330010 | 5 | 05 | 1521 | Budget and treasury | Support Services | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Laptop P. Dawethi - A14/14 | Own Funds | [10 empty] | 10140 |  | 10140 | [11 empty] | 0 | 10140 |  | 10140 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 10140 | 10140 |  | 0 | 0 | 100% | 100% | The laptop has been replaced.
Financial Services | Debtors Management Office | 4.4 - Asset Risk & Financial Services |  | 330015 | 5 | 05 | 1517 | Budget and treasury | Support Services | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Laptop - Z. Mjali - A14/12 | Own Funds | [10 empty] | 10251 |  | 10251 | 0 |  | 0 |  |  | 0 |  |  | 0 | 10251 |  | 10251 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 10251 | 10251 |  | 0 | 0 | 100% | 100% | The laptop has been replaced.
Financial Services | Debtors Management Office | 4.4 - Asset Risk & Financial Services |  | 330015 | 5 | 05 | 1533 | Budget and treasury | Support Services | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Laptop G. Simons - A14/37 | Own Funds | [10 empty] | 18500 |  | 18500 | [20 empty] | 0 |  |  | 0 | 16405.72 |  | 16405.72 | [9 empty] | 0 | 16405.72 | 16405.72 |  | 2094.28 | 2094.28 | 88.68% | 88.68% | The laptop has been replaced.
Financial Services |  | 4.11 - Customer Care Office |  | 330020 | 4 | 01 | 1508 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 260 | 001 | New-260 | Yes |  |  |  | KPA4 | All Wards | CCTV Cameras for BCMM Cash Offices | Own Funds |  |  |  |  | 0 |  | 0 |  | 1500000 |  | 1500000 | -1500000 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 1500000
[26 empty] | TOTAL : FINANCIAL SERVICES |  | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 2350000 | 431902 | 2835567 | -1500000 | 1335567 | 19074.32 | 0 | 19074.32 | 0 | 0 | 0 | 0 | 0 | 0 | 10251 | 0 | 10251 | 24913.5 | 0 | 24913.5 | 0 | 0 | 0 | 0 | 0 | 0 | 336208.06 | 0 | 336208.06 | 67878.88 | 0 | 67878.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82874.79 | 458325.76 | 458325.76 | 0 | 877241.24 | 877241.24 | 34.32% | 34.32% |  | 2000000 | 500000 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0
[32 empty] | 0 |  | 0 | [74 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF CORPORATE SERVICES | [25 empty] | DIRECTORATE OF CORPORATE SERVICES | [5 empty] | 0 |  | 0 | [74 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Corporate services |  | 5.1 - Office of The Director of Corporate Services |  | 405005 | 4 | 01 | 1509 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA1 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 13230 |  | 13230 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 13230 | 13230 |  | 486770 | 486770 | 2.646% | 2.646% | The informal tender for office furniture and equipment will be advertised on the 07 April 2015 for seven days and it is expected that the process will be finalised by 24 April 2015 and expenditure will show at the end of April 2015. | 500000 | 500000
Corporate services |  | 4.4 - Asset Risk & Financial Services |  | 415010 | 5 | 05 | 1516 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 150000 | 150000 |  | 150000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 150000 | 150000 | 0% | 0% | Procurement process underway and the expenditure will show at the end of May 2015.
Corporate services |  | 5.4 - Auxilliary & Telecommunication Support |  | 415010 | 6 | 01 | 1510 | Corporate Services | Support Services |  |  |  | 05 | 04 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Vehicle | Own Funds c/o | [9 empty] | 150000 | 150000 |  | 150000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 150000 | 150000 | 0% | 0% | Procurement process underway and the expenditure will show at the end of May 2015.
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1510 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Procurement of Pre-Payment Vending Machines | Own Funds | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 | 168270 |  | 168270 |  |  | 0 | 1728 |  | 1728 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1728 | 169998 | 169998 |  | 330002 | 330002 | 34% | 34% | The remainder of funding will be used to purchase extra machines for the new identified sites by April 2015 and the full amount will be spent. | 0 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 23472.6 |  | 23472.6 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23472.6 | 23472.6 |  | 476527.4 | 476527.4 | 4.695% | 4.695%
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1511 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Systems Intergration - (Process Implementation) | Own Funds | 5250000 | -250000 | 5000000 |  | 5000000 |  | 5000000 |  | 1000000 |  | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | The funding will be used for feasibility study and specialist to assist in the process for the integration of all the municipal systems. The funding will be moved to operating projects during the adjustment budget process. | 12000000 | 12000000 |  |  |  | 0 |  | 0 | 581900 |  | 581900 | 581900 | 581900 | 1191020 |  | 1191020 | 574780.65 |  | 574780.65 | 553836.65 |  | 553836.65 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1548136.26 | 2901537.3 | 2901537.3 |  | 2098462.7 | 2098462.7 | 58.03% | 58.03%
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1512 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Security Software | Own Funds |  |  |  |  | 0 |  | 0 |  | 2400000 |  | 2400000 |  | 2400000 | 0 | 0 | 0 |  |  | 0 | 2135.27 |  | 2135.27 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 2135.27 | 2135.27 |  | 2397864.73 | 2397864.73 | 0.08897% | 0.08897% | Procurement process underway, anticipating expenditure in April/May. | 0 | 0
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1513 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Infrastructure Network Upgrade | Own Funds | 0 |  | 0 |  | 0 |  | 0 |  | 2000000 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Procurement process underway, anticipating expenditure in April/May.. | 4000000 | 4000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Corporate services |  | 4.4 - Asset Risk & Financial Services |  | 415025 | 5 | 05 | 1540 | Corporate Services | Support Services |  |  |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Replacement of a Biometer Reader - A11/96 | Own Funds | [11 empty] | 11000 | 11000 | [26 empty] | 0 | [9 empty] | 9237 | 0 | 0 |  | 11000 | 11000 | 0% | 0% | Procurement process underway, anticipating expenditure in April/May.
Corporate services |  | 4.4 - Asset Risk & Financial Services |  | 415025 | 5 | 05 | 1541 | Corporate Services | Support Services |  |  |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Replacement of a Biometer Reader - A11/97 | Own Funds | [11 empty] | 11000 | 11000 | [26 empty] | 0 | [9 empty] | 9237 | 0 | 0 |  | 11000 | 11000 | 0% | 0% | Procurement process underway, anticipating expenditure in April/May.
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 6 | 01 | 1507 | Corporate Services | Support Services |  |  |  | 05 | 04 | 01 | 01 | 270 | 002 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Infrastructure Upgrade | Own Funds c/o | [9 empty] | 7154862 | 7154862 |  | 7154862 |  |  | 0 |  |  | 0 | 362979.88 |  | 362979.88 |  |  | 0 | 1703875.87 |  | 1703875.87 |  |  | 0 |  |  | 0 | 74122.81 |  | 74122.81 |  |  | 0 | [9 empty] | 131720.82 | 2140978.56 | 2140978.56 |  | 5013883.44 | 5013883.44 | 29.92% | 29.92% | Procurement process underway
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 6 | 01 | 1508 | Corporate Services | Support Services |  |  |  | 05 | 04 | 01 | 01 | 270 | 002 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Duncan Village ICT Centre - DVRI | Own Funds c/o | [9 empty] | 137926 | 137926 |  | 137926 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 114824.56 |  | 114824.56 |  |  | 0 |  |  | 0 | [10 empty] | 114824.56 | 114824.56 |  | 23101.44 | 23101.44 | 83.25% | 83.25% | The project is completed.
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 6 | 01 | 1509 | Corporate Services | Support Services |  |  |  | 05 | 04 | 01 | 01 | 270 | 002 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Systerms - ( Anti Virus) | Own Funds c/o | [9 empty] | 723345 | 723345 |  | 723345 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 122807.83 |  | 122807.83 |  |  | 0 |  |  | 0 |  |  | 0 | 45657.05 |  | 45657.05 | [9 empty] | 0 | 168464.88 | 168464.88 |  | 554880.12 | 554880.12 | 23.29% | 23.29% | The funding will be spent by end of the financial year 2014/2015.
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1514 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Computer Equipment - BCMM | Own Funds | 1000000 |  | 1000000 |  | 1000000 |  | 1000000 |  | 2000000 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 | 53630.52 |  | 53630.52 | 353865.69 |  | 353865.69 | 171700.95 |  | 171700.95 | 282764.22 |  | 282764.22 |  |  | 0 | 33548.3 |  | 33548.3 | 273343.74 |  | 273343.74 |  |  | 0 |  |  | 0 |  |  | 0 | 204210.81 | 1168853.42 | 1168853.42 |  | 831146.58 | 831146.58 | 58.44% | 58.44% | The funding will be spent by end of the financial year 2014/2015. | 0 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 491628.54 |  | 491628.54 | 295850.02 |  | 295850.02 | 110520 |  | 110520 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 82826.35 | 897998.56 | 897998.56 |  | 102001.44 | 102001.44 | 89.8% | 89.8%
Corporate services | Management Information Services | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1515 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | IT Infrastructure Servers | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | Procurement is completed and payment is being processed. | 2000000 | 2000000
Corporate services | Management Information Services | 5.7 - H.R. Administration |  | 420005 | 4 | 28 | 1501 | Corporate Services | Support Services | 4 | 28 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Office Furniture and Equipment and Computers | ISDG | 100000 |  | 100000 |  | 100000 |  | 100000 |  | 100000 |  | 100000 |  | 100000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 100000 | 100000 | 0% | 0% | Procurement of computers and other equipment is underway, the expenditure is expected to show by end of April 2015 through IT. | 100000 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 19673.6 | 2754.3 | 22427.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 65646.91 | 19673.6 | 22427.9 |  | 80326.4 | 77572.1 | 19.67% | 22.43%
Corporate services | H.R. Administration | 5.7 - H.R. Administration |  | 420005 | 4 | 01 | 1518 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Computers | KPA1 | All Wards | Electronic Attandance Control System | Own Funds | 0 |  | 0 |  | 0 |  | 0 |  | 2000000 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 111037.37 | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Procurement process underway | 1500000 | 1000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Corporate services | H.R. Administration | 4.4 - Asset Risk & Financial Services |  | 420005 | 5 | 05 | 1507 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 8500 | 8500 |  | 8500 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 5916.19 | 0 | 0 |  | 8500 | 8500 | 0% | 0% | Procurement process underway
Corporate services | H.R. Administration | 4.4 - Asset Risk & Financial Services |  | 420005 | 5 | 05 | 1520 | Budget and treasury | Support Services |  |  |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of Laptop V. Forosi - A13/78 | Own Funds | [10 empty] | 10707 |  | 10707 | [8 empty] | 0 |  |  | 0 | 10707 |  | 10707 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 10707 | 10707 |  | 0 | 0 | 100% | 100% | Project completed.
Corporate services | Occupational Risk Mnagement | 5.8 - Occupational Risk Management |  | 420010 | 4 | 01 | 1519 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other assets | Land & Buildings | KPA1 | All Wards | Extensions to Employee Wellness Centre | Own Funds | 0 |  | 0 |  | 0 |  | 0 |  | 2500000 |  | 2500000 | -180000 | 2320000 | 0 | 0 | 0 |  |  | 0 | 2761.12 |  | 2761.12 |  |  | 0 |  |  | 0 | 5881.04 |  | 5881.04 |  |  | 0 |  |  | 0 | 40680.72 |  | 40680.72 |  |  | 0 |  |  | 0 |  |  | 0 | 1993355.28 | 49322.88 | 49322.88 |  | 2270677.12 | 2270677.12 | 2.126% | 2.126% | Procurement process underway | 0 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1516 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Land & Buildings | KPA1 | All Wards | ICT Networks and Communications for Call Centre | Own Funds |  |  |  |  | 0 |  | 0 |  | 800000 |  | 800000 |  | 800000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 800000 | 800000 | 0% | 0% | Procurement process underway. | 500000 | 200000
Corporate services |  | 5.6 - Management Information Services |  | 415025 | 4 | 01 | 1517 | Corporate Services | Support Services | 4 | 01 |  | 05 | 04 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets | Land & Buildings | KPA1 | All Wards | IT Hardware for Call Centre | Own Funds |  |  |  |  | 0 |  | 0 |  | 800000 |  | 800000 |  | 800000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 800000 | 800000 | 0% | 0% | Project has commenced, funding will be spent by the end of the financial year 2014/15. | 1500000 | 500000
[26 empty] | TOTAL : CORPORATE SERVICES |  | 6850000 | -250000 | 6600000 | 0 | 6600000 | 0 | 6600000 | 0 | 15100000 | 8324633 | 23435340 | -158000 | 23277340 | 0 | 0 | 0 | 0 | 0 | 0 | 589776.79 | 0 | 589776.79 | 353865.69 | 0 | 353865.69 | 2010819.65 | 0 | 2010819.65 | 288645.26 | 0 | 288645.26 | 114824.56 | 0 | 114824.56 | 120901.11 | 0 | 120901.11 | 359681.51 | 0 | 359681.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2466442.47 | 3838514.57 | 3838514.57 | 0 | 19438825.43 | 19438825.43 | 16.49% | 16.49% |  | 22100000 | 20200000 | 0 | 0 | 0 | 0 | 0 | 0 | 581900 | 0 | 581900 | 581900 | 581900 | 1682648.54 | 0 | 1682648.54 | 894103.27 | 0 | 894103.27 | 684030.25 | 2754.3 | 686784.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1696609.52 | 3842682.06 | 3845436.36 | 0 | 2757317.94 | 2754563.64 | 58.22% | 58.26% |  |  | 0
[32 empty] | 0 |  | 0 | [26 empty] | 0 | [47 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF ENGINEERING SERVICES | [25 empty] | DIRECTORATE OF ENGINEERING SERVICES | [5 empty] | 0 |  | 0 | [26 empty] | 0 | [47 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Engineering Services | Office of the Director of Engineering Services | 6.1 - Office of The Director of Engineering Services |  | 505005 | 4 | 01 | 1520 | Other | Support Services | 4 | 01 |  | 05 | 05 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA2 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 133843.34 |  | 133843.34 | 61515.61 |  | 61515.61 |  |  | 0 |  |  | 0 |  |  | 0 | 55226.68 | 195358.95 | 195358.95 |  | 304641.05 | 304641.05 | 39.07% | 39.07% | Procurement process underway | 500000 | 500000
Engineering Services | Scientific Services | 6.9 - Sewerage Admin |  | 510005 | 4 | 01 | 1559 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Water |  | KPA2 | All Wards | Upgrading of Laboratory Infrastructure | Own Funds | [9 empty] | 2000000 | 2000000 |  | 2000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 188721.45 | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Procurement process underway
Engineering Services | Scientific Services | 6.9 - Sewerage Admin |  | 510005 | 6 | 01 | 1511 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 002 | Renewal-70 |  | Yes | Water |  | KPA2 | All Wards | Upgrading of Laboratory Infrastructure | Own Funds c/o | [9 empty] | 1574513 | 1574513 |  | 1574513 |  |  | 0 |  |  | 0 |  |  | 0 | 8580 |  | 8580 |  |  | 0 |  |  | 0 | 209335.97 |  | 209335.97 | 96842.49 |  | 96842.49 | 139867.98 |  | 139867.98 | [9 empty] | 194864.21 | 454626.44 | 454626.44 |  | 1119886.56 | 1119886.56 | 28.87% | 28.87% | Procurement process underway
Engineering Services | Sewerage Admin | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1520 | Waste Water Management | Waste Water | 4 | 36 |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Bulk Sanitation Provision - Programme | USDG | 37854000 |  | 37854000 | 20000000 | 57854000 |  | 57854000 |  | 176507892 | -176013841 | 494051 |  | 494051 | 76820 | 0 | 76820 | 555847.54 | 74348.55 | 630196.09 | -138617.26 | 0 | -138617.26 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 494050.28 | 568398.83 |  | 0.72 | -74347.83 | 100% | 115% | Project progressing well. | 190000000 | 97000000 |  |  |  | 0 | 3961956.8 | 4516630.75 | 7810659.85 | 1250665.11 | 9061324.96 | 11772616.65 | 13577955.71 | 8848276.78 | 1132017.03 | 9980293.81 | 9756441.29 | 1265741.02 | 11022182.31 | 16134838.1 | 1207170.73 | 17342008.83 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 46512172.82 | 51922440.66 | 625034.64 | 11341827.18 | 5931559.34 | 80.4% | 89.75% | 12000000000%
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1552 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Waste Water Infrastructure Capacity (KWT Reg Scheme) | USDG | [9 empty] | 22857892 | 22857892 | -10000000 | 12857892 |  |  | 0 |  |  | 0 | 543944.88 | 76152.28 | 620097.16 |  |  | 0 |  |  | 0 | 3021799.41 | 423051.91 | 3444851.32 |  |  | 0 | 56397.38 | 7895.64 | 64293.02 | 3719193.3 | 520687.06 | 4239880.36 | [9 empty] | 2094347.78 | 7341334.97 | 8369121.86 |  | 5516557.03 | 4488770.14 | 57.1% | 65.09% | Phase 1: Project on arbitration, institution looking at finalizing the matter and re-advertise. .Phase 2: Mechanical & Electrical Works contract awarded . Phase 2: Civil Works contract was awarded but another bidder appealed the award to preferred bidder.Phase 3: Annual contractor has been appointed to conduct the work.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1553 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Reeston Phase 3 Bulk Services Sewer | USDG | [9 empty] | 50000000 | 50000000 |  | 50000000 |  |  | 0 | 2978423.71 | 372528.8 | 3350952.51 | 3869608.52 | 481925.25 | 4351533.77 | 2840418.79 | 364233.26 | 3204652.05 | 3173219.13 | 444250.67 | 3617469.8 | 7226876.47 | 933787.31 | 8160663.78 |  |  | 0 | 1221490.96 | 157841.76 | 1379332.72 | 3086351.59 | 424348.68 | 3510700.27 | [9 empty] | 0 | 24396389.17 | 27575304.9 |  | 25603610.83 | 22424695.1 | 48.79% | 55.15% | Civil works on going. Mechanical & Electrical Works contract awarded but another bidder appealed the award to preferred bidder.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1554 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Mdantsane Infrastructure- Refurbishment/ Augmentation | USDG | [9 empty] | 20000000 | 20000000 |  | 20000000 |  |  | 0 | 5202755.74 | 663036.59 | 5865792.33 | -2086248.95 | 414183.12 | -1672065.83 | 1281854.55 | 179459.64 | 1461314.19 | 1111763.54 | 155646.89 | 1267410.43 | 3586413.81 | 502097.93 | 4088511.74 |  |  | 0 | 1193462.16 | 167084.71 | 1360546.87 | 1254312.12 | 175603.7 | 1429915.82 | [9 empty] | 0 | 11544312.97 | 13801425.55 |  | 8455687.03 | 6198574.45 | 57.72% | 69.01% | Project progressing well.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1555 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Diversion of Amalinda & Wilsonia Effluent | USDG | [9 empty] | 1017458 | 1017458 |  | 1017458 |  |  | 0 |  |  | 0 | 439435.42 | 61520.96 | 500956.38 | 55372.69 | 7752.18 | 63124.87 | 510710.62 | 71499.49 | 582210.11 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 1005518.73 | 1146291.36 |  | 11939.27 | -128833.36 | 98.83% | 112.7% | Phase 1A complete. Design for phase 2 has been completed.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1556 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Sanitation Backlog Eradication - (Coastal) | USDG | [9 empty] | 40000000 | 40000000 |  | 40000000 |  |  | 0 | 940264.83 | 153505.26 | 1093770.09 | 3422872.13 | 445761.59 | 3868633.72 | 320973.21 | 31374.86 | 352348.07 | 1367811.75 | 191493.65 | 1559305.4 | 6456124.68 | 897716.76 | 7353841.44 | 61085.35 | 8551.95 | 69637.3 | 1024493.96 | 131405.9 | 1155899.86 | 2324594.46 | 325375.88 | 2649970.34 | [9 empty] | 8311328.52 | 15918220.37 | 18103406.22 |  | 24081779.63 | 21896593.78 | 39.8% | 45.26% | Annual contractor appointed
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1557 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Eastern Beach Sewers | USDG | [9 empty] | 1056888 | 1056888 |  | 1056888 |  |  | 0 |  |  | 0 | 927094.74 | 129793.26 | 1056888 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 96337.37 | 13487.23 | 109824.6 |  |  | 0 | [9 empty] | 0 | 1023432.11 | 1166712.6 |  | 33455.89 | -109824.6 | 96.83% | 110.4% | Funding fully spent
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1558 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Sludge Handling & Chlorination Facilities | USDG | [9 empty] | 1729909 | 1729909 |  | 1729909 |  |  | 0 | 180844.29 | 25318.2 | 206162.49 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 180844.29 | 206162.49 |  | 1549064.71 | 1523746.51 | 10.45% | 11.92% | Project progressing well
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1559 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Ablution Blocks | USDG | [9 empty] | 3949029 | 3949029 |  | 3949029 |  |  | 0 | 75961.4 | 10634.59 | 86595.99 |  |  | 0 | 278866.52 | 39041.31 | 317907.83 | 359721.22 | 50360.97 | 410082.19 | 172225.11 | 24111.51 | 196336.62 | 858424.12 | 120179.37 | 978603.49 | 605620.62 | 84969.56 | 690590.18 | 25315.04 | 0 | 25315.04 | [9 empty] | 1206100.22 | 2376134.03 | 2705431.34 |  | 1572894.97 | 1243597.66 | 60.17% | 68.51% | The Ablution Blocks project on going. Annual contractors have been appointed for provision of Ablution Facilities and fencing
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1460 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Ablution Blocks | USDG | [9 empty] | 3949029 | 0 |  | 0 | -276650.91 |  | -276650.91 | 25315.04 |  | 25315.04 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 251335.87 | 0 | 251335.87 | [10 empty] | 2.9104e-11 | 0 |  | -2.9104e-11 | 0 | #DIV/0! | #DIV/0! | The Ablution Blocks project on going. Annual contractors have been appointed for provision of Ablution Facilities and fencing
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1560 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Berlin Sewers | USDG | [9 empty] | 5029611 | 5029611 |  | 5029611 |  |  | 0 | 116918.57 | 16368.59 | 133287.16 | 593257.87 | 83056.1 | 676313.97 | 468158.58 | 65542.2 | 533700.78 |  |  | 0 | 936024.16 | 131043.39 | 1067067.55 | 1049252.41 | 146895.33 | 1196147.74 | 65432.41 |  | 65432.41 | 40076.41 | 5610.7 | 45687.11 | [9 empty] | 23317.97 | 3269120.41 | 3717636.72 |  | 1760490.59 | 1311974.28 | 65% | 73.91% | Project is progressing well
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1561 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Hoodpoint Marine Outfall | USDG | [9 empty] | 505949 | 505949 |  | 505949 |  |  | 0 |  |  | 0 |  |  | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 180850 | 9160.54 | 190010.54 | 177028.74 | 24784.02 | 201812.76 | [9 empty] | 0 | 357878.74 | 391823.3 |  | 148070.26 | 114125.7 | 70.73% | 77.44% | Consultant has been appointed for assesment of the buliding .
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1568 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes |  |  |  |  | West Bank Restitution Sewer Infrastructure | USDG | [9 empty] | 10000000 | 10000000 |  | 10000000 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 25319 | 25319 |  |  | 0 | [9 empty] | 10000000 | 0 | 25319 |  | 10000000 | 9974681 | 0% | 0.2532% | Annual contractor on site to complete the outstanding works.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1569 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes |  |  |  |  | Quinera WWTW | USDG | [9 empty] | 12200000 | 12200000 | -5000000 | 7200000 | [8 empty] | 0 | 2575489.78 | 360568.57 | 2936058.35 |  |  | 0 | 236784.59 | 33149.84 | 269934.43 |  |  | 0 | 100421.75 | 14059.04 | 114480.79 |  |  | 0 | [9 empty] | 0 | 2912696.12 | 3320473.57 |  | 4287303.88 | 3879526.43 | 40.45% | 46.12% | Certificate of completion has been issued, invoices being processed.
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1570 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes |  |  |  |  | Gqozo Village Phase 2 | USDG | [9 empty] | 10000000 | 10000000 | -5000000 | 5000000 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 5000000 | 5000000 | 0% | 0% | Procurement process underway.
Engineering Services | Sewerage Admin | 6.9 - Sewerage Admin |  | 515010 | 4 | 01 | 1521 | Waste Water Management | Waste Water | 4 | 01 |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 | 13,28,5,10,16,27,31,32,33,1,2,3,6,10,18,19,47 | Bulk Sanitation Provision - Replacing Existing Infrastructure | Own Funds |  |  |  |  | 0 |  | 0 |  | 40000000 | -2000000 | 38000000 |  | 38000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1669780 |  | 1669780 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 1669780 | 1669780 |  | 36330220 | 36330220 | 4.394% | 4.394% | Procurement process underway | 40000000 | 40000000
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1571 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 |  | Nord Avenue Pump Station | USDG | [11 empty] | 276568 | 276568 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [5 empty] | 0 |  |  | 0 | [10 empty] | 0 | 0 |  | 276568 | 276568 | 0% | 0% | Complete
Engineering Services |  | 6.9 - Sewerage Admin | Waste Water | 515010 | 4 | 36 | 1572 | Waste Water Management | Waste Water |  |  |  | 05 | 05 | 01 | 01 | 070 | 001 | Renewal-70 |  | Yes | Waste water Management | Sewerage | KPA2 |  | Quinera Treatment Works | USDG | [11 empty] | 964292 | 964292 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [5 empty] | 0 |  |  | 0 | [10 empty] | 0 | 0 |  | 964292 | 964292 | 0% | 0% | Commissioning of works
Engineering Services |  | 4.4 - Asset Risk & Financial Services |  | 515010 | 5 | 05 | 1538 | Budget and treasury | Waste Water | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  |  |  |  | All Wards | Replacement of Computer,Furniture & Vacuum Cleaner | Own Funds | [9 empty] | 21000 | 21000 |  | 21000 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 | 0 |  | 21000 | 21000 | 0% | 0% | Insurance claim
Engineering Services | Water Treatment Works | 6.20 - Water Administration | Water | 520005 | 4 | 36 | 1521 | Water | Water | 4 | 36 |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes | Road Transport | Roads | KPA2 | 34,37,38,39,40,41,43,44,49,35,11,12,13,14,42,48,50,17,20,23,1-25 & 28,29,30,31, & 33,27,31,33,36,1,2,7,14,17,20,21,22,23,30,2,8,25,34,44,41 | Bulk Water Provision - Programme | USDG | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 | 0 |  | 195288.57 | 195288.57 |  | 125133.92 | 125133.92 |  | 187200.94 | 187200.94 |  | 529175 | 529175 |  | 295875.92 | 295875.92 |  | 122009.57 | 122009.57 |  | 367976.37 | 367976.37 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1822660.29 |  |  | -1822660.29 |  | 0% | Projects are progressing well , some of the projects are at procurement process is underway. Site hand over for the Construction of Ncera Phase 2C took place in January 2015. | 51000000 | 51000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [13 empty] | 0 |  |  | 0 |  | 0% |  | 73000000
Engineering Services |  | 6.20 - Water Administration | Water | 520005 | 4 | 36 | 1521 | Water | Water |  |  |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes |  |  |  |  | Quinera Treatment Works | USDG | [9 empty] | 964292 | 964292 | -964292 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! | Project for New KWT/Bisho water treatment works is at design stage and Bonke/Kwalini rising main is 80% complete
Engineering Services |  | 6.20 - Water Administration | Water | 520005 | 4 | 36 | 1521 | Water | Water |  |  |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes |  |  |  |  | West Bank Restitution - Water | USDG | [8 empty] | 8000000 | 124923 | 8574923 |  | 8574923 |  |  | 0 | 638219.97 |  | 638219.97 | 183304.04 |  | 183304.04 |  |  | 0 | 423627.72 |  | 423627.72 | 252954.82 |  | 252954.82 |  |  | 0 | 290572.82 |  | 290572.82 |  |  | 0 | [9 empty] | 2124036.37 | 1788679.37 | 1788679.37 |  | 6786243.63 | 6786243.63 | 20.86% | 20.86% | Project under litigation, institution looking at finalizing the matter before re-advertising . Funding has been re-allocated to Water Supply Coastal Areas and backlog eradication project, which is within the bulk water programme
Engineering Services |  | 6.20 - Water Administration | Water | 520005 | 4 | 36 | 1521 | Water | Water |  |  |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes |  |  |  |  | KWT and Bisho Infrastructure(Water) | USDG | [8 empty] | 7000000 |  | 7000000 |  | 7000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1524440.11 | 499111.01 | 2023551.12 | [9 empty] | 3152464.76 | 1524440.11 | 2023551.12 |  | 5475559.89 | 4976448.88 | 21.78% | 28.91% | Project for New KWT/Bisho water treatment works is at design stage and Bonke/Kwalini rising main is 80% complete
Engineering Services |  | 6.20 - Water Administration | Water | 520005 | 4 | 36 | 1521 | Water | Water |  |  |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes |  |  |  |  | Amahleke Water Supply | USDG | [8 empty] | 1000000 |  | 1000000 |  | 1000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 138929.57 |  | 138929.57 |  |  | 0 |  |  | 0 |  |  | 0 | [10 empty] | 138929.57 | 138929.57 |  | 861070.43 | 861070.43 | 13.89% | 13.89% | Professional Service Provide is currently busy with designs for Amahleke Regional Storage.
Engineering Services |  | 6.20 - Water Administration | Water | 520005 | 4 | 36 | 1521 | Water | Water |  |  |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes |  |  |  |  | Augmentation of Water Treatment Capacity | USDG | [8 empty] | 9000000 | -2607386 | 6392614 |  | 6392614 |  |  | 0 | 250680.5 |  | 250680.5 | 140960.36 |  | 140960.36 | 2369829.5 |  | 2369829.5 | 620687.27 |  | 620687.27 | 1463585.25 |  | 1463585.25 | 673960.44 |  | 673960.44 | 351140.37 |  | 351140.37 | 181236.83 |  | 181236.83 | [9 empty] | 225071.05 | 6052080.52 | 6052080.52 |  | 340533.48 | 340533.48 | 94.67% | 94.67% | Contractor are onsite, the projects are progressing well
Engineering Services |  | 6.20 - Water Administration | Water | 520005 | 4 | 36 | 1521 | Water | Water |  |  |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes |  |  |  |  | Upgrade Water Networks in terms of Densification and Augmentation | USDG | [8 empty] | 3000000 |  | 3000000 |  | 3000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 58242.68 |  | 58242.68 | 294964.01 |  | 294964.01 | 197536.5 |  | 197536.5 | 350162 |  | 350162 | 927665.75 |  | 927665.75 | [9 empty] | 551650.24 | 1828570.94 | 1828570.94 |  | 1171429.06 | 1171429.06 | 60.95% | 60.95% | Project is progressing well
Engineering Services |  | 6.20 - Water Administration | Water | 520005 | 4 | 36 | 1521 | Water | Water |  |  |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes |  |  |  |  | Water Supply Coastal Areas and backlog eradication | USDG | [8 empty] | 24500000 | -1541292 | 22958708 |  | 22958708 |  |  | 0 | 622147.77 |  | 622147.77 | 605055.76 |  | 605055.76 | 152094.21 |  | 152094.21 | 1368618.36 |  | 1368618.36 | 105576.85 |  | 105576.85 |  |  | 0 | 1636527.49 |  | 1636527.49 | 931735.82 |  | 931735.82 | [9 empty] | 10064077.49 | 5421756.26 | 5421756.26 |  | 17536951.74 | 17536951.74 | 23.62% | 23.62% | Contractors are onsite, the projects are progressing well
Engineering Services |  | 6.20 - Water Administration | Water | 520005 | 4 | 36 | 1521 | Water | Water |  |  |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes |  |  |  |  | Nord Avenue Pump Station | USDG | [9 empty] | 276568 | 276568 | -276568 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Engineering Services | Water Treatment Works | 6.20 - Water Administration |  | 520005 | 4 | 01 | 1522 | Water | Water | 4 | 01 |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes | Road Transport | Roads | KPA2 | 34,37,38,39,40,41,43,44,49,35,11,12,13,14,42,48,50,17,20,23,1-25 & 28,29,30,31, & 33,27,31,33,36,1,2,7,14,17,20,21,22,23,30,2,8,25,34,44,41 | Bulk Water Provision Replacing of Existing Infrastructure | Own Funds |  |  |  |  | 0 |  | 0 |  | 40000000 |  | 40000000 |  | 40000000 | 0 | 0 | 0 | 268846.57 |  | 268846.57 | 1115607.01 |  | 1115607.01 | 240444.21 |  | 240444.21 | 3167217.07 |  | 3167217.07 | 2432365.14 |  | 2432365.14 | 2554498.87 |  | 2554498.87 | 2500679.12 |  | 2500679.12 | 4958805.85 |  | 4958805.85 |  |  | 0 |  |  | 0 |  |  | 0 | 22183269.87 | 17238463.84 | 17238463.84 |  | 22761536.16 | 22761536.16 | 43.1% | 43.1% | Replacement of old water mains & water meters and installation of zonal & new domestic water meters is progressing well. | 40000000 | 40000000
Engineering Services | Water Admin | 6.20 - Water Administration | Water | 520005 | 4 | 36 | 1522 | Water | Water | 4 | 36 |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes | Road Transport | Roads | KPA2 | 34,37,38,39,40,41,43,44,49,35,11,12,13,14,42,48,50,17,20,23,1-25 & 28,29,30,31, & 33,27,31,33,36,1,2,7,14,17,20,21,22,23,30,2,8,25,34,44,41 | West Bank Restitution - Water | USDG | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 5000000 |  | 5000000 |  | 5000000 | 0 | 0 | 0 | 67797.4 | 9491.64 | 77289.04 |  |  | 0 | 235705.26 | 32998.73 | 268703.99 |  |  | 0 | 115299.59 | 16141.94 | 131441.53 |  |  | 0 |  |  | 0 | 3327791.83 | 465890.86 | 3793682.69 |  |  | 0 |  |  | 0 |  |  | 0 |  | 3746594.08 | 4271117.25 |  | 1253405.92 | 728882.75 | 74.93% | 85.42% | Project under litigation, institution looking at finalizing the matter before re-advertising . Funding has been re-allocated to Water Supply Coastal Areas and backlog eradication project, which is within the bulk water programme | 0 | 0 |  |  |  | 0 | -1849660.37 | -1849660.37 |  |  | 0 | -1849660.37 | -1849660.37 |  |  | 0 |  |  | 0 | 3541740.65 |  | 3541740.65 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1692080.28 | 1692080.28 |  | 8307919.72 | 8307919.72 | 16.92% | 16.92%
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1523 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Urban Roads - Programme | USDG | 30000000 |  |  |  | 0 |  | 0 |  | 0 | 1581556 | 1581556 |  | 1581556 | -47814.16 | 0 | -47814.16 | 75959.59 |  | 75959.59 |  |  | 0 |  |  | 0 |  |  | 0 | 375385.2 | 52553.93 | 427939.13 |  |  | 0 |  |  | 0 | 401958.81 | 56274.23 | 458233.04 |  |  | 0 |  |  | 0 |  |  | 0 | 347669.08 | 805489.44 | 914317.6 |  | 776066.56 | 667238.4 | 50.93% | 57.81% | Project under construction | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1562 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Upgrade Mdantsane Roads | USDG | 30000000 |  |  |  | 0 |  | 0 |  | 30000000 | 3063757 | 33063757 | 0 | 33063757 |  | 0 | 0 |  |  | 0 |  |  | 0 | 791918.6 | 110868.6 | 902787.2 | 302105.26 | 42294.74 | 344400 | 13526548.61 | 1721501.64 | 15248050.25 | 648211.6 | 0 | 648211.6 | 5434612.48 | 737892.73 | 6172505.21 | 5760242.97 | 760547.56 | 6520790.53 |  |  | 0 |  |  | 0 |  |  | 0 | 1735777.23 | 26463639.52 | 29836744.79 |  | 6600117.48 | 3227012.21 | 80.04% | 90.24% | Project under construction | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1563 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Quinera Arterial Road | USDG | 30000000 |  |  |  | 0 |  | 0 |  | 30000000 | 2325132 | 32325132 | -1000000 | 31325132 |  | 0 | 0 | 1370589 | 175671.96 | 1546260.96 | 279125.87 | 39077.62 | 318203.49 | 4769537.59 | 612733.41 | 5382271 | 2589616.25 | 362546.28 | 2952162.53 | 2456556.52 | 307847.26 | 2764403.78 |  |  | 0 |  |  | 0 | 4356428.13 | 581916.93 | 4938345.06 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 15821853.36 | 17901646.82 |  | 15503278.64 | 13423485.18 | 50.51% | 57.15% | Project under construction | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1564 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Fleet Street | USDG | 30000000 |  |  |  | 0 |  | 0 |  | 20000000 | 463013 | 20463013 |  | 20463013 |  | 0 | 0 | 1170655.39 | 163891.76 | 1334547.15 | 318205.64 | 44548.79 | 362754.43 | 322430.4 | 45140.26 | 367570.66 | -1157661.74 | 162072.63 | -995589.11 | 5244063.61 | 734168.89 | 5978232.5 | 869298.64 | 121701.81 | 991000.45 |  |  | 0 | 3937335.99 | 551227.04 | 4488563.03 |  |  | 0 |  |  | 0 |  |  | 0 | 9269952.78 | 10704327.93 | 12527079.11 |  | 9758685.07 | 7935933.89 | 52.31% | 61.22% | Annual Contractor completing the current phase of the project | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1565 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Gonubie Main Road | USDG | 30000000 |  |  |  | 0 |  | 0 |  | 30000000 | -9310863 | 20689137 | -1000000 | 19689137 |  | 0 | 0 | 153007.76 | 21421.09 | 174428.85 | 209352.69 | 29309.38 | 238662.07 | 694059.61 | 97168.35 | 791227.96 | 963730.12 | 134922.22 | 1098652.34 | 17302322.35 | 2422325.13 | 19724647.48 | 365236.7 | 51133.14 | 416369.84 |  |  | 0 | -196517.8 | 48773.65 | -147744.15 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 19491191.43 | 22296244.39 |  | 197945.57 | -2607107.39 | 98.99% | 113.2% | Expenditure on project to be balanced | 90000000 | 80000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | #DIV/0! |  | 150000000
Engineering Services |  | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1567 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 |  | RDP Houses- Roads Refurbishment | USDG | [9 empty] | 1431601 | 1431601 | 3000000 | 4431601 | [8 empty] | 0 |  |  | 0 | 1033346.59 | 144668.52 | 1178015.11 | 501088.64 | 70152.41 | 571241.05 |  |  | 0 | 1418029.09 | 199743.53 | 1617772.62 | 212321.92 | 29725.07 | 242046.99 | [9 empty] | 1523398.94 | 3164786.24 | 3609075.77 |  | 1266814.76 | 822525.23 | 71.41% | 81.44% | Project under construction
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1524 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 11, 12, 14, 17, 20, 20, 21, 22, 23, 30, 42,48 50 | Upgading of Mdantsane Roads | USDG | 0 |  |  |  | 0 |  | 0 |  | 53000000 |  | 53000000 | -1000000 | 52000000 | 0 | 0 | 0 | 5803174.76 | 783490.07 | 6586664.83 | 16914156.71 | 1582124.54 | 18496281.25 | 15681456.24 | 2086278.72 | 17767734.96 | 9592832.52 | 1342996.56 | 10935829.08 | 5455143.54 | 847359.31 | 6302502.85 |  |  | 0 | 113212.32 | 15849.72 | 129062.04 | 809299.19 | 226284.36 | 1035583.55 |  |  | 0 |  |  | 0 |  |  | 0 | 1151238.75 | 54369275.28 | 61253658.56 |  | -2369275.28 | -9253658.56 | 104.6% | 117.8% | Expenditure on project to be balanced | 60000000 | 60000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [13 empty] | 0 |  |  | 0 |  | 0%
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1525 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 46 | Rehabilitation of BCMM Bridges | USDG | 0 |  |  |  | 0 |  | 0 |  | 8000000 |  | 8000000 |  | 8000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 161349.81 | 22588.97 | 183938.78 | 1974608.25 | 276445.15 | 2251053.4 |  |  | 0 | 1819118.04 | 121623.67 | 1940741.71 | 373942.39 | 52351.94 | 426294.33 | 321826.05 | 45055.65 | 366881.7 |  |  | 0 |  |  | 0 |  |  | 0 | 917575.14 | 4650844.54 | 5168909.92 |  | 3349155.46 | 2831090.08 | 58.14% | 64.61% | Project under construction | 5000000 | 10000000 | [16 empty] | 0 |  |  | 0 | [16 empty] | 0 |  |  |  | 80000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1526 | Road transport | Other - BCM Fleet | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 24,26,31, 33, 35,36, 37, 38, 39, 40, 41, 49, 44, 43, 45, | Procurement of Graders for Rural Roads | USDG | 25000000 |  | 25000000 | 8000000 | 33000000 | 3500000 | 36500000 |  | 10000000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | Procurement process underway | 30000000 | 30000000 |  |  |  | 0 | 2916096.53 | 3323571.44 | 5902572.57 | 533811.63 | 6436384.2 | 8818669.1 | 9759955.64 | 4676639.56 | 948056.69 | 5624696.25 | 4623433.85 | 647280.74 | 5270714.59 | 4357834.3 | 610096.82 | 4967931.12 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2038718.1 | 22476576.81 | 25623297.6 |  | 10523423.19 | 7376702.4 | 68.11% | 77.65% | 110000000
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1527 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 24,26,31, 33, 35,36, 37, 38, 39, 40, 41, 49, 44, 43, 45, | Rehabilitation of Rural Roads | USDG |  |  |  |  | 0 |  | 0 |  | 15000000 | 445804 | 15445804 |  | 15445804 | 0 | 0 | 0 | 1400662.06 | 196092.69 | 1596754.75 | 1662796.5 | 232791.49 | 1895587.99 | 1857472.2 | 260046.1 | 2117518.3 | 981726.02 | 137441.64 | 1119167.66 | 5744904.79 | 804286.67 | 6549191.46 | 1239285.67 | 173499.99 | 1412785.66 | 2478628.25 | 347007.94 | 2825636.19 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 39989.6 | 15365475.49 | 17516642.01 |  | 80328.51 | -2070838.01 | 99.48% | 113.4% | Project under construction | 0 | 0
Engineering Services | Roads and Stormwater Drainage | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1528 | Road transport | Roads | 4 | 36 |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 | 21,22,23,46,47,28 | Quinera Arterial Road | USDG | 15000000 |  | 15000000 | -6000000 | 9000000 |  | 9000000 |  | 2000000 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 993125.4 | 139037.56 | 1132162.96 | 112716.5 | 0 | 112716.5 | 297945.8 | 41585.54 | 339531.34 | 544901.03 | 0 | 544901.03 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1948688.73 | 2129311.83 |  | 51311.27 | -129311.83 | 97.43% | 106.5% | Project under construction | 0 | 0 |  |  |  | 0 |  | 0 | 90883.71 |  | 90883.71 | 90883.71 | 90883.71 |  |  | 0 |  |  | 0 | 7999784.83 |  | 7999784.83 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 8090668.54 | 8090668.54 |  | 909331.46 | 909331.46 | 89.9% | 89.9%
Engineering Services |  | 6.34 - Roads Administration | Roads | 525025 | 4 | 36 | 1573 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | New-30 | Yes |  | Road Transport | Roads | KPA2 |  | Upgrading of Roads | USDG | [11 empty] | 9199000 | 9199000 | [23 empty] | 0 |  |  | 0 | [9 empty] | 7371721.93 | 0 | 0 |  | 9199000 | 9199000 | 0% | 0% | Orders generated, work in progress
Engineering Services |  | 6.34 - Roads Administration |  | 525025 | 4 | 01 | 1561 | Road transport | Roads |  |  |  | 05 | 05 | 01 | 01 | 030 | 001 | Renewal-30 |  | Yes | Road Transport | Roads | KPA2 |  | Roads - Renewal of Existing Roads | Own Funds | [11 empty] | 120000000 | 120000000 | [23 empty] | 0 | 4238860.24 |  | 4238860.24 | [9 empty] | 7345764.58 | 4238860.24 | 4238860.24 |  | 115761139.76 | 115761139.76 | 3.532% | 3.532%
Engineering Services | Roads and Stormwater Drainage | 4.4 - Asset Risk & Financial Services |  | 525025 | 5 | 05 | 1531 | Budget and treasury | Roads | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of 2 x Computers & Furniture - A13/70 | Own Funds | [10 empty] | 45000 |  | 45000 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 45000 | 45000 | 0% | 0% | Procurement process underway
Engineering Services | Fleet management - Braelyn | 6.43 - Fleet Management - Braelyn |  | 530020 | 4 | 01 | 1523 | Electricity | Other - BCM Fleet | 4 | 01 |  | 05 | 05 | 01 | 01 | 250 | 001 | New-250 | Yes |  | Other assets | Vehicles | KPA2 | All Wards | BCMM Fleet, Plant and Specialised Equipment and Specialised Solid Waste Vehicles | Own Funds | 0 |  | 0 |  | 0 |  | 0 |  | 18300000 |  | 18300000 |  | 18300000 | 0 | 0 | 0 | 1888532.64 |  | 1888532.64 | 10484165.53 |  | 10484165.53 | 4549898.98 |  | 4549898.98 |  |  | 0 |  |  | 0 | 1363030.7 |  | 1363030.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 18285627.85 | 18285627.85 |  | 14372.15 | 14372.15 | 99.92% | 99.92% | Project is progressing well | 18000000 | 18000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Engineering Services |  | 6.43 - Fleet Management - Braelyn |  | 530020 | 6 | 01 | 1512 | Electricity | Other - BCM Fleet |  |  |  | 05 | 05 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Other assets | Vehicles | KPA2 | All Wards | BCMM Fleet | Own Funds c/o | [9 empty] | 3997668 | 3997668 |  | 3997668 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3921558.46 |  | 3921558.46 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 3921558.46 | 3921558.46 |  | 76109.54 | 76109.54 | 98.1% | 98.1% | Procurement process is underway
Engineering Services |  | 6.43 - Fleet Management - Braelyn |  | 530020 | 6 | 01 | 1513 | Electricity | Electricity |  |  |  | 05 | 05 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Other assets | Vehicles | KPA2 | All Wards | Electricity Dept. - Specialised Plant and Equipment | Own Funds c/o | [9 empty] | 3000000 | 3000000 |  | 3000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2562672.99 |  | 2562672.99 | [9 empty] | 0 | 2562672.99 | 2562672.99 |  | 437327.01 | 437327.01 | 85.42% | 85.42% | Procurement process is underway
Engineering Services | Electricity Administration | 4.4 - Asset Risk & Financial Services |  | 535005 | 5 | 05 | 1509 | Budget and treasury | Electricity | 4 | 01 |  | 05 | 05 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 8500 | 8500 |  | 8500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 8500 | 8500 | 0% | 0% | Procurement process underway
Engineering Services |  | 4.4 - Asset Risk & Financial Services |  | 535010 | 5 | 05 | 1513 | Budget and treasury | Electricity | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 39900 | 39900 |  | 39900 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 39900 | 39900 | 0% | 0% | Procurement process underway
Engineering Services |  | 4.4 - Asset Risk & Financial Services |  | 535010 | 5 | 05 | 1537 | Budget and treasury | Electricity | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of Urban Substation 11KV Breaker | Own Funds | [9 empty] | 123451 | 123451 |  | 123451 | [20 empty] | 0 | 123450.95 |  | 123450.95 |  |  | 0 | [10 empty] | 123450.95 | 123450.95 |  | 0.05 | 0.05 | 100% | 100%
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design |  | 535025 | 4 | 01 | 1524 | Electricity | Electricity | 4 | 01 |  | 05 | 05 | 01 | 01 | 060 | 001 | Renewal-60 |  | Yes | Electricity | Electricity reticulation | KPA2 | 16, 18,29,35 | Bulk Electricity Infrastructure Upgrade(Ring-Fenced 4% of the Total Electricity Revenue) | Own Funds | 5285700 |  | 438631.88 |  | 438631.88 | 29084305 | 29522936.88 |  | 40000000 |  | 40000000 |  | 40000000 | 0 | 0 | 0 | 153718.89 |  | 153718.89 | 531767.37 |  | 531767.37 | 2301904.56 |  | 2301904.56 | 536394.46 |  | 536394.46 | 2212899.89 |  | 2212899.89 |  |  | 0 | 2105981.41 |  | 2105981.41 | 7154554.94 |  | 7154554.94 |  |  | 0 |  |  | 0 |  |  | 0 | 1320189.67 | 14997221.52 | 14997221.52 |  | 25002778.48 | 25002778.48 | 37.49% | 37.49% | 85% of Electrical projects are at various installation stages - funding for switch houses re-allocated as building tender delayed and will not be awarded in time for work to be completed - funds allocated to the new Qunenera to Gonubie link from Life Hospital. | 50000000 | 60000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 438631.88 | 438631.88 | 0% | 0%
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design |  | 535025 | 4 | 01 | 1525 | Electricity | Electricity | 4 | 01 |  | 05 | 05 | 01 | 01 | 060 | 001 | Renewal-60 |  | Yes | Electricity | Electricity reticulation | KPA2 | 16, 18,29,35 | Bulk Electricity Infrastructure Upgrade - Replacing Existing Infrastructure | Own Funds |  |  |  |  | 0 |  | 0 |  | 40000000 |  | 40000000 |  | 40000000 | 0 | 0 | 0 | 551972.49 |  | 551972.49 | 4746762.37 |  | 4746762.37 | 5945207.95 |  | 5945207.95 | 1926827.29 |  | 1926827.29 | 9172114.02 |  | 9172114.02 | -4734550.65 |  | -4734550.65 | 1105938.91 |  | 1105938.91 | 7413761.28 |  | 7413761.28 |  |  | 0 |  |  | 0 |  |  | 0 | 2391720.98 | 26128033.66 | 26128033.66 |  | 13871966.34 | 13871966.34 | 65.32% | 65.32% | 85 % Electrical projects are at various installation stages .There are also orders that have been submitted for processing. - New Cable installation Queenspark - Park Ave - Thorne St valued at R11m has commenced. | 40000000 | 40000000
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design |  | 535025 | 4 | 56 | 1533 | Electricity | Electricity | 4 | 56 |  | 05 | 05 | 01 | 01 | 060 | 001 | New-60 | Yes |  | Electricity | Electricity reticulation | KPA2 | 1,3,19, | INEP Electrification Programme | DoE(Intergrated National Electrification Programme) | 1329000 |  | 1329000 | -1329000 | 0 |  | 0 |  | 27000000 |  | 27000000 | -6413000 | 20587000 | 34346 | 0 | 34346 | 128806.07 |  | 128806.07 | 2895383.81 | 423386.58 | 3318770.39 | 9399037.37 | 702294.26 | 10101331.63 | 2741800.57 | 997423.06 | 3739223.63 | 6615.16 | 926.12 | 7541.28 | 49043.73 | 6866.12 | 55909.85 | 3425392.02 | 479554.88 | 3904946.9 | 586958.94 | 77799.2 | 664758.14 |  |  | 0 |  |  | 0 |  |  | 0 | 40392.57 | 19267383.67 | 21955633.89 |  | 1319616.33 | -1368633.89 | 93.59% | 106.6% | Budget allocation to be amended with next adjustment budget - As per the DoE revised to R20,587,000 | 27000000 | 12000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design | Electricity | 535025 | 4 | 36 | 1529 | Electricity | Electricity | 4 | 36 |  | 05 | 05 | 01 | 01 | 060 | 001 | New-60 | Yes |  | Electricity | Electricity reticulation | KPA2 | 1,2, 7, 8, 9,10 | INEP Electrification Programme - Counterfunding | USDG | 1600000 |  | 1600000 |  | 1600000 |  | 1600000 |  | 5000000 |  | 5000000 |  | 5000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1461848.76 | 184192.94 | 1646041.7 | 1221297.46 | 163756.07 | 1385053.53 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 2683146.22 | 3031095.23 |  | 2316853.78 | 1968904.77 | 53.66% | 60.62% | Messrs Benkro awarded the contract - work commenced 05/01/2015 | 5000000 | 5000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 1600000 | 1600000 | 0% | 0% | 5000000
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design | Electricity | 535025 | 4 | 36 | 1530 | Electricity | Electricity | 4 | 36 |  | 05 | 05 | 01 | 01 | 060 | 001 | New-60 | Yes |  | Electricity | Electricity reticulation | KPA2 | 2,7,8,9,11,12 | Electrification of Informal Dwelling Areas within BCMM | USDG | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 | 131675.29 | 18434.54 | 150109.83 | 374455.86 | 52423.82 | 426879.68 | 1598235.55 | 209410.26 | 1807645.81 | 582021.35 | 78536.07 | 660557.42 | 1511660.38 | 214579.38 | 1726239.76 | 70150.18 | 3364.23 | 73514.41 | 90792.25 | 1953.88 | 92746.13 | 1548768.91 | 216827.64 | 1765596.55 |  |  | 0 |  |  | 0 |  |  | 0 |  | 5907759.77 | 6703289.59 |  | 4092240.23 | 3296710.41 | 59.08% | 67.03% | Work is progressing well | 15000000 | 20000000 |  |  |  | 0 | 799580.21 | 911521.46 |  |  | 0 | 799580.21 | 911521.46 | 4082.92 | 571.61 | 4654.53 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 803663.13 | 916175.99 |  | 9196336.87 | 9083824.01 | 8.037% | 9.162% | 25000000
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design | Electricity | 535025 | 4 | 36 | 1531 | Electricity | Electricity | 4 | 36 |  | 05 | 05 | 01 | 01 | 060 | 001 | New-60 | Yes |  | Electricity | Electricity reticulation | KPA2 | 10,15,29,28,36,46 | Street Lighting and Highmasts within BCMM Areas of Supply - Informal Settlements | USDG | 853700 |  | 853700 |  | 853700 |  | 853700 |  | 3500000 |  | 3500000 |  | 3500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 194085.28 | 27171.94 | 221257.22 |  |  | 0 | 270120.47 | 37816.87 | 307937.34 |  |  | 0 | 85122 | 11917.08 | 97039.08 | 951070.43 | 133149.86 | 1084220.29 |  |  | 0 |  |  | 0 |  |  | 0 | 73723.23 | 1500398.18 | 1710453.93 |  | 1999601.82 | 1789546.07 | 42.87% | 48.87% | Smaller lighting projects have been completed - High Mast Lighting Contract funding re-allocated to Alexander Rd KWT upgrade | 3500000 | 3500000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 853700 | 853700 | 0% | 0% | 3500000
Engineering Services | Electricity Planning & Design | 6.46 - Electricity Planning & Design | Electricity | 535025 | 4 | 36 | 1532 | Electricity | Electricity | 4 | 36 |  | 05 | 05 | 01 | 01 | 060 | 001 | Renewal-60 |  | Yes | Electricity | Electricity reticulation | KPA2 | 10,15,29,28,36,46 | Replacement and Refurbishment of Bulk ELECT Infrastructure | USDG |  |  |  |  | 0 |  | 0 |  | 9199000 |  | 9199000 | -9199000 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! | This funding will be moved to the project "Upgrading of roads' in the Mid year adjustment budget | 2000000 | 8000000
Engineering Services |  | 6.46 - Electricity Planning & Design |  | 535025 | 4 | 01 | 1562 | Electricity | Electricity |  |  |  | 05 | 05 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Electricity | Electricity reticulation | KPA2 |  | Low Frequency Tester | Own Funds | [11 empty] | 311000 | 311000 | [23 empty] | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 311000 | 311000 | 0% | 0%
Engineering Services |  | 6.46 - Electricity Planning & Design |  | 535025 | 4 | 01 | 1563 | Electricity | Electricity |  |  |  | 05 | 05 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Electricity | Electricity reticulation | KPA2 |  | Office furniture and Equipment (Electricity) | Own Funds | [11 empty] | 60000 | 60000 | [23 empty] | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 60000 | 60000 | 0% | 0%
Engineering Services | Water Admin | 6.20 - Water Administration |  | 520005 | 4 | 75 | 1501 | Water | Water | 4 |  |  | 05 | 05 | 01 | 01 | 040 | 001 | Renewal-40 |  | Yes | Road Transport | Roads | KPA2 | 34,37,38,39,40,41,43,44,49,35,11,12,13,14,42,48,50,17,20,23,1-25 & 28,29,30,31, & 33,27,31,33,36,1,2,7,14,17,20,21,22,23,30,2,8,25,34,44,41 | Upgrade Water Supply in Rural Areas | LGTH |  |  |  |  | 0 |  | 0 |  | 188726 |  | 188726 |  | 188726 | 0 | 0 | 0 |  |  | 0 | 178585.49 |  | 178585.49 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 178585.49 | 178585.49 |  | 10140.51 | 10140.51 | 94.63% | 94.63% | 95% of the budget has been spent,project is progressing well
[26 empty] | TOTAL : ENGINEERING SERVICES |  | 256922400 | 0 | 102075331.88 | 20671000 | 122746331.88 | 32584305 | 155330636.88 | 0 | 665695618 | 12264061 | 674505650 | 93958000 | 768463650 | -213299.07 | 0 | -213299.07 | 24752777.27 | 2879522.9 | 27632300.17 | 48211032.36 | 4221188.7 | 52432221.06 | 59094381.44 | 5441872.56 | 64536254 | 34228966.3 | 5121773.54 | 39350739.84 | 91212472.04 | 10609531.68 | 101822003.72 | 11327193.23 | 875825.18 | 12203018.41 | 28419170.87 | 3051249.93 | 31470420.8 | 66426788.79 | 5332749.17 | 71759537.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93903591.09 | 363459483.23 | 400993196.89 | 0 | 405004166.77 | 367470453.11 | 47.3% | 52.18% |  | 1027000000 | 895000000 | 0 | 0 | 0 | 0 | 5827973.17 | 6902063.28 | 13804116.13 | 1784476.74 | 15588592.87 | 19632089.3 | 22490656.15 | 13528999.26 | 2080645.33 | 15609644.59 | 14379875.14 | 1913021.76 | 16292896.9 | 32034197.88 | 1817267.55 | 33851465.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038718.1 | 79575161.58 | 88244663.07 | 625034.64 | 43171170.3 | 34501668.81 | 64.83% | 71.89% |  |  | 0
[32 empty] | 0 |  | 0 | [20 empty] | 0 | [5 empty] | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 | [32 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF DEVELOPMENT PLANNING | [25 empty] | DIRECTORATE OF DEVELOPMENT PLANNING | [5 empty] | 0 |  | 0 | [26 empty] | 0 | [47 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Directorate of Development Planning | Director's Office | 7.1 - Office of The Director of Planning & Economic Dev. |  | 605005 | 4 | 01 | 1526 | Planning and Development | Planning and development | 4 | 01 |  | 05 | 06 | 01 | 01 | 270 | 001 | New-270 | Yes |  |  |  | KPA2 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 |  | 500000 |  | 500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 5100 |  | 5100 | 2418 |  | 2418 | 5806 |  | 5806 |  |  | 0 | 31582.91 |  | 31582.91 | 15083.4 |  | 15083.4 |  |  | 0 |  |  | 0 |  |  | 0 | 170533.45 | 59990.31 | 59990.31 | 0 | 440009.69 | 440009.69 | 12% | 12% | Procurement Processes are underway. Some Items are on order, whilst delivery is expected for other Items. | 500000 | 500000
Directorate of Development Planning |  | 7.11 - City Planning |  | 615070 | 6 | 01 | 1514 | Planning and Development | Planning and development |  |  |  | 05 | 06 | 01 | 01 | 312 | 002 | Renewal-312 |  | Yes | Other assets | Other Assets | KPA2 | All Wards | Upgrading of the City Hall | Own Funds c/o | [9 empty] | 5395309 | 5395309 |  | 5395309 |  |  | 0 |  |  | 0 | 1609065.89 |  | 1609065.89 | 478955.34 |  | 478955.34 | 571594.05 |  | 571594.05 | 128320.44 |  | 128320.44 | 591344.94 |  | 591344.94 | 515299.66 |  | 515299.66 | 1321.4 |  | 1321.4 | [9 empty] | 969709.32 | 3895901.72 | 3895901.72 | 0 | 1499407.28 | 1499407.28 | 72.21% | 72.21% | Practical Completion accepted on 13 March 2015. Works Completion now to be finalised.
Directorate of Development Planning | Architecture | 7.12 - Architecture | Development & Transport Planning | 615075 | 4 | 36 | 1534 | Planning and Development | Planning and development | 4 | 36 |  | 05 | 06 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other assets | Other Assets | KPA2 | All Wards | Upgrade KWT Payments Hall | USDG | 2800000 |  | 2800000 | -2800000 | 0 |  | 0 |  | 5000000 |  | 5000000 | -4450000 | 550000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 797099.25 | 0 | 0 | 0 | 550000 | 550000 | 0% | 0% | Professional service provider currently undertaking the necessary designs and specifications. | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0%
Directorate of Development Planning | Architecture | 4.4 - Asset Risk & Financial Services |  | 615075 | 5 | 05 | 1530 | Budget and treasury | Planning and development | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of CPU - A12/118 | Own Funds | [10 empty] | 8500 |  | 8500 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 8500 | 8500 | 0% | 0% | Replacement of CPU will be processed through the ICT Department. Finalisation of the matter by ICT Dept. is still awaited.
Directorate of Development Planning |  | 7.12 - Architecture |  | 615075 | 6 | 01 | 1515 | Planning and Development | Planning and development |  |  |  | 05 | 06 | 01 | 01 | 312 | 002 | Renewal-312 |  | Yes | Other assets | Other Assets | KPA2 | All Wards | Upgrade KWT Payments Hall | Own Funds c/o | [9 empty] | 477792 | 477792 | -477792 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | Due to restarting the project, this budget will not be spent before the 2014/15 financial year-end. Budget to be adjusted into 2015/16 fiancial year for construction costs.
Directorate of Development Planning | Land Administration | 7.13 - Land Administration | Development & Transport Planning | 615080 | 4 | 36 | 1535 | Planning and Development | Planning and development | 4 | 36 |  | 05 | 06 | 01 | 01 | 311 | 001 | New-311 | Yes |  | Other assets | Land & Buildings | KPA2 | All Wards | Land Acquisition | USDG | 20000000 |  | 20000000 | -11000000 | 9000000 |  | 9000000 |  | 5500000 |  | 5500000 |  | 5500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2727909.65 | 381753.35 | 3109663 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 2727909.65 | 3109663 | 0 | 2772090.35 | 2390337 | 49.6% | 56.54% | In respect of Portion 3 of Farm 1952, Service Provider has been appointed to conduct valuation of the property. In respect of remainder of Erf 17532, Deed of Sal was signed, appointment of Conveyancer was facilitated by Owner, purchase price together with transfer costs was paid to Conveyancer. An instruction to subdivide the land parcel was forwarded to City Planning. await relevant Transfer documents from Conveyancer. | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 295925.4 | 23537.64 | 319463.04 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 295925.4 | 319463.04 | 0 | 8704074.6 | 8680536.96 | 3.288% | 3.55%
Directorate of Development Planning | Transport Planning & Operations Admin | 7.30 - Transport Planning & Operations Admin | Development & Transport Planning | 620005 | 4 | 36 | 1536 | Planning and development | Planning and development | 4 | 36 |  | 05 | 06 | 01 | 01 | 050 | 001 | New-50 | Yes |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 | All Wards | Integrated Transport Plan Implementation Programme | USDG | 3000000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 24000000 |  | 24000000 | 4450000 | 28450000 | 52995 | 1576.4 | 54571.4 | 1754959.43 | 276099.8 | 2031059.23 | 1633771.02 | 228727.97 | 1862498.99 | 922399.1 | 1576.4 | 923975.5 | 1878949.14 | 260598.37 | 2139547.51 | 1419543.35 | 107220.9 | 1526764.25 | 1270856.32 | 27623.98 | 1298480.3 | 2797646.38 | 343194.79 | 3140841.17 | 2756974.96 | 474031.09 | 3231006.05 |  |  | 0 |  |  | 0 |  |  | 0 | 5721042.87 | 14488094.7 | 16208744.4 | 0 | 13961905.3 | 12241255.6 | 50.92% | 56.97% | Traffic calming measures have been completed in Beacon Bay, Cambridge, Braelyn, Duncan Village, Amalinda, Sweetwaters, KWT CBD, Willow Park, Zwelitsha, Mzamomhle, Mdantsane and Sunnyridge. Sidewalks have been completed in Phakamisa, Mdantsane and Potsdam. The sidewalks in Scenery Park are nearing completion. Side walks in N.U.1 and Cranberry S.P.S will start after the Easter holidays. Traffic signals have been identified on NEX, Robbie de Lange, Potters Pass and Gullsway however only Robbie De Lange will be implemented due to the unavailabilty of cable. Guidance signs are at manufacturing stage, awaiting delivery . Needs Camp / Potsdam Bridge progressing through detailed designs stage. - Guardrails have been identified and installed in Mdantsane, Braelyn, Zwelitsha, Phakamisa and Sweetwaters will start after the Easter holidays. - KwaTshatshu Bridge awarded 1 August 2014, inception stage complete,feasibility study report approved and detailed design stage has commenced. - Construction of Taxi/Bus embayments in Scenery Park, Cambridge and Mdantsane are in progress. Amalinda, Ginsberg, Dimbaza embayments and Bonza Bay Main Road taxi rank construction is progressing well. | 30000000 | 59500000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 162616.91 | 22766.37 | 185383.28 | 234124.03 | 32777.36 | 266901.39 | 866586.58 | 121322.12 | 987908.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 853992.67 | 1263327.52 | 1440193.37 | 0 | 1736672.48 | 1559806.63 | 42.11% | 48.01%
Directorate of Development Planning | Transport Planning & Operations Admin | 7.30 - Transport Planning & Operations Admin |  | 620005 | 6 | 81 | 1501 | Planning and development | Planning and development |  |  |  | 05 | 06 | 01 | 01 | 050 | 002 | New-50 | Yes |  | Other |  | KPA2 | All Wards | BCMET Roads | BCMET c/o | [9 empty] | 256818 | 256818 |  | 256818 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 122174.32 |  | 122174.32 | -122174.32 |  | -122174.32 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 256818 | 256818 | 0% | 0% | Work to be continued on Amalinda Main Road sidewalk project.
Directorate of Development Planning |  | 7.16 - Building Maintenance - Coastal / Central |  | 615095 | 4 | 01 | 1527 | Planning and Development | Planning and development | 4 | 01 |  | 05 | 06 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Rehabilitation of Midland Existing Municipal Buildings and Old Mutual Building (Finance) | Own Funds |  |  |  |  | 0 |  | 0 |  | 2471000 |  | 2471000 | -2000000 | 471000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 14700 |  | 14700 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 263080 | 14700 | 14700 | 0 | 456300 | 456300 | 3.121% | 3.121% | Work under way at the Old Mutual and plans have been drawn up for alterations on the Top floor for the GM Assets and Risks. There has been budget committed amounting to R136,330 for office alterations for the GM assets and Risks, further expenditure will occur in the nest two months. | 10000000 | 5000000
Directorate of Development Planning |  | 7.16 - Building Maintenance - Coastal / Central |  | 615095 | 4 | 01 | 1528 | Planning and Development | Planning and development | 4 | 01 |  | 05 | 06 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Building Refurbishments and Upgrading of Lifts for BCMM Buildings | Own Funds |  |  |  |  | 0 | 400000 | 400000 |  | 1424288 |  | 1424288 | -1224288 | 200000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 158000 | 0 | 0 | 0 | 200000 | 200000 | 0% | 0% | Professional service provider currently undertaking the necessary designs and specifications. | 820661 | 7755051 | [40 empty] | 8000000
Directorate of Development Planning |  | 7.16 - Building Maintenance - Coastal / Central |  | 615095 | 4 | 01 | 1529 | Planning and Development | Planning and development | 4 | 01 |  | 05 | 06 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 | All Wards | SCM Inventory Warehousing and Fencing | Own Funds |  |  |  |  | 0 | 400000 | 400000 |  | 6000000 | -4500000 | 1500000 | -1280000 | 220000 | 0 | 0 | 0 | 1146359.07 |  | 1146359.07 | -1146359.07 |  | -1146359.07 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 171750 | 0 | 0 | 0 | 220000 | 220000 | 0% | 0% | Professional service provider has been appointed -Official order has been generated. Consultant to formalise contract and undertake the necessary designs and specifications. | 900000 | 900000 | [40 empty] | 8000000
[26 empty] | TOTAL : DEVELOPMENT PLANNING |  | 25800000 | 0 | 25800000 | -13800000 | 12000000 | 800000 | 12800000 | 0 | 44895288 | 1629919 | 46533707 | -4982080 | 41551627 | 52995 | 1576.4 | 54571.4 | 2901318.5 | 276099.8 | 3177418.3 | 2096477.84 | 228727.97 | 2325205.81 | 1406454.44 | 1576.4 | 1408030.84 | 2575135.51 | 260598.37 | 2835733.88 | 1431495.47 | 107220.9 | 1538716.37 | 1876901.26 | 27623.98 | 1904525.24 | 3344528.95 | 343194.79 | 3687723.74 | 5501289.41 | 855784.44 | 6357073.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8251214.89 | 21186596.38 | 23288999.43 | 0 | 20365030.62 | 18262627.57 | 50.99% | 56.05% |  | 42220661 | 73655051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162616.91 | 22766.37 | 185383.28 | 234124.03 | 32777.36 | 266901.39 | 1162511.98 | 144859.76 | 1307371.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 853992.67 | 1559252.92 | 1759656.41 | 0 | 10440747.08 | 10240343.59 | 12.99% | 14.66%
[32 empty] | 0 |  | 0 | [74 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF ECONOMIC DEVELOPMENT | [25 empty] | DIRECTORATE OF ECONOMIC DEVELOPMENT | [5 empty] | 0 |  | 0
Directorate of Economic Development | Local Economic Development | 4.4 - Asset Risk & Financial Services |  | 635005 | 5 | 05 | 1523 | Budget and treasury | Planning and development | 5 | 05 |  | 05 | 03 | 03 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of 2 x Laptops - LED A13/86 | Own Funds | [10 empty] | 26000 |  | 26000 | [11 empty] | 0 |  |  | 0 | 20802 |  | 20802 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 20802 | 20802 |  | 5198 | 5198 | 80.01% | 80.01% | Procurement process underway.
Directorate of Economic Development |  | 7.35 - Local Economic Development | Development & Transport Planning | 635005 | 4 | 36 | 1537 | Planning and Development | Planning and development | 4 | 36 |  | 05 | 07 | 01 | 01 | 120 | 001 | New-120 | Yes |  |  |  | KPA3 |  | Enabling Infrastructure Programme - LED | USDG | 10000000 | 10000000 | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1126995.51 | 153635.37 | 1280630.88 |  |  | 0 |  |  | 0 |  |  | 0 | 2142403.58 | 1126995.51 | 1280630.88 |  | 8873004.49 | 8719369.12 | 11.27% | 12.81% | The service provider is on site working and additional milestones are being covered. The project will be completed within the financial year in terms of the project schedule. | 10000000 | 10000000
[26 empty] | TOTAL : ECONOMIC DEVELOPMENT | [5 empty] | 0 |  | 0 |  | 10000000 | 0 | 10026000 | 0 | 10026000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 0 | 20802 | 0 | 0 | 0 | 0 | 0 | 0 | 1126995.51 | 153635.37 | 1280630.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2142403.58 | 1147797.51 | 1301432.88 | 0 | 8878202.49 | 8724567.12 | 11.45% | 12.98% |  | 10000000 | 10000000
[32 empty] | 0 |  | 0
DIRECTORATE OF HEALTH AND PUBLIC SAFETY | [25 empty] | DIRECTORATE OF HEALTH AND PUBLIC SAFETY | [5 empty] | 0 |  | 0 | [17 empty] | 0 | [56 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Health and Public Safety | Office of the Director of Health & Public Safety | 8.1 - Office of The Director of Health & Public Safety |  | 705005 | 4 | 01 | 1530 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 30000 |  | 30000 |  | 30000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 10000 |  | 10000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 10000 | 10000 |  | 20000 | 20000 | 33.33% | 33.33% | Procurement process underway. Requisition for office chairs is being proccesed. | 500000 | 500000
Health and Public Safety | Health Administration | 8.1 - Office of The Director of Health & Public Safety |  | 710005 | 4 | 01 | 1553 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Health) | Own Funds |  |  |  |  | 0 |  | 0 |  | 70000 |  | 70000 |  | 70000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 4560 |  | 4560 |  |  | 0 | 10014 |  | 10014 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 26205.46 | 14574 | 14574 | 12908.46 | 55426 | 55426 | 20.82% | 20.82% | Furniture & Equipment delivered. Balance still to be delivered. Procurement process underway.
Health and Public Safety |  | 8.4 - Health Support |  | 710010 | 6 | 01 | 1517 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 271 | 002 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Municipal Health Services - IT & Database Development | Own Funds c/o | [9 empty] | 216000 | 216000 | -216000 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! | As per the adjustment budget this funding will be transferred to the Operating Budget
Health and Public Safety | Public Safety Administration | 8.1 - Office of The Director of Health & Public Safety |  | 725005 | 4 | 01 | 1554 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (GM Public Safety) | Own Funds |  |  |  |  | 0 |  | 0 |  | 21000 |  | 21000 |  | 21000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 21000 |  | 21000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 21000 | 21000 |  | 0 | 0 | 100% | 100% | Project completed.
Health and Public Safety | Fire & Rescue Services | 8.13 - Fire and Rescue Services |  | 725010 | 4 | 01 | 1533 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 360 | 001 | New-360 | Yes |  | Community |  | KPA2 | 1 to 50 | Fire Engine | Own Funds |  |  |  |  | 0 |  | 0 |  | 4000000 |  | 4000000 | -400000 | 3600000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3110725.68 | 0 | 0 |  | 3600000 | 3600000 | 0% | 0% | Requisition for fire engine has been submitted on the 9 March 2015. Procurement process underway. | 4000000 | 4000000
Health and Public Safety | Fire & Rescue Services | 8.1 - Office of The Director of Health & Public Safety |  | 725010 | 4 | 01 | 1555 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Fire & Rescue Sercices) | Own Funds |  |  |  |  | 0 |  | 0 |  | 80000 |  | 80000 |  | 80000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 42999 |  | 42999 |  |  | 0 |  |  | 0 | 36700.75 |  | 36700.75 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 79699.75 | 79699.75 | 30701.75 | 300.25 | 300.25 | 99.62% | 99.62% | Project progressing well
Health and Public Safety | Fire & Rescue Services | 4.4 - Asset Risk & Financial Services |  | 725010 | 5 | 05 | 1526 | Budget and treasury | Public safety | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of V3030 & V3018 - Written off - M12/203 & M12/233 | Own Funds | [10 empty] | 600000 |  | 600000 | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 600000 | 600000 | 0% | 0% | Specifications for the bush tenders has been submitted to Fleet Management in October for procurement.
Health and Public Safety | Fire & Rescue Services | 4.4 - Asset Risk & Financial Services |  | 725010 | 5 | 05 | 1529 | Budget and treasury | Public safety | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of V3029 - FLN384EC - M13/232 | Own Funds | [10 empty] | 600000 |  | 600000 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 600000 | 600000 | 0% | 0% | Procurement process underway with Fleet Management handling it.
Health and Public Safety |  | 8.13 - Fire and Rescue Services |  | 725010 | 6 | 01 | 1518 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 312 | 002 | New-312 | Yes |  | Other assets | Land & Buildings | KPA2 | All Wards | KWT Fire Station | Own Funds c/o | [9 empty] | 353709 | 353709 |  | 353709 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 80000.01 |  | 80000.01 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 80000.01 | 80000.01 |  | 273708.99 | 273708.99 | 22.62% | 22.62% | This project is at completion and handover stage.
Health and Public Safety |  | 8.13 - Fire and Rescue Services |  | 725010 | 6 | 01 | 1521 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Community |  |  | All Wards | Replacement of 2X Bush Fire Vehicles written off | Own Funds c/o | [9 empty] | 532200 | 532200 |  | 532200 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 532200 | 532200 | 0% | 0% | Specifications for the bush tenders has been submitted to Fleet Management in October for procurement.
Health and Public Safety |  | 8.13 - Fire and Rescue Services |  | 725010 | 6 | 01 | 1522 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Community |  |  | All Wards | Replacement of 5X Air Conditioners | Own Funds c/o | [9 empty] | 80000 | 80000 |  | 80000 |  |  | 0 |  |  | 0 | 79776.8 |  | 79776.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 79776.8 | 79776.8 |  | 223.2 | 223.2 | 99.72% | 99.72% | Project completed.
Health and Public Safety |  | 8.13 - Fire and Rescue Services |  | 725010 | 4 | 01 | 1565 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  |  | All Wards | Fire Equipment | Own Funds | [11 empty] | 1200000 | 1200000 | [23 empty] | 0 |  |  | 0 | [10 empty] | 0 | 0 |  | 1200000 | 1200000 | 0% | 0% | Specifications and business plan completed and submitted to Management for approval.
Health and Public Safety |  | 8.14 - Security Services |  | 725015 | 4 | 01 | 1534 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  |  | All Wards | Closed Circuit Television Network - CCTV | Own Funds | [8 empty] | 2000000 |  | 2000000 | 0 | 2000000 |  |  | 0 | 761505.76 |  | 761505.76 | -761455.82 |  | -761455.82 |  |  | 0 |  |  | 0 | 169330.5 |  | 169330.5 | -169380.44 |  | -169380.44 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 2000000 | 2000000 | 0% | 2.91e-15% | Procurement process underway. Tender was awarded at Bid Adjudication Committee on the 23 March 2015 (BAC Minute No 44/15). Management to fast track process.
Health and Public Safety | Law Enforcement Services | 8.14 - Security Services |  | 725015 | 4 | 01 | 1568 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  |  | All Wards | Upgrading of Existing CCTV Control Room | Own Funds | [11 empty] | 300000 | 300000 | [26 empty] | 0 | [9 empty] | 0 | 0 | 0 |  | 300000 | 300000 | 0% | 0% | Meeting held on 31 March 2015 wherein it was advised that the Building Maintenance Annual contract had been awarded and that the majority of work to be carried out will be done this current financial year, estimating two months to complete.
Health and Public Safety |  | 8.14 - Security Services |  | 725015 | 6 | 01 | 1516 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 271 | 002 | New-260 | Yes |  | Community |  |  | All Wards | Closed Circuit Television Network - CCTV c/o | Own Funds c/o | [9 empty] | 1196101 | 1196101 |  | 1196101 |  |  | 0 |  |  | 0 | 316911.22 |  | 316911.22 | 177174.39 |  | 177174.39 | 30168.27 |  | 30168.27 | 69166.66 |  | 69166.66 |  |  | 0 | 45802.97 |  | 45802.97 | 63056.5 |  | 63056.5 | [10 empty] | 702280.01 | 702280.01 |  | 493820.99 | 493820.99 | 58.71% | 58.71% | Security cameras installed and needs to be linked to radio antennaes on high mast site which must still be finalised. The process of leasing high mast site has been initiated.
Health and Public Safety | Law Enforcement Services | 8.14 - Security Services |  | 725015 | 4 | 01 | 1535 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 250 | 001 | New-250 | Yes |  | Community | Other Assets | KPA2 | 1 to 50 | Fire Arms - Traffic and Law Enforcement | Own Funds | 50000 |  | 50000 |  | 50000 |  | 50000 |  | 100000 |  | 100000 |  | 100000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 86850 |  | 86850 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 86850 | 86850 |  | 13150 | 13150 | 86.85% | 86.85% | Project completed. | 0 | 200000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 43280 |  | 43280 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 43280 | 43280 |  | 6720 | 6720 | 86.56% | 86.56%
Health and Public Safety | Law Enforcement Services | 8.1 - Office of The Director of Health & Public Safety |  | 725015 | 4 | 01 | 1557 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Law Enforcement) | Own Funds |  |  |  |  | 0 |  | 0 |  | 14110 |  | 14110 |  | 14110 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 10186.85 | 0 | 0 |  | 14110 | 14110 | 0% | 0% | Procurement process underway.
Health and Public Safety |  | 8.14 - Security Services |  | 725015 | 6 | 01 | 1520 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 270 | 002 | New-270 | Yes |  | Community |  |  | All Wards | Security Equipment - DVRI | Own Funds c/o | [9 empty] | 40000 | 40000 |  | 40000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 40000 | 40000 | 0% | 0% | A discussion with Duncan Village Redevelopment Initiative section in order to fast track the project is currently undertaken
Health and Public Safety |  | 8.14 - Security Services |  | 725015 | 4 | 01 | 1566 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  |  |  | CCTV Cameras for BCMM Cash Offices | Own Funds | [11 empty] | 1500000 | 1500000 | [23 empty] | 0 |  |  | 0 | [10 empty] | 0 | 0 |  | 1500000 | 1500000 | 0% | 0% | Tender was awarded at Bid Adjudication Committee on the 23 March 2015 (BAC Minute No 44/15). Management to fast track process.
Health and Public Safety |  | 8.14 - Security Services |  | 725015 | 4 | 01 | 1567 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  |  |  | Equipment for Law Enforcement Services | Own Funds | [11 empty] | 100000 | 100000 | [23 empty] | 0 |  |  | 0 | [10 empty] | 0 | 0 |  | 100000 | 100000 | 0% | 0% | Specifications and business plan completed and submitted to Management for approval.
Health and Public Safety | Traffic Administration | 8.1 - Office of The Director of Health & Public Safety |  | 725020 | 4 | 01 | 1556 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Traffic Services) | Own Funds |  |  |  |  | 0 |  | 0 |  | 211190 |  | 211190 |  | 211190 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 50316 |  | 50316 | 18510 |  | 18510 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 68826 | 68826 | 20899 | 142364 | 142364 | 32.59% | 32.59% | Furniture & Equipment delivered. Balance still to be delivered. Procurement process underway.
Health and Public Safety | Traffic Administration | 4.4 - Asset Risk & Financial Services |  | 725020 | 5 | 05 | 1511 | Budget and treasury | Public safety | 4 | 01 |  | 05 | 03 | 03 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 145000 | 145000 |  | 145000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 145000 | 145000 | 0% | 0% | Procurement process underway.
Health and Public Safety | Traffic Administration | 4.4 - Asset Risk & Financial Services |  | 725020 | 5 | 05 | 1522 | Budget and treasury | Public safety | 5 | 05 |  | 05 | 03 | 03 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Replacement of CPU & Monitor - A12/110 | Own Funds | [10 empty] | 10000 |  | 10000 | [11 empty] | 0 |  |  | 0 | 7569.32 |  | 7569.32 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 7569.32 | 7569.32 |  | 2430.68 | 2430.68 | 75.69% | 75.69% | Project completed.
Health and Public Safety | Traffic Control | 8.16 - Traffic Control | Public Safety | 725025 | 4 | 36 | 1538 | Public safety | Public safety | 4 | 36 |  | 05 | 07 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Community | Land & Buildings/ Fire Stations | KPA2 | 35 | KWT Traffic Building | USDG | 1500000 |  | 1500000 | 500000 | 2000000 | -2000000 | 0 | 2000000 | 3000000 |  | 3000000 | -930265 | 2069735 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2069735 | 0 | 0 |  | 2069735 | 2069735 | 0% | 0% | Draft Plans for Main building completed. First invoice to be submitted by end of March 2015 for the first stage of deliverables. Second invoice before end of June 2015. Plans to be presented to the Traffic Dept in April 2015. | 6000000 | 6000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0%
Health and Public Safety | Traffic Control | 8.16 - Traffic Control |  | 725025 | 4 | 01 | 1536 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 250 | 001 | New-250 | Yes |  | Community | Other Assets | KPA2 | 20 | Mdantsane Testing Station - Equipment | Own Funds | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 200000 | 1102.63 | 0 | 1102.63 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 22837.5 |  | 22837.5 |  |  | 0 |  |  | 0 |  |  | 0 |  | 23940.13 | 23940.13 | 12622 | 176059.87 | 176059.87 | 11.97% | 11.97% | Furniture & Equipment delivered. Balance still to be delivered. Procurement process underway. | 0 | 0 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Health and Public Safety | Environmental Health |  |  | 710030 | 4 | 01 | 1531 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Air Monitoring Station | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 1800000
Health and Public Safety | Disaster Management |  |  | 725055 | 4 | 01 | 1542 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Tactic Radio Network | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 800000
Health and Public Safety | Disaster Management |  |  | 725055 | 4 | 01 | 1543 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Early Warning Systems | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 500000
Health and Public Safety | Traffic Control |  |  | 725025 | 4 | 01 | 1537 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Road Closure and Events Equipment | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 200000
Health and Public Safety | Traffic Control |  |  | 725025 | 4 | 01 | 1538 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Traffic Enforcement Equipment | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 1000000
Health and Public Safety | Fire & Rescue Services |  |  | 725010 | 4 | 01 | 1532 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 1 to 50 | Fire Equipment | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 2000000
Health and Public Safety | Traffic Control |  |  | 725025 | 4 | 01 | 1539 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 250 | 001 | New-250 | Yes |  | Community |  | KPA2 | 27 | Vehicle Pound | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 200000
Health and Public Safety | Vehicle Test Station / Examination |  |  | 725035 | 4 | 01 | 1540 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 260 | 001 | New-260 | Yes |  | Community |  | KPA2 | 27,1,41 | Vehicle Test Station Equipment | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 2000000
Health and Public Safety | Vehicle Test Station / Examination |  |  | 725035 | 4 | 01 | 1541 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 312 | 001 | Renewal-312 |  | Yes | Community |  | KPA2 | 27,1,41 | Upgrade Vehicle Test Station | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  | 0 | 2000000
Health and Public Safety |  | 8.16 - Traffic Control |  | 725025 | 4 | 01 | 1564 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 250 | 001 | New-260 | Yes |  | Community |  |  |  | Equipment for Traffic Services | Own Funds | [11 empty] | 100000 | 100000 | [23 empty] | 0 |  |  | 0 | [10 empty] | 0 | 0 |  | 100000 | 100000 | 0% | 0% | Specifications and business plan completed and submitted to Management for approval.
Health and Public Safety |  | 8.18 - Vehicle Test Station / Examination |  | 725035 | 6 | 01 | 1519 | Public safety | Public safety |  |  |  | 05 | 07 | 01 | 01 | 312 | 002 | New-312 | Yes |  |  |  |  | All Wards | Learners Licence Centre - Mdantsane | Own Funds c/o | [9 empty] | 798970 | 798970 | 200000 | 998970 |  |  | 0 |  |  | 0 | 366421.75 |  | 366421.75 |  |  | 0 | 44666.78 |  | 44666.78 | 110254.72 |  | 110254.72 | 169380.44 |  | 169380.44 |  |  | 0 |  |  | 0 | [9 empty] | 43760.8 | 690723.69 | 690723.69 | 43760 | 308246.31 | 308246.31 | 69.14% | 69.14% | Project is progressing well. Balance of funds for the fencing and minor additional works
Health and Public Safety | Disaster Management | 8.1 - Office of The Director of Health & Public Safety |  | 725055 | 4 | 01 | 1558 | Public safety | Public safety | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | 1 to 50 | Office Furniture and Equipment (Disaster Management) | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 73700 |  | 73700 |  | 73700 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 73700 | 73700 | 0% | 0% | Procurement process underway.
Health and Public Safety | Disaster Management | 4.4 - Asset Risk & Financial Services |  | 725055 | 5 | 05 | 1506 | Budget and treasury | Public safety | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Asset Replacements - Insurance | Own Funds |  |  | 0 |  | 0 |  | 0 |  |  | 95000 | 95000 |  | 95000 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 9792.6 |  | 9792.6 | 61630.7 |  | 61630.7 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 71423.3 | 71423.3 |  | 23576.7 | 23576.7 | 75.18% | 75.18% | Computers & Furniture supplied and delivered. Specifications being drawn up for radios for the Disaster Management Centre to be submitted to Supply Chain Management.
[26 empty] | TOTAL : HEALTH AND PUBLIC SAFETY |  | 1750000 | 0 | 1750000 | 500000 | 2250000 | -2000000 | 250000 | 2000000 | 9800000 | 3456980 | 14466980 | 1853735 | 16320715 | 1102.63 | 0 | 1102.63 | 761505.76 | 0 | 761505.76 | 1653.95 | 0 | 1653.95 | 177174.39 | 0 | 177174.39 | 235476.65 | 0 | 235476.65 | 502511.91 | 0 | 502511.91 | 50316 | 0 | 50316 | 121027.72 | 0 | 121027.72 | 85894 | 0 | 85894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5260613.79 | 1936663.01 | 1936663.01 | 120891.21 | 14384051.99 | 14384051.99 | 11.87% | 11.87% |  | 10500000 | 21200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43280 | 0 | 43280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43280 | 43280 | 0 | 2206720 | 2206720 | 1.924% | 1.924% |  |  | 0
[30 empty] | 0 |  | 0 |  | 0 | [74 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
DIRECTORATE OF COMMUNITY SERVICES | [25 empty] | DIRECTORATE OF COMMUNITY SERVICES |  |  |  | 0 |  | 0 |  | 0 | [74 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Community Services | Environmental Administration Support | 9.1 - Office of The Director of Community Services |  | 755005 | 4 | 01 | 1544 | Community and social services | Support Services | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 | All Wards | Office Furniture and Equipment (Directorate) | Own Funds |  |  | 0 |  | 0 |  | 0 |  | 200000 |  | 200000 |  | 200000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 24411.1 |  | 24411.1 |  |  | 0 | 25867.08 |  | 25867.08 | 27800 |  | 27800 | 40045.5 |  | 40045.5 |  |  | 0 |  |  | 0 |  |  | 0 | 75543.56 | 118123.68 | 118123.68 | 97109 | 81876.32 | 81876.32 | 59.06% | 59.06% | Furniture is being purchased as required, procurement processes in progress | 500000 | 500000
Community Services | Environmental Services | 9.4 - Environmental Services | Environmental Services | 755010 | 4 | 36 | 1539 | Community and social services | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 150 | 001 | New-150 | Yes |  | Community | Recreational Facilities | KPA2 | 13, 21,23 | Development of Community Parks(Inland, Midlands and Coastal) | USDG | 3000000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 2000000 |  | 2000000 | 1685051 | 3685051 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 4196.91 |  | 4196.91 |  |  | 0 |  |  | 0 | 179759.6 | 25166.34 | 204925.94 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1220944.15 | 183956.51 | 209122.85 | 65026 | 3501094.49 | 3475928.15 | 4.992% | 5.675% | Tender awarded 31 March 2015 for development of parks. Orders for fencing have been received. | 0 | 0 |  |  |  | 0 |  | 0 | 4531.56 | 634.41 | 5165.97 | 4531.56 | 5165.97 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4531.56 | 5165.97 |  | 2995468.44 | 2994834.03 | 0.1511% | 0.1722%
Community Services | Cleansing Administration Support | 4.4 - Asset Risk & Financial Services |  | 755010 | 5 | 05 | 1505 | Budget and treasury | Amenities | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Asset Replacements - Insurance | Own Funds |  |  | 0 |  | 0 |  | 0 |  |  | 13676 | 13676 |  | 13676 |  |  | 0 |  |  | 0 | 13675.44 |  | 13675.44 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 13675.44 | 13675.44 | 0 | 0.56 | 0.56 | 100% | 100% | Assets have been replaced
Community Services | Cleansing Administration Support | 4.4 - Asset Risk & Financial Services |  | 755010 | 5 | 05 | 1532 | Budget and treasury | Amenities | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of 7 Brushcutters | Own Funds | [10 empty] | 84000 |  | 84000 | [20 empty] | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 | 0 | 0 | 84000 | 84000 | 0% | 0% | Procurement process underway
Community Services |  | 4.4 - Asset Risk & Financial Services |  | 755010 | 5 | 05 | 1536 | Budget and treasury | Amenities | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of 4 Brushcutters & 1 Blower | Own Funds | [10 empty] | 52000 |  | 52000 | [20 empty] | 0 |  |  | 0 |  |  | 0 | [10 empty] | 0 | 0 |  | 52000 | 52000 | 0% | 0% | Procurement process underway
Community Services |  | 4.4 - Asset Risk & Financial Services |  | 755010 | 5 | 05 | 1539 | Budget and treasury | Amenities |  |  |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of furniture & Equipment A13/75 | Own Funds | [11 empty] | 34000 | 34000 | [26 empty] | 0 | [10 empty] | 0 | 0 |  | 34000 | 34000 | 0% | 0% | Procurement process underway
Community Services | Interments | 9.7 - Interments | Environmental Services | 755025 | 4 | 36 | 1540 | Environmental Protection | Environmental Services | 4 | 36 |  | 05 | 07 | 01 | 01 | 220 | 001 | New-220 | Yes |  | Other assets | Cemeteries | KPA2 | All Wards | Development and Upgrading of Cemeteries(Inland, Midland and Coastal) | USDG | 12040943 |  | 8040943 | 3000000 | 11040943 | 7500000 | 18540943 |  | 10000000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 284773.45 | 39868.28 | 324641.73 | 1140075.38 | 115219.71 | 1255295.09 | 800777.17 | 112108.8 | 912885.97 | -317077.49 |  | -317077.49 | 1180350.88 | 165249.12 | 1345600 |  |  | 0 |  |  | 0 |  |  | 0 | 3666287.66 | 3088899.39 | 3521345.3 | 3349210 | 6911100.61 | 6478654.7 | 30.89% | 35.21% | Project progressing well | 8000000 | 8000000 |  |  |  | 0 | 91583.2 | 94326.92 | 581732.54 | 8018.19 | 589750.73 | 673315.74 | 684077.65 | 660644.36 | 88006.48 | 748650.84 | 1691335.57 | 212536.29 | 1903871.86 | 3734448.25 | 432675.81 | 4167124.06 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4981912.06 | 6759743.92 | 7503724.41 |  | 4281199.08 | 3537218.59 | 61.22% | 67.96% | 10000000
Community Services |  | 9.7 - Interments |  | 755025 | 6 | 01 | 1523 | Environmental Protection | Amenities |  |  |  | 05 | 07 | 01 | 01 | 250 | 002 | New-250 | Yes |  | Other assets |  |  | All Wards | Cemetery Vehicles | Own Funds c/o | [9 empty] | 1700000 | 1700000 |  | 1700000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 1700000 | 1700000 | 0% | 0% | Procurement process underway
Community Services | Interments | 4.4 - Asset Risk & Financial Services |  | 755025 | 5 | 05 | 1512 | Budget and treasury | Amenities | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 57250 | 57250 |  | 57250 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 57250 | 57250 | 0% | 0% | Procurement process underway
Community Services | Libraries | 4.4 - Asset Risk & Financial Services |  | 760010 | 5 | 05 | 1508 | Budget and treasury | Amenities | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 1700 | 1700 |  | 1700 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1341 |  | 1341 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 1341 | 1341 |  | 359 | 359 | 78.88% | 78.88% | Project complete.
Community Services | Halls | 9.14 - Halls | Amenities | 760025 | 4 | 36 | 1541 | Community and social services | Amenities |  |  |  | 05 | 07 | 01 | 01 | 170 | 001 | New-170 | Yes |  | Other assets |  | KPA2 | All Wards | Construction of Nompumelelo Halls | USDG |  |  | 4000000 |  | 4000000 | -3000000 | 1000000 |  | 7000000 |  | 7000000 | -3500000 | 3500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 10666.4 | 1493.3 | 12159.7 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 174152 | 10666.4 | 12159.7 |  | 3489333.6 | 3487840.3 | 0.3048% | 0.3474% | Procurement process underway. The provision of Professional Consultancy Services is at Bid Adjudication Committee level. We are in the process of obtaining quotations to clear and level the erf and erect fencing around it. | 0 | 0 | [19 empty] | 0 | [14 empty] | 0 |  | 4000000 | 4000000 | 0% | 0%
Community Services | Halls | 9.14 - Halls | Amenities | 760025 | 4 | 36 | 1542 | Community and social services | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 170 | 001 | New-170 | Yes |  | Other assets | Halls | KPA2 | All Wards | Development and Upgrading of Community Halls - War Memorial Hall Upgrade of Parking Area, O.R.Tambo Hall Upgrade of Parking Area, Egoli Community Hall( New Hall), Needs Camp Community Hall Upgrade, Orient Theatre Upgrade, Continuation of KWT Town Hall and NU 5 Hall Mdantsane | USDG | 10000000 |  | 10000000 | -4000000 | 6000000 | -5000000 | 1000000 |  | 3000000 |  | 3000000 | 3500000 | 6500000 | 0 | 0 | 0 | 47492.13 | 5262.9 | 52755.03 | 121503.65 | 17010.51 | 138514.16 |  |  | 0 | 502484.64 | 21527.67 | 524012.31 | 139036 | 0 | 139036 |  |  | 0 | 533094.28 | 74633.2 | 607727.48 | 1333591.76 | 175808.05 | 1509399.81 |  |  | 0 |  |  | 0 |  |  | 0 | 2410699.74 | 2677202.46 | 2971444.79 | 1180593 | 3822797.54 | 3528555.21 | 41.19% | 45.71% | Tarring has commenced at OR Tambo Hall. Needs Camp hall is 90% complete. Tarring has commenced at War Memorial Hall and Cambridge town hall. | 9000000 | 9000000 |  |  |  | 0 | 123401.18 | 126631 | 485376.34 | 65891.88 | 551268.22 | 608777.52 | 677899.22 | 295837.21 | 8054.91 | 303892.12 | 132480 |  | 132480 | 727758.62 | 16971.31 | 744729.93 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1574808.82 | 1764853.35 | 1859001.27 |  | 4235146.65 | 4140998.73 | 29.41% | 30.98% | 20000000
Community Services |  | 9.14 - Halls |  | 760025 | 6 | 01 | 1524 | Community and social services | Amenities |  |  |  | 05 | 07 | 01 | 01 | 170 | 002 | New-170 | Yes |  | Other assets |  |  | All Wards | Reeston Community Hall Renovations | Own Funds c/o | [9 empty] | 100000 | 100000 | -100000 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! | Additional funding being sought
Community Services |  | 9.14 - Halls |  | 760025 | 6 | 01 | 1525 | Community and social services | Amenities |  |  |  | 05 | 07 | 01 | 01 | 170 | 002 | New-170 | Yes |  | Other assets |  |  | All Wards | Continuation of Refurbishment of KWT Hall / Cambridge | Own Funds c/o | [9 empty] | 1075698 | 1075698 |  | 1075698 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 315540 | 0 | 0 |  | 1075698 | 1075698 | 0% | 0% | Contractor has commenced for the installation of New sewer system at Cambridge Hall. King Wiliams Town hall and Cambridge hall - procurement processs underway.
Community Services |  | 9.14 - Halls |  | 760025 | 6 | 01 | 1534 | Community and social services | Support Services |  |  |  | 05 | 07 | 01 | 01 | 260 | 002 | New-260 | Yes |  | Other assets |  |  | All Wards | Replacement of 2 X Hifgh back chairs, 1 X Piano and 2 X Bar Stools | Own Funds c/o | [9 empty] | 51000 | 51000 |  | 51000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 19500 | 0 | 0 |  | 51000 | 51000 | 0% | 0% | Procurement process underway
Community Services |  | 9.14 - Halls |  | 760025 | 6 | 01 | 1535 | Community and social services | Support Services |  |  |  | 05 | 07 | 01 | 01 | 260 | 002 | New-260 | Yes |  | Other assets |  |  | All Wards | Replacement of Stove and Fridge | Own Funds c/o | [9 empty] | 12000 | 12000 |  | 12000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 11500 |  | 11500 | [9 empty] | 0 | 11500 | 11500 |  | 500 | 500 | 95.83% | 95.83% | Project complete
Community Services |  | 9.14 - Halls |  | 760025 | 4 | 35 | 1510 | Community and social services | Amenities |  |  |  | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other assets |  |  | All Wards | Reeston MPCC - DVRI | HSDG-(MPCC) | [9 empty] | 10068500 | 10068500 | -9368500 | 700000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 665300 |  | 665300 | [9 empty] | 1578445.9 | 665300 | 665300 |  | 34700 | 34700 | 95.04% | 95.04% | Budget has been requested to be reduced in mid year budget adjustment. Balance of funding will be used for refurbishment.
Community Services |  | 4.4 - Asset Risk & Financial Services |  | 760025 | 5 | 05 | 1534 | Community and social services | Amenities | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of Furniture & Equipment | Own Funds | [10 empty] | 636263 |  | 636263 | [20 empty] | 0 |  |  | 0 | 18825 |  | 18825 | [9 empty] | 7991.8 | 18825 | 18825 |  | 617438 | 617438 | 2.959% | 2.959% | Procurement process underway
Community Services |  | 9.14 - Halls |  | 760025 | 4 | 15 | 1501 | Community and social services | Amenities |  |  |  | 05 | 07 | 01 | 01 | 170 | 001 | New-170 | Yes |  |  |  |  | All Wards | John Dube Village | DEDEAT | [11 empty] | 199168 | 199168 | [23 empty] | 0 |  |  | 0 | [10 empty] | 0 | 0 |  | 199168 | 199168 | 0% | 0% | Informal tender processes are underway for Purchasing of Chairs for Scenery Park Hall
Community Services | Sportsfields | 9.16 - Sportsfields |  | 765010 | 4 | 01 | 1545 | Community and social services | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Other assets |  | KPA2 | All Wards | Sports equipment and structures | Own Funds | [8 empty] | 1500000 |  | 1500000 |  | 1500000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 335950 |  | 335950 | 28620 |  | 28620 | 29997.54 |  | 29997.54 | 239740 |  | 239740 | 358773.36 |  | 358773.36 | 260647.72 |  | 260647.72 |  |  | 0 |  |  | 0 |  |  | 0 | 232953.31 | 1253728.62 | 1253728.62 |  | 246271.38 | 246271.38 | 83.58% | 83.58% | Cricket covers and goal posts received. Trailer received on 13/02/2015. Pedestrian roller was received. Awaiting for orders for athletics equipment's from Supply Chain Management Amendments to specifications document completed for Kudu Mowers and Brushcutters and was resubmitted to Supply Chain Management for advertisement. | 0 | 0
Community Services | Sportsfields | 9.16 - Sportsfields |  | 765010 | 4 | 01 | 1546 | Community and social services | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Other assets | Sportsfields | KPA2 | All Wards | Equipment for Jan Smuts Stadium | Own Funds | [8 empty] | 41907 |  | 41907 |  | 41907 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 28997.54 |  | 28997.54 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 6842.11 | 28997.54 | 28997.54 |  | 12909.46 | 12909.46 | 69.19% | 69.19% | Two marking machines were received by Sportsfields. Procurement of outstanding equipment is in progress
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1543 | Community and social services | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Other assets | Swimming Pool | KPA2 | All Wards | Redevelopment of Mdantsane NU 2 Swimming Pool and Upgrading of Waterworld | USDG | 5000000 |  | 5000000 | -5000000 | 0 |  | 0 |  | 15000000 | -5000000 | 10000000 | -4500000 | 5500000 | 0 | 0 | 0 |  |  | 0 | 2024.82 | 283.48 | 2308.3 | 2540.24 |  | 2540.24 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 4565.06 | 4848.54 |  | 5495434.94 | 5495151.46 | 0.083% | 0.08816% | Professional Service Provider that will be appointed for Human Settlement will be utilized. Cancellation of tender will be submitted to Supply Chain Management | 5000000 | 5000000 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0! |  |  | 10000000
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1544 | Community and social services | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Other assets | Sportsfields | KPA2 | All Wards | Upgrading of Dimbaza and Zwelitsha Stadium | USDG | 4000000 |  | 4000000 | 1800000 | 5800000 | -5384413 | 415587 |  | 2250000 |  | 2250000 |  | 2250000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 675463.6 | 0 | 0 |  | 2250000 | 2250000 | 0% | 0% | Site inspection for Dimbaza Stadium was on the 13/03/2015. Human Settlement Professional Service Provider’s will be utilized. Zwelitsha Stadium – Order was received for fencing and contractor is on site. Caretaker house order was received for renovations. | 4750000 | 4750000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 2111.29 | 295.58 | 2406.87 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2111.29 | 2406.87 |  | 5797888.71 | 5797593.13 | 0.0364% | 0.0415%
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1545 | Community and social services | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Other assets | Sportsfields | KPA2 | All Wards | Upgrading of Floodlights at Victoria Grounds, Bhisho Stadium, Ginsberg stadium, Sisa Dukashe Stadium, Alfred Schoeman Stadium, North End Stadium, Jan Smuts Stadium, Amalinda Stadium, and Gompo Stadium | USDG | 5000000 |  | 5000000 | -1000000 | 4000000 | -2500000 | 1500000 |  | 3000000 |  | 3000000 | -1685051 | 1314949 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 978025.7 | 136923.61 | 1114949.31 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 4716.6 | 660.35 | 5376.95 |  |  | 0 |  |  | 0 |  |  | 0 |  | 982742.3 | 1120326.26 |  | 332206.7 | 194622.74 | 74.74% | 85.2% | Procurement process underway. Formal tender for the appointment of a Professional Service Provider was advertised and was closed on the 10/03/2015. | 0 | 0 |  |  |  | 0 |  | 0 | 7827.24 | 1095.81 | 8923.05 | 7827.24 | 8923.05 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7827.24 | 8923.05 |  | 3992172.76 | 3991076.95 | 0.1957% | 0.2231%
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1546 | Community and social services | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Other assets |  | KPA2 | All Wards | Upgrading of Phakamisa and Mount Coke sports fields | USDG | [8 empty] | 1000000 |  | 1000000 |  | 1000000 | 0 | 0 | 0 | 190000 |  | 190000 | 746098.5 | 0 | 746098.5 | -91626.13 |  | -91626.13 | 29500 |  | 29500 | 28980 | 0 | 28980 | -844472.37 | 0 | -844472.37 | 29400 |  | 29400 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 763760 | 87880 | 87880 |  | 912120 | 912120 | 8.788% | 8.788% | Refurbishment of fencing at Phakamisa has been completed on the 01/02/2015. Combination goalposts for Phakamisa and Mount Coke have been delivered but not yet installed. Contractor is on site at Phakamisa sports field Orders for the earthworks was received from Supply Chain Management for both Mount Coke and Phakamisa sports field.
Community Services | Sportsfields | 9.16 - Sportsfields | Amenities | 765010 | 4 | 36 | 1566 | Community and social services | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes | Other assets | Swimming Pool | KPA2 | All Wards | Upgrading of Waterworld | USDG | [9 empty] | 5000000 | 5000000 | -3000000 | 2000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Professional Service Provider that will be appointed for Human Settlement will be utilized. Cancellation of tender will be submitted to Supply Chain Management
Community Services |  | 4.4 - Asset Risk & Financial Services |  | 765010 | 5 | 05 | 1535 | Community and social services | Amenities | 5 | 05 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  |  | All Wards | Replacement of Desk & Microwave | Own Funds | [10 empty] | 13800 |  | 13800 | [20 empty] | 0 |  |  | 0 |  |  | 0 | [11 empty] | 0 |  | 13800 | 13800 | 0% | 0% | Procurement process underway.
Community Services |  | 9.16 - Sportsfields |  | 765010 | 6 | 36 | 1501 | Sport and recreation | Amenities |  |  |  | 05 | 07 | 01 | 01 | 160 | 002 | Renewal-160 |  | Yes |  |  |  |  | Completion of Upgrading of 2010 Stadium | DSRAC c/o | [9 empty] | 2686285 | 2686285 |  | 2686285 |  |  | 0 |  |  | 0 | 180000 |  | 180000 | 68800 |  | 68800 | 137600 |  | 137600 | 122500 |  | 122500 | 844472.37 |  | 844472.37 |  |  | 0 |  |  | 0 | [9 empty] | 23500 | 1353372.37 | 1353372.37 |  | 1332912.63 | 1332912.63 | 50.38% | 50.38% | Grass planting and construction of portable stands at Newlands Sport fields and Ndevana Sportfield have been completed. Rehabilitation of Guard House at Bhisho Stadium in progress.
Community Services |  | 9.16 - Sportsfields |  | 765010 | 6 | 01 | 1526 | Sport and recreation | Amenities |  |  |  | 05 | 07 | 01 | 01 | 160 | 002 | Renewal-160 |  | Yes |  |  |  |  | Upgrading of Resort and Purchase of Equipment | Own Funds c/o | [9 empty] | 384660 | 384660 |  | 384660 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 145655.79 |  | 145655.79 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 104617.23 | 145655.79 | 145655.79 |  | 239004.21 | 239004.21 | 37.87% | 37.87% | 5 Machines was received, 3 washing machines were installed on the 24/03/2015. Awaiting Service Provider to come and fix the electricity and to install 2 tumble dryers. Measurements for curtains were taken by a Service Provider in 20 chalets and awaiting delivery. curtains. Fencing of the river side is on hold, awaiting approval from DEDEAT for the erection of fence, also awaiting permit from Agriculture, Forestry & Fisheries for pruning of milk wood that is in the way where the fence is going to be erected.
Community Services | Swimming Pools | 9.17 - Swimming Pools |  | 765015 | 4 | 01 | 1547 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 160 | 001 | Renewal-160 |  | Yes |  |  | KPA2 |  | Refurbishment of Swimming Pools | Own Funds | [8 empty] | 2000000 |  | 2000000 |  | 2000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | Procurement process underway. Tender specification document for heating system at Joan Harrison Pool is at Bid Specification Committee Stage | 2500000 | 0
Community Services | Aquarium | 9.18 - Aquarium | Amenities | 765020 | 4 | 36 | 1547 | Sport and recreation | Amenities | 4 | 36 |  | 05 | 07 | 01 | 01 | 190 | 001 | Renewal-190 |  | Yes |  |  | KPA2 |  | Relocation of Aquarium | USDG | [8 empty] | 1000000 |  | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Procurement process underway. Specification for formal tender was presented on Bid Specification Committee and it was differed with minor amendments. Informal tender was utilized for remedial work- specification document was submitted to Architects Division for implementation. | 5000000 | 10000000
Community Services | Zoo | 9.19 - Zoo |  | 765025 | 4 | 01 | 1548 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 190 | 001 | Renewal-190 |  | Yes |  |  | KPA2 |  | Upgrading of Zoo Facilities | Own Funds | [8 empty] | 1000000 |  | 1000000 | -400000 | 600000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 4244.94 |  | 4244.94 | 201039.96 |  | 201039.96 |  |  | 0 |  |  | 0 |  |  | 0 | 109392.8 | 205284.9 | 205284.9 |  | 394715.1 | 394715.1 | 34.21% | 34.21% | Procurement process underway. Tender for construction of boundary wall closed on the 26/02/2015. informal tender specifications are being finalized for electrification of enclosures. Professonal Service Provider from Human Settlements maybe utilized. | 1500000 | 0
Community Services | Zoo | 9.16 - Sportsfields |  | 765025 | 4 | 01 | 1549 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 190 | 001 | Renewal-190 |  | Yes |  |  | KPA2 |  | FEL Zoo - Aquarium | Own Funds | [8 empty] | 238502 |  | 238502 |  | 238502 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 238502 | 238502 | 0% | 0% | Procurement process underway. Aquarium - Informal tender for Upgrade of Seabird Rehabilitation pool and Repairs to Penguin Enclosure Balustrade submitted to Supply Chain Management for re-advertisement.
Community Services | Beaches | 9.20 - Beaches |  | 765030 | 4 | 01 | 1550 | Sport and recreation | Amenities | 4 | 01 |  | 05 | 07 | 01 | 01 | 190 | 001 | Renewal-190 |  | Yes |  |  | KPA2 |  | Upgrading of Beaches Facilities | Own Funds | [8 empty] | 1000000 |  | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Procurement process underway | 1500000 | 0
Community Services | Cleansing Administration Support | 9.1 - Office of The Director of Community Services |  | 770005 | 4 | 01 | 1552 | Community and social services | Waste Management | 4 | 01 |  | 05 | 07 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Community |  | KPA2 |  | Office Furniture and Equipment (Solid Waste Management) | Own Funds | [8 empty] | 300000 |  | 300000 |  | 300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 4800 |  | 4800 |  |  | 0 |  |  | 0 |  |  | 0 | 111829.15 | 4800 | 4800 |  | 295200 | 295200 | 1.6% | 1.6% | Procurement process underway
Community Services | Cleansing Administration Support | 4.4 - Asset Risk & Financial Services |  | 770005 | 5 | 05 | 1510 | Budget and treasury | Amenities | 4 | 01 |  | 05 | 02 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds | [9 empty] | 1700000 | 1700000 |  | 1700000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1700000 |  | 1700000 |  |  | 0 |  |  | 0 | [10 empty] | 1700000 | 1700000 |  | 0 | 0 | 100% | 100% | Project complete
Community Services |  | 9.17 - Swimming Pools |  | 770005 | 6 | 01 | 1527 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 271 | 002 | New-260 | Yes | [5 empty] | Grass Cutting Equipment | Own Funds c/o | [9 empty] | 668126 | 668126 | 400000 | 1068126 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 128560 |  | 128560 | 16400 |  | 16400 | 15075.38 |  | 15075.38 |  |  | 0 | 2021.05 |  | 2021.05 | [9 empty] | 20729 | 162056.43 | 162056.43 |  | 906069.57 | 906069.57 | 15.17% | 15.17% | Procurement process underway . Project progressing well
Community Services |  | 9.23 - Refuse Removal |  | 770010 | 6 | 01 | 1533 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes |  | Community | Refuse | KPA2 | All Wards | Acquisition of Solid Waste Plant | Own Funds c/o | [9 empty] | 8804587 | 8804587 |  | 8804587 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 7190755.44 |  | 7190755.44 | 1580662.54 |  | 1580662.54 |  |  | 0 |  |  | 0 | [10 empty] | 8771417.98 | 8771417.98 |  | 33169.02 | 33169.02 | 99.62% | 99.62% | The project is progressing well
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1528 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Upgrade & Refurbishment Disposal Sites - Phase 2 - Design & Construction of 3rd and 4th Cell and Ancillary Works | Own Funds c/o | [9 empty] | 1774658 | 1774658 |  | 1774658 |  |  | 0 |  |  | 0 | 1488773.47 |  | 1488773.47 |  |  | 0 | 189188.75 |  | 189188.75 |  |  | 0 |  |  | 0 |  |  | 0 | 96600 |  | 96600 | [9 empty] | 0 | 1774562.22 | 1774562.22 |  | 95.78 | 95.78 | 99.99% | 99.99% | Phase 2 of the project complete
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1529 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Solid Waste Programme- Weigh Bridge KWT | Own Funds c/o | [9 empty] | 2000000 | 2000000 |  | 2000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 6140.35 |  | 6140.35 | [9 empty] | 0 | 6140.35 | 6140.35 |  | 1993859.65 | 1993859.65 | 0.307% | 0.307% | Project progressing well
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1530 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Waste Management Programme - Plant and Equipment | Own Funds c/o | [9 empty] | 1268845 | 1268845 |  | 1268845 |  |  | 0 |  |  | 0 |  |  | 0 | 3201.75 |  | 3201.75 | 1258179 |  | 1258179 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 1261380.75 | 1261380.75 |  | 7464.25 | 7464.25 | 99.41% | 99.41% | Project complete
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1531 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Counterfunding - Leiden Twinning - Solid Waste Drop-Off Points | Own Funds c/o | [9 empty] | 967405 | 967405 |  | 967405 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 |  | 967405 | 967405 | 0% | 0% | Awaiting delivery from the service provider
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 6 | 01 | 1532 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 002 | New-100 | Yes | [5 empty] | Specialised Solid Waste Vehicles | Own Funds c/o | [9 empty] | 4000000 | 4000000 |  | 4000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3595377.72 |  | 3595377.72 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 | 3595377.72 | 3595377.72 |  | 404622.28 | 404622.28 | 89.88% | 89.88% | Awaiting delivery of outstanding machinery
Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 9.27 - E.L Regional Waste Disposal Site & Transfer Station | Waste Management | 770030 | 4 | 36 | 1548 | Waste Management | Waste Management | 4 | 36 |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes |  | Community | Refuse | KPA2 | Will provide ward no, as soon as land is availed/identified | Construction of Transfer Stations - 3 x Sites | USDG | 0 |  | 0 |  | 0 |  | 0 |  | 5000000 |  | 5000000 | -5000000 | 0 | 0 | 0 | 0 | 3976.02 | 556.64 | 4532.66 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 3976.02 | 4532.66 |  | -3976.02 | -4532.66 | #DIV/0! | #DIV/0! | Procurement process underway | 5000000 | 5000000 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0%
Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 9.27 - E.L Regional Waste Disposal Site & Transfer Station | Waste Management | 770030 | 4 | 36 | 1549 | Waste Management | Waste Management | 4 | 36 |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes |  |  |  | KPA2 |  | KWT Tanery Site | USDG | [8 empty] | 1000000 |  | 1000000 |  | 1000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 1000000 | 1000000 | 0% | 0% | Procurement process underway | 1000000 | 1000000
Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 9.27 - E.L Regional Waste Disposal Site & Transfer Station | Waste Management | 770030 | 4 | 36 | 1550 | Waste Management | Waste Management | 4 | 36 |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes |  | Community | Refuse | KPA2 | 25 | Construction and Rehabilitation of Waste Cells | USDG | 0 |  | 0 |  | 0 |  | 0 |  | 20000000 |  | 20000000 | -10000000 | 10000000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 10000000 | 10000000 | 0% | 0% | Procurement process underway | 20710100 | 14412415 |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0% | 0%
Community Services |  | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 4 | 01 | 1560 | Waste Management | Waste Management |  |  |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes | [5 empty] | Solid Waste Mechanical Plant and Vehicles | Own Funds | [9 empty] | 40000000 | 40000000 |  | 40000000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1804757.34 |  | 1804757.34 | 7697190 |  | 7697190 |  |  | 0 |  |  | 0 | [9 empty] | 9334705.04 | 9501947.34 | 9501947.34 |  | 30498052.66 | 30498052.66 | 23.75% | 23.75% | 8 Compactor Trucks and 2 x TLB's have been delivered
Community Services | E.L.Regional Waste Disposal Site & Transfer Station | 9.27 - E.L Regional Waste Disposal Site & Transfer Station |  | 770030 | 4 | 01 | 1551 | Waste Management | Waste Management | 4 | 01 |  | 05 | 07 | 01 | 01 | 100 | 001 | New-100 | Yes |  | Community |  | KPA2 |  | 17800 X240 Litre Wheelie Bins | Own Funds |  |  | 0 | 51990000 | 14240000 |  | 14240000 |  | 10000000 |  | 10000000 |  | 10000000 | 0 | 0 | 0 | 641246.4 |  | 641246.4 | 961869.6 |  | 961869.6 | 2235456.2 |  | 2235456.2 |  |  | 0 | 3411868.2 |  | 3411868.2 | 630903.2 |  | 630903.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 7881343.6 | 7881343.6 |  | 2118656.4 | 2118656.4 | 78.81% | 78.81% | Project complete. balance of funding will be utlized for purchasing of street litter bins | 10000000 | 10000000 | [19 empty] | 0 | [13 empty] | 0 | 0 |  | 14240000 | 14240000 | 0% | 0%
[26 empty] | TOTAL : COMMUNITY SERVICES |  | 39040943 | 0 | 39040943 | 46790000 | 48080943 | -8384413 | 39696530 | 0 | 86530409 | 77334390 | 164650862 | -31735332 | 132915530 | 0 | 0 | 0 | 882714.55 | 5819.54 | 888534.09 | 3513945.48 | 17293.99 | 3531239.47 | 3565542.21 | 136923.61 | 3702465.82 | 2583316.94 | 61395.95 | 2644712.89 | 17637410.81 | 116713.01 | 17754123.82 | 12869974.97 | 137275.14 | 13007250.11 | 636235.09 | 74633.2 | 710868.29 | 3825578.82 | 341717.52 | 4167296.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20852897.05 | 45514718.87 | 46406490.83 | 4691938 | 87400811.13 | 86509039.17 | 34.24% | 34.91% |  | 74460100 | 67662415 | 0 | 0 | 0 | 0 | 214984.38 | 220957.92 | 1079467.68 | 75640.29 | 1155107.97 | 1294452.06 | 1376065.89 | 956481.57 | 96061.39 | 1052542.96 | 1825926.86 | 212831.87 | 2038758.73 | 4462206.87 | 449647.12 | 4911853.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6556720.88 | 8539067.36 | 9379221.57 | 0 | 39541875.64 | 38701721.43 | 17.76% | 19.51%
0
[26 empty] | TOTAL : CAPITAL PROJECTS - ALL DIRECTORATES | [9 empty] | 932007423 | 120419027 | 1051131063 | 112327298 | 1163458361 | 4279296.15 | 305995.65 | 4585291.8 | 36998451.88 | 3733785.71 | 40732237.59 | 63771348.91 | 5239427.37 | 69010776.28 | 82385306.63 | 6648328.33 | 89033634.96 | 52978431.48 | 5551241.11 | 58529672.59 | 123416513.71 | 12467760.79 | 135884274.5 | 30396944.51 | 1286844.48 | 31683788.99 | 47087499.42 | 5363753.96 | 52451253.38 | 104078327.73 | 8714407.92 | 112792735.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139403947.18 | 545392120.42 | 594703665.74 | 4812829.21 | 618066240.58 | 568754695.26 | 46.88% | 51.12%
Asset Replacement |  | 4.4 - Asset Risk & Financial Services |  | 320005 | 5 | 05 | 1501 | Budget and treasury | Support Services | 4 | 01 |  | 05 | 03 | 01 | 01 | 270 | 001 | New-270 | Yes |  | Other assets |  | KPA4 | All Wards | Asset Replacements - Insurance | Own Funds |  |  |  |  | 0 |  | 0 |  | 10000000 |  | 5353643 |  | 5286643 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 5286643 | 5286643 | 0% | 0% | This is to be used to replace assets iro insurance claims. | 10000000 | 10000000
0
[26 empty] | TOTAL : BCMM CAPITAL BUDGET |  | #REF! | #REF! | #REF! | #REF! | #REF! | 12199892 | #REF! | 2000000 | 942007423 | 120419027 | 1056484706 | 112327298 | 1168745004 | 4279296.15 | 305995.65 | 4585291.8 | 36998451.88 | 3733785.71 | 40732237.59 | 63771348.91 | 5239427.37 | 69010776.28 | 82385306.63 | 6648328.33 | 89033634.96 | 52978431.48 | 5551241.11 | 58529672.59 | 123416513.71 | 12467760.79 | 135884274.5 | 30396944.51 | 1286844.48 | 31683788.99 | 47087499.42 | 5363753.96 | 52451253.38 | 104078327.73 | 8714407.92 | 112792735.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139403947.18 | 545392120.42 | 594703665.74 | 4812829.21 | 623352883.58 | 574041338.26 | 46.66% | 50.88% |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
91458961
106541039
[26 empty] | Projects Deleted from the list |  | #REF!
Directorate of Development Planning |  |  |  | 620005 | [14 empty] | Renewal-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks |  |  | Public Transport Facilities | PTISG |  |  |  |  | 0 |  | 0 |  | 0 | [49 empty] | 0 | 50000000 | [42 empty] | 50000000
Directorate of Development Planning |  |  |  | 615095 | [14 empty] | Renewal-312 |  |  | Other | Car Parks,Bus termonals & Taxi ranks |  |  | Replacement of Lift Shoprite Building | Own Funds |  |  |  |  | 0 |  | 0 |  | 0 | [49 empty] | 0 | 3500000
[36 empty] | 0 | [49 empty] | 0 | 3500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Oxford Street Mall (Pedestrianisation/Public Transport Zone) | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [49 empty] | 0 | 6000000 | [42 empty] | 6000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Northwest Expressway widening and extension to Amalinda Main Road | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [49 empty] | 0 | 5000000 | [42 empty] | 5000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Fitzpatrick Road/Currie Street Link Road (Sleeper Site) | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [49 empty] | 0 | 4000000 | [42 empty] | 4000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Non-Motorised Transport Facilities Implementation | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [49 empty] | 0 | 5000000 | [42 empty] | 5000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Traffic congestion improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [49 empty] | 0 | 2000000 | [42 empty] | 2000000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Bonza Bay Road LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [49 empty] | 0 | 1500000 | [42 empty] | 1500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Vincent and Berea LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [49 empty] | 0 | 1500000 | [42 empty] | 1500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | KWT LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [49 empty] | 0 | 1500000 | [42 empty] | 1500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Mdantsane LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [49 empty] | 0 | 1500000 | [42 empty] | 1500000
Directorate of Development Planning |  |  |  | 620005 |  |  |  | Planning and Development | Planning and development | [7 empty] | 050 |  | New-50 |  |  | Other | Car Parks,Bus termonals & Taxi ranks | KPA2 |  | Bhisho LSDF traffic improvements | USDG |  |  |  |  | 0 |  | 0 |  | 0 | [49 empty] | 0 | 1500000 | [42 empty] | 1500000
[36 empty] | 86530409 | [49 empty] | 75960100
[36 empty] | 86530409 | [49 empty] | 75960100
[36 empty] | 0 | [49 empty] | 0
[38 empty] | 507185871 | [8 empty] | 549298835
[38 empty] | 507135271 | [8 empty] | 549349435
[38 empty] | 50600 | [8 empty] | -50600
0
17000000

## Summaries
2014/2015 - 2016/2017 CAPITAL BUDGET PER FUNDING SOURCE
| M |  |  | AE | AF |  | AH | [33 empty] | AI | Aj |  | Aj
Funding | 2013/2014 Approved Budget | 2013/2014 Rollover Adjustment Budget | 2013/2014 Conditional Grants Rollover Adjustment Budget | Mid-Year Adjustments | 2013/2014 Mid-Year Adjusted Budget | 2014/2015 DoRA | 2014/2015 Approved Capital Budget | 2014/2015 Rollover Adjustment Budget | 2014/2015 Mid year Adjustment Budget | July 2014 | July 2014 (VAT incl) | August 2014 | August 2014 (VAT incl) | September 2014 | September 2014 (VAT incl) | October 2014 | October 2014 (VAT incl) | November 2014 | November 2014 (VAT incl) | December 2014 | December 2014 (VAT incl) | January 2015 | January 2015 (VAT incl) | February 2015 | February 2015 (VAT incl) | March 2015 | March 2015 (VAT incl) | April 2015 | April 2015 (VAT incl) | May 2015 | May 2015 (VAT incl) | June 2015 | June 2015 (VAT incl) | YTD Expenditure | YTD Expenditure (VAT) incl) | Commitments as per Venus | Variance | Variance ( VAT incl) | % Expenditure | % Expenditure (VAT incl) | 2015/2016 Draft Capital Budget | 2016/2017 Draft Capital Budget | NT | DoRA
Own Funds | 21878631.88 | 21878631.88 | 21878631.88 | 30084305 | 51962936.88 |  | 241225697 | 276725697 | 393242409 | 20176.95 | 20176.95 | 5426887.92 | 5426887.92 | 16172829.34 | 16172829.34 | 16338247.16 | 16338247.16 | 6066404.97 | 6066404.97 | 19653365.76 | 19653365.76 | 9400268.42 | 9400268.42 | 6861460.05 | 6861460.05 | 26501083.31 | 26501083.31 | [6 empty] | 106440723.88 | 106440723.88 | 49794207.19 | 286801685.12 | 286801685.12 | 27.07% | 27.07% | 256870661 | 270555051 | Own funds |  |  | 286801685.12 | 255845288 | 261320661 | 276905051
Own Funds c/o | [6 empty] | 0 | 55139872 | 54643881 |  |  | 0 | 0 | 4223929.01 | 4223929.01 | 669236.82 | 669236.82 | 4049040.55 | 4049040.55 | 11335930.78 | 11335930.78 | 6602182.29 | 6602182.29 | 732067.93 | 732067.93 | 3546781.07 | 3546781.07 | [6 empty] | 31159168.45 | 31159168.45 | 2566652.65 | 23484712.55 | 23484712.55 | 57.02% | 57.02% | [5 empty] | 23484712.55
Total Own Funding |  |  | 21878631.88 | 30084305 | 51962936.88 | 0 | 241225697 | 331865569 | 447886290 | 20176.95 | 20176.95 | 5426887.92 | 5426887.92 | 20396758.35 | 20396758.35 | 17007483.98 | 17007483.98 | 10115445.52 | 10115445.52 | 30989296.54 | 30989296.54 | 16002450.71 | 16002450.71 | 7593527.98 | 7593527.98 | 30047864.38 | 30047864.38 | 0 | 0 | 0 | 0 | 0 | 0 | 137599892.33 | 137599892.33 | 52360859.84 | 310286397.67 | 310286397.67 | 30.72% | 30.72% | 256870661 | 270555051 |  |  |  | 310286397.67 | -14619591 | -4450000 | -6350000
DoE(Intergrated National Electrification Programme) | 0 | 0 | 0 | 0 | 0 |  | 27000000 | 27000000 | 20587000 | 34346 | 34346 | 128806.07 | 128806.07 | 2895383.81 | 3318770.39 | 9399037.37 | 10101331.63 | 2741800.57 | 3739223.63 | 6615.16 | 7541.28 | 49043.73 | 55909.85 | 3425392.02 | 3904946.9 | 586958.94 | 664758.14 | [6 empty] | 19267383.67 | 21955633.89 | 40392.57 | 1319616.33 | -1368633.89 | 93.59% | 106.6% | 27000000 | 12000000 | N |  |  | -1368633.89
Department of Sports, Recreation, Arts and Culture c/o | [7 empty] | 2686285 | 2686285 |  |  | 0 | 0 | 180000 | 180000 | 68800 | 68800 | 137600 | 137600 | 122500 | 122500 | 844472.37 | 844472.37 | 0 | 0 | 0 | 0 | [6 empty] | 1353372.37 | 1353372.37 | 23500 | 1332912.63 | 1332912.63 | 50.38% | 50.38% |  |  | P |  |  | 1332912.63
Department of Economic Affairs and Tourism | [8 empty] | 199168 | [14 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 |  | 199168 | 199168 | 0% | 0% | [5 empty] | 199168
Local Government, Traditional Affairs and Housing | [6 empty] | 188726 | 188726 | 188726 | 0 | 0 | 0 | 0 | 178585.49 | 178585.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 178585.49 | 178585.49 | 0 | 10140.51 | 10140.51 | 94.63% | 94.63% | 0 | 0 | P |  |  | 10140.51
Infrastructure Skills Development Grant | 100000 | 100000 | 100000 | 0 | 100000 |  | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 100000 | 100000 | 0% | 0% | 100000 | 0 | N |  |  | 100000
BCMET c/o | [7 empty] | 256818 | 256818 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 122174.32 | 122174.32 | -122174.32 | -122174.32 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 256818 | 256818 | 0% | 0% | [5 empty] | 256818
Leiden c/o | [6 empty] | 0 | 458860 | 458860 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 458860 | 458860 | 0% | 0% | [5 empty] | 458860
Neigbourhood Development Partnership Grant | 10000000 | 10000000 | 10000000 | -10000000 | 0 |  | 5000000 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 107792 | 107792 | 2583366.68 | 2960128.89 | 0 | 0 | 0 | 0 | 154576.68 | 176217.41 | 1439984.69 | 1562472.27 | 25842.68 | 108570.93 | [6 empty] | 4311562.73 | 4915181.5 | 572888.26 | 688437.27 | 84818.5 | 86.23% | 98.3% | 16878000 | 17744000 | N |  |  | 84818.5
Urban Settlement Development Grant | 238119983 | 238119983 | 238119983 | -7384413 | 230735570 |  | 639824500 | 639824500 | 639024500 | 1979773.14 | 2285768.79 | 28086910.53 | 31820696.24 | 37979284.1 | 42795324.89 | 43344629.73 | 48913901.59 | 29320100.24 | 33873918.29 | 91908294.19 | 104375128.86 | 11151171.27 | 12409508.9 | 34628594.73 | 39390306.23 | 61992436.81 | 70546317.28 | [6 empty] | 340391194.74 | 386410871.07 | 84827860.61 | 298633305.26 | 252613628.93 | 53.27% | 60.47% | 1021810100 | 1025627100 | N |  | #REF! | 252613628.93 | 33464500 | 37147900 | 38147900 | OPEX
Human Settlement Development Grant | 23924600 | 23924600 | 23924600 | -500000 | 23424600 |  | 18600000 | 18600000 | 31495081 | 2245000.06 | 2245000.06 | 3355847.36 | 3355847.36 | 2012123.67 | 2012123.67 | 3349250.38 | 3349250.38 | -4555.42 | -4555.42 | 377191.88 | 377191.88 | 1968625.75 | 1968625.75 | 0 | 0 | 11706833.15 | 11706833.15 | [6 empty] | 25010316.83 | 25010316.83 | 0 | 6484764.17 | 6484764.17 | 79.41% | 79.41% | 44900000 | 59300000 | P |  |  | 6484764.17
Human Settlement Development Grant c/o | [6 empty] | 0 | 20435448 | 20162276 |  |  | 0 | 0 | 21421.49 | 21421.49 | 6632738.49 | 6632738.49 | 10545866.25 | 10545866.25 | 134790.26 | 134790.26 | 226604 | 226604 | 0 | 0 | -946908.23 | -946908.23 | [6 empty] | 16614512.26 | 16614512.26 | 0 | 3547763.74 | 3547763.74 | 82.4% | 82.4% |  |  | P |  |  | 3547763.74
Human Settlement Development Grant-MPCC | 0 | 0 | 0 | 0 | 0 |  | 10068500 | 10068500 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 665300 | 665300 | [6 empty] | 665300 | 665300 | 1578445.9 | 34700 | 34700 | 95.04% | 95.04% | 13068500 | 0 | P |  |  | 34700
Total Grants | 272144583 | 272144583 | 272144583 | -17884413 | 254260170 | 0 | 700781726 | 724619137 | 720858714 | 4259119.2 | 4565114.85 | 31571563.96 | 35305349.67 | 43374590.56 | 48614017.93 | 65377822.65 | 72026150.98 | 42862985.96 | 48414227.07 | 92427217.17 | 104894977.96 | 14394493.8 | 15681338.28 | 39493971.44 | 44857725.4 | 74030463.35 | 82744871.27 | 0 | 0 | 0 | 0 | 0 | 0 | 407792228.09 | 457103773.41 | 87043087.34 | 313066485.91 | 263754940.59 | 56.57% | 63.41% | 1123756600 | 1114671100 |  |  |  | 263754940.59
0
TOTAL PER FUNDING | 272144583 | 272144583 | 294023214.88 | 12199892 | 306223106.88 | 0 | 942007423 | 1056484706 | 1168745004 | 4279296.15 | 4585291.8 | 36998451.88 | 40732237.59 | 63771348.91 | 69010776.28 | 82385306.63 | 89033634.96 | 52978431.48 | 58529672.59 | 123416513.71 | 135884274.5 | 30396944.51 | 31683788.99 | 47087499.42 | 52451253.38 | 104078327.73 | 112792735.65 | 0 | 0 | 0 | 0 | 0 | 0 | 545392120.42 | 594703665.74 | 139403947.18 | 623352883.58 | 574041338.26 | 46.66% | 50.88% | 1380627261 | 1385226151 | 0 | 0 | 0 | 574041338.26 | 673289000 | 1058958000 | 1063775000
0
1168745004
C5C | 2013/2014 Approved Budget | 2013/2014 Rollover Adjustment Budget | 2013/2014 Conditional Grants Rollover Adjustment Budget | Mid-Year Adjustments | 2013/2014 Mid-Year Adjusted Budget | 2014/2015 DoRA | 2014/2015 Approved Capital Budget | 2014/2015 Rollover Adjustment Budget | 2014/2015 Mid-Year Adjustment Budget | July 2014 | July 2014 (VAT incl) | August 2014 | August 2014 (VAT incl) | September 2014 | September 2014 (VAT incl) | October 2014 | October 2014 (VAT incl) | November 2014 | November 2014 (VAT incl) | December 2014 | December 2014 (VAT incl) | January 2015 | January 2015 (VAT incl) | February 2015 | February 2015 (VAT incl) | March 2015 | March 2015 (VAT incl) | April 2015 | April 2015 (VAT incl) | May 2015 | May 2015 (VAT incl) | June 2015 | June 2015 (VAT incl) | YTD Expenditure | YTD Expenditure (VAT) incl) | Commitments as per Venus | Variance | Variance ( VAT incl) | % Expenditure | % Expenditure (VAT incl)
1.1 - Office of The Director of Executive Support | 0 | 12750000 | 12750000 | -10000000 | 2750000 |  | 500000 | 6270397 | 6270397 | 0 | 0 | 0 | 0 | 0 | 0 | 279834.11 | 279834.11 | 0 | 0 | 0 | 0 | 3699 | 3699 | 0 | 0 | 619535.75 | 619535.75 | [6 empty] | 903068.86 | 903068.86 | 786473.31 | 5367328.14 | 5367328.14 | 14.4% | 14.4%
1.11 - Development Co-Operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458860 | 458860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 458860 | 458860 | 0% | 0%
1.2 - Executive Mayor, Speaker & Mayoral Committee | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
1.8 - City Hall | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2.1 - Office of The Municipal Manager & Support Services | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 7000000 | 7000000 | 6500000 | 0 | 0 | 170805 | 194717.7 | 107792 | 107792 | 2712625.98 | 3089388.19 | 0 | 0 | 15594.59 | 15594.59 | 173739.08 | 197407.53 | 1448874.69 | 1572606.87 | 62108.78 | 146736.28 | [6 empty] | 4691540.12 | 5324243.16 | 597990.61 | 1808459.88 | 1175756.84 | 72.18% | 81.91%
3.1 - Mdantsane Urban Renewal Unit | [6 empty] | 10068500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
3.2 - Office of The Chief Operations Officer | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 0 | 0 | 14706.1 | 14706.1 | 0 | 0 | 45043.26 | 45043.26 | 0 | 0 | 14084.26 | 14084.26 | 0 | 0 | 0 | 0 | 34330.97 | 34330.97 | [6 empty] | 108164.59 | 108164.59 | 39871.73 | 391835.41 | 391835.41 | 21.63% | 21.63%
3.3 - Housing Department | 0 | 0 | 0 | 0 | 0 |  | 79567608 | 100305255 | 155685230 | 4419423.27 | 4723842.52 | 7514624.7 | 8063055.47 | 9250670.49 | 10022887.2 | 14732515.11 | 15423708.66 | 11308976.93 | 11416450.18 | 12293497.37 | 13927792.57 | 3960720.45 | 4183172.18 | 12649598.93 | 14420542.79 | 25968245.31 | 27914139.23 | [6 empty] | 102098272.56 | 110095590.8 | 5002831.68 | 53586957.44 | 45589639.2 | 65.58% | 70.72%
4.1 - Office of The Director of Finance | [6 empty] | 500000 | 931902 | 931902 | 19074.32 | 19074.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117610.12 | 117610.12 | 48961.96 | 48961.96 | [6 empty] | 185646.4 | 185646.4 | 81941.91 | 746255.6 | 746255.6 | 19.92% | 19.92%
4.4 - Asset Risk & Financial Services | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 10000000 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 13675.44 | 13675.44 | 17870 | 17870 | 56239.1 | 56239.1 | 91343.02 | 91343.02 | 1719575.96 | 1719575.96 | 134404.95 | 134404.95 | 35230.72 | 35230.72 | [6 empty] | 2068339.19 | 2068339.19 | 49124.18 | 7931660.81 | 7931660.81 | 20.68% | 20.68%
4.3 - Budget Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
4.7 - Salary Office | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
4.9 - Consolidated Billing & Miscellaneous Revenue Office | [6 empty] | 350000 | 350000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218597.94 | 218597.94 | 2511.2 | 2511.2 | [6 empty] | 221109.14 | 221109.14 | 932.88 | 128890.86 | 128890.86 | 63.17% | 63.17%
4.10 - Debtors Management Office | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
4.11 - Customer Care Office | [6 empty] | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
5.1 - Office of The Director of Corporate Services | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13230 | 13230 | 0 | 0 | [6 empty] | 13230 | 13230 | 0 | 486770 | 486770 | 2.646% | 2.646%
5.4 - Auxilliary & Telecommunication Support | [6 empty] | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 150000 | 150000 | 0% | 0%
5.6 - Management Information Services | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 18016133 | 18016133 | 0 | 0 | 0 | 0 | 587015.67 | 587015.67 | 353865.69 | 353865.69 | 2000112.65 | 2000112.65 | 282764.22 | 282764.22 | 114824.56 | 114824.56 | 107671.11 | 107671.11 | 319000.79 | 319000.79 | [6 empty] | 3765254.69 | 3765254.69 | 337659.63 | 14250878.31 | 14250878.31 | 20.9% | 20.9%
5.7 - H.R. Administration | 0 | 0 | 0 | 0 | 0 |  | 2100000 | 2100000 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 111037.37 | 2100000 | 2100000 | 0% | 0%
5.8 - Occupational Risk Management | [6 empty] | 2500000 | 2500000 | 2320000 | 0 | 0 | 0 | 0 | 2761.12 | 2761.12 | 0 | 0 | 0 | 0 | 5881.04 | 5881.04 | 0 | 0 | 0 | 0 | 40680.72 | 40680.72 | [6 empty] | 49322.88 | 49322.88 | 1993355.28 | 2270677.12 | 2270677.12 | 2.126% | 2.126%
5.9 - Labour Relations | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
5.10 - Organisational Development | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
6.1 - Office of The Director of Engineering Services | [6 empty] | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133843.34 | 133843.34 | 61515.61 | 61515.61 | [6 empty] | 195358.95 | 195358.95 | 55226.68 | 304641.05 | 304641.05 | 39.07% | 39.07%
6.9 - Sewerage Admin | 0 | 0 | 0 | 0 | 0 | 0 | 216507892 | 220415300 | 201656160 | -199830.91 | -199830.91 | 10076331.12 | 11392071.7 | 7571347.35 | 9263739.91 | 7829714.12 | 8877686.14 | 6523226.26 | 7436477.93 | 21636248.23 | 24581206.88 | 2178097.85 | 2453724.5 | 4641349.1 | 5252572.48 | 12687855.51 | 14164265.55 | [6 empty] | 72944338.63 | 83221914.18 | 22018680.15 | 128711821.37 | 118434245.82 | 36.17% | 41.27%
6.20 - Water Administration | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 97688726 | 95355831 | 94114971 | 0 | 0 | 1847692.21 | 2052472.42 | 2223512.66 | 2348646.58 | 2998073.18 | 3218272.85 | 5638393.1 | 6167568.1 | 4803675.23 | 5115693.09 | 3425995.81 | 3548005.38 | 5129081.8 | 5497058.17 | 11851676.19 | 12816678.06 | [6 empty] | 37918100.18 | 40764394.65 | 38300569.78 | 56196870.82 | 53350576.35 | 40.29% | 43.31%
6.25 - Water Treatment Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
6.34 - Roads Administration | [6 empty] | 198000000 | 198000000 | 327199000 | -47814.16 | -47814.16 | 9974048.56 | 11314616.13 | 19383637.41 | 21311489.23 | 24278224.45 | 27513048.86 | 16280303.27 | 18883691.01 | 51599138.66 | 58698371.46 | 5053867.15 | 5521825.76 | 10116370.33 | 11510801.73 | 20386656.53 | 22686461.02 | [6 empty] | 157024432.2 | 177392491.04 | 29703088.03 | 170174567.8 | 149806508.96 | 47.99% | 54.22%
6.36 - Roads and Stormwater Drainage | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
6.43 - Fleet Management - Braelyn | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 18300000 | 25297668 | 25297668 | 0 | 0 | 1888532.64 | 1888532.64 | 10484165.53 | 10484165.53 | 4549898.98 | 4549898.98 | 0 | 0 | 0 | 0 | 5284589.16 | 5284589.16 | 0 | 0 | 2562672.99 | 2562672.99 | [6 empty] | 24769859.3 | 24769859.3 | 0 | 527808.7 | 527808.7 | 97.91% | 97.91%
6.46 - Electricity Planning & Design | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 134699000 | 134699000 | 119458000 | 34346 | 34346 | 966172.74 | 984607.28 | 8548369.41 | 9024179.81 | 19438470.71 | 20377347.17 | 5787043.67 | 6863002.8 | 13173409.92 | 13426732.29 | -4615356.74 | -4605126.39 | 8275075.35 | 8952694.13 | 18876411.96 | 19467944.73 | [6 empty] | 70483943.02 | 74525727.82 | 3826026.45 | 48974056.98 | 44932272.18 | 59% | 62.39%
7.1 - Office of The Director of Planning & Economic Dev. | [6 empty] | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 5100 | 5100 | 2418 | 2418 | 5806 | 5806 | 0 | 0 | 31582.91 | 31582.91 | 15083.4 | 15083.4 | [6 empty] | 59990.31 | 59990.31 | 170533.45 | 440009.69 | 440009.69 | 12% | 12%
7.11 - City Planning | [6 empty] | 0 | 5395309 | 5395309 | 0 | 0 | 0 | 0 | 1609065.89 | 1609065.89 | 478955.34 | 478955.34 | 571594.05 | 571594.05 | 128320.44 | 128320.44 | 591344.94 | 591344.94 | 515299.66 | 515299.66 | 1321.4 | 1321.4 | [6 empty] | 3895901.72 | 3895901.72 | 969709.32 | 1499407.28 | 1499407.28 | 72.21% | 72.21%
7.12 - Architecture | 0 | 0 | 0 | 0 | 0 |  | 5000000 | 5477792 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 797099.25 | 550000 | 550000 | 0% | 0%
7.13 - Land Administration | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 5500000 | 5500000 | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2727909.65 | 3109663 | [6 empty] | 2727909.65 | 3109663 | 0 | 2772090.35 | 2390337 | 49.6% | 56.54%
7.16 - Building Maintenance - Coastal / Central | [6 empty] | 9895288 | 5395288 | 891000 | 0 | 0 | 1146359.07 | 1146359.07 | -1146359.07 | -1146359.07 | 0 | 0 | 0 | 0 | 0 | 0 | 14700 | 14700 | 0 | 0 | 0 | 0 | [6 empty] | 14700 | 14700 | 592830 | 876300 | 876300 | 1.65% | 1.65%
7.30 - Transport Planning & Operations Admin | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 24000000 | 24256818 | 28706818 | 52995 | 54571.4 | 1754959.43 | 2031059.23 | 1633771.02 | 1862498.99 | 922399.1 | 923975.5 | 2001123.46 | 2261721.83 | 1297369.03 | 1404589.93 | 1270856.32 | 1298480.3 | 2797646.38 | 3140841.17 | 2756974.96 | 3231006.05 | [6 empty] | 14488094.7 | 16208744.4 | 5721042.87 | 14218723.3 | 12498073.6 | 50.47% | 56.46%
7.35 - Local Economic Development | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1126995.51 | 1280630.88 | [6 empty] | 1126995.51 | 1280630.88 | 2142403.58 | 8873004.49 | 8719369.12 | 11.27% | 12.81%
7.36 - Market | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
8.1 - Office of The Director of Health & Public Safety | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63999 | 63999 | 4560 | 4560 | 50316 | 50316 | 75224.75 | 75224.75 | 0 | 0 | [6 empty] | 194099.75 | 194099.75 | 36392.31 | 305900.25 | 305900.25 | 38.82% | 38.82%
8.3 - Health Administration | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
8.4 - Health Support | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 0 | 216000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
8.12 - Public Safety Administration | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
8.13 - Fire and Rescue Services | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 4000000 | 4965909 | 5765909 | 0 | 0 | 0 | 0 | 79776.8 | 79776.8 | 0 | 0 | 0 | 0 | 80000.01 | 80000.01 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 159776.81 | 159776.81 | 3110725.68 | 5606132.19 | 5606132.19 | 2.771% | 2.771%
8.14 - Security Services | 0 | 0 | 0 | 0 | 0 | 0 | 2100000 | 3336101 | 5236101 | 0 | 0 | 761505.76 | 761505.76 | -444544.6 | -444544.6 | 177174.39 | 177174.39 | 117018.27 | 117018.27 | 238497.16 | 238497.16 | -169380.44 | -169380.44 | 45802.97 | 45802.97 | 63056.5 | 63056.5 | [6 empty] | 789130.01 | 789130.01 | 0 | 4446970.99 | 4446970.99 | 15.07% | 15.07%
8.15 - Traffic Administration | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
8.16 - Traffic Control | [6 empty] | 3200000 | 3200000 | 2369735 | 1102.63 | 1102.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22837.5 | 22837.5 | [6 empty] | 23940.13 | 23940.13 | 2069735 | 2345794.87 | 2345794.87 | 1.01% | 1.01%
8.18 - Vehicle Test Station / Examination | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 0 | 798970 | 998970 | 0 | 0 | 0 | 0 | 366421.75 | 366421.75 | 0 | 0 | 44666.78 | 44666.78 | 110254.72 | 110254.72 | 169380.44 | 169380.44 | 0 | 0 | 0 | 0 | [6 empty] | 690723.69 | 690723.69 | 43760.8 | 308246.31 | 308246.31 | 69.14% | 69.14%
8.23 - Disaster Management | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
9.1 - Office of The Director of Community Services | [6 empty] | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24411.1 | 24411.1 | 0 | 0 | 25867.08 | 25867.08 | 27800 | 27800 | 44845.5 | 44845.5 | [6 empty] | 122923.68 | 122923.68 | 187372.71 | 377076.32 | 377076.32 | 24.58% | 24.58%
9.2 - Cleansing Administration Support | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
9.4 - Environmental Services | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 2000000 | 2000000 | 3685051 | 0 | 0 | 0 | 0 | 0 | 0 | 4196.91 | 4196.91 | 0 | 0 | 0 | 0 | 179759.6 | 204925.94 | 0 | 0 | 0 | 0 | [6 empty] | 183956.51 | 209122.85 | 1220944.15 | 3501094.49 | 3475928.15 | 4.992% | 5.675%
9.7 - Interments | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 10000000 | 11700000 | 11700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284773.45 | 324641.73 | 1140075.38 | 1255295.09 | 800777.17 | 912885.97 | -317077.49 | -317077.49 | 1180350.88 | 1345600 | [6 empty] | 3088899.39 | 3521345.3 | 3666287.66 | 8611100.61 | 8178654.7 | 26.4% | 30.1%
9.14 - Halls | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 21307198 | 12037866 | 0 | 0 | 47492.13 | 52755.03 | 121503.65 | 138514.16 | 0 | 0 | 502484.64 | 524012.31 | 149702.4 | 151195.7 | 0 | 0 | 533094.28 | 607727.48 | 2010391.76 | 2186199.81 | [6 empty] | 3364668.86 | 3660404.49 | 4498337.64 | 8673197.14 | 8377461.51 | 27.95% | 30.41%
9.16 - Sportsfields | 0 | 0 | 0 | 0 | 0 |  | 23030409 | 26101354 | 16916303 | 0 | 0 | 190000 | 190000 | 928123.32 | 928406.8 | 1322687.35 | 1459610.96 | 195720 | 195720 | 327133.33 | 327133.33 | 239740 | 239740 | 388173.36 | 388173.36 | 265364.32 | 266024.67 | [6 empty] | 3856941.68 | 3994809.12 | 1807136.25 | 13059361.32 | 12921493.88 | 22.8% | 23.62%
9.17 - Swimming Pools | [6 empty] | 2000000 | 2668126 | 3068126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128560 | 128560 | 16400 | 16400 | 15075.38 | 15075.38 | 0 | 0 | 2021.05 | 2021.05 | [6 empty] | 162056.43 | 162056.43 | 20729 | 2906069.57 | 2906069.57 | 5.282% | 5.282%
9.18 - Aquarium | [6 empty] | 1000000 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 1000000 | 1000000 | 0% | 0%
9.19 - Zoo | [6 empty] | 1000000 | 1000000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4244.94 | 4244.94 | 201039.96 | 201039.96 | [6 empty] | 205284.9 | 205284.9 | 109392.8 | 394715.1 | 394715.1 | 34.21% | 34.21%
9.20 - Beaches | [6 empty] | 1000000 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 1000000 | 1000000 | 0% | 0%
9.22 - Cleansing Administration Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
9.23 - Refuse Removal | 0 | 0 | 0 | 0 | 0 |  | 0 | 8804587 | 8804587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7190755.44 | 7190755.44 | 1580662.54 | 1580662.54 | 0 | 0 | 0 | 0 | [6 empty] | 8771417.98 | 8771417.98 | 0 | 33169.02 | 33169.02 | 99.62% | 99.62%
9.27 - E.L Regional Waste Disposal Site & Transfer Station | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 36000000 | 86010908 | 71010908 | 0 | 0 | 645222.42 | 645779.06 | 2450643.07 | 2450643.07 | 2238657.95 | 2238657.95 | 1447367.75 | 1447367.75 | 8812003.26 | 8812003.26 | 8328093.2 | 8328093.2 | 0 | 0 | 102740.35 | 102740.35 | [6 empty] | 24024728 | 24025284.64 | 9334705.04 | 46986180 | 46985623.36 | 33.83% | 33.83%
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 942007423 | 1056484706 | 1168745004 | 4279296.15 | 4585291.8 | 36998451.88 | 40732237.59 | 63771348.91 | 69010776.28 | 82385306.63 | 89033634.96 | 52978431.48 | 58529672.59 | 123416513.71 | 135884274.5 | 30396944.51 | 31683788.99 | 47087499.42 | 52451253.38 | 104078327.73 | 112792735.65 | 0 | 0 | 0 | 0 | 0 | 0 | 545392120.42 | 594703665.74 | 139403947.18 | 623352883.58 | 574041338.26 | 57.9% | 63.13%
[8 empty] | 1056484706 | 1168745004
942007423
[8 empty] | 0 | 0
0
C5 | 2013/2014 Approved Budget | 2013/2014 Rollover Adjustment Budget | 2013/2014 Conditional Grants Rollover Adjustment Budget | Mid-Year Adjustments | 2013/2014 Mid-Year Adjusted Budget | 2014/2015 DoRA | 2014/2015 Approved Capital Budget | 2014/2015 Rollover Adjustment Budget | 2014/2015 Mid-Year Adjustment Budget | July 2014 | July 2014 (VAT incl) | August 2014 | August 2014 (VAT incl) | September 2014 | September 2014 (VAT incl) | October 2014 | October 2014 (VAT incl) | November 2014 | November 2014 (VAT incl) | December 2014 | December 2014 (VAT incl) | January 2015 | January 2015 (VAT incl) | February 2015 | February 2015 (VAT incl) | March 2015 | March 2015 (VAT incl) | April 2015 | April 2015 (VAT incl) | May 2015 | May 2015 (VAT incl) | June 2015 | June 2015 (VAT incl) | YTD Expenditure | YTD Expenditure (VAT) incl) | Commitments as per Venus | Variance | Variance ( VAT incl) | % Expenditure | % Expenditure (VAT incl)
Capital Expenditure - Standard
Governance and administration | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 |  | 34950000 | 49115229 | 46935229 | 19074.32 | 19074.32 | 170805 | 194717.7 | 711244.23 | 711244.23 | 3364195.78 | 3740957.99 | 2056351.75 | 2056351.75 | 395582.87 | 395582.87 | 2011838.6 | 2035507.05 | 2040388.81 | 2164120.99 | 1109204.92 | 1193832.42 | 0 | 0 | 0 | 0 | 0 | 0 | 11878686.28 | 12511389.32 | 3950523.37 | 35056542.72 | 34423839.68 | 25.31% | 26.66% | 53478000 | 50944000
Executive and council | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 |  | 7500000 | 13729257 | 13229257 | 0 | 0 | 170805 | 194717.7 | 107792 | 107792 | 2992460.09 | 3369222.3 | 0 | 0 | 15594.59 | 15594.59 | 177438.08 | 201106.53 | 1448874.69 | 1572606.87 | 681644.53 | 766272.03 | [6 empty] | 5594608.98 | 6227312.02 | 1384463.92 | 7634648.02 | 7001944.98 | 42.29% | 47.07% | 19378000 | 20244000
Budget and treasury office | 500000 | 500000 | 500000 | 500000 | 500000 |  | 12350000 | 12119839 | 10597839 | 19074.32 | 19074.32 | 0 | 0 | 13675.44 | 13675.44 | 17870 | 17870 | 56239.1 | 56239.1 | 91343.02 | 91343.02 | 1719575.96 | 1719575.96 | 470613.01 | 470613.01 | 67878.88 | 67878.88 | [6 empty] | 2456269.73 | 2456269.73 | 105533.17 | 8141569.27 | 8141569.27 | 23.18% | 23.18% | 12000000 | 10500000
Corporate services | 500000 | 500000 | 500000 | 500000 | 500000 |  | 15100000 | 23266133 | 23108133 | 0 | 0 | 0 | 0 | 589776.79 | 589776.79 | 353865.69 | 353865.69 | 2000112.65 | 2000112.65 | 288645.26 | 288645.26 | 114824.56 | 114824.56 | 120901.11 | 120901.11 | 359681.51 | 359681.51 | [6 empty] | 3827807.57 | 3827807.57 | 2460526.28 | 19280325.43 | 19280325.43 | 16.56% | 16.56% | 22100000 | 20200000
Community and public safety | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 |  | 140466517 | 169392850 | 209457228 | 4420525.9 | 4724945.15 | 8528328.69 | 9082022.36 | 10301951.41 | 11091462.11 | 16281617.02 | 17109734.18 | 12257276.72 | 12386277.64 | 13217729.25 | 14853517.75 | 4456403.13 | 4704021.2 | 13723939.23 | 15569516.29 | 28628936.82 | 30751299.14 | 0 | 0 | 0 | 0 | 0 | 0 | 111816708.17 | 120272795.82 | 18134492.55 | 97640519.83 | 89184432.18 | 53.38% | 57.42% | 203218500 | 317214685
Community and social services | 500000 | 500000 | 500000 | 500000 | 500000 |  | 35291907 | 47249168 | 30479836 | 0 | 0 | 237492.13 | 242755.03 | 869626.97 | 886920.96 | 1258084.26 | 1395007.87 | 585015.74 | 606543.41 | 208679.94 | 210173.24 | -399105.69 | -373939.35 | 949067.64 | 1023700.84 | 2339426.58 | 2515894.98 | [6 empty] | 6048287.57 | 6507056.98 | 7593665.32 | 24431548.43 | 23972779.02 | 19.84% | 21.35% | 19250000 | 19250000
Sport and recreation | 0 | 0 | 0 | 0 | 0 |  | 5238502 | 8309447 | 7909447 | 0 | 0 | 0 | 0 | 180000 | 180000 | 68800 | 68800 | 137600 | 137600 | 268155.79 | 268155.79 | 844472.37 | 844472.37 | 4244.94 | 4244.94 | 201039.96 | 201039.96 | [6 empty] | 1704313.06 | 1704313.06 | 237510.03 | 6205133.94 | 6205133.94 | 21.55% | 21.55% | 10500000 | 10000000
Public safety | 500000 | 500000 | 500000 | 500000 | 500000 |  | 9800000 | 13016980 | 14870715 | 1102.63 | 1102.63 | 761505.76 | 761505.76 | 1653.95 | 1653.95 | 177174.39 | 177174.39 | 225684.05 | 225684.05 | 433311.89 | 433311.89 | 50316 | 50316 | 121027.72 | 121027.72 | 85894 | 85894 | [6 empty] | 1857670.39 | 1857670.39 | 5260613.79 | 13013044.61 | 13013044.61 | 12.49% | 12.49% | 10500000 | 21200000
Housing | 0 | 0 | 0 | 0 | 0 |  | 90136108 | 100817255 | 156197230 | 4419423.27 | 4723842.52 | 7529330.8 | 8077761.57 | 9250670.49 | 10022887.2 | 14777558.37 | 15468751.92 | 11308976.93 | 11416450.18 | 12307581.63 | 13941876.83 | 3960720.45 | 4183172.18 | 12649598.93 | 14420542.79 | 26002576.28 | 27948470.2 | [6 empty] | 102206437.15 | 110203755.39 | 5042703.41 | 53990792.85 | 45993474.61 | 65.43% | 70.55% | 162968500 | 266764685
Health | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
Economic and environmental services | 500000 | 500000 | 500000 | 500000 | 500000 |  | 262895288 | 266225207 | 390442127 | 5180.84 | 6757.24 | 12875367.06 | 14492034.43 | 21480115.25 | 23636695.04 | 25684678.89 | 28921079.7 | 19140212.23 | 22044066.62 | 54170709.51 | 61492382.92 | 7731545.58 | 8339236.97 | 13143821.79 | 14881447.98 | 28195292.33 | 31669765.75 | 0 | 0 | 0 | 0 | 0 | 0 | 182426923.48 | 205483466.65 | 43762994.16 | 208015203.52 | 184958660.35 | 46.72% | 52.63% | 605220661 | 591655051
Planning and development | 500000 | 500000 | 500000 | 500000 | 500000 |  | 54895288 | 56525207 | 51543127 | 52995 | 54571.4 | 2901318.5 | 3177418.3 | 2096477.84 | 2325205.81 | 1406454.44 | 1408030.84 | 2575135.51 | 2835733.88 | 1431495.47 | 1538716.37 | 1876901.26 | 1904525.24 | 3344528.95 | 3687723.74 | 6628284.92 | 7637704.73 | [6 empty] | 22313591.89 | 24569630.31 | 10393618.47 | 29229535.11 | 26973496.69 | 43.29% | 47.67% | 52220661 | 83655051
Road transport | 0 | 0 | 0 | 0 | 0 |  | 198000000 | 198000000 | 327199000 | -47814.16 | -47814.16 | 9974048.56 | 11314616.13 | 19383637.41 | 21311489.23 | 24278224.45 | 27513048.86 | 16280303.27 | 18883691.01 | 51599138.66 | 58698371.46 | 5053867.15 | 5521825.76 | 10116370.33 | 11510801.73 | 20386656.53 | 22686461.02 | [6 empty] | 157024432.2 | 177392491.04 | 29703088.03 | 170174567.8 | 149806508.96 | 47.99% | 54.22% | 545000000 | 500000000
Environmental protection | 0 | 0 | 0 | 0 | 0 |  | 10000000 | 11700000 | 11700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284773.45 | 324641.73 | 1140075.38 | 1255295.09 | 800777.17 | 912885.97 | -317077.49 | -317077.49 | 1180350.88 | 1345600 | [6 empty] | 3088899.39 | 3521345.3 | 3666287.66 | 8611100.61 | 8178654.7 | 26.4% | 30.1% | 8000000 | 8000000
Trading services | 500000 | 500000 | 500000 | 500000 | 500000 |  | 503195618 | 571251420 | 521410420 | -165484.91 | -165484.91 | 15423951.13 | 16963463.1 | 31278038.02 | 33571374.9 | 37054814.94 | 39261863.09 | 19524590.78 | 22042976.58 | 55632492.08 | 59142790.96 | 16197157.2 | 16605023.77 | 18045506.25 | 19702324.78 | 46083378.05 | 49116322.73 | 0 | 0 | 0 | 0 | 0 | 0 | 239074443.54 | 256240655 | 73500710.42 | 282335976.46 | 265169765 | 45.85% | 49.14% | 518210100 | 424912415
Electricity | 0 | 0 | 0 | 0 | 0 |  | 152999000 | 159996668 | 144755668 | 34346 | 34346 | 2854705.38 | 2873139.92 | 19032534.94 | 19508345.34 | 23988369.69 | 24927246.15 | 5787043.67 | 6863002.8 | 13173409.92 | 13426732.29 | 669232.42 | 679462.77 | 8275075.35 | 8952694.13 | 21439084.95 | 22030617.72 | [6 empty] | 95253802.32 | 99295587.12 | 3826026.45 | 49501865.68 | 45460080.88 | 65.8% | 68.6% | 160500000 | 166500000
Water | 0 | 0 | 0 | 0 | 0 |  | 97688726 | 95355831 | 94114971 | 0 | 0 | 1847692.21 | 2052472.42 | 2223512.66 | 2348646.58 | 2998073.18 | 3218272.85 | 5638393.1 | 6167568.1 | 4803675.23 | 5115693.09 | 3425995.81 | 3548005.38 | 5129081.8 | 5497058.17 | 11851676.19 | 12816678.06 | [6 empty] | 37918100.18 | 40764394.65 | 38300569.78 | 56196870.82 | 53350576.35 | 40.29% | 43.31% | 91000000 | 91000000
Waste water management | 500000 | 500000 | 500000 | 500000 | 500000 |  | 216507892 | 220415300 | 201656160 | -199830.91 | -199830.91 | 10076331.12 | 11392071.7 | 7571347.35 | 9263739.91 | 7829714.12 | 8877686.14 | 6523226.26 | 7436477.93 | 21636248.23 | 24581206.88 | 2178097.85 | 2453724.5 | 4641349.1 | 5252572.48 | 12687855.51 | 14164265.55 | [6 empty] | 72944338.63 | 83221914.18 | 22018680.15 | 128711821.37 | 118434245.82 | 36.17% | 41.27% | 230000000 | 137000000
Waste management | 0 | 0 | 0 | 0 | 0 |  | 36000000 | 95483621 | 80883621 | 0 | 0 | 645222.42 | 645779.06 | 2450643.07 | 2450643.07 | 2238657.95 | 2238657.95 | 1575927.75 | 1575927.75 | 16019158.7 | 16019158.7 | 9923831.12 | 9923831.12 | 0 | 0 | 104761.4 | 104761.4 | [6 empty] | 32958202.41 | 32958759.05 | 9355434.04 | 47925418.59 | 47924861.95 | 40.75% | 40.75% | 36710100 | 30412415
Other | 500000 | 500000 | 500000 | 500000 | 500000 |  | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 133843.34 | 133843.34 | 61515.61 | 61515.61 | [6 empty] | 195358.95 | 195358.95 | 55226.68 | 304641.05 | 304641.05 | 39.07% | 39.07% | 500000 | 500000
Total Capital Expenditure - Standard | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 |  | 942007423 | 1056484706 | 1168745004 | 4279296.15 | 4585291.8 | 36998451.88 | 40732237.59 | 63771348.91 | 69010776.28 | 82385306.63 | 89033634.96 | 52978431.48 | 58529672.59 | 123416513.71 | 135884274.5 | 30396944.51 | 31683788.99 | 47087499.42 | 52451253.38 | 104078327.73 | 112792735.65 | 0 | 0 | 0 | 0 | 0 | 0 | 545392120.42 | 594703665.74 | 139403947.18 | 623352883.58 | 574041338.26 | 46.66% | 50.88% | 1380627261 | 1385226151
[7 empty] | 942007423 | 1056484706 | 1168745004
[7 empty] | 0 | 0 | 0
[42 empty] | DoRA |  |  |  |  | 673289000 | 700458000 | 743775000
[42 empty] | Diff |  |  |  |  | 0 | -358500000 | -320000000 | USD
|  |  |  | 189271546 |  | 230735570 | 667025500 | [33 empty] | 690810100
[6 empty] | 21156250 | 31264500 | [33 empty] | 32147900
|  |  |  | 189271546 | 0 | 251891820 | 698290000 | [33 empty] | 722958000
|  |  |  | 176071546 |  | 613305000 | 698290000 | [33 empty] | 722958000
|  |  |  | 803061 |  | 361413180 | 0 | [33 empty] | 0
12396939
2014/2015 - 2016/2017 CAPITAL BUDGET PER DIRECTORATE
Directorate | 2013/2014 Approved Budget | 2013/2014 Rollover Adjustment Budget | 2013/2014 Conditional Grants Rollover Adjustment Budget | Mid-Year Adjustments | 2013/2014 Mid-Year Adjusted Budget | 2014/2015 DoRA | 2014/2015 Approved Capital Budget | 2014/2015 Rollover Adjustment Budget | 2014/2015 Mid-year Adjustment Budget | July 2014 | July 2014 (VAT incl) | August 2014 | August 2014 (VAT incl) | September 2014 | September 2014 (VAT incl) | October 2014 | October 2014 (VAT incl) | November 2014 | November 2014 (VAT incl) | December 2014 | December 2014 (VAT incl) | January 2015 | January 2015 (VAT incl) | February 2015 | February 2015 (VAT incl) | March 2015 | March 2015 (VAT incl) | April 2015 | April 2015 (VAT incl) | May 2015 | May 2015 (VAT incl) | June 2015 | June 2015 (VAT incl) | YTD Expenditure | YTD Expenditure (VAT) incl) | Commitments as per Venus | Variance | Variance ( VAT incl) | % Expenditure | % Expenditure (VAT incl) | 2015/2016 Capital Budget | 2016/2017 Capital Budget |  | 2016/2017 Capital Budget
1. Executive Support Services | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 6840376 | 6851376 | 0 | 0 | 0 | 0 | 0 | 0 | 287453.11 | 287453.11 | 0 | 0 | 0 | 0 | 23274.96 | 23274.96 | 10954 | 10954 | 619535.75 | 619535.75 | [6 empty] | 941217.82 | 941217.82 | 797299.31 | 5910158.18 | 5910158.18 | 13.74% | 13.74% | 500000 | 500000 |  | 500000
2. Municipal Manager's Office | 12750000 | 12750000 | 12750000 | -10000000 | 2750000 |  | 7000000 | 7008500 | 6508500 | 0 | 0 | 170805 | 194717.7 | 107792 | 107792 | 2712625.98 | 3089388.19 | 0 | 0 | 15594.59 | 15594.59 | 173739.08 | 197407.53 | 1448874.69 | 1572606.87 | 62108.78 | 146736.28 | [6 empty] | 4691540.12 | 5324243.16 | 603906.8 | 1816959.88 | 1184256.84 | 72.08% | 81.8% | 18878000 | 19744000 |  | 19744000 |  |  |  | 77950000
3. Human Settlements | 0 | 0 | 0 | 0 | 0 | 0 | 90136108 | 100828081 | 156208056 | 4419423.27 | 4723842.52 | 7529330.8 | 8077761.57 | 9250670.49 | 10022887.2 | 14777558.37 | 15468751.92 | 11319802.93 | 11427276.18 | 12307581.63 | 13941876.83 | 3960720.45 | 4183172.18 | 12649598.93 | 14420542.79 | 26002576.28 | 27948470.2 | [6 empty] | 102217263.15 | 110214581.39 | 5042703.41 | 53990792.85 | 45993474.61 | 65.44% | 70.56% | 162968500 | 266764685 |  | 0 |  |  |  | 321031108
4. Directorate of Financial Services | 0 | 0 | 0 | 0 | 0 |  | 2350000 | 2835567 | 1335567 | 19074.32 | 19074.32 | 0 | 0 | 0 | 0 | 10251 | 10251 | 24913.5 | 24913.5 | 0 | 0 | 0 | 0 | 336208.06 | 336208.06 | 67878.88 | 67878.88 | [6 empty] | 458325.76 | 458325.76 | 82874.79 | 877241.24 | 877241.24 | 34.32% | 34.32% | 2000000 | 500000 |  | 500000 |  |  |  | 398981108
5. Directorate of Corporate Services | 6600000 | 6600000 | 6600000 | 0 | 6600000 |  | 15100000 | 23435340 | 23277340 | 0 | 0 | 0 | 0 | 589776.79 | 589776.79 | 353865.69 | 353865.69 | 2010819.65 | 2010819.65 | 288645.26 | 288645.26 | 114824.56 | 114824.56 | 120901.11 | 120901.11 | 359681.51 | 359681.51 | [6 empty] | 3838514.57 | 3838514.57 | 2466442.47 | 19438825.43 | 19438825.43 | 16.49% | 16.49% | 22100000 | 20200000 |  | 20200000
6. Directorate of Engineering Services |  |  | 122746331.88 | 32584305 | 155330636.88 |  | 665695618 | 674505650 | 768463650 | -213299.07 | -213299.07 | 24752777.27 | 27632300.17 | 48211032.36 | 52432221.06 | 59094381.44 | 64536254 | 34228966.3 | 39350739.84 | 91212472.04 | 101822003.72 | 11327193.23 | 12203018.41 | 28419170.87 | 31470420.8 | 66426788.79 | 71759537.96 | [6 empty] | 363459483.23 | 400993196.89 | 93903591.09 | 405004166.77 | 367470453.11 | 47.3% | 52.18% | 1027000000 | 895000000 |  | 895000000 |  |  |  | 255845288
7. Directorate of Development Planning |  |  | 12000000 | 800000 | 12800000 | 12000000 | 44895288 | 46533707 | 41551627 | 52995 | 54571.4 | 2901318.5 | 3177418.3 | 2096477.84 | 2325205.81 | 1406454.44 | 1408030.84 | 2575135.51 | 2835733.88 | 1431495.47 | 1538716.37 | 1876901.26 | 1904525.24 | 3344528.95 | 3687723.74 | 5501289.41 | 6357073.85 | [6 empty] | 21186596.38 | 23288999.43 | 8251214.89 | 20365030.62 | 18262627.57 | 50.99% | 56.05% | 42220661 | 73655051 |  | 156655051 |  |  |  | 673289000
8. Directorate of Economic Development | [6 empty] | 10000000 | 10026000 | 10026000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20802 | 20802 | 0 | 0 | 0 | 0 | 1126995.51 | 1280630.88 | [6 empty] | 1147797.51 | 1301432.88 | 2142403.58 | 8878202.49 | 8724567.12 | 11.45% | 12.98% | 10000000 | 10000000
9. Directorate of Health & Public Safety |  |  | 2250000 | -2000000 | 250000 | 2250000 | 9800000 | 14466980 | 16320715 | 1102.63 | 1102.63 | 761505.76 | 761505.76 | 1653.95 | 1653.95 | 177174.39 | 177174.39 | 235476.65 | 235476.65 | 502511.91 | 502511.91 | 50316 | 50316 | 121027.72 | 121027.72 | 85894 | 85894 | [6 empty] | 1936663.01 | 1936663.01 | 5260613.79 | 14384051.99 | 14384051.99 | 11.87% | 11.87% | 10500000 | 21200000 |  | 21200000 |  |  |  | 929134288
10 .Directorate of Community Services | 48080943 | 48080943 | 48080943 | -8384413 | 39696530 | 48080943 | 86530409 | 164650862 | 132915530 | 0 | 0 | 882714.55 | 888534.09 | 3513945.48 | 3531239.47 | 3565542.21 | 3702465.82 | 2583316.94 | 2644712.89 | 17637410.81 | 17754123.82 | 12869974.97 | 13007250.11 | 636235.09 | 710868.29 | 3825578.82 | 4167296.34 | [6 empty] | 45514718.87 | 46406490.83 | 20852897.05 | 87400811.13 | 86509039.17 | 34.24% | 34.91% | 74460100 | 67662415 |  | 67662415
TOTAL DIRECTORATES | 67430943 | 67430943 | 204427274.88 | 12999892 | 217427166.88 | 62330943 | 932007423 | 1051131063 | 1163458361 | 4279296.15 | 4585291.8 | 36998451.88 | 40732237.59 | 63771348.91 | 69010776.28 | 82385306.63 | 89033634.96 | 52978431.48 | 58529672.59 | 123416513.71 | 135884274.5 | 30396944.51 | 31683788.99 | 47087499.42 | 52451253.38 | 104078327.73 | 112792735.65 | 0 | 0 | 0 | 0 | 0 | 0 | 545392120.42 | 594703665.74 | 139403947.18 | 618066240.58 | 568754695.26 | 46.88% | 51.12% | 1370627261 | 1375226151 |  | 1181461466 |  |  |  | 0.42941
Asset Replacement | 0 | 0 | 0 | 0 | 0 |  | 10000000 | 5353643 | 5286643 | 0 | 0 | [25 empty] | 5286643 | 5286643 | 0% | 0% | 10000000 | 10000000 |  | 10000000
GRAND - TOTAL | 67430943 | 67430943 | 204427274.88 | 12999892 | 217427166.88 | 62330943 | 942007423 | 1056484706 | 1168745004 | 4279296.15 | 4585291.8 | 36998451.88 | 40732237.59 | 63771348.91 | 69010776.28 | 82385306.63 | 89033634.96 | 52978431.48 | 58529672.59 | 123416513.71 | 135884274.5 | 30396944.51 | 31683788.99 | 47087499.42 | 52451253.38 | 104078327.73 | 112792735.65 | 0 | 0 | 0 | 0 | 0 | 0 | 545392120.42 | 594703665.74 | 139403947.18 | 623352883.58 | 574041338.26 | 46.66% | 50.88% | 1380627261 | 1385226151 |  | 1191461466 |  | 942007423 |  | #REF! |  | 1024127261 | #REF! | #REF! | #REF! | 1069226151
F
A5 - Schedule | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 |  | Budget Year 2014/15 | [33 empty] | Budget Year 2014/15 | Budget Year 2014/15
Capital Expenditure - Standard
Governance and administration | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 |  | 34950000 | [33 empty] | 53478000 | 50944000
Executive and council | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 |  | 7500000 | [33 empty] | 19378000 | 20244000
Budget and treasury office | 500000 | 500000 | 500000 | 500000 | 500000 |  | 12350000 | [33 empty] | 12000000 | 10500000
Corporate services | 500000 | 500000 | 500000 | 500000 | 500000 |  | 15100000 | [33 empty] | 22100000 | 20200000
Community and public safety | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 |  | 140466517 | [33 empty] | 203218500 | 317214685
Community and social services | 500000 | 500000 | 500000 | 500000 | 500000 |  | 35291907 | [33 empty] | 19250000 | 19250000
Sport and recreation | 0 | 0 | 0 | 0 | 0 |  | 5238502 | [33 empty] | 10500000 | 10000000
Public safety | 500000 | 500000 | 500000 | 500000 | 500000 |  | 9800000 | [33 empty] | 10500000 | 21200000
Housing | 0 | 0 | 0 | 0 | 0 |  | 90136108 | [33 empty] | 162968500 | 266764685
Health | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Economic and environmental services | 500000 | 500000 | 500000 | 500000 | 500000 |  | 262895288 | [33 empty] | 605220661 | 591655051
Planning and development | 500000 | 500000 | 500000 | 500000 | 500000 |  | 54895288 | [33 empty] | 52220661 | 83655051
Road transport | 0 | 0 | 0 | 0 | 0 |  | 198000000 | [33 empty] | 545000000 | 500000000
Environmental protection | 0 | 0 | 0 | 0 | 0 |  | 10000000 | [33 empty] | 8000000 | 8000000
Trading services | 500000 | 500000 | 500000 | 500000 | 500000 |  | 503195618 | [33 empty] | 518210100 | 424912415
Electricity | 0 | 0 | 0 | 0 | 0 |  | 152999000 | [33 empty] | 160500000 | 166500000
Water | 0 | 0 | 0 | 0 | 0 |  | 97688726 | [33 empty] | 91000000 | 91000000
Waste water management | 500000 | 500000 | 500000 | 500000 | 500000 |  | 216507892 | [33 empty] | 230000000 | 137000000
Waste management | 0 | 0 | 0 | 0 | 0 |  | 36000000 | [33 empty] | 36710100 | 30412415
Other | 500000 | 500000 | 500000 | 500000 | 500000 |  | 500000 | [33 empty] | 500000 | 500000
Total Capital Expenditure - Standard | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 |  | 942007423 | [33 empty] | 1380627261 | 1385226151
Funded by:
National Government | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [33 empty] | 0 | 0
Provincial Government | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [33 empty] | 0 | 0
District Municipality | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Other transfers and grants | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Transfers recognised - capital | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [33 empty] | 0 | 0
Public contributions & donations | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [33 empty] | 0 | 0
Borrowing | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Internally generated funds | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [33 empty] | 0 | 0
Total Capital Funding | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | [33 empty] | 0 | 0
Q
SA - 34a - Schedule | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 |  | Budget Year 2014/15 | [33 empty] | Budget Year 2014/15 | Budget Year 2014/15
Capital expenditure on NEW ASSETS by Asset Class/Sub-class
Infrastructure | 0 | 0 | 0 | 0 | 0 |  | 225500000 | [33 empty] | 487210100 | 460412415
Infrastructure - Road transport | 0 | 0 | 0 | 0 | 0 |  | 110000000 | [33 empty] | 360000000 | 320000000
Roads, Pavements & Bridges | 0 | 0 | 0 | 0 | 0 |  | 110000000 | [33 empty] | 360000000 | 320000000
Storm water
Infrastructure - Electricity | 0 | 0 | 0 | 0 | 0 |  | 45500000 | [33 empty] | 50500000 | 40500000
Generation
Transmission & Reticulation | 0 | 0 | 0 | 0 | 0 |  | 45500000 | [33 empty] | 50500000 | 40500000
Street Lighting | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Infrastructure - Water | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Dams & Reservoirs
Water purification
Reticulation | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Infrastructure - Sanitation | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Reticulation | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Sewerage purification
Infrastructure - Other | 0 | 0 | 0 | 0 | 0 |  | 70000000 | [33 empty] | 76710100 | 99912415
Waste Management | 0 | 0 | 0 | 0 | 0 |  | 36000000 | [33 empty] | 36710100 | 30412415
Transportation | 0 | 0 | 0 | 0 | 0 |  | 24000000 | [33 empty] | 30000000 | 59500000
Gas
Other | 0 | 0 | 0 | 0 | 0 |  | 10000000 | [33 empty] | 10000000 | 10000000
Community | 0 | 0 | 0 | 0 | 0 |  | 22000000 | [33 empty] | 17000000 | 17000000
Parks & gardens | 0 | 0 | 0 | 0 | 0 |  | 2000000 | [33 empty] | 0 | 0
Sportsfields & stadia | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Swimming pools | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Community halls | 0 | 0 | 0 | 0 | 0 |  | 10000000 | [33 empty] | 9000000 | 9000000
Libraries | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Recreational facilities | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Fire, safety & emergency
Security and policing
Buses | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Clinics | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Museums & Art Galleries
Cemeteries | 0 | 0 | 0 | 0 | 0 |  | 10000000 | [33 empty] | 8000000 | 8000000
Social rental housing
Other | 0 | 0 | 0 | 0 | 0
Heritage assets | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Buildings
Other
Investment properties | 0 | 0 | 0 | 0 | 0 |  | 89536108 | [33 empty] | 162318500 | 266264685
Housing development | 0 | 0 | 0 | 0 | 0 |  | 89536108 | [33 empty] | 162318500 | 266264685
Other
Other assets | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 |  | 59650000 | [33 empty] | 78128000 | 84144000
General vehicles | 0 | 0 | 0 | 0 | 0 |  | 18600000 | [33 empty] | 18000000 | 18400000
Specialised vehicles | 0 | 0 | 0 | 0 | 0 |  | 4000000 | [33 empty] | 4000000 | 4000000
Plant & equipment | 0 | 0 | 0 | 0 | 0 |  | 3500000 | [33 empty] | 1500000 | 8300000
Computers - hardware/equipment | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Furniture and other office equipment | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 |  | 28550000 | [33 empty] | 37750000 | 35700000
Abattoirs
Markets | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Civic Land and Buildings | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Other Buildings
Other Land
Surplus Assets - (Investment or Inventory)
Other | 0 | 0 | 0 | 0 | 0 |  | 5000000 | [33 empty] | 16878000 | 17744000
Agricultural assets | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
List sub-class
Biological assets | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
List sub-class
Intangibles | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Computers - software & programming
Other (list sub-class)
Total Capital Expenditure on new assets | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 |  | 396686108 | [33 empty] | 744656600 | 827821100
Specialised vehicles | 0 | 0 | 0 | 0 | 0 |  | 4000000 | [33 empty] | 4000000 | 4000000
Refuse | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Fire | 0 | 0 | 0 | 0 | 0 |  | 4000000 | [33 empty] | 4000000 | 4000000
Conservancy | [6 empty] | 0 | [33 empty] | 0 | 0
Ambulances
SA - 34b - Schedule | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 | Budget Year 2013/14 |  | Budget Year 2014/15 | [33 empty] | Budget Year 2014/15 | Budget Year 2014/15
Capital expenditure on RENEWAL OF EXISTING ASSETS by Asset Class/Sub-class
Infrastructure | 0 | 0 | 0 | 0 | 0 |  | 491395618 | [33 empty] | 598000000 | 516000000
Infrastructure - Road transport | 0 | 0 | 0 | 0 | 0 |  | 88000000 | [33 empty] | 185000000 | 180000000
Roads, Pavements & Bridges | 0 | 0 | 0 | 0 | 0 |  | 88000000 | [33 empty] | 185000000 | 180000000
Storm water | 0 | 0 | 0 | 0 | 0
Infrastructure - Electricity | 0 | 0 | 0 | 0 | 0 |  | 89199000 | [33 empty] | 92000000 | 108000000
Generation | 0 | 0 | 0 | 0 | 0
Transmission & Reticulation | 0 | 0 | 0 | 0 | 0 |  | 89199000 | [33 empty] | 92000000 | 108000000
Street Lighting | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Infrastructure - Water | 0 | 0 | 0 | 0 | 0 |  | 97688726 | [33 empty] | 91000000 | 91000000
Dams & Reservoirs
Water purification
Reticulation | 0 | 0 | 0 | 0 | 0 |  | 97688726 | [33 empty] | 91000000 | 91000000
Infrastructure - Sanitation | 0 | 0 | 0 | 0 | 0 |  | 216507892 | [33 empty] | 230000000 | 137000000
Reticulation | 0 | 0 | 0 | 0 | 0 |  | 216507892 | [33 empty] | 230000000 | 137000000
Sewerage purification
Infrastructure - Other | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Waste Management | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Transportation | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Gas
Other | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Community | 0 | 0 | 0 | 0 | 0 |  | 28030409 | [33 empty] | 20250000 | 19750000
Parks & gardens | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Sportsfields & stadia | 0 | 0 | 0 | 0 | 0 |  | 24791907 | [33 empty] | 12250000 | 9750000
Swimming pools | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Community halls | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Libraries | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Recreational facilities | 0 | 0 | 0 | 0 | 0 |  | 3238502 | [33 empty] | 8000000 | 10000000
Fire, safety & emergency
Security and policing
Buses | [6 empty] | 0 | [33 empty] | 0 | 0
Clinics | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Museums & Art Galleries | 0 | 0 | 0 | 0 | 0
Cemeteries | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Social rental housing
Other | 0 | 0 | 0 | 0 | 0
Heritage assets | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Buildings
Other
Investment properties | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Housing development | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Other
Other assets | 0 | 0 | 0 | 0 | 0 |  | 20395288 | [33 empty] | 17720661 | 21655051
General vehicles | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Specialised vehicles | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Plant & equipment | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Computers - hardware/equipment | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Furniture and other office equipment | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Abattoirs
Markets | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Civic Land and Buildings | 0 | 0 | 0 | 0 | 0 |  | 20395288 | [33 empty] | 17720661 | 21655051
Other Buildings
Other Land
Surplus Assets - (Investment or Inventory)
Other | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Agricultural assets | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
List sub-class
Biological assets | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
List sub-class
Intangibles | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Computers - software & programming
Other (list sub-class)
Total Capital Expenditure on renewal of assets | 0 | 0 | 0 | 0 | 0 |  | 539821315 | [33 empty] | 635970661 | 557405051 |  |  |  |  | 936507423 | -5500000
Specialised vehicles | 0 | 0 | 0 | 0 | 0 |  | 0 | [33 empty] | 0 | 0
Refuse | [6 empty] | 0 | [33 empty] | 0 | 0
Fire | [6 empty] | 0 | [33 empty] | 0 | 0
Conservancy | [6 empty] | 0 | [33 empty] | 0 | 0
Ambulances
2014/2015 - 2016/2017 CAPITAL BUDGET PER SERVICE
Services | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget |  | 2014/2015 Approved Capital Budget | 2014/2015 Rollover Adjustment Budget | 2014/2015 Mid-year Adjustment Budget | July 2014 | July 2014 (VAT incl) | August 2014 | August 2014 (VAT incl) | September 2014 | September 2014 (VAT incl) | October 2014 | October 2014 (VAT incl) | November 2014 | November 2014 (VAT incl) | December 2014 | December 2014 (VAT incl) | January 2015 | January 2015 (VAT incl) | February 2015 | February 2015 (VAT incl) | March 2015 | March 2015 (VAT incl) | April 2015 | April 2015 (VAT incl) | May 2015 | May 2015 (VAT incl) | June 2015 | June 2015 (VAT incl) | YTD Expenditure | YTD Expenditure (VAT) incl) | Commitments as per Venus | Variance | Variance ( VAT incl) | % Expenditure | % Expenditure (VAT incl) | 2015/2016 Draft Capital Budget | 2016/2017 Draft Capital Budget
Water | 0 | 0 | 10000000 | 0 | 10000000 |  | 97688726 | 95355831 | 94114971 | 0 | 0 | 1847692.21 | 2052472.42 | 2223512.66 | 2348646.58 | 2998073.18 | 3218272.85 | 5638393.1 | 6167568.1 | 4803675.23 | 5115693.09 | 3425995.81 | 3548005.38 | 5129081.8 | 5497058.17 | 11851676.19 | 12816678.06 | [6 empty] | 37918100.18 | 40764394.65 | 38300569.78 | 56196870.82 | 53350576.35 | 40.29% | 43.31% | 91000000 | 91000000
Waste Water | 500000 | 500000 | 57854000 | 0 | 57854000 |  | 216507892 | 220436300 | 201677160 | -199830.91 | -199830.91 | 10076331.12 | 11392071.7 | 7571347.35 | 9263739.91 | 7829714.12 | 8877686.14 | 6523226.26 | 7436477.93 | 21636248.23 | 24581206.88 | 2178097.85 | 2453724.5 | 4641349.1 | 5252572.48 | 12687855.51 | 14164265.55 | [6 empty] | 72944338.63 | 83221914.18 | 22018680.15 | 128732821.37 | 118455245.82 | 36.17% | 41.26% | 230000000 | 137000000
Electricity | 0 | 0 | 12892331.88 | 29084305 | 41976636.88 |  | 134699000 | 137870851 | 122629851 | 34346 | 34346 | 966172.74 | 984607.28 | 8548369.41 | 9024179.81 | 19438470.71 | 20377347.17 | 5787043.67 | 6863002.8 | 13173409.92 | 13426732.29 | -4615356.74 | -4605126.39 | 8398526.3 | 9076145.08 | 21439084.95 | 22030617.72 | [6 empty] | 73170066.96 | 77211851.76 | 3826026.45 | 49459784.04 | 45417999.24 | 59.67% | 62.96% | 142500000 | 148500000
Roads and Stormwater | 0 | 0 | 9000000 | 0 | 9000000 |  | 188000000 | 188045000 | 317244000 | -47814.16 | -47814.16 | 9974048.56 | 11314616.13 | 19383637.41 | 21311489.23 | 24278224.45 | 27513048.86 | 16280303.27 | 18883691.01 | 51599138.66 | 58698371.46 | 5053867.15 | 5521825.76 | 10116370.33 | 11510801.73 | 20386656.53 | 22686461.02 | [6 empty] | 157024432.2 | 177392491.04 | 29703088.03 | 160219567.8 | 139851508.96 | 49.5% | 55.92% | 515000000 | 470000000
Housing | 0 | 0 | 81695940 | -800000 | 80895940 |  | 89636108 | 100776115 | 156156090 | 4419423.27 | 4723842.52 | 7514624.7 | 8063055.47 | 9250670.49 | 10022887.2 | 14732515.11 | 15423708.66 | 11308976.93 | 11416450.18 | 12293497.37 | 13927792.57 | 3960720.45 | 4183172.18 | 12649598.93 | 14420542.79 | 25968245.31 | 27914139.23 | [6 empty] | 102098272.56 | 110095590.8 | 5002831.68 | 54057817.44 | 46060499.2 | 65.38% | 70.5% | 162468500 | 266264685
Transport Planning | 500000 | 500000 | 22000000 | 800000 | 22800000 |  | 54895288 | 56559707 | 51577627 | 52995 | 54571.4 | 2901318.5 | 3177418.3 | 2096477.84 | 2325205.81 | 1406454.44 | 1408030.84 | 2575135.51 | 2835733.88 | 1452297.47 | 1559518.37 | 1876901.26 | 1904525.24 | 3344528.95 | 3687723.74 | 6628284.92 | 7637704.73 | [6 empty] | 22334393.89 | 24590432.31 | 10393618.47 | 29243233.11 | 26987194.69 | 43.3% | 47.68% | 52220661 | 83655051
Waste Management / Refuse | 0 | 0 | 14240000 | 0 | 14240000 | 14240000 | 36300000 | 95783621 | 81183621 | 0 | 0 | 645222.42 | 645779.06 | 2450643.07 | 2450643.07 | 2238657.95 | 2238657.95 | 1575927.75 | 1575927.75 | 16019158.7 | 16019158.7 | 9923831.12 | 9923831.12 | 0 | 0 | 109561.4 | 109561.4 | [6 empty] | 32963002.41 | 32963559.05 | 9467263.19 | 48220618.59 | 48220061.95 | 40.6% | 40.6% | 36710100 | 30412415
Amenities | 500000 | 500000 | 22800000 | -15884413 | 6915587 | 14240000 | 40030409 | 58604241 | 41468909 | 0 | 0 | 237492.13 | 242755.03 | 1063302.41 | 1080596.4 | 1326884.26 | 1463807.87 | 698204.64 | 719732.31 | 478176.73 | 479670.03 | 2119499.6 | 2144665.94 | 925512.58 | 1000145.78 | 2484121.04 | 2660589.44 | [6 empty] | 9333193.39 | 9791962.8 | 7624302.64 | 32135715.61 | 31676946.2 | 22.51% | 23.61% | 29250000 | 28750000
Environmental Services | 0 | 0 | 11040943 | 7500000 | 18540943 | 14240000 | 10000000 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284773.45 | 324641.73 | 1140075.38 | 1255295.09 | 800777.17 | 912885.97 | -317077.49 | -317077.49 | 1180350.88 | 1345600 | [6 empty] | 3088899.39 | 3521345.3 | 3666287.66 | 6911100.61 | 6478654.7 | 30.89% | 35.21% | 8000000 | 8000000
Health Services | 0 | 0 | 0 | 0 | 0 | 14240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
Public Safety | 500000 | 500000 | 2250000 | -2000000 | 250000 | 14240000 | 9800000 | 14466980 | 16320715 | 1102.63 | 1102.63 | 761505.76 | 761505.76 | 1653.95 | 1653.95 | 177174.39 | 177174.39 | 235476.65 | 235476.65 | 502511.91 | 502511.91 | 50316 | 50316 | 121027.72 | 121027.72 | 85894 | 85894 | [6 empty] | 1936663.01 | 1936663.01 | 5260613.79 | 14384051.99 | 14384051.99 | 11.87% | 11.87% | 10500000 | 21200000
Support Services | 2500000 | 2500000 | 19350000 | -10000000 | 9350000 | 14240000 | 36150000 | 46288392 | 44074392 | 19074.32 | 19074.32 | 185511.1 | 209423.8 | 697568.79 | 697568.79 | 3409239.04 | 3786001.25 | 2070970.25 | 2070970.25 | 318324.11 | 318324.11 | 337705.68 | 361374.13 | 2078581.2 | 2202313.38 | 1256597 | 1341224.5 | [6 empty] | 10373571.49 | 11006274.53 | 4140665.34 | 33700820.51 | 33068117.47 | 23.54% | 24.97% | 54978000 | 52444000
Other - BCM Fleet | 0 | 0 | 33000000 | 3500000 | 36500000 | 33000000 | 28300000 | 32297668 | 32297668 | 0 | 0 | 1888532.64 | 1888532.64 | 10484165.53 | 10484165.53 | 4549898.98 | 4549898.98 | 0 | 0 | 0 | 0 | 5284589.16 | 5284589.16 | 0 | 0 | 0 | 0 | [6 empty] | 22207186.31 | 22207186.31 | 0 | 10090481.69 | 10090481.69 | 68.76% | 68.76% | 48000000 | 48000000
| 4500000 | 4500000 | 296123214.88 | 12199892 | 308323106.88 |  | 942007423 | 1056484706 | 1168745004 | 4279296.15 | 4585291.8 | 36998451.88 | 40732237.59 | 63771348.91 | 69010776.28 | 82385306.63 | 89033634.96 | 52978431.48 | 58529672.59 | 123416513.71 | 135884274.5 | 30396944.51 | 31683788.99 | 47087499.42 | 52451253.38 | 104078327.73 | 112792735.65 | 0 | 0 | 0 | 0 | 0 | 0 | 545392120.42 | 594703665.74 | 139403947.18 | 623352883.58 | 574041338.26 | 46.66% | 50.88% | 1380627261 | 1385226151
|  |  | 91695940 | -800000 | 90895940 | -62330943 | 0 | [31 empty] | #DIV/0! | #DIV/0! | 0 | 0 | 0 | -1191461466
KEY OBJECTIVES | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget |  | 2014/2015 Approved Capital Budget | 2014/2015 Rollover Adjustment Budget | 2014/2015 Mid-year Adjustment Budget | July 2014 | July 2014 (VAT incl) | August 2014 | August 2014 (VAT incl) | September 2014 | September 2014 (VAT incl) | October 2014 | October 2014 (VAT incl) | November 2014 | November 2014 (VAT incl) | December 2014 | December 2014 (VAT incl) | January 2015 | January 2015 (VAT incl) | February 2015 | February 2015 (VAT incl) | March 2015 | March 2015 (VAT incl) | April 2015 | April 2015 (VAT incl) | May 2015 | May 2015 (VAT incl) | June 2015 | June 2015 (VAT incl) | YTD Expenditure | YTD Expenditure (VAT) incl) | Commitments as per Venus | Variance | Variance ( VAT incl) | % Expenditure | % Expenditure (VAT incl) | 2015/2016 Capital Budget | 2016/2017 Capital Budget
1.Municipal Transformation and Organisational Development | 0 | 0 | 0 | 0 | 0 |  | 15100000 | [31 empty] | 0% | 0% | 22100000 | 20200000
2.Service Delivery and Basic Infrastructure | 0 | 0 | 0 | 0 | 0 |  | 849057423 | [31 empty] | 0% | 0% | 1335527261 | 1343526151
3.Local Economic Development | 0 | 0 | 0 | 0 | 0 |  | 10000000 | [31 empty] | 0% | 0% | 10000000 | 10000000
4.Municipal Financial Viability and Management | 0 | 0 | 0 | 0 | 0 |  | 12350000 | [31 empty] | 0% | 0% | 12000000 | 10500000
5.Good Governance and public Participation | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 |  | 1000000 | [31 empty] | 0% | 0% | 1000000 | 1000000
TOTAL | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 |  | 887507423 | [31 empty] | 0% | 0% | 1380627261 | 1385226151
USDG CAPITAL BUDGET PER SERVICE
Services | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget | 2013/2014 Capital Budget |  | 2014/2015 Approved Capital Budget | 2014/2015 Rollover Adjustment Budget | 2014/2015 Mid-year Adjustment Budget | July 2014 | July 2014 (VAT incl) | August 2014 | August 2014 (VAT incl) | September 2014 | September 2014 (VAT incl) | October 2014 | October 2014 (VAT incl) | November 2014 | November 2014 (VAT incl) | December 2014 | December 2014 (VAT incl) | January 2015 | January 2015 (VAT incl) | February 2015 | February 2015 (VAT incl) | March 2015 | March 2015 (VAT incl) | April 2015 | April 2015 (VAT incl) | May 2015 | May 2015 (VAT incl) | June 2015 | June 2015 (VAT incl) | YTD Expenditure | YTD Expenditure (VAT) incl) | Commitments as per Venus | Variance | Variance ( VAT incl) | % Expenditure | % Expenditure (VAT incl)
Water | 0 | 0 | 10000000 | 0 | 10000000 |  | 57500000 | 55167105 | 53926245 | 0 | 0 | 1578845.64 | 1783625.85 | 929320.16 | 1054454.08 | 2757628.97 | 2977828.64 | 2471176.03 | 3000351.03 | 2371310.09 | 2683327.95 | 871496.94 | 993506.51 | 2628402.68 | 2996379.05 | 6892870.34 | 7857872.21 | [6 empty] | 20501050.85 | 23347345.32 | 38300569.78 | 34666054.15 | 31819759.68 | 37.16% | 42.32%
Waste Water | 500000 | 500000 | 57854000 | 0 | 57854000 |  | 176507892 | 178840787 | 160081647 | -199830.91 | -199830.91 | 10076331.12 | 11392071.7 | 7571347.35 | 9263739.91 | 7821134.12 | 8869106.14 | 6523226.26 | 7436477.93 | 21636248.23 | 24581206.88 | 1968761.88 | 2244388.53 | 4544506.61 | 5155729.99 | 10878207.53 | 12354617.57 | [6 empty] | 70819932.19 | 81097507.74 | 22018680.15 | 108020854.81 | 97743279.26 | 39.6% | 45.35%
Electricity | 0 | 0 | 12892331.88 | 29084305 | 41976636.88 |  | 27699000 | 27699000 | 18500000 | 0 | 0 | 131675.29 | 150109.83 | 374455.86 | 426879.68 | 1792320.83 | 2028903.03 | 582021.35 | 660557.42 | 1781780.85 | 2034177.1 | 70150.18 | 73514.41 | 1637763.01 | 1835826.91 | 3721136.8 | 4234870.37 | [6 empty] | 10091304.17 | 11444838.75 | 3826026.45 | 17607695.83 | 16254161.25 | 36.43% | 41.32%
Roads and Stormwater | 0 | 0 | 9000000 | 0 | 9000000 |  | 198000000 | 198000000 | 207199000 | -47814.16 | -47814.16 | 9974048.56 | 11314616.13 | 19383637.41 | 21311489.23 | 24278224.45 | 27513048.86 | 16280303.27 | 18883691.01 | 51599138.66 | 58698371.46 | 5053867.15 | 5521825.76 | 10116370.33 | 11510801.73 | 16147796.29 | 18447600.78 | [6 empty] | 152785571.96 | 173153630.8 | 29703088.03 | 45214428.04 | 24846369.2 | 77.16% | 87.45%
Housing | 0 | 0 | 81695940 | -800000 | 80895940 |  | 60867608 | 60867608 | 103997873 | 2174423.21 | 2478842.46 | 4158777.34 | 4707208.11 | 7217125.33 | 7989342.04 | 4750526.24 | 5441719.79 | 767666.1 | 875139.35 | 11781515.23 | 13415810.43 | 1765490.7 | 1987942.43 | 12649598.93 | 14420542.79 | 15208320.39 | 17154214.31 | [6 empty] | 60473443.47 | 68470761.71 | 5002831.68 | 394164.53 | -7603153.71 | 99.35% | 112.5%
Transport Planning | 500000 | 500000 | 22000000 | 800000 | 22800000 |  | 44500000 | 44500000 | 44500000 | 52995 | 54571.4 | 1754959.43 | 2031059.23 | 1633771.02 | 1862498.99 | 922399.1 | 923975.5 | 1878949.14 | 2139547.51 | 1419543.35 | 1526764.25 | 1270856.32 | 1298480.3 | 2797646.38 | 3140841.17 | 6611880.12 | 7621299.93 | [6 empty] | 18342999.86 | 20599038.28 | 10393618.47 | 26157000.14 | 23900961.72 | 41.22% | 46.29%
Waste Management / Refuse | 0 | 0 | 14240000 | 0 | 14240000 | 14240000 | 26000000 | 26000000 | 11000000 | 0 | 0 | 3976.02 | 4532.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 3976.02 | 4532.66 | 9467263.19 | 25996023.98 | 25995467.34 | 0.01529% | 0.01743%
Amenities | 500000 | 500000 | 22800000 | -15884413 | 6915587 | 14240000 | 32250000 | 32250000 | 23064949 | 0 | 0 | 237492.13 | 242755.03 | 869626.97 | 886920.96 | 888939.81 | 1025863.42 | 531984.64 | 553512.31 | 178682.4 | 180175.7 | -844472.37 | -844472.37 | 562494.28 | 637127.48 | 1338308.36 | 1514776.76 | [6 empty] | 3763056.22 | 4196659.29 | 7624302.64 | 28486943.78 | 28053340.71 | 11.67% | 13.01%
Environmental Services | 0 | 0 | 11040943 | 7500000 | 18540943 | 14240000 | 12000000 | 12000000 | 13685051 | 0 | 0 | 0 | 0 | 0 | 0 | 4196.91 | 4196.91 | 284773.45 | 324641.73 | 1140075.38 | 1255295.09 | 980536.77 | 1117811.91 | -317077.49 | -317077.49 | 1180350.88 | 1345600 | [6 empty] | 3272855.9 | 3730468.15 | 3666287.66 | 8727144.1 | 8269531.85 | 27.27% | 31.09%
Health Services | 0 | 0 | 0 | 0 | 0 | 14240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
Public Safety | 500000 | 500000 | 2250000 | -2000000 | 250000 | 14240000 | 3000000 | 3000000 | 2069735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 5260613.79 | 3000000 | 3000000 | 0% | 0%
Support Services | 2500000 | 2500000 | 19350000 | -10000000 | 9350000 | 14240000 | 1500000 | 1500000 | 1000000 | 0 | 0 | 170805 | 194717.7 | 0 | 0 | 129259.3 | 129259.3 | 0 | 0 | 0 | 0 | 14483.7 | 16511.42 | 8890 | 10134.6 | 13566.1 | 15465.35 | [6 empty] | 337004.1 | 366088.37 | 4140665.34 | 1162995.9 | 1133911.63 | 22.47% | 24.41%
Other - BCM Fleet | 0 | 0 | 33000000 | 3500000 | 36500000 | 33000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
| 4500000 | 4500000 | 296123214.88 | 12199892 | 308323106.88 |  | 639824500 | 639824500 | 639024500 | 1979773.14 | 2285768.79 | 28086910.53 | 31820696.24 | 37979284.1 | 42795324.89 | 43344629.73 | 48913901.59 | 29320100.24 | 33873918.29 | 91908294.19 | 104375128.86 | 11151171.27 | 12409508.9 | 34628594.73 | 39390306.23 | 61992436.81 | 70546317.28 | 0 | 0 | 0 | 0 | 0 | 0 | 340391194.74 | 386410871.07 | 139403947.18 | 299433305.26 | 253413628.93 | 53.2% | 60.39%
0

## Housing
BUFFALO CITY METROPOLITAN MUNICIPALITY
2014-2017 DRAFT CAPITAL BUDGET
Directorate | Cost centre name | C5C | USDG Service | Cost Centre No. | A5 | Service | V1 | V1 | V1 | VT | VT | VT | VT | VT | VT | 34a & 34b | New Asset | Renewal | A9 | Asset Sub Class- SA36 | KPA'S | Ward No. | Project Name | Funding Source | 2013/2014 Approved Budget | Adjustment | 2013/2014 Rollover Adjustment Budget | Adjustments | 2013/14 Conditional Grants Rollover Adjustment Budget | Mid-Year Adjustments | 2013/2014 Mid-Year Adjusted Budget | Savings | 2014/2015 Draft Capital Budget | 2015/2016 Draft Capital Budget | 2016/2017 Draft Capital Budget | July Expenditure | July Expenditure(VAT inc.) | August Expenditure | August Expenditure ( VAT inc.) | September Expenditure | Vat | September Expenditure (VAT inc.) | 1st Quarter Expenditure (Exc. VAT) | 1st Quarter Expenditure (incl. VAT) | October Expenditure | Vat | October Expenditure (VAT inc.) | November Expenditure | Vat | November Expenditure (VAT inc.) | December Expenditure | Vat | December Expenditure (VAT inc.) | January Expenditure | January Expenditure (VAT inc.) | February Expenditure | February Expenditure (VAT inc.) | March Expenditure | March Expenditure (VAT inc.) | April Expenditure | April Expenditure (VAT inc.) | May Expenditure | May Expenditure ( VAT inc.) | June Expenditure | June Expenditure ( VAT inc.) | Commitments as per Venus | YTD Expenditure | YTD Expenditure ( VAT inc.) | Commitments (Outstanding invoices for work done not yet paid) | Available Budget | Available Budget ( Budget -Expenditure including VAT) | % Expenditue | % Expenditue including VAT) | 2017/2018 Draft Capital Budget | 2018/2019 Draft Capital Budget | 2017/2018 Draft Capital Budget | Comments
[55 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
CHIEF OPERATIONS OFFICER | [22 empty] | CHIEF OPERATIONS OFFICE | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Chief Operations Officer |  |  |  | 250005 | Housing | Support Services | [9 empty] | New-270 |  |  | Other | Housing | KPA2 |  | Office Furniture and Equipment (Directorate) | Own Funds |  |  |  |  | 0 |  | 0 |  | 500000 | 500000 | 500000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 01 | 1407 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 |  | Beneficiary Administration (Procure GPS Devices) | Own Funds | 200000 |  | 200000 |  | 200000 | 200000 | 400000 |  | 100000 | 150000 | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Beneficiary Registration DVRI Projects (Reeston, Cambridge, DVRI Pilot, Braelyn ext 10, C Section and Triangular Site, D Hostel) | HSDG - Opex | [8 empty] | 500000 | 100000 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Beneficiary Registration (Potsdam Unit V, Cluster 3, Orange Groove, Mdantsane Zone CC, Cluster 1, Cluster 2, Peelton Cluster, Hanover, Skobeni, Sunny South, Ilitha North, Dimbaza 110, Dimbaza Phase 3,Potsdam Village; North Kanana, Ikhwezi Block 1 & 2, Amalinda Co-op, Eradication of Wooden Houses to Formal Houses | HSDG - Opex | [8 empty] | 1350000 | 1000000 | 1000000
[33 empty] | 1950000 | 1250000 | 1000000
Chief Operations Officer | DVRI | 3.2 - Office of The Chief Operations Officer |  | 250005 | Housing | Housing | 4 | 39 | 1401 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | Reeston MPCC - DVRI | HSDG-Special Fund | 2100000 |  | 2100000 |  | 2100000 |  | 2100000 |  | 10068500 | 13068500 | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 33675 |  | 33675 | 53800 |  | 53800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 87475 | 87475 |  | 2012525 | 2012525 | 4.165% | 4.165%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1403 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3: Stage 2 - P1 & P3 | HSDG | 11684600 |  | 11684600 |  | 11684600 |  | 11684600 |  | 7000000 | 9000000 | 55265000 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8771929.82 | 0 | 0 |  | 11684600 | 11684600 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Reeston Phase 3: Stage 2 - P5 | HSDG | [8 empty] | 30000000 | 30000000 | 100000000
[33 empty] | 47068500 | 52068500 | 155265000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1404 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 3 - P1 & P3 | HSDG | 10000000 |  | 10000000 |  | 10000000 |  | 10000000 |  | 8722000 | 19134500 | 36795436 |  | 0 | 48240 | 48240 |  |  | 0 | 48240 | 48240 |  |  | 0 |  |  | 0 | 18152.9 |  | 18152.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 66392.9 | 66392.9 |  | 9933607.1 | 9933607.1 | 0.6639% | 0.6639% |  |  |  |  | 74651936
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Reeston Phase 3 Stage 3 P5 | HSDG | [8 empty] | 14965387 | 59804569 | 30000000
[33 empty] | 23687387 | 78939069 | 66795436
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1401 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 2 -P1 & P3 | USDG | 6815400 |  | 6815400 |  | 6815400 | 5000000 | 11815400 |  | 6815400 | 100000 | 100000 |  | 0 | 4119.6 | 4119.6 | -4119.6 | 0 | -4119.6 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3614075.5 | 0 | 0 |  | 6815400 | 6815400 | 0% | 0% | 55265000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1404 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 13 | Reeston Phase 3 Stage 3 - P1 & P3 | USDG | [8 empty] | 0 | 10000000 | 62923951.73 | [42 empty] | 72923951.73
[33 empty] | 6815400 | 10100000 | 63023951.73
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Potsdam Village Phase 1 & 2 - P5 | HSDG - Opex | [8 empty] | 50000 | 200000 | 36000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1409 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam Ikhwezi Block 1 - P1 & P3 | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 | 1600000 | 1600000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 175438.6 | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1410 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam Ikhwezi Block 2 - P1 & P3 | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 | 2000000 | 2000000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1411 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 23 | Potsdam Village- P1 & P3 | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 | 2000000 | 2000000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1412 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 24 | Potsdam North Kanana - P1 | USDG | 200000 |  | 200000 | 300000 | 500000 |  | 500000 |  | 500000 | 2300000 | 2300000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0% | 10000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Potsdam Ikhwezi Block 1 - P5 | HSDG - Opex | [8 empty] | 500000 | 500000 | 10000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Potsdam Ikhwezi Block 2- P5 | HSDG - Opex | [8 empty] | 500000 | 500000 | 10000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Potsdam North Kanana - P5 | HSDG - Opex | [8 empty] | 500000 | 500000 | 10000000
[33 empty] | 3550000 | 9600000 | 73900000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1414 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 36 | Dimbaza Destitute 27 Units - P1 & P3 | USDG | 2500000 |  | 2500000 | -2300000 | 200000 |  | 200000 |  | 200000 | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 169290 | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Dimbaza 110 -P 5 (Top Structure) | HSDG - Opex | [8 empty] | 7100000 | 0 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Dimbaza Destitute 27 Units - P5 | HSDG - Opex | [8 empty] | 500000 | 500000 | 0
[33 empty] | 7800000 | 500000 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1416 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 36 | Disaster Project | USDG | 500000 |  | 500000 | -500000 | 0 |  | 0 |  | 1000000 | 200000 | 200000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1415 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 45 | Ilitha North 177 Units | USDG | 700000 |  | 700000 |  | 700000 |  | 700000 |  | 1500000 | 1000000 | 1000000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 700000 | 700000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Ilitha North - 177 Units P5 | HSDG - Opex | [8 empty] | 0 | 500000 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Ilitha Eradication of Wooden Houses to Formal Houses | HSDG - Opex | [8 empty] | 18180294 | 6000000 | 0
[33 empty] | 19680294 | 7500000 | 1000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | DVRI Planning Budget (FROM 8.7MIL) | Dept of LGTH - Opex | [8 empty] | 5000000 | 0 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1420 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | DVRI Pilot Project (Mekeni, Haven Hills, Competition Site) P1 & P3 | USDG | 2500000 |  | 2500000 | 1000000 | 3500000 |  | 3500000 |  | 775000 | 0 | 0 |  | 0 |  | 0 | 81590 | 11422.6 | 93012.6 | 81590 | 93012.6 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 81590 | 93012.6 |  | 3418410 | 3406987.4 | 2.331% | 2.658%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | DVRI Pilot Project (Mekeni, Haven Hills, Competition Site) P5 | HSDG - Opex | [8 empty] | 5000000 | 0 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1402 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 15 | Duncan Village Proper | HSDG | 350000 |  | 350000 |  | 350000 |  | 350000 |  | 700000 | 3300000 | 10000000 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 350000 | 350000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1406 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | C Section and Triangular Site - P1 & P3 | HSDG | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 2000000 | 2000000 | 10000000 |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 3707.64 |  | 3707.64 | -3707.64 |  | -3707.64 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1407 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 2 | D Hostel - P1 & P3 | HSDG | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 2000000 | 2000000 | 10000000 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | C Section and Triangular Site - P5 | HSDG - Opex | [8 empty] | 0 | 300000 | 30000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | D Hostel - P5 | HSDG - Opex | [8 empty] | 0 | 300000 | 30000000
[33 empty] | 15475000 | 7900000 | 90000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Mdantsane Zone 18CC - P5 | HSDG - Opex | [8 empty] | 3109500 | 2551000 | 65000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1402 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 23 | Mdantsane Zone 18 CC Phase 2 - P1 & P3 | USDG | 3000000 |  | 3000000 |  | 3000000 | -1000000 | 2000000 |  | 10000000 | 13500000 | 13500000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 382.04 | 382.04 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 382.04 |  | 3000000 | 2999617.96 | 0% | 0.01273% | 16500000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1410 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 |  | Mdantsane Zone CC Phase 2 P1 & P3 | HSDG | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 8500000 | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
[33 empty] | 13109500 | 24551000 | 78500000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1419 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1 | Block Yard TRA - P1 & P3 | USDG | 500000 |  | 500000 | 1831500 | 2331500 |  | 2331500 |  | 100000 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 295.58 | 295.58 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 175180.32 | 0 | 295.58 |  | 2331500 | 2331204.42 | 0% | 0.01268%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1404 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 19 | Second Creek (Turn Key) - P1 & P3 | USDG | 8000000 |  | 8000000 | 1800000 | 9800000 |  | 9800000 |  | 100000 | 0 | 0 |  | 0 | 149203.55 | 170092.05 | 761056.68 | 106547.93 | 867604.61 | 910260.23 | 1037696.66 |  |  | 0 | 340800.89 | 47712.12 | 388513.01 | 751461.26 |  | 751461.26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2002522.38 | 2177670.93 |  | 7797477.62 | 7622329.07 | 20.43% | 22.22%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Second Creek - P5 | HSDG - Opex | [8 empty] | 1000000 | 0 | 0
[33 empty] | 1100000 | 0 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1421 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 9 | Amalinda Co- Op | USDG | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 1100000 | 1000000 | 1000000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0% | 6000000
Chief Operations Officer |  |  |  | 255005 | Housing | Housing | [9 empty] | New-80 |  |  | Other | Housing | KPA2 |  | Amalinda Fairlands Pi & P2 | USDG | 0 |  | 0 |  | 0 |  | 0 |  | 1250000 | 1300000 | 1300000
Chief Operations Officer |  |  |  | 255005 | [18 empty] | Amalinda Co - Op P5 | HSDG - Opex | [8 empty] | 0 | 500000 | 0
Chief Operations Officer |  |  |  | 255005 | [18 empty] | Amalinda Fairlands P5 | HSDG - Opex | [8 empty] | 500000 | 4000000 | 6000000
[33 empty] | 2850000 | 6800000 | 8300000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1405 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 48,12,21,11,17,11,20 | Cluster 1 (Masibambane; Masibulele; Velwano; Ilinge and Dacawa) | USDG | 3500000 |  | 3500000 |  | 3500000 |  | 3500000 |  | 12452208 | 34000000 | 94440733 |  | 0 | 4737.54 | 4737.54 | -4737.54 | 0 | -4737.54 | 0 | 0 |  |  | 0 |  |  | 0 | 9997.5 | 1399.65 | 11397.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 9997.5 | 11397.15 |  | 3490002.5 | 3488602.85 | 0.2856% | 0.3256% | 73047792 |  |  |  | 144392941
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1411 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 |  | Cluster 1 (Masibambane; Masibulele; Velwano; Ilinge and Dacawa) | HSDG | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6000000 | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Cluster 1 (Masibambane; Masibulele; Velwano; Ilinge and Dacawa) P5 | HSDG | [8 empty] | 1250000 | 100190955 | 33000000
[33 empty] | 13702208 | 140190955 | 127440733
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1412 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 |  | Cluster 2 (Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe) | HSDG | 0 |  | 0 |  | 0 |  | 0 |  | 6500000 | 10000000 | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | #DIV/0!
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1406 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 17,14, | Cluster 2 (Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe) | USDG | 3500000 |  | 3500000 |  | 3500000 | -2500000 | 1000000 |  | 5000000 | 10000000 | 10000000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | -3707.64 |  | -3707.64 | 3707.64 |  | 3707.64 | 2574.75 | 360.46 | 2935.21 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2574.75 | 2935.21 |  | 3497425.25 | 3497064.79 | 0.07356% | 0.08386% | 46000000
Chief Operations Officer |  | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 6 | 36 | 1417 | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes | [5 empty] | Cluster 2 (Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe) | USDG c/o |  |  | 0 | 9590 | 9590 |  | 9590 |  | 0 | 0 | 0 | [17 empty] | 0 | [14 empty] | 0 |  | 9590 | 9590 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Cluster 2 (Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe) P5 (Name Change) | HSDG - Opex | [8 empty] | 6000000 | 7000000 | 33000000
[33 empty] | 17500000 | 27000000 | 43000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1407 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 10 | Cluster 3 (Fynbos Informal 1, Fynbos Informal 2, Ndancama) P1 & P3 | USDG | 5524440 |  | 5524440 | -1300000 | 4224440 | -2000000 | 2224440 |  | 7275000 | 29650000 | 19900000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 417514 | 58451.96 | 475965.96 | 168266.6 | 23557.32 | 191823.92 | 13864.37 | 1941.01 | 15805.38 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 599644.97 | 683595.26 |  | 3624795.03 | 3540844.74 | 14.19% | 16.18% | 68000000
Chief Operations Officer |  | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 6 | 36 | 1418 | 05 | 02 | 01 | 01 | 080 | 002 | New-80 | Yes | [5 empty] | Cluster 3 (Fynbos Informal 1, Fynbos Informal 2, Ndancama) P1 & P3 | USDG c/o |  |  | 0 | 1344861 | 1344861 |  | 1344861 | [21 empty] | 0 | [14 empty] | 0 |  | 1344861 | 1344861 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Cluster 3 (Fynbos 1; Fynbos 2; Ndancama, ) P5 | HSDG - Opex | [8 empty] | 300000 | 100861424 | 26000000
[33 empty] | 7575000 | 130511424 | 45900000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1408 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 31 | Sunny South - P1 & P3 | USDG | 10000000 |  | 10000000 | 4000000 | 14000000 |  | 14000000 |  | 8000000 | 0 | 0 |  | 0 |  | 0 | 312750 |  | 312750 | 312750 | 312750 | 34750 | 43785 | 78535 | 793348.34 | 107369.96 | 900718.3 | 439562.11 | 61538.7 | 501100.81 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1580410.45 | 1793104.11 |  | 12419589.55 | 12206895.89 | 11.29% | 12.81%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1408 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes | [5 empty] | Sunny South -P5 | HSDG - Opex | [8 empty] | 11000000 | 10500000 | 0
[33 empty] | 19000000 | 10500000 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1405 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 9 | Braelyn ext 10 - P1 & P3 | HSDG | 500000 |  | 500000 |  | 500000 | -500000 | 0 |  | 2000000 | 2000000 | 69000000 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 500000 | 500000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Braelyn Ext 10 North - P5 | HSDG - Opex | [8 empty] | 5000000 | 30000000 | 57000000
[33 empty] | 7000000 | 32000000 | 126000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1417 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 43 | Tyutyu Phase 3 P1 & P3 Units | USDG | 200000 |  | 200000 | 0 | 200000 |  | 200000 |  | 500000 | 200000 | 200000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 200000 | 200000 | 0% | 0%
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | [18 empty] | Tyutyu Phase 2 - P 5 (Top Structure) | HSDG - Opex | [8 empty] | 1000000 | 0 | 0
[33 empty] | 1500000 | 200000 | 200000
Chief Operations Officer | Housing Department | 3.3 - Housing Department | Housing | 255005 | Housing | Housing | 4 | 36 | 1418 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 46 | Westbank Restitution - P1 & P3 | USDG | 2000000 |  | 2000000 | 0 | 2000000 |  | 2000000 |  | 5000000 | 500000 | 500000 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 2000000 | 2000000 | 0% | 0% | 140000000 |  | R70mill from 15/16
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | Housing | Housing | 4 | 35 | 1409 | 05 | 02 | 01 | 01 | 080 | 001 | New-80 | Yes |  | Other | Housing | KPA2 | 1,10 | Housing Needs Database and Accreditation (Capacity Enhancement) | HSDG | 390000 |  | 390000 |  | 390000 |  | 390000 |  | 500000 | 1000000 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 60641.08 |  | 60641.08 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 60641.08 | 60641.08 |  | 329358.92 | 329358.92 | 15.55% | 15.55%
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Housing Needs Database and Accreditation | HSDG - Opex | [8 empty] | 10327914 | 10818705 | 0
[33 empty] | 10827914 | 11818705 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Reconstruction of Storm Damaged Houses
[33 empty] | 23000000 | 100000 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Peelton Cluster (Majali, Mdange, Kwatrain, Nkqonqweni, Drayini & Esixekweni) - P5 | [9 empty] | 1000000 | 1000000 | 5000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Hanover - P5 | [9 empty] | 1000000 | 1000000 | 5000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Skobeni - P5 | [9 empty] | 1000000 | 1000000 | 5000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Relocation of beneficiaries to formal houses for all housing programmes - All Projects | [9 empty] | 2140000 | 5350000 | 3000000
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | Beneficiary Education ( All Projects) | [9 empty] | 150000 | 150000 | 0
Chief Operations Officer | Housing Department | 3.3 - Housing Department |  | 255005 | [18 empty] | MURP Sustainability Plan | [9 empty] | 500000 | 0 | 0
[23 empty] | TOTAL : CHIEF OPERATIONS OFFICE |  | 76264440 | 0 | 76264440 | 7085951 | 83550391 | -800000 | 82750391 | 0 | 255581203 | 561229653 | 899525120.73 | 0 | 0 | 206300.69 | 227189.19 | 1146539.54 | 117970.53 | 1264510.07 | 1352840.23 | 1491699.26 | 452264 | 102236.96 | 554500.96 | 1396731.91 | 179317.02 | 1576048.93 | 1289412.89 | 65239.82 | 1354652.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12905914.24 | 4491249.03 | 4976901.86 | 0 | 78859141.97 | 78373489.14 | 5.375% | 5.957% |  |  | 0
[33 empty] | 152423095 | 375226653 | 495000000
[33 empty] | 103158108 | 186003000 | 404525120.73
[33 empty] | 255581203 | 561229653 | 899525120.73
[33 empty] | 0 | 0 | 0